ACTION PLAN OF ICAR-KVK, GADAG

FOR THE YEAR 2016-17

Submitted to

Director

ICAR-ATARI, Zone VIII

Bengaluru - 560024

`

By

ICAR - K.H.PATIL KRISHI VIGYAN KENDRA

Hulkoti-582 205   Dist : GADAG, Karnataka State

Website : www.khpkvk.org

e-mail : kvkhulkoti@gmail.com

Contents

| Sl. No. | PARTICULARS | Page No. |
| --- | --- | --- |
| 1 | General information about the Krishi Vigyan Kendra | 1 |
| 2 | Details of staff as on date | 1-2 |
| 3 | Details of SAC meeting conducted during 2015-16 | 2-3 |
| 4 | Capacity Building of KVK Staff | 4 |
| 5 | Proposed cluster of KVKs | 4 |
| 6 | Operational areas details proposed during 2016-17 | 5-12 |
| 7 | Plan for Technology Assessment & Refinement | 13-15 |
| 8 | Plan for Front Line Demonstrations | 16-26 |
| 9 | Plan for training programmes | 27-37 |
|  | Training programme for farmers / farmwomen |  |
|  | Training for rural youths |  |
|  | Training programme for Extension personnel |  |
|  | Vocational training for young farmers |  |
|  | Sponsored trainings |  |
| 10 | Extension programmes planned | 38-42 |
| 11 | Activities proposed as Knowledge and Resource Center | 42-47 |
| 12 | Plan for Revolving Fund | 48 |
| 13 | Activities of soil, water and plant testing | 49 |
| 14 | Target for E-linkage | 49-50 |
| 15 | Activities planned under RWH | 50 |
| 16 | Budget | 51-52 |

###### ICAR-AGRICULTURAL TECHNOLOGY APPLICATION RESEARCH INSTITUTE, ZONE VIII BENGALURU

###### PROFORMA FOR ACTION PLAN OF KVKs IN ZONE VIII FOR 2016-17

###### 1. General information about the Krishi Vigyan Kendra

| 1.1 | Name and address of KVK with Phone, Fax and e-mail | : | ICAR-K.H. Patil Krishi Vigyan Kendra Hulkoti – 582205 Dist.: Gadag, State: Karnataka Phone : (08372) 289606 Fax : (08372) 289474 E-mail : khpatil_kvk_hulkoti@yahoo.com, kvkhulkoti@gmail.com Website: www.khpkvk.org |
| --- | --- | --- | --- |
| 1.2 | Name and address of host organization | : | Agricultural Science Foundation Hulkoti – 582205 District: Gadag, State: Karnataka Phone : (08372) 289069 Fax : (08372) 289474 E-mail : asf_hulkoti@yahoo.co.in Website: www.asf.net.in |
| 1.3 | Year of sanction | : | 1985 |
| 1.4 | Website address of KVK and date of last update |  | www.khpkvk.org, updated on 11-02-2016 |

2. Details of staff as on date

| Sl. No. | Sanctioned post | Name of the incumbent |  | If Permanent, Please indicate |  | If Temporary, pl. indicate the consolidated amount paid (Rs./month) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Discipline | Current Pay Band | Current Grade Pay | Date of joining |  |
| 2.1 | Senior Scientist and Head | Dr. L.G. Hiregoudar | Crop Physiology | 37400-67000 | 10000 | 19.10.1985 | - |
| 2.2 | Scientist | Mr. S.K.Mudlapur | Plant Protection | 15600-39100 | 6600 | 22.07.1985 | - |
| 2.3 | Scientist | Mr. S.H.Adapur | Ag. Extension | 15600-39100 | 6600 | 22.11.1990 | - |
| 2.4 | Scientist | Smt. S.S.Rayanagoudar | Home Science | 15600-39100 | 6600 | 20.07.1993 | - |
| 2.5 | Scientist | Mr. V.D.Vaikunthe | Agronomy | 15600-39100 | 6600 | 23.07.1985 | - |
| 2.6 | Scientist | Mr. K.T.Patil | Horticulture | 15600-39100 | 6600 | 25.07.1985 | - |
| 2.7 | Scientist | Mr. N.H.Bhandi | Soil Science | 15600-39100 | 6000 | 01.06.2005 | - |
| 2.8 | Programme Assistant | Mr. B.M.Murgod | Animal Husbandry | 9300-34800 | 4200 | 25.06.2007 | - |
| 2.9 | Computer Programmer | Smt. L.S.Asuti | - | 9300-34800 | 4600 | 01.06.2005 | - |
| 2.10 | Farm Manager | Mr. Suresh L. Halemani | - | 9300-34800 | 4200 | 01.02.2011 | - |
| 2.11 | Accountant/Superintendent | Mr. M.B. Jakkanagoudar | - | 9300-34800 | 4200 | 25.06.2007 | - |
| 2.12 | Stenographer | Vacant | - | - | - | - | - |
| 2.13 | Driver 1 | Mr. N.L. Hadapad | - | 5200-20200 | 2000 | 03.09.1992 | - |
| 2.14 | Driver 2 | Mr. G.D. Madivalar | - | 5200-20200 | 2000 | 20.07.1995 | - |
| 2.15 | Supporting staff 1 | Mr. S.B. Kotabagi | - | 5200-20200 | 1900 | 18.07.1985 | - |
| 2.16 | Supporting staff 2 | Mr. V.R. Navalli | - | 5200-20200 | 1900 | 20.07.1993 | - |

3. Details of SAC meeting conducted during 2015-16 :

| Sl. No | Date | Major recommendations | Status of action taken in brief | Tentative date of SAC meeting proposed during 2016-17 |
| --- | --- | --- | --- | --- |
| 3.1 | 19-02-2016 | Advise farmers of Gadag district not to take up ratoon crop in Bt. Cotton and put refugee crops with Bt. Cotton to reduce incidence of pest and disease. | It will be followed in all trainings and extension activities to be carried out during Kharif 2016-17 | July, 2016 |
|  |  | Layout demonstrations on Redgram & Redgram based intercropping in Gadag district. | During Kharif 2016-17, demonstrations will be laid out |  |
|  |  | Create awareness about possibility of outbreak of pink boll worm in Bt. Cotton as observed during last year in Gadag district through training and extension literature in collaboration with Department of Agriculture. | It will be carried out during Kharif 2016-17 |  |
|  |  | Demonstrate transplanted Redgram crop in KVK Farm to show to district farmers as the yield and price of Redgram are high and remunerative respectively. | It will be taken up during Kharif 2016-17 in KVK farm |  |
|  |  | Send SMSs to all farmers to take up precautionary measures to tackle foot & mouth disease in animals | Messages will be sent during first week of March, 2016 |  |
|  |  | Encourage farmers to take up Tree Mulberry cultivation with V-1 variety which suits to dryland condition through trainings in collaboration with Sericulture Department. | Training shall be conducted in last week of February, 2016. |  |
|  |  | Add grazing Guniea grass, Hedge Lucerne and Multicut Sorghum under FLDs on fodder crops. | These crops have been added in the Action Plan for 2016-17 |  |
|  |  | Issue soil health cards to maximum numbers of farmers of 14 villages to be adopted by KVK for the year 2016-17. | It will be carried out during 2016-17 in collaboration with Karnataka State Department of Agriculture |  |
|  |  | Enhance area under FLDs on Maize + Redgram as there is a need to increase the productivity of pulses. | Accordingly, the area under Maize + Redgram FLD is enhanced in the Action Plan 2016-17 |  |
|  |  | Organise a week long awareness programme about Pradhan Mantri Phasala Vima Yojane from 30th March to 5th April involving about 1000 farmers of the district in collaboration with Department of Agriculture, Horticulture etc and Reliance Foundation (NGO) working in the district | This will be carried as per the instructions of ICAR |  |
|  |  | Provide technical back-up to Reliance Foundation formed SHGs taking up various income generating activities | Technical backup to SHGs shall be facilitated during 2016-17 |  |

4. Capacity Building of KVK Staff

4.1. Plan of Human Resource Development of KVK personnel during 2016-17

| S. No | New Areas of Training | Institution proposed to attend | Justification |
| --- | --- | --- | --- |
| 4.1.1 | Supply and value chain management in agribusiness | NAARM, Hyderabad | To build the capacity of farmers of emerging FPOs in the district |
| 4.1.2 | Vegetable seed production technology | IIHR, Bangalore | Open pollinated varieties are required for vegetable production as it reduces the cost of cultivation |
| 4.1.3 | Cashew nut processing technology | NRC on Cashew, Puttur | To promote Cashew processing, as area under Cashew nut is increasing |
| 4.1.4 | Production technology in Sugarcane | Sugarcane Breeding Institute, Coimbatore | Sugarcane area in the district is increasing |
| 4.1.5 | Market led extension & new dimension of agriculture marketing | National Institute of Agricultural Marketing, Jaipur | To understand the frontier area of market led extension and agricultural marketing |

4.2. Cross-learning across KVKs during 2016-17

| S. No | Name of the KVK proposed | Specific learning areas |
| --- | --- | --- |
| 4.2.1 | Within ring – ICAR KVK, Tumkur, Karnataka | Revolving fund activities |
| 4.2.2 | Within the zone – ICAR KVK, Erode, TamilNadu | Farmers Producers Organisations |
| 4.2.3 | Outside zone – ICAR KVK, Ahamadanagar, Maharastra | IT related interventions |

5. Proposed cluster of KVKs (3 to 5 neighboring KVKs) to be formed for sharing knowledge/expertise, resources and activities during 2016-17

| S.No. | Name of the KVKs included in the cluster | What do you intend to share with Cluster KVKs | What do you expect from Cluster KVKs |
| --- | --- | --- | --- |
| 5.1 | KVK, Vijayapura | Expertise on FPOs | Dryland technologies & value addition in Sorghum |
| 5.2 | KVK, Haveri | Rain water harvesting technologies | Millet production technology |
| 5.3 | KVK, Dharwad | Value addition in agriculture produce | Greenhouse production technology |

6. Operational areas details proposed during 2016-17

| S.No. | Major crops & enterprises being practiced in cluster villages | Prioritized problems in these crops/ enterprise | Extent of area (Ha/No.) affected by the problem in the district | Names of Cluster Villages identified for intervention | Proposed Intervention (OFT, FLD, Training, extension activity etc.)* |
| --- | --- | --- | --- | --- | --- |
| 6.1 | Field crops | Decreased soil fertility due to less use / non-use of organic manures | 1.10 lakh ha. | Eklaspur cluster comprising of Eklaspur, Haithapur & Venkatapur villages in Mundaragi taluk Kochalapur cluster comprising of Kochalapur, Totaganti & Kodikoppa villages in Ron taluk Khanapur cluster comprising of Khanapur, Gangapur & Naganur villages in Naragund taluk Nabhapur cluster comprising of Nabhapur & Kabalayta Katti villages in Gadag taluk Yalavatti cluster comprising of Yalavatti, Madolli & Yatnalli villages in Shirahatti taluk | FLD on enhancement of soil fertility through production & usage of organic inputs (Vermicompost, Composting, Jeevamrutha & Ghana Jeevamrutha) Trainings on organic input preparation & soil fertility management Method demonstration on organic input preparation Supply of literature on organic input preparation Soil Test Campaigns Soil Testing in collaboration with Karnataka State Department of Agriculture Making Soil Test Reports available to Farmers in all 14 villages with appropriate recommendations |
| 6.2 | Maize (Irrigated) | Low productivity due to less use of macro & non use of secondary and micro nutrients | 12000 ha. | Khanapur cluster comprising of Khanapur, Gangapur & Naganur villages in Naragund taluk Kochalapur cluster comprising of Kochalapur, Totaganti & Kodikoppa villages in Ron taluk Nabhapur cluster comprising of Nabhapur & Kabalayta Katti villages in Gadag taluk | FLD on ICM practices FLD on Maize + Redgram and Kharif Sorghum + Redgram based intercropping system Capacity building on ICM in maize and intercropping systems Farm advisory services Organisation of field day Supply of literature on ICM practices Rendering Kisan Mobile Advisory Services to farmers Demonstration of functional clothing kit |
|  |  | High incidence of stem borer |  |  |  |
|  |  | High incidence of Turcicum leaf blight |  |  |  |
|  |  | High incidence of weed |  |  |  |
|  |  | Non-profitability due to mono cropping |  |  |  |
|  |  | Health problems during threshing & winnowing |  |  |  |
| 6.3 | Rabi Sorghum | Low productivity of existing M 35-1 variety | 35000 ha | Eklaspur cluster comprising of Eklaspur, Haithapur & Venkatapur villages in Mundaragi taluk | OFT: Assessment of SPV-2217, BJV-44 & CSV-29R varieties for higher productivity in sand mulched condition in Eklaspur cluster of villages |
|  |  | Moisture stress |  |  |  |
|  |  | Lack of value addition |  | Khanapur cluster comprising of Khanapur, Gangapur & Naganur villages in Naragund taluk Kochalapur cluster comprising of Kochalapur, Totaganti & Kodikoppa villages in Ron taluk Nabhapur cluster comprising of Nabhapur & Kabalayta Katti villages in Gadag taluk Yalavatti cluster comprising of Yalavatti, Madolli & Yatnalli villages in Shirahatti taluk | FLD on introduction of SPV-2217 & BJV-44 varieties in remaining 4 clusters Demonstration of cycle weeder Training programme on ICM practices Farm advisory services Organisation of field day & exhibition of value added products of sorghum |
| 6.4 | Wheat | Low productivity due to imbalanced nutrition in Malaprabha Command area and incidence of rust & stem borer | 8000 ha | Khanapur cluster comprising of Khanapur, Gangapur & Naganur villages in Naragund taluk | FLD on ICM practices Demonstration of improved sickle Training programmes on INM and management of stem borer & rust Organisation of field day Farm advisory services |
|  |  | Drudgery in harvesting of wheat |  |  |  |
| 6.5 | Bt. Cotton | High incidence of Jassids | 15000 ha. | Khanapur cluster comprising of Khanapur, Gangapur & Naganur villages in Naragund taluk Nabhapur cluster comprising of Nabhapur & Kabalayta Katti villages in Gadag taluk | Trainings on ICM practices Supply of relevant literatures Supply of yellow sticky trap on cost basis |
|  |  | High incidence of Mealy bugs |  |  |  |
|  |  | High incidence of Midge |  |  |  |
|  |  | Incidence of leaf reddening |  |  |  |
|  |  | Lack of knowledge on appropriate production technology |  |  |  |
| 6.6 | Greengram | Moisture stress in critical stages | 25000 ha. | Khanapur cluster comprising of Khanapur, Gangapur & Naganur villages in Naragund taluk Eklaspur cluster comprising of Eklaspur, Haithapur & Venkatapur villages in Mundaragi taluk Kochalapur cluster comprising of Kochalapur, Totaganti & Kodikoppa villages in Ron taluk Yalavatti clustercomprising of Yalavatti, Madolli & Yatnalli villages in Shirahatti taluk Nabhapur cluster comprising of Nabhapur & Kabalayta Katti villages in Gadag taluk | FLD on ICM in Greengram (DGGV-2 variety) Training on ICM practices Training & method demonstration on grading through spiral separator Field day |
|  |  | High incidence of pod borer |  |  |  |
|  |  | Incidence of powdery mildew in late sown situation |  |  |  |
|  |  | Decreased productivity due to use of existing shining Moong variety |  |  |  |
| 6.7 | Bengalgram | Low productivity due to high Incidence of wilt in existing variety of A-1 | 35000 ha. | Khanapur cluster comprising of Khanapur, Gangapur & Naganur villages in Naragund taluk | Assessment of GBM-2 variety for higher productivity & suitability for mechanic harvesting in Malaprabha command area |
|  |  | High incidence of pod borer |  |  |  |
|  |  |  |  | Eklaspur cluster comprising of Eklaspur, Haithapur & Venkatapur villages in Mundaragi taluk Kochalapur cluster comprising of Kochalapur, Totaganti & Kodikoppa villages in Ron taluk | Training on ICM practices Supply of literature on ICM practices Field days |
|  |  | Lack of knowledge on appropriate production technology |  |  |  |
|  |  | Drudgery in harvesting of Bengalgram |  |  |  |
|  |  | Less market price due to uncleaned and ungraded produce |  |  |  |
| 6.8 | Groundnut (Spreading) (Kharif season) | Low productivity due to mono cropping | 18000 ha. | Kochalapur cluster comprising of Kochalapur, Totaganti & Kodikoppa villages in Ron taluk | Assessment of Redgram + Greengram / Blackgram based cropping system for higher profitability Training on ICM practices Farm advisory services Rendering Kisan Mobile Advisory Services to farmers |
|  |  | Low productivity due to imbalanced nutrition |  |  |  |
|  |  | High incidence of Serpentine leaf minor |  |  |  |
|  |  | High incidence of root grub |  |  |  |
| 6.9 | Groundnut (Rabi / Summer season) | Low productivity in existing TMV-2 variety | 8000 ha | Kochalapur cluster comprising of Kochalapur, Totaganti & Kodikoppa villages in Ron taluk | FLD on introduction of DH-101 variety along with ICM practices for higher productivity Training on ICM practices Farm advisory services |
|  |  | High incidence of collar rot |  |  |  |
|  |  | Imbalanced nutrition |  |  |  |
|  |  | Incidence of leaf minor |  |  |  |
|  |  | Incidence of weed |  |  |  |
| 6.10 | Sunflower | Imbalanced nutrition High incidence of necrosis disease Incidence of hairy caterpillar & helothis | 10000 ha | Khanapur cluster comprising of Khanapur, Gangapur & Naganur villages in Naragund taluk Eklaspur cluster comprising of Eklaspur, Haithapur & Venkatapur villages in Mundaragi taluk | Trainings on ICM practices Farm advisory services Rendering Kisan Mobile Advisory Services to farmers |
| 6.11 | Onion | High incidence of purple blotch disease Incidence of bulb rot High incidence of weed Non availability of seeds of new variety | 8000 ha | Khanapur cluster comprising of Khanapur, Gangapur & Naganur villages in Naragund taluk Kochalapur cluster comprising of Kochalapur, Totaganti & Kodikoppa villages in Ron taluk Eklaspur cluster comprising of Eklaspur, Haithapur & Venkatapur villages in Mundaragi taluk Yalavatti cluster comprising of Yalavatti, Madolli & Yatnalli villages in Shirahatti taluk Nabhapur cluster comprising of Nabhapur & Kabalayta Katti villages in Gadag taluk | FLD on introduction of Arka Kalyan variety along with ICM practices Trainings on ICM in onion crop Seed production activities Supply of quality seeds of Arka Kalyan variety Supply of relevant literature Field day |
| 6.12 | Chilli | Low productivity due to non-practicing of ICM practices | 6000 ha | Yalavatti cluster comprising of Yalavatti, Madolli & Yatnalli villages in Shirahatti block | FLD on ICM in Chilli crop Training on ICM Supply of relevant literature Farm advisory services Rendering Kisan Mobile Advisory Services to farmers |
| 6.13 | Existing Rainfed cropping system | Non profitability in existing cropping pattern due to vagaries of Mansoon and lack of crop diversification in field crops resulting in income insecurity to the farmers Lack of knowledge on alternate cropping system and crop diversification to sustain vagaries of Mansoon. | 70% of farm families | Khanapur cluster comprising of Khanapur, Gangapur & Naganur villages in Naragund taluk Yalavatti cluster comprising of Yalavatti, Madolli & Yatnalli villages in Shirahatti block | FLD on Introduction of tamarind for drought mitigation |
|  |  |  |  | Kochalapur cluster comprising of Kochalapur, Totaganti & Kodikoppa villages in Ron taluk | FLD on introduction of dryland mango and tamarind for income security |
|  |  |  |  | Eklaspur cluster comprising of Eklaspur, Haithapur & Venkatapur villages in Mundaragi taluk | FLD on Introduction of tamarind for drought mitigation FLD on introduction of Ashwagandha FLD on introduction of DHFt-109-3 foxtail millet variety |
|  |  |  |  | Nabhapur cluster comprising of Nabhapur & Kabalayta Katti villages in Gadag taluk | FLD on introduction of dryland mango cultivation for income security |
|  |  |  |  |  | Apart from FLD, trainings & farm advisory services will be rendered. |
| 6.14 | Field crops | Crop loss due to attack of deer and monkeys | 15000 ha | Kochalapur cluster comprising of Kochalapur, Totaganti & Kodikoppa villages in Ron taluk Eklaspur cluster comprising of Eklaspur, Haithapur & Venkatapur villages in Mundaragi taluk | Awareness programmes on dispersal of wild animals |
| 6.15 | CB Cows & Buffaloes | Low productivity of milk due to non feeding of green fodder | 30000 Nos. | Nabhapur cluster comprising of Nabhapur & Kabalayta Katti villages in Gadag taluk Khanapur cluster comprising of Khanapur, Gangapur & Naganur villages in Naragund taluk Eklaspur cluster comprising of Eklaspur, Haithapur & Venkatapur villages in Mundaragi taluk Kochalapur cluster comprising of Kochalapur, Totaganti & Kodikoppa villages in Ron taluk Yalavatti cluster comprising of Yalavatti, Madolli & Yatnalli villages in Shirahatti block | FLD on fodder and azolla production Training on scientific management of dairy animals Supply of literature on Fodder & Azolla production Field day on fodder production Animal health camp Rendering Kisan Mobile Advisory Services to farmers |
|  |  | High incidence of Ecto-Endo parasite in milking animals |  |  |  |
|  |  | Increase in inter-calving period |  |  |  |
|  |  | New born calves mortality |  |  |  |
|  |  | Incidence of mastitis |  |  |  |
| 6.16 | Goats | Low body weight gain due to mineral deficiency and worm in goat kids | 4000 Nos |  | FLD on management of mineral deficiency and ecto-endo parasites in goat kids Trainings on scientific management of goats |
| 6.17 | Nutrition and reproductive health education for school children and young girls | Lack of knowledge on personal hygiene and reproductive health | Majority of school children & young girls are facing problems in these areas | All clusters | Trainings on balanced diet and nutrition Trainings on reproductive health and personal hygiene to young girls Providing relevant literature |
| 6.18 | Nutrition and health | Less consumption of fruits and vegetables | >80% farm families consume less fruits and vegetables | All clusters | Trainings on balanced diet and nutrition Training on Importance of millets in diet Training on Value addition in millets Providing relevant literature |
| 6.19 | FIG/CIG | Farmers are not organized for technical purposes | All villages | All clusters | Organising farmers into FIG/CIG Capacity building of FIG/CIG Preparing FIG/CIG as forum for transfer of technologies |
| 6.20 | Enterprise | Delayed mental and psycho motor development in children | All villages | All clusters | FLD on stimulatory toy kits for psychomotor development in children |
| 6.21 | Enterprise | Increase in health problems due to excess smoke in kitchen | All villages | All clusters | Demonstration of Envirofit chulha |
| 6.22 | Value addition in milk | Lack of value addition | Majority of the villages in the district | Kochalapur cluster comprising of Kochalapur, Totaganti & Kodikoppa villages in Ron taluk Nabhapur cluster comprising of Nabhapur & Kabalayta Katti villages in Gadag taluk Khanapur cluster comprising of Khanapur, Gangapur & Naganur villages in Naragund taluk | FLD on value addition and marketing of milk products |
| 6.23 | Value addition in Tamarind | Lack of value addition Less price for the unprocessed Tamarind Lack of knowledge on packing and marketing of produce | 10-15 villages where Tamarind is grown | Kochalapur cluster comprising of Kochalapur, Totaganti & Kodikoppa villages in Ron taluk | FLD on value addition and marketing of Tamarind products |

7.	Technology Assessment during 2016-17

| S. No. | Crop/ enterprise | Prioritized problem | Title of intervention | Technology options | Source of Technology | Name of critical input | Qty per trial | Cost per trial | No. of trials | Total cost for the intervention (Rs.) | Parameters to be studied | Team members |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 7.1 | Bengalgram | Productivity of A-1 is stagnant even under irrigated condition Scarcity of labours during harvesting | Assessment of potential productivity of GBM-2, JAKI-9218 & JG-14 varieties under irrigated condition & their suitability for mechanised harvesting | Farmers’ Practice Cultivation of Annigeri-1 variety | - | - | - | - | 3 |  | Height of the plant Duration of the crop No. of pods/plant Seed weight (100 No) Cost involved in harvesting Time taken for harvesting Grain yield | Mr. V.D.Vaikunthe, Scientist (Agronomy) & S.K. Mudlapur, Scientist (Plant Protection) |
|  |  |  |  | Technology Option-1 Cultivation of JAKI-9218 variety | UAS, Dharwad | Seeds (JAKI-9218) | 25 Kg | 1750 |  | 5250 |  |  |
|  |  |  |  | Technology Option-2 Assessment of GBM-2 variety | UAS, Raichur | Seeds (GBM-2) | 25 Kg | 1750 |  | 5250 |  |  |
|  |  |  |  | Technology Option-3 Assessment of JG-14 variety | JNAU, Jabalpur | Seeds (JG-14) | 25 Kg | 2000 |  | 6000 |  |  |
|  |  |  |  |  |  |  | Total | 5500 |  | 16500 |  |  |
| 7.2 | Rabi Sorghum | Low productivity of M 35-1 variety in sand mulched areas | Assessment of BJV-44, SPV-2217 & CSV-29R varieties for higher productivity | Farmers’ Practice Cultivation of M 35-1 variety | - | - | - | - | 3 |  | Height of the plant Duration of the crop Grain yield Fodder yield Lodging problem Organoleptic characters of the Rotis Fodder quality | Mr. V.D.Vaikunthe, Scientist (Agronomy), S.K. Mudlapur, Scientist (Plant Protection) & Mrs. Sudha S.R., Scientist (Home Science) |
|  |  |  |  | 2) Technology Option-1 Cultivation of M 35-1 variety | UAS, Dharwad | - | - | - |  | - |  |  |
|  |  |  |  | Technology Option-2 Assessment of BJV-44 variety | UAS, Dharwad | Seeds (BJV-44) | 1.5 Kg | 68 |  | 204 |  |  |
|  |  |  |  | Technology Option-3 Assessment of SPV-2217 variety | UAS, Dharwad | Seeds (SPV-2217) | 1.5 Kg | 68 |  | 204 |  |  |
|  |  |  |  | Technology Option-4 Assessment of CSV-29R variety | UAS, Dharwad | Seeds (CSV-29R) | 1.5 Kg | 68 |  | 204 |  |  |
|  |  |  |  |  |  |  | Total | 204 |  | 612 |  |  |
|  |  |  |  | For all T.Os |  | CaCl2 | 500 gm |  |  | 60 |  |  |
|  |  |  |  |  |  | Azospirillum | 1 Kg |  |  | 60 |  |  |
|  |  |  |  |  |  | Sulphur | 100 gm |  |  | 30 |  |  |
|  |  |  |  |  |  |  | Total |  |  | 762 |  |  |

| S. No. | Crop/ enterprise | Prioritized problem | Title of intervention | Technology options | Source of Technology | Name of critical input | Qty per trial | Cost per trial | No. of trials | Total cost for the intervention (Rs.) | Parameters to be studied | Team members |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 7.3 | Redgram | Low productivity in spreading groundnut due to monocropping | Assessment of different alternative Redgram based inter cropping systems i.e i) Redgram + Greengram (1:2) ii) Redgram + Blackgram (1:2) | Farmers’ Practice Cultivation of spreading groundnut | - | - | - | - | 3 |  | Grain yield Duration of the crop Net profit | Mr. V.D.Vaikunthe, Scientist (Agronomy) & S.K. Mudlapur, Scientist (Plant Protection) |
|  |  |  |  | Technology Option-1 Cultivation of Redgram TS-3R variety | UAS, Dharwad | Seeds (TS-3R) | 5 Kg | 625 |  |  |  |  |
|  |  |  |  |  |  | CaCl2 | 100 gm | 15 |  |  |  |  |
|  |  |  |  |  |  | Rhizobium | 200 gm | 12 |  |  |  |  |
|  |  |  |  |  |  | PSB | 200 gm | 12 |  |  |  |  |
|  |  |  |  |  |  | Trichoderma | 50 gm | 5 |  |  |  |  |
|  |  |  |  |  |  | 13-0-45 | 1 Kg | 130 |  |  |  |  |
|  |  |  |  |  |  | Pulse magic | 2 Kg | 300 |  |  |  |  |
|  |  |  |  |  |  | Emamectin benzoate | 50 gm | 350 |  |  |  |  |
|  |  |  |  |  |  | Total |  | 1449 |  | 4347 |  |  |
|  |  |  |  | Technology Option-2 Assessment of Redgram + Greengram (1:2) intercropping system | UAS, Dharwad | Seeds of Redgram (TS-3R) | 3 Kg | 375 |  |  |  |  |
|  |  |  |  |  |  | Seeds of Greengram (DGGV-2) | 3 Kg | 300 |  |  |  |  |
|  |  |  |  |  |  | CaCl2 | 100 gm | 15 |  |  |  |  |
|  |  |  |  |  |  | Rhizobium | 250 gm | 15 |  |  |  |  |
|  |  |  |  |  |  | PSB | 250 gm | 15 |  |  |  |  |
|  |  |  |  |  |  | Trichoderma | 50 gm | 5 |  |  |  |  |
|  |  |  |  |  |  | 13-0-45 | 2 Kg | 260 |  |  |  |  |
|  |  |  |  |  |  | Pulse magic | 3 Kg | 450 |  |  |  |  |
|  |  |  |  |  |  | Lambda cylahothrin | 250 ml | 155 |  |  |  |  |
|  |  |  |  |  |  | Emamectin benzoate | 50 gm | 350 |  |  |  |  |
|  |  |  |  |  |  | Total |  | 1930 |  | 5790 |  |  |
|  |  |  |  | Technology Option-3 Assessment of Redgram + Blackgram (1:2) intercropping system |  | Seeds of Redgram (TS-3R) | 3 Kg | 375 |  |  |  |  |
|  |  |  |  |  |  | Seeds of Blackgram (DU-1) | 4 Kg | 400 |  |  |  |  |
|  |  |  |  |  |  | Rhizobium | 250 gm | 15 |  |  |  |  |
|  |  |  |  |  |  | PSB | 250 gm | 15 |  |  |  |  |
|  |  |  |  |  |  | Trichoderma | 50 gm | 5 |  |  |  |  |
|  |  |  |  |  |  | 13-0-45 | 2 Kg | 260 |  |  |  |  |
|  |  |  |  |  |  | Pulse magic | 3 Kg | 450 |  |  |  |  |
|  |  |  |  |  |  | Hexaconazole | 200 ml | 150 |  |  |  |  |
|  |  |  |  |  |  | Emamectin benzoate | 50 gm | 350 |  |  |  |  |
|  |  |  |  |  |  |  | Total | 2020 |  | 6060 |  |  |
|  |  |  |  |  |  | Total cost/trial | 5399 |  | 16197 |  |  |
|  |  |  |  |  |  | Grand total of OFTs | 33459 |  |  |

## 8.	Technology Refinement during 2016-17 : NIL

| S. No. | Crop/ enterprise | Prioritized problem | Title of intervention | Technology options | Source of Technology | Name of critical input | Qty per trial | Cost per trial | No. of trials | Total cost for the intervention (Rs.) | Parameters to be studied | Team members |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 8.1 |  |  |  | 1 |  |  |  |  |  |  |  |  |
|  |  |  |  | 2 |  |  |  |  |  |  |  |  |
|  |  |  |  | 3 |  |  |  |  |  |  |  |  |
|  |  |  |  | 4 |  |  |  |  |  |  |  |  |
| 8.2 |  |  |  | 1 |  |  |  |  |  |  |  |  |
|  |  |  |  | 2 |  |  |  |  |  |  |  |  |
|  |  |  |  | 3 |  |  |  |  |  |  |  |  |
| 8.3 |  |  |  | 1 |  |  |  |  |  |  |  |  |
|  |  |  |  | 2 |  |  |  |  |  |  |  |  |
|  |  |  |  | 3 |  |  |  |  |  |  |  |  |

9.	Frontline Demonstrations during 2016-17

| S. No. | Category | Crop/ enterprise | Prioritized problem | Technology to be demonstrated | Specify Hybrid or Variety | Name of the Hybrid or Variety | Source of Technology | Name of critical input | Qty per Demo | Cost per Demo | No. of Demo | Total cost for the Demo (Rs.) | Parameters to be studied | Team members |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 9.1 | Cereals | Maize (Irrigated condition) | Low productivity due to less use of macro & non use of secondary and micro nutrients High incidence of stem borer High incidence of Turcicum leaf blight High incidence of weed Health problems during threshing & winnowing | FLD on Integrated Crop Management Functional clothing kits | Hybrid | CP-818 and Super 900-M gold | UAS, Dharwad | Farmers’ Contribution | 20 (8 ha) |  | Weed intensity/Sq. mtr % of incidence of TLB No. of stem borers/ Sq. mtr. Cob length No of grains/cob Seed weight (100 nos) Yield (Qtl/ha) | Mr. N.H.Bhandi, Scientist (Soil Science), Mr. S.K.Mudlapur, Scientist (Plant Protection), Mr. V.D.Vaikunthe, Scientist (Agronomy), & Mrs. Sudha S.R., Scientist (Home Science) |
|  |  |  |  |  |  |  |  | Seeds | 5 Kg | 650 |  | 13000 |  |  |
|  |  |  |  |  |  |  |  | Urea | 125 Kg | 875 |  | 17500 |  |  |
|  |  |  |  |  |  |  |  | DAP | 67 Kg | 1809 |  | 36180 |  |  |
|  |  |  |  |  |  |  |  | MOP | 46 Kg | 731 |  | 14620 |  |  |
|  |  |  |  |  |  |  |  | FC Total | 4065 |  | 81300 |  |  |
|  |  |  |  |  |  |  |  | KVK contribution |  |  |  |  |
|  |  |  |  |  |  |  |  | ZnSO4 | 10 Kg | 450 |  |  |  |  |
|  |  |  |  |  |  |  |  | Attrazine | 500 gm | 160 |  |  |  |  |
|  |  |  |  |  |  |  |  | Alachlor | 1 ltr | 460 |  |  |  |  |
|  |  |  |  |  |  |  |  | Mancozeb | 500 gm | 180 |  |  |  |  |
|  |  |  |  |  |  |  |  | Flubendimide | 20 ml | 300 |  |  |  |  |
|  |  |  |  |  |  |  |  | DDVP | 250 ml | 150 |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Total | 1700 |  | 34000 |  |  |
|  |  |  |  |  |  |  |  | Protective clothing | 10 Nos. | 2000 |  | 2000 |  |  |
|  |  |  |  |  |  |  |  | KVK’s Contribn. Total | 1025 |  | 36000 |  |  |
|  |  |  |  |  |  |  |  | Grand Total (FC + KVK-C) | 5090 |  | 117300 |  |  |
|  |  | Maize + Redgram | Non-profitability due to mono cropping | FLD on Maize + Redgram (5:1) intercropping system | Variety | TS-3R/ GRG-811 | UAS, Dharwad & UAS, Raichur | Farmers’ Contribution |  | 10 (4 ha) |  | Duration of the crop Grain Yield (Qtl/ha) Net Profitability (Rs./ha) | Mr. V.D.Vaikunthe, Scientist (Agronomy) & Mr. S.K.Mudlapur, Scientist (Plant Protection), |
|  |  |  |  |  |  |  |  | DAP | 54 Kg | 1458 |  |  |  |  |
|  |  |  |  |  |  |  |  | Urea | 76 Kg | 532 |  |  |  |  |
|  |  |  |  |  |  |  |  | MOP | 16 Kg | 272 |  |  |  |  |
|  |  |  |  |  |  |  |  | ZnSO4 | 10 Kg | 450 |  |  |  |  |
|  |  |  |  |  |  |  |  | FC Total | 2712 |  | 27120 |  |  |
|  |  |  |  |  |  |  |  | KVK Contribution |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Redgram Seeds (TS-3R/ GRG-811) | 3 Kg | 375 |  |  |  |  |
|  |  |  |  |  |  |  |  | Carboxin | 10 gm | 20 |  |  |  |  |
|  |  |  |  |  |  |  |  | CaCl2 | 60 gm | 10 |  |  |  |  |
|  |  |  |  |  |  |  |  | 13-0-45 | 1 Kg | 130 |  |  |  |  |
|  |  |  |  |  |  |  |  | Emamectin benzoate | 50 gm | 350 |  |  |  |  |
|  |  |  |  |  |  |  |  | Spinosad | 30 ml | 500 |  |  |  |  |
|  |  |  |  |  |  |  |  | Pulse magic | 2 Kg | 300 |  |  |  |  |
|  |  |  |  |  |  |  |  | KVK’s Contribn. Total |  | 1685 |  | 16850 |  |  |
|  |  |  |  |  |  |  |  | Grand Total (FC + KVK-C) |  | 4397 |  | 43970 |  |  |
|  |  | Wheat | Low productivity due to imbalanced nutrition in Malaprabha Command area and incidence of rust & stem borer Drudgery in harvesting | Integrated Crop Management | Variety | UAS-304 | UAS, Dharwad | Farmers’ Contribution | 5 (2 ha) |  | % incidence of rust & stem borer Grain yield (Qtl/ha) | Mr. S.K.Mudlapur, Scientist (Plant Protection), Mr. N.H.Bhandi, Scientist (Soil Science), Mr. V.D.Vaikunthe, Scientist (Agronomy) & Mrs. Sudha S.R., Scientist (Home Science) |
|  |  |  |  |  |  |  |  | Seeds | 60 Kg | 1500 |  |  |  |  |
|  |  |  |  |  |  |  |  | DAP | 76 Kg | 1292 |  |  |  |  |
|  |  |  |  |  |  |  |  | Urea | 68 Kg | 476 |  |  |  |  |
|  |  |  |  |  |  |  |  | MOP | 33 Kg | 561 |  |  |  |  |
|  |  |  |  |  |  |  |  | 2, 4-D (80%) | 1 Kg | 300 |  |  |  |  |
|  |  |  |  |  |  |  |  | FC Total | 4129 |  | 20645 |  |  |
|  |  |  |  |  |  |  |  | KVK Contribution |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Carboxin | 150 gm | 300 |  |  |  |  |
|  |  |  |  |  |  |  |  | Phosphomidon | 250 ml | 140 |  |  |  |  |
|  |  |  |  |  |  |  |  | Propiconazole | 250 ml | 340 |  |  |  |  |
|  |  |  |  |  |  |  |  | 19-19-19 WS | 1 Kg | 100 |  |  |  |  |
|  |  |  |  |  |  |  |  | KVK’s Contribn. Total | 880 |  | 4400 |  |  |
|  |  |  |  |  |  |  |  | Grand Total (FC + KVK-C) |  | 25045 |  |  |
|  |  | Rabi sorghum | Low productivity of existing M 35-1 variety Moisture stress Deficiency of micro nutrients Lack of value addition | Demonstration of SPV-2217 & BJV-44 varieties | Variety | SPV-2217 & BJV-44 | UAS, Dharwad | Farmers’ Contribution | 20 (8 ha) |  | Height of the plant Duration % of lodging Grain yield (Qtl/ha) Organoleptic evaluation of Roti | Mr. V.D.Vaikunthe, Scientist (Agronomy), Mr. S.K.Mudlapur, Scientist (Plant Protection), & Mrs. Sudha S.R., Scientist (Home Science) |
|  |  |  |  |  |  |  |  | DAP | 25 Kg | 675 |  |  |  |  |
|  |  |  |  |  |  |  |  | Urea | 25 Kg | 175 |  |  |  |  |
|  |  |  |  |  |  |  |  | ZnSO4 | 5 Kg | 225 |  |  |  |  |
|  |  |  |  |  |  |  |  |  | 1075 |  | 21500 |  |  |
|  |  |  |  |  |  |  |  | KVK Contribution |  |  |  |  |
|  |  |  |  |  |  |  |  | Seeds (SPV-2217 & BJV-44) | 3 Kg | 135 |  |  |  |  |
|  |  |  |  |  |  |  |  | CaCl2 | 100 gm | 12 |  |  |  |  |
|  |  |  |  |  |  |  |  | Azospirillum | 200 gm | 15 |  |  |  |  |
|  |  |  |  |  |  |  |  | Sulphur | 15 gm | 5 |  |  |  |  |
|  |  |  |  |  |  |  |  | Zinc Sulphate | 5 Kg | 225 |  |  |  |  |
|  |  |  |  |  |  |  |  | KVK’s Contribn. Total | 392 |  | 7840 |  |  |
|  |  |  |  |  |  |  |  | Grand Total (FC + KVK-C) |  | 1467 |  | 29340 |  |  |
| 9.2 | Millets | Foxtail millet | Low productivity due to cultivation of local variety Lack of value addition | Demonstration of DHFt-109-3 variety | Variety | DHFt-109-3 | UAS, Dharwad | Farmers’ Contribution |  |  | 10 (4 ha) |  | Height of the plant Duration Grain yield (Qtl/ha) Economics of marketing of raw grains and value added product | Mr. V.D.Vaikunthe, Scientist (Agronomy), & Mrs. Sudha S.R., Scientist (Home Science) |
|  |  |  |  |  |  |  |  | DAP | 13 Kg | 351 |  |  |  |  |
|  |  |  |  |  |  |  |  | Urea | 22 Kg | 154 |  |  |  |  |
|  |  |  |  |  |  |  |  | MOP | 25 Kg | 425 |  |  |  |  |
|  |  |  |  |  |  |  |  | FC Total | 930 |  | 9300 |  |  |
|  |  |  |  |  |  |  |  | KVK Contribution |  |  |  |  |
|  |  |  |  |  |  |  |  | Seeds (DHFt-109-3) | 3 Kg | 120 |  | 1200 |  |  |
|  |  |  |  |  |  |  |  | Weighing balance | 1 No. | 5000 |  |  |  |  |
|  |  |  |  |  |  |  |  | Sealing machine | 1 No. | 3000 |  |  |  |  |
|  |  |  |  |  |  |  |  | Packing, colour printing, product & nutrition label | 1000 Nos. | 5000 |  |  |  |  |
|  |  |  |  |  |  |  |  | Raw materials (Spices) |  | 1000 |  | 14000 |  |  |
|  |  |  |  |  |  |  |  | KVK’s Contribn. Total |  | 15200 |  |  |
|  |  |  |  |  |  |  |  | Grand Total (FC + KVK-C) |  | 24500 |  |  |
| 9.3 | Oilseeds |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Summer Groundnut | Low productivity in existing TMV-2 variety High incidence of collar rot Imbalanced nutrition Incidence of leaf minor Incidence of weed | FLD on ICM in DH-101 variety | Variety | DH-101 | UAS, Dharwad | Farmers’ Contribution | 10 (4 ha) |  | Incidence of collar rot Incidence of leaf minor Intensity of weed Pod yield (Qtl/ha) | Mr. V.D.Vaikunthe, Scientist (Agronomy), Mr. N.H.Bhandi, Scientist (Soil Science) , & Mr. S.K.Mudlapur, Scientist (Plant Protection) |
|  |  |  |  |  |  |  |  | Seeds (Pods) | 40 Kg | 2800 |  |  |  |  |
|  |  |  |  |  |  |  |  | DAP | 76 Kg | 2052 |  |  |  |  |
|  |  |  |  |  |  |  |  | MOP | 16 Kg | 272 |  |  |  |  |
|  |  |  |  |  |  |  |  | Profenophos | 200 ml | 140 |  |  |  |  |
|  |  |  |  |  |  |  |  | Nimbecidine | 200 ml | 95 |  |  |  |  |
|  |  |  |  |  |  |  |  | Total |  | 5359 |  | 53590 |  |  |
|  |  |  |  |  |  |  |  | KVK Contribution |  |  |  |  |
|  |  |  |  |  |  |  |  | Pods (DH-101) | 40 Kg | 3200 |  |  |  |  |
|  |  |  |  |  |  |  |  | Rhizobium | 1 Kg | 60 |  |  |  |  |
|  |  |  |  |  |  |  |  | PSB | 1 Kg | 60 |  |  |  |  |
|  |  |  |  |  |  |  |  | Trichoderma | 500 gm | 50 |  |  |  |  |
|  |  |  |  |  |  |  |  | ZnSO4 | 10 Kg | 450 |  |  |  |  |
|  |  |  |  |  |  |  |  | Gypsum | 200 Kg | 750 |  |  |  |  |
|  |  |  |  |  |  |  |  | Pendimethalin | 500 ml | 250 |  |  |  |  |
|  |  |  |  |  |  |  |  | Profenophos | 250 ml | 150 |  |  |  |  |
|  |  |  |  |  |  |  |  | KVK’s Contribn. Total | 4970 |  | 49700 |  |  |
|  |  |  |  |  |  |  |  | Grand Total (FC + KVK-C) | 10329 |  | 103290 |  |  |
| 9.4 | Pulses | Green gram | Moisture stress in critical stages High incidence of pod borer Incidence of powdery mildew in late sown situation Decreased productivity due to repeated use of existing shining Moong variety | ICM in DGGV-2 | Variety | DGGV-2 | UAS, Dharwad | Farmers’ Contribution |  |  | Plant height No. of pods per plant Seed weight (100no) Percentage of disease incidence Pod borer incidence Time , cost incurred & mandays required for cleaning, grading of grains Yield(Qtl/ha) & Market price for cleaned & graded grains | Mr. V.D.Vaikunthe, Scientist (Agronomy), Mr. S.K.Mudlapur, Scientist (Plant Protection), & Mrs. Sudha S.R., Scientist (Home Science) |
|  |  |  |  |  |  |  |  | DAP | 25 Kg | 675 | 15 (6 ha) |  |  |  |
|  |  |  |  |  |  |  |  | Gypsum | 50 Kg | 188 |  |  |  |  |
|  |  |  |  |  |  |  |  | FC Total | 863 |  | 12945 |  |  |
|  |  |  |  |  |  |  |  | KVK Contribution |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Seeds (DGGV-2) | 5 Kg | 500 |  |  |  |  |
|  |  |  |  |  |  |  |  | Trichoderma | 50 gm | 5 |  |  |  |  |
|  |  |  |  |  |  |  |  | Rhizobium | 200 gm | 15 |  |  |  |  |
|  |  |  |  |  |  |  |  | PSB | 200 gm | 15 |  |  |  |  |
|  |  |  |  |  |  |  |  | CaCl2 | 100 gm | 12 |  |  |  |  |
|  |  |  |  |  |  |  |  | 13-0-45 | 1 Kg | 130 |  |  |  |  |
|  |  |  |  |  |  |  |  | Pulse magic | 2 Kg | 300 |  |  |  |  |
|  |  |  |  |  |  |  |  | Lambda Cyhalothrin | 250 ml | 155 |  |  |  |  |
|  |  |  |  |  |  |  |  | Propiconazole | 250 ml | 340 |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | 1472 |  | 22080 |  |  |
|  |  |  |  |  |  |  |  | Bund former | 2 nos | 3000 |  |  |  |  |
|  |  |  |  |  |  |  |  | Cycle weeder | 4 nos | 6000 |  |  |  |  |
|  |  |  |  |  |  |  |  | Spiral Separator | 2 nos | 16000 |  | 25000 |  |  |
|  |  |  |  |  |  |  |  | KVK’s Contribn. Total | 15166 |  | 47080 |  |  |
|  |  |  |  |  |  |  |  | Grand Total (FC + KVK-C) | 17902 |  | 60025 |  |  |
| 9.5 | Commercial crops |  |  |  |  |  |  |  |  |  |  |
| 9.6 | Horticultural crops | Onion | Low productivity in existing variety Low keeping quality bulbs in existing variety High incidence of thrips & purple blotch High incidence of weeds Lack of knowledge on seed production technology | ICM in Arka Kalyan variety | Variety | Arka Kalyan | IIHR, Bangalore | Farmers’ Contribution |  |  | Bulb weight Bulb diameter % of disease index Yield (Qtl/ha) | Mr. K.T.Patil Scientist (Horticulture) & Mr. S.K.Mudlapur, Scientist (Plant Protection) |
|  |  |  |  |  |  |  |  | Urea | 70 | 490 | 35 (14 ha) |  |  |  |
|  |  |  |  |  |  |  |  | DAP | 75 | 2025 |  |  |  |  |
|  |  |  |  |  |  |  |  | MOP | 84 | 1411 |  |  |  |  |
|  |  |  |  |  |  |  |  | 13:00:45 | 0.8 | 100 |  |  |  |  |
|  |  |  |  |  |  |  |  | Quizalofop ethyl | 450 ml | 820 |  |  |  |  |
|  |  |  |  |  |  |  |  | FC Total | 4846 |  | 169610 |  |  |
|  |  |  |  |  |  |  |  | KVK Contribution |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Seeds (Arka Kalyan) | 1 Kg | 1200 |  |  |  |  |
|  |  |  |  |  |  |  |  | KVK’s Contribn. Total | 1200 |  | 42000 |  |  |
|  |  |  |  |  |  |  |  | Grand Total (FC + KVK) | 6046 |  | 212210 |  |  |
|  |  | Chilli | Low productivity due to non-practice of ICM technologies | ICM technology | Variety | Byadagi | UHS, Bagalkot | Farmers’ Contribution | 5 (2 ha) |  | Yield (Qtl/ha) % of leaf spot, powdery mildew No. of thrips & mites/leaf No. of pod borers / plant | Mr. K.T.Patil Scientist (Horticulture) & Mr. S.K.Mudlapur, Scientist (Plant Protection) |
|  |  |  |  |  |  |  |  | Urea | 76 Kg | 532 |  |  |  |  |
|  |  |  |  |  |  |  |  | DAP | 54 Kg | 1450 |  |  |  |  |
|  |  |  |  |  |  |  |  | MOP | 33 Kg | 561 |  |  |  |  |
|  |  |  |  |  |  |  |  | FC Total | 2543 |  | 12715 |  |  |
|  |  |  |  |  |  |  |  | KVK Contribution |  |  |  |  |
|  |  |  |  |  |  |  |  | Vegetable special | 2 Kg | 500 |  |  |  |  |
|  |  |  |  |  |  |  |  | 19-19-19 | 2 Kg | 250 |  |  |  |  |
|  |  |  |  |  |  |  |  | 13-00-45 | 2 Kg | 250 |  |  |  |  |
|  |  |  |  |  |  |  |  | Total | 1000 |  | 5000 |  |  |
|  |  |  |  |  |  |  |  | Grand Total (FC + KVK-C) | 3543 |  | 17715 |  |  |
|  |  | Ashwaganda | Unsustainable income from existing rabi crops | FLD on Ashwaganda | Variety | Jawahar | UHS, Bagalkot | Farmers’ Contribution |  |  | Yield Comparative cost & benefit analysis with other rabi crops in rainfed condition | Mr. K.T.Patil Scientist (Horticulture), Mr. S.K.Mudlapur, Scientist (Plant Protection) & Mr. S.H.Adapur Scientist (Ag. Extension) |
|  |  |  |  |  |  |  |  | DAP | 14 Kg | 250 | 5 (2 ha) |  |  |  |
|  |  |  |  |  |  |  |  | MOP | 40 Kg | 672 |  |  |  |  |
|  |  |  |  |  |  |  |  | Vermicompost | 2 Qtl | 1000 |  |  |  |  |
|  |  |  |  |  |  |  |  | FC Total | 1922 |  | 9610 |  |  |
|  |  |  |  |  |  |  |  | KVK Contribution |  |  |  |  |
|  |  |  |  |  |  |  |  | Seeds (Jawahar) | 4 Kg | 600 |  | 3000 |  |  |
|  |  |  |  |  |  |  |  | Grand Total (FC + KVK-C) | 2522 |  | 12610 |  |  |
|  |  | Fruit orchard | Drought prone rainfed agriculture No crop diversification Low yield in Red & Black soil | Dryland horticulture in Red soil (Mango), intercrop with spreading groundnut and in Black Soil Tamarind Intercropped with Greengram & Bengalgram | Variety | Alphanso in Mango under Red soil | UHS, Bagalkot | Mango grafts @ Rs.80/graft | 50 Nos. | 4000 | 10 (4 ha) | 40000 | Growth parameters | Mr. K.T.Patil Scientist (Horticulture) & Mr. S.K.Mudlapur, Scientist (Plant Protection) |
|  |  |  |  |  |  |  |  | Tamarind grafts @ Rs.60/graft | 50 Nos. | 3000 | 5 (2 ha) | 15000 |  |  |
|  |  |  |  |  |  | PKM-1 Tamarind under black soil |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Total |  |  |  | 55000 |  |  |
| 9.7 | Livestock |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Cattle | Cow/ She Buffaloe | Low productivity of milk | Fodder & Azolla Production Units : Cultivation & feeding of perennial grasses and other forage crops and Azolla as a feed supplement to milching animals |  |  |  | Farmers’ Contribution for fodder & Azolla production |  |  | Growth & yield parameters of all fodders Milk yield (per lactation) Fat percentage & SNF content | Dr. B.M.Murgod Programme Assistant (Animal Husbandry) |
|  |  |  |  |  |  |  |  | Urea | 25 Kg | 225 | 10 Nos. |  |  |  |
|  |  |  |  |  |  |  |  | DAP | 15 Kg | 375 |  |  |  |  |
|  |  |  |  |  |  |  |  | MOP | 10 Kg | 170 |  |  |  |  |
|  |  |  |  |  |  |  |  | Excavation of pit (12x4x1) |  | 250 |  |  |  |  |
|  |  |  |  |  |  |  |  | Micronutrient mixture | 1 Kg | 200 |  |  |  |  |
|  |  |  |  |  |  |  |  | FC Total |  | 1220 |  | 12200 |  |  |
|  |  |  |  |  |  |  |  | KVK Contribution |  |  |  |  |  |  |
|  |  |  |  |  | Grass | Hybrid Napier – DHN-6 | Indian Grassland and Fodder Research Institute, RRS, Dharwad | Slips | 436 Nos. | 436 |  |  |  |  |
|  |  |  |  |  | Grass | Multicut Jowar – COFS-29 |  | Seeds | 200 gm | 80 |  |  |  |  |
|  |  |  |  |  | Grass | Guinea grass and grazing guinea grass |  | Slips | 872 Nos. | 436 |  |  |  |  |
|  |  |  |  |  | Grass | Rhodes Grass |  | Slips | 1452 Nos. | 726 |  |  |  |  |
|  |  |  |  |  | Grass | Signal Grass |  | Slips | 1452 Nos. | 726 |  |  |  |  |
|  |  |  |  |  | Dicot forage crop | Lucerne and Hedge Lucerne |  | Seeds | 100 gm | 80 |  |  |  |  |
|  |  |  |  |  |  | Stylo-santhes Hamata |  | Seeds | 60 gm | 18 |  |  |  |  |
|  |  |  |  |  |  |  |  | Azolla culture | 1 Kg | 100 |  |  |  |  |
|  |  |  |  |  |  |  |  | Poly Tarpaulin (HDPE 200 GSM) sheets (12' x 9') | 1 | 1100 |  |  |  |  |
|  |  |  |  |  |  |  |  | KVK’s Contribn. Total | 4002 |  | 40020 |  |  |
|  |  |  |  |  |  |  |  | Grand Total (FC + KVK-C) | 5222 |  | 52220 |  |  |
|  | Small ruminants | Goat kids | Low body weight gain in kids due to mineral deficiency & worm infestation | Giving of mineral lick block & oral drench of Ivermectin liquid | - | - | Taminlnadu Veterinary & Animal Science University, Chennai and KVK, Namakkal, Tamilnadu state and KVAFSU, Bidar | Dicalcium Phosphate | 676 gm | 120 | 20 Nos. | 6320 | Body weight gain | Dr. B.M.Murgod Programme Assistant (Animal Husbandry) |
|  |  |  |  |  |  |  |  | Sodium Phosphate | 169 gm | 36 |  |  |  |  |
|  |  |  |  |  |  |  |  | Calcium carbonate | 74 gm | 24 |  |  |  |  |
|  |  |  |  |  |  |  |  | Manganese sulphate | 20 ml | 6 |  |  |  |  |
|  |  |  |  |  |  |  |  | Ferrous sulphate | 33 mg | 12 |  |  |  |  |
|  |  |  |  |  |  |  |  | Zinc oxide | 16 mg | 12 |  |  |  |  |
|  |  |  |  |  |  |  |  | Copper sulphate | 5 mg | 12 |  |  |  |  |
|  |  |  |  |  |  |  |  | Cobalt chloride | 4 mg | 12 |  |  |  |  |
|  |  |  |  |  |  |  |  | Potassium lodide | 3 mg | 9 |  |  |  |  |
|  |  |  |  |  |  |  |  | Ivermectin liquid | 100 ml | 73 |  |  |  |  |
|  |  |  |  |  |  |  |  | Total |  | 316 |  | 6320 |  |  |
| 9.8 | Fisheries |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9.9 | Others | Field crops (Rabi Sorghum) | Less soil fertility due to non-addition of organic manures | Soil fertility enhancement through DDemonstration of vermicompost unit | Variety | M 35-1 | UAS, Dharwad | Farmers’ Contribution | 5 |  | Quantity of vermicompost, Azolla, vermi wash & Jeevamrutha produced Effect on moisture holding capacity Growth and yield parameters of Rabi Sorghum grown using organic inputs during rabi season of 2016-17 | Mr. S.K.Mudlapur, Scientist (Plant Protection) & Mr. N.H.Bhandi, Scientist (Soil Science) |
|  |  |  |  |  |  |  |  | Wooden poles size 10 ft x 12 inch Girth | 8 No | 2400 |  |  |  |  |
|  |  |  |  |  |  |  |  | Wooden poles Size: 14 ft x 8 Girth | 10 No | 2250 |  |  |  |  |
|  |  |  |  |  |  |  |  | Sieve machine | 1 | 1200 |  |  |  |  |
|  |  |  |  |  |  |  |  | FYM | 1 ton | 3500 |  |  |  |  |
|  |  |  |  |  |  |  |  | FC Total | 9350 |  | 46750 |  |  |
|  |  |  |  |  |  |  |  | KVK Contribution |  |  |  |  |
|  |  |  |  |  |  |  |  | Cement bricks @ 25/brick | 200 | 5000 |  | 52600 |  |  |
|  |  |  |  |  |  |  |  | Earthworms @ 400 | 4 Kg | 1600 |  |  |  |  |
|  |  |  |  | ii)Demonstration of Jeevamrutha & GhanaJeevamrutha preparation unit |  |  | UAS, Dharwad | Cement Tank (4 ft height x 3 ft diameter) | 1 No. | 1200 |  |  |  |  |
|  |  |  |  | (iii)Demonstratio n of Azolla unit (Vermicmpost is blended with Azolla culture to enhance Nitrogen content in vermicompost. Hence Azolla preparation is included as a demonstration component) |  |  | UAS, Dharwad | Cement Tank (1 ft height x 6 ft diameter) | 1 No. | 2500 |  |  |  |  |
|  |  |  |  |  |  |  |  | Azolla culture | 1 kg | 100 |  |  |  |  |
|  |  |  |  |  |  |  |  | Compost culture | 2 Kg | 120 |  |  |  |  |
|  |  |  |  |  |  |  |  | KVK’s Contribn. Total | 10520 |  |  |  |  |
|  |  |  |  |  |  |  |  | Grand Total (FC + KVK-C) | 19870 |  | 99350 |  |  |
|  | Others | Optimum development of infants | Delayed motor and mental development in infants and children | Stimulation kit for psychomotor development in infants | - | - | RHSc UAS, Dharwad | Stimulatory toy kit | 1 | 4000 | 5 | 20000 | Mental Development Index Psychomotor Development Index | Mrs. Sudha S.R., Scientist (Home Science) |
|  |  | Envirofit chulha | Excess smoke in kitchen | Demonstration of Envirofit chulha | - | - | Colarado University Engines & Energy conversion laboratory | Envirofit chulha | 1 | 2000 | 5 | 10000 | Time required for cooking Quantity of fuel required for cooking Smoke in kitchen as felt by farm women | Mrs. Sudha S.R., Scientist (Home Science) |
|  |  | Value addition & marketing of milk product | Lack of value addition Drudgery in churning butter | Demonstration of value addition of milk | - | - | - | Butter churner | 1 | 3000 | 3 | 39000 | Economics of selling milk products and milk | Mrs. Sudha S.R., Scientist (Home Science) |
|  |  |  |  |  |  |  |  | Sealing machine | 1 | 3000 |  |  |  |  |
|  |  |  |  |  |  |  |  | Packaging materials of different sizes | 1000 Nos. | 2000 |  |  |  |  |
|  |  |  |  |  |  |  |  | Weighing machine | 1 | 5000 |  |  |  |  |
|  |  | Value addition & marketing of Tamarind product | Lack of value addition Lack of knowledge on packing and marketing Less price for the unprocessed produce | Preparation and packing of Toffee and lollypop | - | - | MGRI, Wardha,Maharastra state | Sealing machine | 1 | 3000 | 1 | 9000 | Economics of selling raw Tamarind and value added Tamarind products | Mrs. Sudha S.R., Scientist (Home Science) |
|  |  |  |  |  |  |  |  | Packing materials | 1 Kg | 1000 |  |  |  |  |
|  |  |  |  |  |  |  |  | Weighing balance | 1 | 5000 |  |  |  |  |
| Grand Total of FLDs |  |  | 194 | 459010 |  |  |

10	Training for Farmers/ Farm Women during 2016-17

| S.No. | Thematic area | Crop / Enterprise | Major problem | Related field intervention (OFT/FLD)* | Training Course Title** | No. of Courses | Expected No. of participants | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 10.1 | Crop Production | Maize | Low yield due to imbalanced nutrition Incidence of stem borer | FLD | ICM in Maize & inter-cropping systems | 2 | 40 | Mr. V.D.Vaikunthe, Scientist (Agronomy), Mr. S.K.Mudlapur Scientist (Plant Protection), & Mr. N.H.Bhandi, Scientist (Soil Science) |
|  |  | Spreading Groundnut | Low productivity due to imbalanced nutrition & pest incidence | - | ICM in Spreading Groundnut | 1 | 30 | Mr. V.D.Vaikunthe, Scientist (Agronomy) & Mr. N.H.Bhandi, Scientist (Soil Science) |
|  |  | Redgram | Introduction of Redgram based intercropping systems to enhance the profitability in comparison with mono cropping of spreading groundnut | OFT | Training on Redgram based inter cropping systems | 1 | 15 | Mr. V.D.Vaikunthe, Scientist (Agronomy) |
|  |  | Sunflower | Low productivity due to imbalanced nutrition and high incidence of pest and disease | - | ICM practices | 1 | 25 | Mr. V.D.Vaikunthe, Scientist (Agronomy) & Mr. N.H.Bhandi, Scientist (Soil Science) & Mr. S.K.Mudlapur, Scientist (Plant Protection) |
|  |  | Rabi Sorghum | Low productivity of existing M 35-1 variety with moisture stress problem | FLD | ICM practices | 2 | 50 | Mr. V.D.Vaikunthe, Scientist (Agronomy) & Mr. N.H.Bhandi, Scientist (Soil Science) & Mr. S.K.Mudlapur, Scientist (Plant Protection |
|  |  | Rabi Sorghum | Low productivity of existing M 35-1 variety under sand mulched condition | OFT | ICM practices in sand mulched area | 1 | 25 | Mr. V.D.Vaikunthe, Scientist (Agronomy) & Mr. N.H.Bhandi, Scientist (Soil Science) |
|  |  | Bengalgram | Low productivity due to high incidence of pest and disease | - | ICM practices | 2 | 50 | Mr. V.D.Vaikunthe, Scientist (Agronomy), Mr. S.K.Mudlapur, Scientist (Plant Protection) & Mr. N.H.Bhandi, Scientist (Soil Science) |
|  |  | Groundnut (Summer) | Low productivity in existing TMV-2 variety | FLD | ICM practices | 1 | 25 | Mr. V.D.Vaikunthe, Scientist (Agronomy), Mr. S.K.Mudlapur, Scientist (Plant Protection) & Mr. N.H.Bhandi, Scientist (Soil Science) |
| 10.2 | Horticulture Production | Onion | High incidence of weed High incidence of purple blotch Imbalance nutrition | FLD on ICM in Onion | ICM practices in onion Seed production technologies | 1 | 15 | Mr. K.T.Patil, Scientist (Horticulture), Mr. S.K.Mudlapur, Scientist (Plant Protection) & Mr. N.H.Bhandi, Scientist (Soil Science) |
|  |  | Chilli | Low yield in Byadagi variety High incidence of Murda High incidence of powdery mildew Flower & fruits drops | FLD on ICM in Chilli | ICM practices in Chilli | 1 | 30 | Mr. K.T.Patil, Scientist (Horticulture), Mr. S.K.Mudlapur, Scientist (Plant Protection) & Mr. N.H.Bhandi, Scientist (Soil Science) |
|  |  | Ashwagandha | Unsustainable income from existing rabi crops | FLD on introduction of Jawahar variety of Ashwagandha | ICM practices in Ashwagandha | 1 | 30 | Mr. K.T.Patil, Scientist (Horticulture) & Mr. S.K.Mudlapur, Scientist (Plant Protection) |
|  |  | Fruit crops | No crop diversification Low yield in red & black soil | FLD on dryland horticulture technologies in red and black soil | Dryland horticulture technologies | 1 | 30 | Mr. K.T.Patil, Scientist (Horticulture) & Mr. S.K.Mudlapur, Scientist (Plant Protection) |
| 10.3 | Livestock Production | Dairy animals | Low productivity of milk due to Non cultivation of fodder crops Incidence of ecto-endo parasites | FLD on fodder production | Promotion of fodder production technologies for getting higher milk productivity in dairy animals Management of ecto-endo parasites & mastitis in CB Cows | 1 | 30 | Dr. B.M.Murgod Programme Assistant (Animal Husbandry) |
|  |  |  | Imbalanced nutrition | FLD on Azolla | Cultivation and feeding of Azolla for balanced nutrition | 1 | 30 | Dr. B.M.Murgod Programme Assistant (Animal Husbandry) |
| 10.4 | Home Science | Enterprise | Health problems due to excess smoke in kitchen | FLD on chulhas | Importance of using fuel & less smoke producing chulhas | 5 | 120 | Mrs. Sudha S.R., Scientist (Home Science) |
|  |  | Existing SHGs | Less knowledge about IGAs | - | Multiple IGAs through SHGs | 5 | 150 | Mrs. Sudha S.R., Scientist (Home Science) |
|  |  | Maize | Health problems during threshing & winnowing | FLD on ICM practices | Functional clothing for agricultural operations in Maize | 2 | 50 | Mrs. Sudha S.R., Scientist (Home Science) |
|  |  | Bengalgram | Drudgery in harvesting of Bengalgram | - | Awareness on drudgery reduction measures during harvesting of Bengalgram | 2 | 30 | Mrs. Sudha S.R., Scientist (Home Science) |
|  |  | Wheat | Drudgery in harvesting of Wheat | FLD on ICM practices | Usage of improved sickle in reducing drudgery of farmwomen in harvesting | 1 | 10 | Mrs. Sudha S.R., Scientist (Home Science) |
| 10.5 | Plant Protection | Greengram | High incidence of pest & disease | FLD | Training on pod borer & powdery mildew management | 2 | 45 | Mr. S.K.Mudlapur, Scientist (Plant Protection) |
|  |  | Bt. Cotton | High incidence of pest & disease | - | Training on sucking pest & disease management | 1 | 25 | Mr. S.K.Mudlapur, Scientist (Plant Protection) |
|  |  | Sunflower | High incidence of pest & disease | - | Management of hairy caterpillar & powdery mildew | 1 | 25 | Mr. S.K.Mudlapur, Scientist (Plant Protection) |
|  |  | Bengalgram | High incidence of pests | - | Management of pod borer | 2 | 50 | Mr. S.K.Mudlapur, Scientist (Plant Protection) |
|  |  | Wheat | High incidence of pest & disease | FLD | Management of stem borer & rust | 1 | 25 | Mr. S.K.Mudlapur, Scientist (Plant Protection) |
|  |  | Groundnut (Summer) | High incidence of pest & disease | FLD | Management of collar rot & leaf minor | 1 | 30 | Mr. S.K.Mudlapur, Scientist (Plant Protection) |
| 10.6 | Production of Inputs at Site | All field crops | Decreased soil fertility due to non use of organic manure | FLD | Training on organic input preparation & soil fertility management | 3 | 75 | Mr. S.K.Mudlapur, Scientist (Plant Protection) & Mr. N.H.Bhandi, Scientist (Soil Science) |
| 10.7 | Soil Health and Fertility | All crops | Low soil fertility | FLD | Soil fertility management | 5 | 125 | Mr. N.H.Bhandi, Scientist (Soil Science) |
| 10.8 | PHT and value addition | Bengalgram / Greengram | Lack of value addition & less market price | FLD on ICM practices | Grading of Greengram / Bengalgram for better market prices | 2 | 60 | Mr. V.D.Vaikunthe, Scientist (Agronomy) & Mrs. Sudha S.R., Scientist (Home Science) |
|  |  | Sorghum | Lack of value addition | FLD on Sorghum | Incorporation of Sorghum in daily diet using value added Sorghum products | 3 | 90 | Mrs. Sudha S.R., Scientist (Home Science) |
|  |  | Millets | Lack of consumption of millets | FLD on foxtail millet & value addition | Importance & value addition of millets | 4 | 120 | Mrs. Sudha S.R., Scientist (Home Science) |
| 10.9 | Capacity Building Group Dynamics | FIG/ CIG | Lack of mobilization | - | Orientation on FIG/CIG, capacity building and management | 30 | 600 | Mr. S.H.Adapur Scientist (Ag. Extension) |
|  |  | FPO | Lack of knowledge on FPO formation and management | - | Orientation on FPO formation and management | 1 | 30 | Mr. S.H.Adapur Scientist (Ag. Extension) |
| 10.10 | Farm Mechanization | Bengalgram |  | OFT | Training on mechanized harvesting | 1 | 25 | Mr. V.D.Vaikunthe, Scientist (Agronomy) |
| 10.11 | Fisheries Production Technologies |  |  |  |  |  |  |  |
| 10.12 | Mushroom production |  |  |  |  |  |  |  |
| 10.13 | Agro forestry |  |  |  |  |  |  |  |
| 10.14 | Bee Keeping |  |  |  |  |  |  |  |
| 10.15 | Sericulture |  |  |  |  |  |  |  |
|  | Others, pl. specify |  |  |  |  |  |  |  |
|  |  |  |  |  | Total | 89 | 2110 |  |

11. Training for Rural Youth during 2016-17

| S.No. | Thematic area | Crop / Enterprise | Major problem | Related field intervention (OFT/FLD)* | Training Course Title** | No. of Courses | Expected No. of participants | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 11.1 | Crop Production |  |  |  |  |  |  |  |
| 11.2 | Horticulture Production |  |  |  |  |  |  |  |
| 11.3 | Livestock Production | Dairy enterprise | Low productivity of milk | - | Skill upgradation training on dairy management practices | 4 | 100 | Dr. B.M.Murgod Programme Assistant (Animal Husbandry) |
|  |  | Sheep & Goat | Low body weight in lambs & kids |  | Feed and endo parasite management | 1 | 25 | Dr. B.M.Murgod Programme Assistant (Animal Husbandry) |
| 11.4 | Home Science | Health and hygiene to young girls | Lack of knowledge on health, nutrition and personal hygiene | - | Training on balanced diet and personal hygiene for young girls | 5 | 300 | Mrs. Sudha S.R., Scientist (Home Science) |
| 11.5 | Plant Protection |  |  |  |  |  |  |  |
| 11.6 | Production of Inputs at Site |  |  |  |  |  |  |  |
| 11.7 | Soil Health and Fertility |  |  |  |  |  |  |  |
| 11.8 | PHT and value addition |  |  |  |  |  |  |  |
| 11.9 | Capacity Building Group Dynamics |  |  |  |  |  |  |  |
| 11.10 | Farm Mechanization |  |  |  |  |  |  |  |
| 11.11 | Fisheries Production Technologies |  |  |  |  |  |  |  |
| 11.12 | Mushroom production |  |  |  |  |  |  |  |
| 11.13 | Agro forestry |  |  |  |  |  |  |  |
| 11.14 | Bee Keeping |  |  |  |  |  |  |  |
| 11.15 | Sericulture |  |  |  |  |  |  |  |
|  | Others, pl. specify |  |  |  |  |  |  |  |
|  |  |  |  |  | Total | 10 | 425 |  |

### 12 Training for Extension Personnel during 2016-17

| S.No. | Thematic area | Training Course Title** | No. of Courses | Expected No. of participants | Names of the team members involved |
| --- | --- | --- | --- | --- | --- |
| 12.1 | Crop Production | ICM practices & intercropping systems in pulse crops | 2 | 40 | Mr. V.D.Vaikunthe, Scientist (Agronomy), Mr. S.K.Mudlapur, Scientist (Plant Protection) & Mr. N.H.Bhandi, Scientist (Soil Science) |
|  |  | Production technology on Sunflower & Summer Groundnut | 1 | 25 | Mr. V.D.Vaikunthe, Scientist (Agronomy), Mr. S.K.Mudlapur, Scientist (Plant Protection) & Mr. N.H.Bhandi, Scientist (Soil Science) |
| 12.2 | Home Science | Livelihood improvement of SHGs through capacity building of extension personnel under NRLM | 1 | 50 | Mrs. Sudha S.R., Scientist (Home Science), Mr. S.H.Adapur Scientist (Ag. Extension), Dr. B.M.Murgod, Programme Assistant (Animal Husbandry) Mr. V.D.Vaikunthe, Scientist (Agronomy) & Mr. S.K.Mudlapur, Scientist (Plant Protection) |
|  |  | Reproductive health & related aspects to Anganwadi teachers | 1 | 50 | Mrs. Sudha S.R., Scientist (Home Science), |
| 12.3 | Capacity Building and Group Dynamics | FPO formation and management | 1 | 30 | Mr. S.H.Adapur Scientist (Ag. Extension) |
| 12.4 | Horticulture |  |  |  |  |
| 12.5 | Livestock Production & Management |  |  |  |  |
| 12.6 | Plant Protection |  |  |  |  |
| 12.7 | Farm Mechanization |  |  |  |  |
| 12.8 | PHT and value addition |  |  |  |  |
| 12.9 | Production of Inputs at Site | Training on production & usage of organic inputs | 1 | 20 | Mr. S.K.Mudlapur, Scientist (Plant Protection) |
| 12.10 | Sericulture |  |  |  |  |
| 12.11 | Fisheries |  |  |  |  |
|  | Others |  |  |  |  |
|  |  | Total | 7 | 215 |  |

## 13 Vocational trainings during 2016-17

| Sl.No. | Thematic area and the Crop/Enterprise | Training title* | No. of programmes and Duration (days) | Type of Clientele (SHGs, NYKs, School students, Women, Youth etc.) | Expected No. of participants | Sponsoring agency if any | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 13.1 | Crop Production |  |  |  |  |  |  |
| 13.2 | Home Science |  |  |  |  |  |  |
| 13.3 | Capacity Building and Group Dynamics |  |  |  |  |  |  |
| 13.4 | Horticulture |  |  |  |  |  |  |
| 13.5 | Livestock Production & Management | Scientific management of dairy animals | 10 (6 days) | Women & youths | 300 | AH & VS Dept., ASF, ZP etc | Dr. B.M.Murgod, Programme Assistant (Animal Husbandry) |
| 13.6 | Plant Protection |  |  |  |  |  |  |
| 13.7 | Farm Mechanization |  |  |  |  |  |  |
| 13.8 | PHT and value addition | Training on Food Procesing | 1 (6 days) | SHG members | 30 | - | Mrs. Sudha S.R., Scientist (Home Science) & Mr. S.H.Adapur Scientist (Ag. Extension) |
| 13.9 | Production of Inputs at Site |  |  |  |  |  |  |
| 13.10 | Sericulture |  |  |  |  |  |  |
| 13.11 | Fisheries |  |  |  |  |  |  |
|  | Total |  | 11 |  | 330 |  |  |

## 14 Sponsored trainings during 2016-17

| Sl.No. | Thematic area and the Crop/Enterprise | Training title* | No. of programmes and Duration (days) | Type of Participants (SHGs, NYKs, School students, Women, Youth etc.) | Expected number of participants | Sponsoring agency | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 14.1 | Crop Production | Soil, water and crop management | 10 (2 days) | Farmers & farm women | 500 | CADA, Malaprabha & Ghataprabha Projects, Belgaum | Mr. V.D.Vaikunthe, Scientist (Agronomy), Mr. N.H.Bhandi, Scientist (Soil Science), Mr. S.H.Adapur Scientist (Ag. Extension) Mr. S.K.Mudlapur, Scientist (Plant Protection) & Mr. K.T.Patil, Scientist (Horticulture) |
|  |  | Production technology for Kharif and Rabi crops | 15 (2-3 days) | Farmers & farm women | 500 | KSDA, Gadag | All Staff |
| 14.2 | Home Science | Income Generating Activities | 4 (6 days) | NRLM workers | 250 | ZP, Gadag | All Staff |
| 14.3 | Capacity Building and Group Dynamics |  |  |  |  |  |  |
| 14.4 | Horticulture | Dryland horticulture | 5 (2 days) | Farmers & farm women | 200 | Horticulture Department | Mr. K.T.Patil, Scientist (Horticulture), Mr. N.H.Bhandi, Scientist (Soil Science) & Mr. S.K.Mudlapur, Scientist (Plant Protection) |
| 14.5 | Livestock Production & Management |  |  |  |  |  |  |
| 14.6 | Plant Protection |  |  |  |  |  |  |
| 14.7 | Farm Mechanization |  |  |  |  |  |  |
| 14.8 | PHT and value addition |  |  |  |  |  |  |
| 14.9 | Production of Inputs at Site |  |  |  |  |  |  |
| 14.10 | Sericulture |  |  |  |  |  |  |
| 14.11 | Fisheries |  |  |  |  |  |  |
|  |  | Total | 15 |  | 700 |  |  |

* Programme title should specify the major technologies/skills to be transferred /refreshed.

## 15. Extension programmes during 2016-17

| Sl.No. | Extension Programme/ Activity* | No. of programmes or activities | Expected number of participants | Names of the team members involved |
| --- | --- | --- | --- | --- |
| 15.1 | Advisory Services |  |  |  |
|  | Field crops | 70 | 150 | Mr. V.D.Vaikunthe, Scientist (Agronomy) & Mr. S.K.Mudlapur, Scientist (Plant Protection) |
|  | Horticultural crops | 50 | 100 | Mr. K.T.Patil, Scientist (Horticulture) & Mr. S.K.Mudlapur, Scientist (Plant Protection) |
|  | Soil test based nutrient application | 50 | 150 | Mr. N.H.Bhandi, Scientist (Soil Science) |
|  | Contingent crop planning | 20 | 350 | Mr. V.D.Vaikunthe, Scientist (Agronomy) & Mr. K.T.Patil, Scientist (Horticulture) |
|  | Alternate Land Use Systems | 10 | 150 | Mr. K.T.Patil, Scientist (Horticulture) & Mr. N.H.Bhandi, Scientist (Soil Science) |
|  | Livestock development | 25 | 300 | Dr. B.M.Murgod Programme Assistant (Animal Husbandry) |
|  | Women health and nutrition | 20 | 300 | Mrs. Sudha S.R., Scientist (Home Science) |
|  | Women drudgery reduction equipments | 20 | 300 | Mrs. Sudha S.R., Scientist (Home Science) |
|  | Marketing information | 25 | 1000 | Mr.S.H.Adapur, Scientist (Ag. Extension) |
|  | Organic input preparation | 15 | 150 | Mr. S.K.Mudlapur, Scientist (Plant Protection) |
| 15.2 | Diagnostic Visits | 20 | 50 | Mr. V.D.Vaikunthe, Scientist (Agronomy), Mr. S.K.Mudlapur, Scientist (Plant Protection), Mr. K.T.Patil, Scientist (Horticulture) & Mr. N.H.Bhandi, Scientist (Soil Science) |
| 15.3 | Field Days |  |  |  |
|  | Maize | 1 | 100 | Mr. V.D.Vaikunthe, Scientist (Agronomy), Mr. N.H.Bhandi, Scientist (Soil Science) & Mr. S.K.Mudlapur, Scientist (Plant Protection) |
|  | Rabi Sorghum | 1 | 100 | Mr. V.D.Vaikunthe, Scientist (Agronomy), Mr. N.H.Bhandi, Scientist (Soil Science) & Mr. S.K.Mudlapur, Scientist (Plant Protection) |
|  | Foxtail millet | 1 | 100 | Mr. V.D.Vaikunthe, Scientist (Agronomy), Mr. N.H.Bhandi, Scientist (Soil Science) & Mr. S.K.Mudlapur, Scientist (Plant Protection) |
|  | Groundnut (Summer) | 1 | 100 | Mr. V.D.Vaikunthe, Scientist (Agronomy), Mr. N.H.Bhandi, Scientist (Soil Science) & Mr. S.K.Mudlapur, Scientist (Plant Protection) |
|  | Onion | 1 | 100 | Mr. K.T.Patil, Scientist (Horticulture), Mr. S.K.Mudlapur, Scientist (Plant Protection) & Mr. N.H.Bhandi, Scientist (Soil Science) |
|  | Chilli | 1 | 100 | Mr. K.T.Patil, Scientist (Horticulture), Mr. S.K.Mudlapur, Scientist (Plant Protection) & Mr. N.H.Bhandi, Scientist (Soil Science) |
|  | Fodder production | 1 | 60 | Mr.S.H.Adapur, Scientist (Ag. Extension) & Dr. B.M.Murgod Programme Assistant (Animal Husbandry) |
|  | Bengalgram | 1 | 75 | Mr. V.D.Vaikunthe, Scientist (Agronomy) & Mr. S.K.Mudlapur, Scientist (Plant Protection) |
|  | Greengram | 1 | 75 | Mr. V.D.Vaikunthe, Scientist (Agronomy) & Mr. S.K.Mudlapur, Scientist (Plant Protection) |
|  | Ashwagandha | 1 | 75 | Mr. K.T.Patil, Scientist (Horticulture) |
|  | Value addition | 2 | 60 | Mrs. Sudha S.R., Scientist (Home Science) |
| 15.4 | Group Discussions |  |  |  |
|  | Kharif season crops | 5 | 150 | Mr.S.H.Adapur, Scientist (Ag. Extension), Mr. V.D.Vaikunthe, Scientist (Agronomy), Mr. S.K.Mudlapur, Scientist (Plant Protection) & Mr. K.T.Patil, Scientist (Horticulture) |
|  | Rabi season crops | 5 | 150 | Mr.S.H.Adapur, Scientist (Ag. Extension), Mr. V.D.Vaikunthe, Scientist (Agronomy), Mr. S.K.Mudlapur, Scientist (Plant Protection) & Mr. K.T.Patil, Scientist (Horticulture) |
|  | IGA activities | 3 | 90 | Mrs. Sudha S.R., Scientist (Home Science) |
| 15.5 | Kisan Gosthi |  |  |  |
|  | Soil fertility management strategies | 1 | 150 | Mr.S.H.Adapur, Scientist (Ag. Extension) Mr. N.H.Bhandi, Scientist (Soil Science) & Mr. S.K.Mudlapur, Scientist (Plant Protection) |
|  | Diversification of crop enterprise | 1 | 150 | Mr.S.H.Adapur, Scientist (Ag. Extension) Mr. K.T.Patil, Scientist (Horticulture) & Mr. N.H.Bhandi, Scientist (Soil Science) |
|  | Women health and nutrition | 1 | 150 | Mr.S.H.Adapur, Scientist (Ag. Extension)& Mrs. Sudha S.R., Scientist (Home Science) |
| 15.6 | Film Shows |  |  |  |
|  | Soil and water conservation | 3 | 280 | Mr. N.H.Bhandi, Scientist (Soil Science) |
|  | Crop diversification | 5 | 150 | Mr. K.T.Patil, Scientist (Horticulture) |
|  | Livestock health & nutrition | 3 | 90 | Dr. B.M.Murgod Programme Assistant (Animal Husbandry) |
| 15.7 | Self Help Groups | 10 | 200 | Mrs. Sudha S.R., Scientist (Home Science) |
| 15.8 | Kisan Mela | 1 | 4000 | All staff |
| 15.9 | Exhibition | 3 | 15000 | All staff |
| 15.10 | Scientists' Visit to Farmers Fields | 200 | 800 | Concerned Scientist and programme assistant |
| 15.11 | Plant/Soil Health/Animal Health Camps | 3 | 250 | Mr.S.H.Adapur, Scientist (Ag. Extension), Mr. N.H.Bhandi, Scientist (Soil Science) & Dr. B.M.Murgod Programme Assistant (Animal Husbandry) |
| 15.12 | Farmers’ Interest Groups formation | 50 | 1000 | Mr.S.H.Adapur, Scientist (Ag. Extension) |
| 15.13 | Ex-Trainees Sammelan | 1 | 30 (Dairy farmers) | Dr. B.M.Murgod Programme Assistant (Animal Husbandry) |
| 15.14 | Farmers' Seminar/Workshop | 1 | 100 | Mr.S.H.Adapur, Scientist (Ag. Extension) |
| 15.15 | Method Demonstrations |  |  |  |
|  | Compartment bunding | 3 | 75 | Mr. V.D.Vaikunthe, Scientist (Agronomy) & Mr. N.H.Bhandi, Scientist (Soil Science) |
|  | Opening of conservation furrow | 2 | 50 | Mr. N.H.Bhandi, Scientist (Soil Science) & Mr. V.D.Vaikunthe, Scientist (Agronomy) |
|  | Soil sample collection | 3 | 75 | Mr. N.H.Bhandi, Scientist (Soil Science) |
|  | Seed treatment | 4 | 100 | Mr. V.D.Vaikunthe, Scientist (Agronomy) & Mr. S.K.Mudlapur, Scientist (Plant Protection) |
|  | Nipping in Bengalgram | 2 | 40 | Mr. V.D.Vaikunthe, Scientist (Agronomy) |
|  | Organic input production | 5 | 150 | Mr. S.K.Mudlapur, Scientist (Plant Protection) |
|  | Orchard layout | 10 | 10 | Mr. K.T.Patil, Scientist (Horticulture) |
|  | Cycle weeder | 10 | 300 | Mrs. Sudha S.R., Scientist (Home Science) & Mr. V.D.Vaikunthe, Scientist (Agronomy) |
|  | Spiral separator | 2 | 100 | Mrs. Sudha S.R., Scientist (Home Science)& Mr. V.D.Vaikunthe, Scientist (Agronomy) |
|  | Silage preparation | 5 | 100 | Dr. B.M.Murgod Programme Assistant (Animal Husbandry) |
|  | Concentrated feed preparation | 5 | 100 |  |
|  | Mineral feed supplement preparation | 5 | 100 |  |
|  | Preparation of Hay & Haylage | 5 | 100 |  |
|  | Enrichment of dry fodder | 5 | 100 |  |
| 15.16 | Celebration of Important Days |  |  |  |
|  | World food day | 1 | 100 | Mr.S.H.Adapur, Scientist (Ag. Extension) & other staff |
|  | JaiKisan JaiVigyan week (Technology week) | 5 | 4000-6000 | All staff |
| 15.17 | Special Day Celebration |  |  |  |
|  | World environment day | 1 | 100 | Mr.S.H.Adapur, Scientist (Ag. Extension) & other staff |
| 15.18 | Exposure Visits | 10 | 300 | Concerned staff |
| 15.19 | Awareness Programs |  |  |  |
|  | Soil & water conservation | 4 | 120 | Mr. N.H.Bhandi, Scientist (Soil Science) |
|  | Soil test based nutrient application | 3 | 120 | Mr. N.H.Bhandi, Scientist (Soil Science) |
|  | Contingent crop planning | 5 | 300 | Mr. V.D.Vaikunthe, Scientist (Agronomy) & Mr. K.T.Patil, Scientist (Horticulture) |
|  | Alternate Land Use System | 3 | 120 | Mr. K.T.Patil, Scientist (Horticulture) & Mr. N.H.Bhandi, Scientist (Soil Science) |
|  | Livestock health & nutrition | 3 | 200 | Dr. B.M.Murgod Programme Assistant (Animal Husbandry) |
|  | Women health & nutrition | 5 | 350 | Mrs. Sudha S.R., Scientist (Home Science) |
|  | Drudgery reducing equipments | 5 | 350 | Mrs. Sudha S.R., Scientist (Home Science) |
|  | IGAs to SHGs | 5 | 150 | Mrs. Sudha S.R., Scientist (Home Science) |
|  | Organic input production | 5 | 200 | Mr. S.K.Mudlapur, Scientist (Plant Protection) |
|  | Total | 754 | 30465 |  |

## 16.	Activities proposed as Knowledge and Resource Centre during 2016-17

16.1 Technological knowledge

| Sl.No. | Category | Details of technologies | Area (ha)/ Number | Names of the team members involved |
| --- | --- | --- | --- | --- |
| 16.1.1 | Technology Park/ Crop cafeteria | Pulse crops and their inter crops | 6 Ha | Mr. V.D.Vaikunthe, Scientist (Agronomy) & Mr. S.L.Halemani, Farm manager |
| 16.1.2 | Demonstration Units | Value addition in Amla & Karounda | 1000 farmers/farm women visit to the units | Mrs. Sudha S.R., Scientist (Home Science) |
|  |  | Mixed orchard of fruit crops – Mango, Cashew, Custard apple and Sweet lime | 2000 farmers/farm women | Mr. K.T.Patil, Scientist (Horticulture) |
| 16.1.3 | Lab Analytical services | Soil, water & plant testing | 2200 samples | Mr. N.H.Bhandi, Scientist (Soil Science) |
|  |  | Identification of pest and disease | 50 samples | Mr. S.K.Mudlapur, Scientist (Plant Protection) |
| 16.1.4 | Technology Week (to be celebrated during JaKisan JaiVigyan Week i.e 23-30, Dec, 2016) + Agriculture exhibition on 28-01-2017 at Hulkoti | Technologies relevant to Gadag district | 4000-6000 Nos. | All staff |

16.2 Technological Products

| Sl.No. | Category | Name of the Production Partner Agency, if any | Name of the product | Quantity (q)/ Number planned to be produced during 2016-17 | Names of the team members involved |
| --- | --- | --- | --- | --- | --- |
| 16.2.1 | Seeds | Seed growing farmer | Onion seeds | 20 Qtls | Mr. K.T.Patil, Scientist (Horticulture) & Mr. S.L.Halemani, Farm Manager |
|  |  |  | Greengram (DGGV-2) | 20 Qtl | Mr. V.D.Vaikunthe, Scientist (Agronomy) & Mr. S.L.Halemani, Farm Manager |
|  |  |  | Blackgram (DU-1) | 08 Qtl |  |
|  |  |  | Redgram (TS-3R) | 30 Qtl |  |
|  |  |  | Bengalgram (GBM-2) | 25 Qtl |  |
|  |  |  | Rabi Sorghum (BJV-44) | 10 Qtl |  |
|  |  |  | Rabi Sorghum (SPV-2217) | 10 Qtl |  |
| 16.2.2 | Planting materials |  | Mango (Alphonso) | 2000 Nos. | Mr. K.T.Patil, Scientist (Horticulture) & Mr. S.L.Halemani, Farm Manager |
|  |  |  | Tamarind | 500 Nos. |  |
| 16.2.3 | Bio-products | - | Vermicompost | 20 tonn | Mr. S.K.Mudlapur, Scientist (Plant Protection) Mr. S.L.Halemani, Farm Manager |
|  |  |  | Vermi wash | 1000 liter |  |
|  |  |  | Earthworms | 200 Kgs |  |
|  |  |  | Azolla | 200 Kgs |  |
| 16.2.4 | Livestock strains |  | Lambs & kids | 30 Nos. | Dr. B.M.Murgod Programme Assistant (Animal Husbandry) & Mr. S.L.Halemani, Farm Manager |
| 16.2.5 | Fish fingerlings |  |  |  |  |

16.3 Technological Information

|  | Category | Technological capsules / Number | Names of the team members involved |
| --- | --- | --- | --- |
| 16.3.1 | Technology backstopping to line departments |  |  |
|  | Agriculture | Role of macro & micro nutrients in crop production In-situ soil & water conservation practices | Mr. N.H.Bhandi, Scientist (Soil Science) |
|  |  | Pod borer identification and management in Greengram Groundnut leaf minor and leaf spot : Early identification and management Maize Turcicum leaf blight identification and management Bt. Cotton leaf reddening management Bt. Cotton sucking pest management Bt. Cotton Blackarm and Alternania leaf spot disease identification and management Onion thrips and purple blotch identification and management Chilli murda complex identification and management Bengalgram pod borer and wilt identification and management Mango hopper and powdery mildew identification and management Organic input preparation technology Azolla cultivation | Mr. S.K.Mudlapur, Scientist (Plant Protection) |
|  |  | Chemical weed management Seed priming with CaCl2 for Rabi Sorghum Pair row method of sowing in Rabi Sorghum Opening of conservation furrow for moisture conservation Compartment bunding for soil moisture conservation Nipping in Bengalgram & its importance Contingent crop planning Foliar spray of KNO3 for drought tolerance | Mr. V.D.Vaikunthe, Scientist (Agronomy) |
|  | Horticulture | Weed management in Onion Nutrient management in fruit crops Mango orchard management | Mr. K.T.Patil, Scientist (Horticulture) |
|  |  | Chilli pest and disease management | Mr. K.T.Patil, Scientist (Horticulture) & Mr. S.K.Mudlapur, Scientist (Plant Protection) |
|  | Animal Husbandry | Dairy Project Report | Dr. B.M. Murgod Programme Assistant (Animal Husbandry) |
|  | Fisheries |  |  |
|  | Agricultural Engineering | Laser guided land leveler | Mr. N.H.Bhandi, Scientist (Soil Science) |
|  | Sericulture | Mulberry cultivation through organic farming practices | Mr. S.K.Mudlapur, Scientist (Plant Protection) |
|  | Others, pl. specify | Artificial recharge of groundwater through bore wells and open wells | Mr. N.H.Bhandi, Scientist (Soil Science) |
|  |  | Women & Child Welfare Department and Mahila Samukhya Drudgery reducing equipments in home and farm Nutrition & reproductive health | Mrs. Sudha S.R., Scientist (Home Science) |
| 16.3.2 | Literature/publication | Leaflets |  |
|  |  | Scientific Dairy Management in Dry land Area | Dr. B.M.Murgod Programme Assistant (Animal Husbandry) |
|  |  | Success stories of progressive farmers | Mrs. Sudha S.R., Scientist (Home Science) |
|  |  | Importance of soil and water testing & methods of soil & water sample collection Soil & water conservation measures for dry land agriculture | Mr. N.H.Bhandi, Scientist (Soil Science) & V.D.Vaikunthe, Scientist (Agronomy) |
|  |  | Mango pest and disease management | Mr. S.K.Mudlapur, Scientist (Plant Protection) |
|  |  | Production technologies in Onion Post harvest management in Mango | Mr. K.T.Patil, Scientist (Horticulture) |
|  |  | Production technology in Greengram Integrated crop management in Maize Integrated crop management in Bt. Cotton Production technology in Groundnut Production technology in Bengalgram Production technology in Sunflower | Mr.V.D.Vaikunthe, Scientist (Agronomy), Mr. S.K.Mudlapur, Scientist (Plant Protection) & Mr. N.H.Bhandi, Scientist (Soil Science) |
|  |  | Krishi Vigyan Patrike Importance & methods of soil and water testing Soil & water conservation measures Alternate land use systems Role of nutrients for higher production | Mr. N.H.Bhandi, Scientist (Soil Science) & Mr. V.D.Vaikunthe, Scientist (Agronomy) |
|  |  | Tips on cultivation of onion & chilli Weed management in onion Nutrient management in Mango & Banana Mango orchard management Onion seed production technology | Mr. K.T.Patil, Scientist (Horticulture) |
|  |  | Spiral separator Importance & value addition in millets Value addition in Sorghum | Mrs. Sudha S.R., Scientist (Home Science) |
|  |  | Compartment bunding for moisture conservation Production technology of Maize Paired row method of sowing in Groundnut Integrated nutrient management in Groundnut Wider row method of sowing in Sunflower Foliar spray of boron for seed setting in Sunflower Detopping and its importance in Bengalgram Paired row method of sowing in Rabi Sorghum CaCl2 seed priming & its importance in Rabi Sorghum | Mr. V.D.Vaikunthe, Scientist (Agronomy) |
|  |  | Groundnut defoliator, leaf minor, collar rot and leaf spot management Onion thrips and purple blotch management Chilli murda complex management Banana pest and disease management | Mr. S.K.Mudlapur, Scientist (Plant Protection) |
| 16.3.4 | Electronic Media | TV Programmes: Soil & water conservation measures Alternate land use system for dry land agriculture Recharging of ground water through bore well and open well | Mr. N.H.Bhandi, Scientist (Soil Science) |
|  |  | Income generating activities | Mrs. Sudha S.R., Scientist (Home Science) |
|  |  | Demonstration on enrichment of dry fodder and Azolla cultivation | Dr. B.M.Murgod Programme Assistant (Animal Husbandry) |
|  |  | Vermicompost & Vermiwash preparation and usage | Mr. S.K.Mudlapur, Scientist (Plant Protection) |
|  |  | Dry land horticulture technologies | Mr. K.T.Patil, Scientist (Horticulture) |
|  |  | Dryland agronomic practices for in-situ moisture conservation | Mr. V.D.Vaikunthe, Scientist (Agronomy) |
|  |  | Radio programmes: Soil & water conservation measures Soil fertility management practices Site specific nutrients application for higher production | Mr. N.H.Bhandi, Scientist (Soil Science) |
|  |  | Agro processing Nutrition for teenagers | Mrs. Sudha S.R., Scientist (Home Science) |
|  |  | Organic farming and its importance | Mr. S.K.Mudlapur, Scientist (Plant Protection) |
|  |  | Onion seed production technologies | Mr. K.T.Patil, Scientist (Horticulture) |
|  |  | Resource conservation technologies in Kharif crops | Mr. V.D.Vaikunthe, Scientist (Agronomy) |
| 16.3.5 | Kisan Mobile Advisory Services | Soil Science aspects – 15 Nos. | Mr. N.H.Bhandi, Scientist (Soil Science) |
|  |  | Home Science aspects – 10 Nos. | Mrs. Sudha S.R., Scientist (Home Science) |
|  |  | Plant Protection aspects – 15 Nos. | Mr. S.K.Mudlapur, Scientist (Plant Protection) |
|  |  | Horticulture aspects – 10 Nos. | Mr. K.T.Patil, Scientist (Horticulture) |
|  |  | Agronomic aspects – 20 Nos. | Mr.V.D.Vaikunthe, Scientist (Agronomy) |
|  |  | Animal Science aspects – 15 Nos. | Dr. B.M.Murgod Programme Assistant (Animal Husbandry) |
|  |  | Market information, Input availability & other messages – 20 Nos. | Mrs. Lalita S. Asuti, Computer Programmer |

## 17.	Additional Activities Planned during 2016-17

| S.No. | Name of the agency / scheme | Name of activity | Technical programme with quantification | Financial outlay (Rs.) | Names of the team members involved |
| --- | --- | --- | --- | --- | --- |
| 17.1 |  |  |  |  |  |

18.	Revolving Fund

18.1	Financial status

| Opening balance as on 01.04.2015 (Rs.in Lakh) | Expenditure incurred during 2015-16 (Rs.in Lakh) | Receipts during 2015-16 (Rs.in Lakh) | Closing balance as on 31.01.2016 (Rs.in Lakh) | Expected closing balance by 31.03.2016 (Including value of material in stock/ likely to be produced) |
| --- | --- | --- | --- | --- |
| - 6.34 | 17.20 | 17.83 | -5.71 | 5.00 |

18.2 	Plan of activities under Revolving Fund

| S.No. | Proposed activities | Expected output | Anticipated income (Rs.) | Names of the team members involved |
| --- | --- | --- | --- | --- |
| 18.2.1 | Amla products | 2 Qtl | 30000 | Mrs. Sudha S.R., Scientist (Home Science) & Mr. S.L.Halemani, Farm Manager |
| 18.2.2 | Karounda/Amla pickle | 8 Qtl | 40000 | Mrs. Sudha S.R., Scientist (Home Science) & Mr. S.L.Halemani, Farm Manager |
| 18.2.3 | Onion seed production | 20 Qtl | 300000 | Mr. K.T.Patil, Scientist (Horticulture) & Mr. S.L.Halemani, Farm Manager |
| 18.2.4 | Mango grafts | 2000 | 10000 | Mr. K.T.Patil, Scientist (Horticulture) & Mr. S.L.Halemani, Farm Manager |
| 18.2.5 | Tamarind grafts | 500 | 2500 | Mr. K.T.Patil, Scientist (Horticulture) & Mr. S.L.Halemani, Farm Manager |
| 18.2.6 | Vermicompost production | 15 ton | 60000 | Mr. S.K.Mudlapur, Scientist (Plant Protection) & Mr. S.L.Halemani, Farm Manager |
| 18.2.7 | Vermi wash | 500 liters | 20000 | Mr. S.K.Mudlapur, Scientist (Plant Protection) & Mr. S.L.Halemani, Farm Manager |
| 18.2.8 | Earth worms | 2 Qtl | 60000 | Mr. S.K.Mudlapur, Scientist (Plant Protection) & Mr. S.L.Halemani, Farm Manager |
| 18.2.9 | Milk production | 14600 lit | 158000 | Dr. B.M.Murgod, Programme Assistant (A. Sc.) & Mr. S.L.Halemani, Farm Manager |
| 18.2.10 | Lamb and kid production | 30 Nos | 28740 | Dr. B.M.Murgod, Programme Assistant (A. Sc.) & Mr. S.L.Halemani, Farm Manager |
| 18.2.11 | Mineral lick block production | 1456 Nos | 36500 | Dr. B.M.Murgod, Programme Assistant (A. Sc.) & Mr. S.L.Halemani, Farm Manager |

## 19.	Activities of soil, water and plant testing laboratory during 2016-17

| Sl.No. | Type | No. of samples to be analyzed | Names of the team members involved |
| --- | --- | --- | --- |
| 19.1 | Soil | 2000 | Mr. N.H.Bhandi, Scientist (Soil Science) |
| 19.2 | Water | 200 | Mr. N.H.Bhandi, Scientist (Soil Science) |
| 19.3 | Plant | - | - |
| 19.4 | Others | - | - |

## 20.	E-linkage during 2016-17

| S. No | Nature of activities | Likely period of completion (please set the time frame) | Remarks if any |
| --- | --- | --- | --- |
| 20.1 | Title of the technology module to be prepared - Rabi Sorghum | 15-03-2017 |  |
| 20.2 | Creation and maintenance of relevant database system for KVK |  |  |
|  | Bench mark data | 30-09-2016 |  |
|  | OFT |  | Already maintained |
|  | FLD |  | Already maintained |
|  | Training database |  | Already maintained |
|  | Seeds & planting material |  | Already maintained |
|  | All Extension activities |  | Already maintained |
|  | Farmers visiting to KVK |  | Already maintained |
|  | Field visits |  | Already maintained |
|  | District database |  | Already maintained |
|  | Soil & water test details |  | Already maintained |
|  | Database on KVK (i.e regarding KVK details, host institute details, staff information, KVK land information, KVK infrastructure, demo units, vehicle, office, lab, farm equipment & library) |  | Already maintained |
|  | HRD of KVK staff (i.e training/seminar/workshop attended by KVK staff) |  | Already maintained |
|  | Publications of KVK activities in news papers |  | Already maintained |
|  | Villages covered by KVK since inception |  | Already maintained |
|  | Kisan mobile advisory services – Subscribers and messages sent |  | Already maintained |
|  | Farm implements |  | Already maintained |
| 20.3 | Any other – Updating website of KVK | Every 15 days |  |
|  | Online reporting system of KVK | Entering data every month | Already started |

21.	Activities planned under Rainwater Harvesting Scheme (only to those KVKs which are already having scheme under Rain Water

Harvesting)

| S. No | Activities planned | Remarks if any |
| --- | --- | --- |
| 21.1 | Training on rainwater harvesting measures to farmers & farm women for 200 numbers | - |
| 21.2 | Training on rainwater harvesting measures for 50 extension functionaries | - |
| 21.3 | Exposure visit for rainwater harvesting structures for 200 farmers/farmwomen | - |

22.	Innovative Farmer’s Meet

| Sl.No. | Particulars | Details |
| --- | --- | --- |
| 22.1 | Are you planning for conducing Farm Innovators meet in your district? | No |
| 22.2 | If Yes likely month of the meet |  |
| 22.3 | Brief action plan in this regard |  |

23.	Farmers Field School (FFS) planned : NIL

| S. No | Thematic area | Title of the FFS | Budget proposed in Rs. |
| --- | --- | --- | --- |
| 23.1 | - | - | - |
| 23.2 |  |  |  |

24.Budget - Details of budget  utilization (2015-16) up to 31 January 2016

(Rs. In lakhs)

| S. No. | Particulars | Sanctioned | Released | Expenditure |
| --- | --- | --- | --- | --- |
| 24.1 | Recurring Contingencies |  |  |  |
| 24.1.1 | Pay & Allowances | 130.120 | 130.120 | 110.810 |
| 24.1.2 | Traveling allowances | 1.000 | 1.000 | 0.980 |
| 24.1.3 | Contingencies |  |  |  |
| 24.1.4.1 | Stationery, telephone, postage and other expenditure on office running, publication of Newsletter and library maintenance | 0.800 | 0.800 | 0.970 |
| B | POL, repair of vehicles, tractor and equipments | 1.000 | 1.000 | 1.060 |
| C | Meals/refreshment for trainees | 0.500 | 0.500 | 0.510 |
| D | Training material | 0.250 | 0.250 | 0.250 |
| E | Frontline demonstration except oilseeds and pulses | 4.100 | 4.100 | 2.970 |
| F | On farm testing | 0.250 | 0.250 | 0.190 |
| G | Training of extension functionaries | 0.000 | 0.000 | 0.000 |
| H | Maintenance of buildings | 0.000 | 0.000 | 0.000 |
| I | Establishment of Soil, Plant & Water Testing Laboratory | 0.000 | 0.000 | 0.000 |
| J | Library | 0.050 | 0.050 | 0.040 |
| K | Extension activities | 0.500 | 0.500 | 0.390 |
| 24.1 | Total Recurring | 138.570 | 138.570 | 118.170 |
| 24.2 | Non-Recurring Contingencies | 0.000 | 0.000 | 0.000 |
| 24.2.1 | Works | 0.000 | 0.000 | 0.000 |
| 24.2.2 | Equipments including SWTL & Furniture | 0.000 | 0.000 | 0.000 |
| 24.2.3 | Vehicle (Four wheeler/Two wheeler, please specify) | 0.000 | 0.000 | 0.000 |
| 24.2.4 | Library | 0.000 | 0.000 | 0.000 |
| 24.2 | Total Non Recurring | 0.000 | 0.000 | 0.000 |
| 24.3 | REVOLVING FUND | 0.000 | 0.000 | 0.000 |
| 24.4 | GRAND TOTAL (A+B+C) | 138.570 | 138.570 | 118.170 |

25.Details of Budget Estimate (2016-17) based on proposed action plan

| S. No. | Particulars | BE 2016-17 proposed (Rs.) |
| --- | --- | --- |
| 25.1 | Recurring Contingencies |  |
| 25.1.1 | Pay & Allowances | 153.40 |
| 25.1.2 | Traveling allowances | 2.50 |
| 25.1.3 | Contingencies |  |
| A | Stationery, telephone, postage and other expenditure on office running, publication of Newsletter and library maintenance (Purchase of News Paper & Magazines) | 4.00 |
| B | POL, repair of vehicles, tractor and equipments | 4.00 |
| C | Meals/refreshment for trainees (ceiling upto Rs.40/day/trainee be maintained) | 1.50 |
| D | Training material (posters, charts, demonstration material including chemicals etc. required for conducting the training) | 1.50 |
| E | Frontline demonstration except oilseeds and pulses (minimum of 30 demonstration in a year) | 4.60 |
| F | On farm testing (on need based, location specific and newly generated information in the major production systems of the area) | 0.35 |
| G | Training of extension functionaries | 0.50 |
| H | Maintenance of buildings | 1.00 |
| I | Establishment of Soil, Plant & Water Testing Laboratory | 0.50 |
| J | Library | 0.25 |
| 25.1 | TOTAL Recurring Contingencies | 174.10 |
| 25.2 | Non-Recurring Contingencies |  |
| 25.2.1 | Works | 10.00 |
| 25.2.2 | Equipments including SWTL & Furniture | 1.60 |
| 25.2.3 | Vehicle (Tractor) | 10.00 |
| 25.2.4 | Library (Purchase of assets like books & journals) | 0.50 |
| 25.2 | TOTAL Non-Recurring Contingencies | 22.10 |
| 25.3 | REVOLVING FUND | 0.00 |
| 25.4 | GRAND TOTAL | 196.20 |

-------XXXXXXX-------