Action Plan 2018-19

ICAR-KVK, Ramanagara, Karnataka

###### ICAR-ATARI – ZONE XI, BENGALURU

###### PROFORMA FOR ACTION PLAN OF KVKS IN ZONE XI FOR THE YEAR 2018-19

###### 1. General information about the Krishi Vigyan Kendra

| 1. | Name and address of KVK with Phone, Fax and e-mail, Website | : | ICAR-Krishi Vigyan Kendra, Chandurayanahally, Kalya Post, Magadi Taluk, Ramanagara District. Tele: 91 80 29899388 e-mail id: kvkramanagara@gmail.com & kvk.Ramanagara@icar.gov.in |
| --- | --- | --- | --- |
| 2. | Name and address of host organization | : | University of Agricultural Sciences, GKVK, Bangalore-560065, Grams; UNIVARGIS. Fax: 9180-23516636. Telephone: 08023330153 |
| 3. | Year of sanction | : | April 2010 |
| 4. | Name of agro-climatic zone | : | Zone V- Eastern dry zone |
| 5. | Major farming systems/enterprises | : | Rainfed: Ragi based cropping system, Ragi and pulse cropping system, Pulse based cropping system, Oil seeds based cropping system, Pulse and oil seed based cropping system, Integrated Farming System, Sericulture, Goat, Sheep and Dairy |
|  |  | : | Irrigated: Coconut based cropping system, Arecanut based cropping system, Banana based cropping system, Mango based cropping system, Vegetable based cropping system, Floriculture, Integrated Farming System, Protected cultivation, Sericulture, Goat, Sheep and Dairy |
| 6. | Soil type | : | Clay soil, Gravelly clay soil, Loamy soil, Red sandy loam soil, |
| 7. | Annual rainfall (mm) | : | 874 mm |

2. Details of staff as on date

| # | Sanctioned post | Name of the incumbent | Discipline | Existing Pay band | Grade Pay | Date of joining | Permanent / Temporary | If vacant action plan for filling the post on permanent basis |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Senior Scientist & Head | Dr. Savita S. Manganavar | Home Science | 34700-67000 | 9000 | 05.02.18 | Permanent | - |
| 2 | Scientist | Dr. Lata R. Kulkarni | Home Science | 15600-39000 | 8000 | 01.10.12 | Permanent | - |
| 3 | Scientist | Mr. Syed Mazar Ali | Ag. Engg. | 15600-39000 | 6000 | 31.01.12 | Permanent | - |
| 4 | Scientist | Dr. Dinesh, M.S. | Agronomy | 15600-39000 | 6000 | 01.02.18 | Permanent | - |
| 5 | Scientist | Mrs. Preethu, D.C. | Soil Science | 15600-39000 | 6000 | 05.02.18 | Permanent | - |
| 6 | Scientist | Dr. Rajendraprasad, B. S. | Plant Protection | 15600-39000 | 6000 | 16.02.18 | Permanent | - |
| 8 | Programme Assistant | Mr. Ranganatha, S. C. | Biotechnology | 9300-34800 | 4600 | 14.05.11 | Permanent | - |
| 9 | Computer Programmer | Mr. K. R. Shyamasundar | Commerce, Comp. Sci. | 9300-34800 | 4600 | 19.01.11 | Permanent | - |
| 10 | Farm Manager | Dr. K. J. Sowmya | Seed Technology | 9300-34800 | 4200 | 29.01.14 | Permanent | - |
| 11 | Assistant | Ms. Suma | Commerce | 5500-9000 | - | 02.01.17 | Temporary |  |
| 12 | Stenographer | Mr. Siddappa, G. | Commerce | 5200-20200 | - | 01.10.15 | Temporary | - |
| 13 | Driver 1 | Mr.N.Rajesh | - | 3200-4900 | - | 26.04.10 | Permanent | - |
| 14 | Driver 2 | Mr.V. Krishnappa | - | 5800-10500 | - | 02.09.15 | Permanent | - |
| 15 | Supporting staff 1 | Mrs. Saraswathamma | - | 2550-3200 | - | 18.05.12 | Permanent | - |
| 16 | Supporting staff 2 | Mr. Narasimhachar, E. | - | 2550-3200 | - | 11.05.13 | Temporary | - |

3. Details of SAC meeting conducted during 2018-19

| Sl. No | Tentative date of SAC meeting proposed during 2018-19 |
| --- | --- |
| 01 | July 2018 |

4. Capacity Building of KVK Staff

A. Plan of Human Resource Development of KVK personnel during 2018-19

| # | Category | Area of training | Institution proposed to attend | Justification | Details of trainings attended during 2017-18 |
| --- | --- | --- | --- | --- | --- |
| 1 | Senior Scientist and Head | Promoting FPOs, issues and challenges/ developing business plans | MANAGE/ NAARM, Hyderabad | To support and strengthen FPOs of the district |  |
|  |  | Project management skills | MANAGE/ NAARM, Hyderabad | For proper management and administration |  |
| 2 | Scientist (Home Science) | Value added products | CFTRI, Mysore, CPCRI, Kasaragod, IIHR, Bangalore | To conduct relevant demonstration on value addition & market linkage | - |
| 3 | Scientist (Ag. Engg.) | Food Processing & Farm Machinery | CIAE, Bhopal PHT Scheme, GKVK, IIHR, Bangalore | To acquire knowledge on recent technologies suitable to farmers in the area of farm machinery and value addition | Skill development training on tractor operator |
| 4 | Scientist (Agronomy) | Recent trends in water management technologies | ICAR-CRIDA, Hyderabad | Water management in dryland agriculture | - |
|  |  | Integrated soil nutrient and weed management | National Institute for Plant Health Management (NIPHM), Rajendra Nagar, Hyderabad | To acquire knowledge on soil nutrient & weed management | - |
| 5 | Scientist (Soil Science) | Integrated soil nutrient & rizosphere management | National Institute for Plant Health Management (NIPHM), Rajendra Nagar, Hyderabad | To acquire knowledge on soil nutrient and rizosphere management | - |
|  |  | Soil health management and soil health card scheme | MANAGE, Hyderabad | To acquire knowledge on soil health | - |
| 6 | Scientist (Plant Protection) | Plant Protection polices | National Institute for Plant Health Management (NIPHM), Rajendra Nagar, Hyderabad ICAR-NBAIR, Bangalore | To Acquire the knowledge about newly introduced insect pests in to the country | - |
| 7 | Computer Programmer | Data Base Management or Advanced training programme on agricultural knowledge management | MANAGE, Hyderabad | Skill up-gradation |  |
| 8 | Farm Manager | Seed production & processing | NSP, Bangalore | Skill up-gradation | - |

B. Cross-learning across KVKs

| # | Name of the KVK proposed | Purpose | Mode of learning |
| --- | --- | --- | --- |
| 1 | KVK Mysore, Karnataka | Agri Clinic and processing unit | Cross learning through exposure visit |
| 2 | KVK Belagavi (KLE), Karnataka | Plant health clinic and nursery | Cross learning through exposure visit |
| 3 | KVK Namakkal, Tamil Nadu | Scientific management of livestock and fodder | Cross learning through exposure visit |
| 4 | KVK Mandi, Himachal Pradesh | Exotic vegetable production & entrepreneurship development | Cross learning through exposure visit |
| 5 | KVK Pathanamthitta, Kerala | Value addition in jack fruit, rain water harvesting, subsidiary units | Cross learning through exposure visit |

5. Proposed cluster of KVKs (3 to 5 neighboring KVKs) to be formed for sharing knowledge/expertise, resources and activities

| # | Name of the KVK included in the cluster | Nature of sharing |  |  |
| --- | --- | --- | --- | --- |
|  |  | Knowledge/expertise | Resources (facilities and products) | Activities |
| 1 | KVK, Bangalore Rural | Nursery management | Seedlings and grafting methods | Trainings |
| 2 | KVK, Hiriyur | Seed production in Onion, groundnut and mechanization | Seed production techniques and farm mechanization | FLD & Trainings |
| 3 | KVK, Kolar | Water budgeting and tree mulberry cultivation | Water budgeting techniques, scientific management of tree mulberry | FLD & Trainings exposure visit |
| 4 | KVK, Tumakuru 1 (Konehalli) | Millets cultivation and value addition | Scientific cultivation methods and marketing through CBA | FLD & Trainings |
| 5 | KVK, Tumakuru 2 (Hirehalli) | Mushroom cultivation, nursery & Amla processing | Spawn production, group approach & value addition | FLD & Trainings exposure visit |

6. Plan of Work for 2018-19

A. Operational areas details proposed

| # | Taluk/ block | Name of cluster villages | Major crops & enterprises being practiced | Major problems identified | Identified thrust areas based on problems | If existing from which year |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Existing |  |  |  |  |
| 1 | Ramanagara | 1. Kailancha cluster K. P. Doddi, Aerahalli, Kurubarahalli, Kailancha | Mango Ragi Shade Loving Guinea grass Mulberry, Coconut, Ragi and value addition | Soil and water erosion, low moisture and retention in mango, local long duration varieties, Low yield from conventional fodder crop – Maize (Green Fodder yield -single cut 60 t /ha), Non-av suitable Multicut fodder crops–shade loving, Low mulberry yield due to non application of balanced Nutrients, Poor nutrient status of soil affecting leaf quality, More than 50% soils are deficit in Zn & B (ICRISAT & NBSS&LUP), Non application of micro nutrients, Laborious pre & post harvest operations, Drudgery, High cost of cultivation Less acceptability of value added products from existing varieties due to dark & brown color, Lack of knowledge on processing, value addition, labeling, packaging and branding | ICM, INM, IPDM, S&WC conservation, Farm Mechanization & value addition | 2016-17 |
|  |  | 2. Kootgal cluster Shanuboganahalli, Doddanagavadi, Medaradoddi Kootagal | Mango, Mushroom, Nutrition garden, composting farm waste | Low yield due to Leaf hoppers, PM & fruit fly, Indiscriminate use of chemicals, Severity : 70%Soil and water erosion, low moisture and retention in mango, local long duration varieties, Malnutrition due to mono type vegetable consumptions in schools, Non utilization of resources- Water, Space & organic waste, Low income realization in SHGs, Lack of awareness on nutritious foods, Malnutrition among Vulnerable groups, Unscientific disposal of organic wastes Environmental contamination affecting Soil fertility | IPDM, INM, S&WC and Value addition | 2016-17 |
| 2 | Channapattana | 3. Thimmasandra cluster Harokuppa Thimmasandra, Neralur, Iglur | Fodder, mango, ragi, redgram, composting farm waste | Conventional fodder crop – less yield (Maize single cut 50 t /ha), Unaware about the availability of suitable multi-cut fodder for moisture stress conditions, Soil and water erosion, low moisture and retention in mango, Unscientific disposal of organic wastes, Environmental contamination affecting Soil fertility | ICM, IPDM, INM | 2017-18 |
| 3 | Kanakapura | 4. Chikmaduvadi cluster Gottigere, Chikmaduvadi Maralavadi | Groundnut, ragi, value addition, composting farm waste | Low yield in ground nut– variety (TMV-2 / Samrat) Rust & Leaf Spot, Non adoption of intercropping system, (Var & Diseases), Unscientific disposal of organic wastes, Environmental contamination affecting Soil fertility, Less acceptability of value added products from existing varieties due to dark & brown color, Lack of knowledge on processing, value addition, labeling, packaging and branding | ICM, Value addition | 2016-17 |
| 4 | Magadi | 5. Motaganahalli cluster Basavenahalli Nesepalya, CR halli, Honnaianapalya, Gundammanapalya, Motaganahalli | Fodder, cabbage, groundnut, mechanization, mulberry, guava, Jasmine, composting farm waste | Non application of Micro nutrients, Nutrient deficiency symptoms observed, More than 50% soils are deficit in Zn & B, High cost & timely non-availability of draught power, High seed rate Time consuming & Drudgery, High cost of labour, Low yield & income, Low yield - DM, PM, Leaf miner, Fruit fly & flower drop, Severe crop & yield loss due to wilt & insect pests, Low yield – variety (TMV-2 /Samrat), Rust & Leaf Spot, Laborious inter cultivation & postharvest operations, High cost of labour, non-mechanized operations, Low yield under repeated cutting-Gliricidia, Low milk & fodder yield during lean period, Unscientific disposal of organic wastes, Environmental contamination affecting Soil fertility, Low yield due to poor nutrient management, Kajji bug & fruit fly incidence, Fruit rot and Anthracnose disease | ICM, IPDM, INM, Mechanization, PHT | 2017-18 |
|  |  | 6. Hosapalya, cluster Sugganalli. Bettahalli, Hoojagal, Solur Hosapalya | Redgram, cabbage, Ragi, pea, Nutrition garden, Fishery, Field bean, | Low yield – non availability of improved varieties Yellow mosaic disease severity, Severe crop & yield loss due to wilt & insect pests, Low yield, Lack of photo insensitive var, Local- longer duration, Non application of micronutrients, Indiscriminate use of NPK, High cost of cultivation and less profit, Malnutrition due to mono type vegetable consumptions in schools, Non utilization of resources- Water, Space & organic waste, Non adoption of CFC & Poor Management | ICM, IPDM, INM, Value addition, Fish culture | 2015-16 |

B. Prioritized problems and KVK interventions proposed

| Crop/ enterprise | Taluk/ block | Prioritized problems | Technological solution | Interventions proposed (please tick) |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | OFT | FLD | Training | Extension programmes | Production of technology inputs |
| Fodder, Ragi, Millet, Cowpea, Composting farm waste, Cabbage, Drudgery, Jasmine, Garden pea, Guava, Mechanization, Nutrition garden, Fish, Redgram, pole beans | Magadi | Low yield from traditional fodder shrubs-Gliricidia Only dry fodder during lean period-low milk yield Finger millet sole crop – low income, Non utilization of pre-monsoon rainfall, Unscientific disposal of organic wastes, Environmental contamination affecting Soil fertility, Severe yield loss due to (DBM), High cost & timely non-availability of draught power , High seed rate, Labor and time consuming, Highly perishable, Small holdings, Low price during glut, Low preference on second day, Lack of knowledge on storage, Shelf life affected -70-80%, Non application of Micro nutrients, Nutrient deficiency symptoms observed, More than 50% soils are deficit in Zn & B, Non application of micronutrients, Indiscriminate use of NPK, High cost of cultivation and less profit, Low yield due to poor nutrient management, Kajji bug & fruit fly incidence, Fruit rot and Anthracnose disease, Laborious pre & post harvest operations, Drudgery, High cost of cultivation, Non-mechanized: 90 %, Malnutrition due to mono type vegetable consumptions in schools, Non utilization of resources- Water, Space & organic waste, Non adoption of CFC & Poor Management, Yield gap: 60%, Imbalanced application of nutrients, Severe yield loss due to wilt & insect pests attack, Severity : 65 %, Low yield & income – Nutrient deficiency, Pests & Diseases |  | √ | √ | √ | √ | √ |
| Redgram, Composting farm waste, Value addition | Kanakapura | Low yield – variety (TMV-2 / Samrat), Rust & Leaf Spot, Non adoption of intercropping system (Var & Diseases), Unscientific disposal of organic wastes, Environmental contamination affecting Soil fertility, Less acceptability of value added products from existing varieties due to dark & brown color, Lack of knowledge on processing, value addition, labeling, packaging and branding |  | √ | √ | √ | √ | √ |
| Fodder, Composting farm waste | Channapattana | Conventional fodder crop – less yield (Maize single cut 50 t /ha), Unaware about the availability of suitable multi-cut fodder for moisture stress conditions, Unscientific disposal of organic wastes Environmental contamination affecting Soil fertility |  | √ | √ | √ | √ | √ |
| Fodder, coconut, Mulberry, Mango, Mango, Nutrition Garden, Mushroom | Ramanagara | Conventional fodder crop–low yield (Maize single cut 50 t /ha), Non adoption of suitable multi- cut fodder crops–shade loving, Non-utilization of space in coconut gardens, Low mulberry yield due to non application of balanced Nutrients, Poor nutrient status of soil affecting leaf quality, More than 50% soils are deficit in Zn & B (ICRISAT & NBSS&LUP), Non application of micro nutrients, Low yield due to Leaf hoppers, PM & fruit fly, Indiscriminate use of chemicals, Laborious pre & post harvest operations, Drudgery, High cost of cultivation, Low soil fertility due to erosion, Low water retention, Poor growth & Low yield (50%), Improper management (85%), Malnutrition due to mono type vegetable consumptions in schools, Non utilization of resources- Water, Space & organic waste, Low income realization in SHGs, Lack of awareness on nutritious foods, Malnutrition among Vulnerable groups, soil and water erosion, poor mango orchard management, loss in yield due to low moisture retention in mango |  | - | √ | √ | √ | √ |

7. Details of technological interventions

## Technology Assessment

7.A.1. Crops

| SN | Title | Thematic Area | Crop Category | Crop Name | Variety / Hybrid Name | Farming Situation | Problem Definition | Area (ha) | No. of Trials | Critical Inputs Provided & Total Amount (DBT) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  | 9 | 10 |
| 1 | Performance of perennial shrub fodder-Var. Chaya Cnidoscolus aconitifolius Family: Euphorbiaceae | ICM | Perennial Fodder | Fodder | Chaya | Partial irrigated | Low yield from traditional fodder shrubs-Gliricidia Only dry fodder during lean period-low milk yield | 0.5 | 5 | Nutrient management @ 200:80:80 Kg NPK/ha - Rs. 5000 |
| 2 | Assessment of double cropping system in rainfed condition for higher returns | Double cropping system | Field crops | Cowpea, field bean, sesamum and finger millet | IT-38956-1, HA-4, GT-1/ TMV-3 & GPU-28 | Rainfed | Finger millet sole crop – low income Non utilization of pre-monsoon rainfall | 4 | 5 | Cowpea seeds, Ragi seeds Field bean seeds, Sesame seeds, PSB, rhizobium & Azospirillum, Herbicide-Pendimethalin, PP chemicals; dimithoate & Chlorpyriphos –Rs. 25750 |
| 3 | Assessment of effective management practices for diamond black moth in cabbage | IPDM | Vegetable | Cabbage | - | Rainfed | Severe yield loss due to (DBM) Plutella xylostella Severity: 50-55% | 1 | 7 | Mustard seeds, DBM traps, Sticky traps, Neem & Pongamia soap, Bacillus thuringeinsis Beauveria bassiana, Spinosad (Microbial), Chlorfenapyr, Emamectin benzoate –Rs. 44330 |

| SN | Title | Male |  | Female |  | Farmers Practice | Recommended Practice (RP) | Source of Technology (RP) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Others | SC/ST | Others | SC/ST |  |  |  |
| 1 | 2 | 11 | 12 | 13 | 14 | 15 | 16 | 17 |
| 1 | Performance of perennial shrub fodder-Var. Chaya Cnidoscolus aconitifolius Family: Euphorbiaceae | 5 | - | - | - | Gliricidia | Stylosanthes | IGFRI- Dharwad 2014 |
| 2 | Assessment of double cropping system in rainfed condition for higher returns | 2 | 1 | 2 | - | Sole finger millet | Cowpea -Finger millet | UAS, B |
| 3 | Assessment of effective management practices for diamond back moth in cabbage | 3 | 1 | 2 | 1 | Flubendiamide (0.05%), Emamectin benzoate (0.05%), Spinosad (0.15) %, Fipronil (0.15)%, Rynaxypyr (0.025%), Novaluron (0.15%, Chlorofenapyr (0.1%), Chloropyriphos (0.2%), Deltamethrin (0.15%), Dichlorvos (0.2%), Lambdacylothrin (0.1%), Thiodicarb (0.2%) | Intecropping with Mustard (25:2), Spray the crop with Dichlorvos (0.05%) and 5% NSKE, | UAS (B), |

| SN | Title | Tech. Option1 | To1: Source of Technology | Tech. Option2 | To2: Source of Technology | Tech. Option3 | To3: Source of Technology | Tech. Option4 | To4: Source of Technology |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 |
| 1 | Performance of perennial shrub fodder-Var. Chaya Cnidoscolus aconitifolius Family: Euphorbiaceae | Gliricidia | FP | Stylosanthes | UAS (B) | Hedge leucerne | UAS-B | Chaya | IGFRI- Dharwad 2014 |
| 2 | Assessment of double cropping system in rainfed condition for higher returns | Sole finger millet | FP | Cowpea -Finger millet | UAS (B) | Field bean (Vegetable)-Finger millet | UAS (B) | Sesamum-Finger millet | UAS (B) |
| 3 | Assessment of effective management practices for diamond back moth in cabbage | Flubendiamide (0.05%), Emamectin benzoate (0.05%), Spinosad (0.15)%, Fipronil (0.15)%, Rynaxypyr (0.025%), Novaluron (0.15%, Chlorofenapyr (0.1%), Chloropyriphos (0.2%), Deltamethrin (0.15%), Dichlorvos (0.2%), Lambdacylothrin (0.1%), Thiodicarb (0.2%) | FP | Intecropping with Mustard (25:2), Spray the crop with Dichlorvos (0.05%) and 5% NSKE | UAS (B) | Intercropping with Mustard (trap crop) (25:2), Installation of WOTA-T traps (DBM traps), Use of Sticky traps, Spray of Bt (1g/l), Neem Soap (5g/l), Entomopathogenic fungi (Beauveria bassiana) (0.2%), Emamectin benzoate 5SG (0.05%), Chlorfenapyr 10SC (0.1%), Spinosad 2.5SC (0.15%) | IIVR, Varanasi | - | - |

| SN | Title | Primary Parameter (yield) | Primary Parameter Unit(Q/ha) | Secondary Parameter1 | Secondary Parameter Unit1 | Secondary Parameter2 | Secondary Parameter Unit2 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 26 | 27 | 28 | 29 | 30 | 31 |
| 1 | Performance of perennial shrub fodder-Var. Chaya Cnidoscolus aconitifolius Family: Euphorbiaceae | Survival | % | Green biomass yield | q/ha | Palatability | % |
| 2 | Assessment of double cropping system in rainfed condition for higher returns | Growth of plant | Cm | Yield | q/ha | BC ratio | Ratio |
| 3 | Assessment of effective management practices for diamond back moth in cabbage | DBM incidence | % | Yield | q/ha | BC ratio | Ratio |

7.A.2. Livestock - Nil

7.A.3. Enterprise – Nil

7.A.4. Farm Implement

| S. No. | Title | Thematic Area | Farm Implement Name | Unit Size (Nos) | Problem Definition | No. of Trials | Critical Inputs Provided & Total Amount (DBT) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |
| 1 | Assessment of modified manual operated seed cum fertilizer drill for ragi sowing | Farm mechanization | Manual drawn seed cum fertilizer drill | 1 | High cost & timely non-availability of draught power, High seed rate, Labor and time consuming | 5 | Refinement of manual operated seed drill – Rs. 4000 |

| SN | Title | Male |  | Female |  | Farmers Practice | Recommended Practice (RP) | Source of Technology RP |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Others | SC/ST | Others | SC/ST |  |  |  |
| 1 | 2 | 9 | 10 | 11 | 12 | 13 | 14 | 15 |
| 1 | Assessment of modified manual operated seed cum fertilizer drill for ragi sowing | 3 | 1 | 1 | - | Bullock drawn | Mechanization | KVK, Ramanagara |

| SN | Title | Tech. Option1 | To1: Source of Technology | Tech. Option2 | To2: Source of Technology | Tech. Option3 | To3: Source of Technology | Tech. Option4 | To4: Source of Technology |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 |
| 1 | Assessment of modified manual operated seed cum fertilizer drill for ragi sowing | Bullock drawn seed drill | FP | Manual operated seed cum fertilizer drill with 3 seed bowls | KVK, R | - | - | - | - |

| SN | Title | Primary Parameter (Yield) | Primary Parameter Unit (Q/ha) | Secondary Parameter1 | Secondary Parameter Unit1 | Secondary Parameter2 | Secondary Parameter Unit2 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 24 | 25 | 26 | 27 | 28 | 29 |
| 1 | Assessment of modified manual operated seed cum fertilizer drill for ragi sowing | Yield | q/ha | Field capacity | ha/hr | Field efficiency | % |

7.B Frontline Demonstrations

7.B.1. Crops

| SN | Title | Thematic Area | Crop Category | Crop Name | Variety / Hybrid Name | Farming Situation | No. of demos | Area (ha) | Season | Previous Crop |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |
| 1 | Intercropping of redgram in groundnut for enhanced income | ICM | Field crop | Groundnut Redgram | GKVK-5 & BRG-5 | Rainfed | 10 | 2 | Kharif | Groundnut |
| 2 | Demonstration of Multicut Fodder: COFS-31/ COFS-29 | ICM | Fodder | Fodder sorghum | COFS-31 | Partial irrigation | 10 | 1 | Kharif & rabi | Fodder |
| 3 | Demonstration of shade loving guinea grass var. DGG-1 in coconut garden | ICM | Fodder | Guinea grass | DGG-1 | Partial irrigation | 10 | 1 | Kharif | Fodder |
| 4 | Integrated nutrient management in Mulberry | INM | Commercial crop | Mulberry | - | Partial irrigation | 5 | 2 | Kharif | Mulberry |
| 5 | Integrated crop management in Cabbage | ICM | Vegetable | Cabbage | - | Partial irrigation | 5 | 1 | Kharif | Vegetables |
| 6 | Integrated crop management in Garden Pea (Magadi Local) | ICM | Vegetable | Garden pea | Magadi local | Partial irrigation | 5 | 1 | Kharif | Vegetables |
| 7 | Integrated pest and disease management in mango | IPDM | Fruit | Mango | - | Rainfed | 5 | 4 | Rabi | Mango |
| 8 | Integrated crop management in Guava | ICM | Fruit | Guava | - | Rainfed | 5 | 2 | Kharif | Guava |
| 9 | In-situ moisture conservation practices in mango orchard | S & WC | Fruit | Mango | - | Raifned | 10 | 2 | Rabi | Mango |
| 10 | Nutri-garden for nutritional security among farm families | Health & nutrition | Fruits & vegetables | Fruits & vegetables | - | Irrigation | 3 | - | Kharif & rabi | - |
| 11 | Demonstration of ragi var. KMR 340 & value addition | Value addition | Field crop | Ragi | KMR-340 | Rainfed | 2 | 0.8 | Kharif | Ragi |
| 12 | Integrated crop management in redgram var. BRG-5 (NFSM) | ICM | Field crop | Redgram | BRG-5 | Rainfed | 25 | 10 | Kharif | Redgram |
| 13 | Introduction of potential crop Rice-bean-Var. KBR-1 | ICM | Field crop | Rice bean | KBR-1 | Rainfed | 4 | 0.4 | Kharif | Field crop |

| SN | Title | Male |  | Female |  | Farmers Practice | Recommended Practice | Source of Technology Recommended Practice |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Others | SC/ST | Others | SC/ST |  |  |  |
| 1 | 2 | 10 | 11 | 12 | 13 | 14 | 15 | 16 |
| 1 | Intercropping of redgram in groundnut for enhanced income | 5 | 2 | 2 | 1 | Sole crop | Intercropping of redgram in groundnut | UAS (B) |
| 2 | Demonstration of Multicut Fodder: COFS-31/ COFS-29 | 6 | 1 | 2 | 1 | Fodder Maize | Multi cut fodder | TNAU |
| 3 | Demonstration of shade loving guinea grass var. DGG-1 in coconut garden | 5 | 2 | 1 | 2 | Fodder Maize | Shade loving guinea grass | IGFRI, Jhansi |
| 4 | Integrated nutrient management in mulberry | 2 | 1 | 1 | 1 | Urea & FYM | RDF+Sulphur+ micro nutrient mixture+ bio-fertilizer | CSRTI, Mysore |
| 5 | Integrated crop management in Cabbage | 3 | - | 2 | - | RDF | RDF+AMC+ micro nutrient mixture | IIHR, Hesaraghatta |
| 6 | Integrated crop management in Garden Pea (Magadi Local) | 2 | 1 | 1 | 1 | Indiscriminate use of fertilizers | RDF+ micro nutrient mixture +AMC + sulphur | IIHR, Hesaraghatta |
| 7 | Integrated pest and disease management in mango | 2 | 1 | 2 | - | Indiscriminate use of chemicals | Judicious application of PP chemicals | IIHR, Hesaraghatta |
| 8 | Integrated crop management in guava | 3 | - | 2 | - | Poor management practices | Timely application of management practices | IIHR & TNAU |
| 9 | In-situ moisture conservation practices in mango orchard | 5 | 2 | 2 | 1 | No proper management | In-situ moisture conservation practices | TNAU, UAS (B) |
| 10 | Nutri-garden for nutritional security among farm families | 3 | 1 | 4 | 2 | - | AICRP model of nutrition garden | UAS (B) |
| 11 | Demonstration of ragi var. KMR 340 & value addition | - | - | 2 | - | No practice | Value addition | UAS (B) |
| 12 | Integrated crop management in redgram var. BRG-5 (NFSM) | 12 | 4 | 6 | 3 | Local variety | Wilt resistant BRG-5 | UAS (B) & UAS (R) |
| 13 | Introduction of potential crop Rice-bean-Var. KBR-1 | 4 | - | - | - | Local variety | potential crop Rice-bean-Var. KBR-1 | UAS, B |

| SN | Title | Critical Inputs Provided & Total Amount (DBT) | Primary Parameter (Yield) | Primary Parameter Unit (Q/ha) | Secondary Parameter1 | Secondary Parameter Unit1 | Secondary Parameter2 | Secondary Parameter Unit2 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 17 | 18 | 19 | 20 | 21 | 22 | 23 |
| 1 | Intercropping of redgram in groundnut for enhanced income | Ground nut seeds, Red gram seeds for intercrop Seed treatment, Bio-fertilizer (Rhizobium & PSB), Chlorpyriphos (15ml/kg seed)-Root grub – Rs. 34200 | Yield | q/ha | Income | Rs. | BC ratio | Ratio |
| 2 | Demonstration of multicut fodder: COFS-31/ COFS-29 | Seeds and nutrient management – Rs. 7600 | Yield | q/ha | Palatability | Scale | BC ratio | Ratio |
| 3 | Demonstration of shade loving guinea grass var. DGG-1 in coconut garden | Root slips, nutrient management – Rs. 38030 | Yield | q/ha | Palatability | Scale | BC ratio | Ratio |
| 4 | Integrated nutrient management in Mulberry | Azotobacter, VAM, Bentonite Sulphur POSHAN – Rs. 15300 | Yield | q/ha | Soil nutrient | % | BC ratio | Ratio |
| 5 | Integrated crop management in cabbage | Seeds, Vegetable Special, AMC, Difenthiuron, – Rs. 32175 | Yield | q/ha | Soil nutrient | % | BC ratio | Ratio |
| 6 | Integrated crop management in garden pea (Magadi local) | AMC, Vegetable Special, Carbendazim, Flubendiamide – Rs. 12870 | Yield | q/ha | Soil nutrient | % | BC ratio | Ratio |
| 7 | Integrated pest and disease management in mango | Mango special, Lamda cyhalothrin & Imidacloprid, Sealer-Healer+ CoC+DDVP, Traps, Wettible Sulphur & Hexaconazole – Rs. 32660 | Yield | q/ha | Incidence of leaf hopper | % | BC ratio | Ratio |
| 8 | Integrated crop management in guava | ZnSo4, Boric acid, Potassium Chloride, Dimethoate, Traps & Deltamethrin, Dithane M-45, Thiaphenate Methyl – Rs. 12260 | Yield | q/ha | Kajji bug damage | % | BC ratio | Ratio |
| 9 | In-situ moisture conservation practices in mango orchard | Micro catchment techniques, Vetivera grass, macuna seeds, mango special, - Rs. 31000 | Yield | q/ha | Fruit retention | % | BC ratio | Ratio |
| 10 | Nutri-garden for nutritional security among farm families | Vegetable seeds Kit, Seedlings (curry leaf, amla, lime, drumstick, pomello, papaya, citron, Chakramuni, guava & sapota), Neem soap, Neem cake, AMC, Vegetable Special, Compost culture, sprayer – Rs. 45000 | Yield | q/ha | Food adequacy | % | BC ratio | Ratio |
| 11 | Demonstration of ragi var. KMR 340 & value addition | Seeds, weighing balance, sealing machine, packaging materials & lables – Rs. 22400 | Yield | q/ha | Consumer preference | Scale | BC ratio | Ratio |
| 12 | Integrated crop management in redgram var. BRG-5 (NFSM) | BRG-5 Seeds (15 kg) /ha @ 150/kg Recommended Dose of Fertilizers, Pulse magic, Trichoderma viridae 2.5 kg / ha @ 150/ kg, HaNPV – 200 ml, Pheramone traps + Lures, PP Chemicals: (Chlorantranaliprole-pod borer, profenofos-Maruca, propargite-mites) Soil sample analysis (Pre & Post) @150/ sample, Cycle Weeder - 2 Nos. (custom hiring) – Rs. 98350 | Yield | q/ha | Wilt incidence | % | BC ratio | Ratio |
| 13 | Introduction of potential crop Rice-bean-Var. KBR-1 | Seeds @15kg/ha, Bio fertilizers (Rhizobium &PSB @1kg/ha), Nutrient management (40:40:20 kg NPK/ha), Need based PP measures, Dimithoate @1.7 ml/litre, Profinophos @2 ml/litr, Mancozeb @2gm/litr – 6940 | Yield | q/ha | Bo. of branches/ plant | Number | No. of pods/ plant | number |

7.B.2. Livestock

| SN | Title | Thematic Area | Livestock Category | Livestock Name | No. of units | No. of Demos |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |
| 1 | Demonstration of composite fish culture in farm ponds | Scientific fish cultivation | Fishery | Catla, Rohu, Grass carp, Common carp | 5 | 5 |

| SN | Title | Male |  | Female |  | Farmers Practice | Recommended Practice | Source of Technology Recommended Practice |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Others | SC/ST | Others | SC/ST |  |  |  |
| 1 | 2 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |
| 1 | Demonstration of composite fish culture in farm ponds | 3 | - | 2 | - | Mono culture | Composite fish culture cultivation | UAS (B) |

| SN | Title | Critical Inputs Provided & Total Amount (DBT) | Primary Parameter | Primary Parameter Unit | Secondary Parameter1 | Secondary Parameter Unit1 | Secondary Parameter2 | Secondary Parameter Unit2 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 17 | 18 | 19 | 20 | 21 | 22 | 23 |
| 1 | Demonstration of composite fish culture in farm ponds | Fingerlings, initial feed – Rs. 13500 | Yield | Kgs | Survivability | % | BC ratio | Ratio |

7.B.3. Enterprise

| SN | Title | Thematic Area | Enterprise | Livestock Name | Variety / Species | No. of units | No of Demos |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |
| 1 | Oyster mushroom production for nutrition & economic security | IGA | Mushroom production | - | Oyster | 2 | 2 |
| 2 | Osmotic dehydration of fruit bits for enhanced income | Value addition & marketing | Dry fruit bits production | - | - | 1 | 1 |

| SN | Title | Male |  | Female |  | Farmers Practice | Recommended Practice | Source of Technology Recommended Practice |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Others | SC/ST | Others | SC/ST |  |  |  |
| 1 | 2 | 9 | 10 | 11 | 12 | 13 | 14 | 15 |
| 1 | Oyster mushroom production for nutrition & economic security | - | - | 2 | - | No practice | Scientific mushroom cultivation | IIHR, Bangalore |
| 2 | Osmotic dehydration of fruit bits for enhanced income | - | - | 1 | - | No practice | Osmotic dehydration & production of dry fruit bits | IIHR, Bangalore |

| SN | Title | Critical Inputs Provided & Total Amount (DBT) | Primary Parameter | Primary Parameter Unit | Secondary Parameter1 | Secondary Parameter Unit1 | Secondary Parameter2 | Secondary Parameter Unit2 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 17 | 18 | 19 | 20 | 21 | 22 | 23 |
| 1 | Oyster mushroom production for nutrition & economic security | Spawn, PP covers, packaging materials, lables, sprayer, Formaline - Rs. 15500 | Yield | Kgs | Income | Rs. | BC ratio | Ratio |
| 2 | Osmotic dehydration of fruit bits for enhanced income (EDP mode) | Silpaulin sheet, Weighing balance, Sealing Machine, Refractometer, Packing and labeling material, technology cost – 30000 | Yield | Kgs | Profit | Rs. | Consumer preference | Scale |

7.B.4. Farm Implement

| SN | Title | Thematic Area | Farm Implement Name | Cost of Implement | Area (ha) | Season | Labour Required (Check) | Labor Required (demo) | % save | Time saved to cover/ha (hrs) | No. of demos |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| 1 | Mechanization in groundnut (GKVK-5) from pre to post-harvest operations | Farm mechanization | Tractor drawn seed cum fertilizer drill, | 55000 | 4 | Kharif/ Rabi | 10 | 3 | 50 | 35 | 10 |
|  |  |  | Cycle weeder, | 2500 |  |  |  |  |  |  |  |
|  |  |  | Solar sprayer, | 8000 |  |  |  |  |  |  |  |
|  |  |  | Thresher | 105000 |  |  |  |  |  |  |  |
| 2 | Integrated crop management in Ragi KMR-630 & mechanization | Farm mechanization | Tractor drawn seed drill, | 55000 | 4 | Kharif/ Rabi | 15 | 5 | 58 | 45 | 10 |
|  |  |  | Combined Harvester | 600000 |  |  |  |  |  |  |  |
|  |  |  | Ragi harvester | 101000 |  |  |  |  |  |  |  |

| SN | Title | Male |  | Female |  | Farmers Practice | Recommended Practice | Source of Technology Recommended Practice |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Others | SC/ST | Others | SC/ST |  |  |  |
| 1 | 2 | 13 | 14 | 15 | 16 | 17 | 18 | 19 |
| 1 | Mechanization in groundnut (GKVK-5) from pre to post-harvest operations | 6 | 1 | 2 | 1 | Manual operation | Mechanization | UAS, B & UAS, R |
| 2 | Integrated crop management in Ragi KMR-630 & mechanization | 5 | 2 | 3 | - | Manual operation | Mechanization | UAS, B & UAS, R |

| SN | Title | Critical Inputs Provided & Total Amount (DBT) | Primary Parameter (Yield) | Primary Parameter Unit (Q/ha) | Secondary Parameter1 | Secondary Parameter Unit1 | Secondary Parameter2 | Secondary Parameter Unit2 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 17 | 18 | 19 | 20 | 21 | 22 | 23 |
| 1 | Mechanization in groundnut (GKVK-5) from pre to post-harvest operations | Custom hiring charges – Rs. 25000 | Yield | q/ha | Field capacity | Ha/hr | Field efficiency | % |
| 2 | Integrated crop management in Ragi KMR-630 & mechanization | Custom hiring charges – Rs. 23500 | Yield | q/ha | Field capacity | Ha/hr | Field efficiency | % |

C. Trainings

| SN | Training Category (OFT/ FLD/Oth) | Training Type (Regular/ Vocational/ Sponsored/ Rural Youth/ Extension ) | Training location (On/Off) | Training For (General Rural Youth/ Extension ) | Duration (Days) | Title | Thematic Area |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |
| 1 | FLD | Regular | On | General | 2 | Entrepreneurship development through processing and value addition to millets | Value addition |
| 2 | FLD | Regular | On | General | 2 | Processing and value addition to horticulture crops for higher returns | Value addition |
| 3 | FLD | Regular | On | General | 2 | Utilization of underutilized foods towards achieving nutrition security | Nutrition security |
| 4 | FLD | Regular | On | General | 2 | Mushroom Cultivation for nutrition and economic security | Nutrition security |
| 5 | FLD | Regular | On | General | 2 | Resource conservation technologies in Agriculture engineering | Farm Machinery |
| 6 | FLD/ OFT | Regular | On | General | 2 | Effective management of time, labour & money through mechanization in Ragi and Groundnut | Farm Machinery |
| 7 | FLD | Regular | On | General | 2 | Soil & Water conservation practices in in Mango | S & WC |
| 8 | FLD | Regular | On | General | 2 | Effective structures to conserve soil & water erosion in undulated areas | S & WC |
| 9 | Others | Regular | On | Extn. Functionaries | 1 | Addressing malnutrition among schools children through nutrition garden and hygiene | Nutrition security |
| 10 | Others | Regular | On | General | 1 | Diabetes Mellitus- Causes, complications & management | Health and nutrition |
| 11 | OFT | Regular | On | General | 2 | Double cropping system for higher yield and returns under rainfed conditions | ICM |
| 12 | FLD | Regular | On | General | 2 | Improved Production Practices in Groundnut | ICM |
| 13 | FLD | Regular | On | General | 2 | Herbicide application technology in field crops | ICM |
| 14 | FLD | Regular | On | General | 2 | Importance of soil health &nutrient management | Soil health |
| 15 | OFT | Regular | On | General | 2 | Agricultural waste recycling – efficient method of composting | Waste recycling |
| 16 | OFT/FLD | Regular | On | General | 2 | IPDM in cabbage | IPDM |
| 17 | FLD | Regular | On | General | 2 | ICM in guava | ICM |
| 18 | FLD | Regular | On | General | 2 | IPDM in mango | IPDM |
| 19 | FLD | Regular | On | General | 2 | Holistic management of redgram | ICM |
| 20 | Others | Regular | On | General | 2 | Awareness on health and nutrition for municipal workers | Health and nutrition |
| 21 | OFT | Regular | On | General | 2 | Different storage techniques to enhance shelf life of jasmine | Shelf life |
| 22 | OFT | Regular | On | General | 2 | Integrated nutrient management | INM |
| 23 | FLD | Regular | On | General | 2 | Effective structures to conserve soil & water erosion in undulated areas | Soil and Water conservation |
| 24 | FLD | Regular | On | General | 2 | ICM in cabbage | ICM |
| 25 | Others | Regular | Off | General | 1 | Nutritional importance of Mango & jack & its Value Addition | Value addition |
| 26 | FLD | Regular | Off | General | 1 | Importance of Nutrition garden and its layout | Nutrition security |
| 27 | FLD | Regular | Off | General | 1 | Biodegradable waste management for healthy environment | Soil health |
| 28 | Others | Regular | Off | General | 1 | Nutritional importance of milk & value addition | Value addition |
| 29 | Others | Regular | Off | Extn. Functionaries | 1 | Integrated approaches to address of malnutrition among adolescent girls | Food and nutrition |
| 30 | Others | Regular | Off | Extn. Functionaries | 1 | Integrated approaches to address Malnutrition among preschool children. | Health and nutrition |
| 31 | Others | Regular | Off | General | 1 | Demonstration of Mushroom production & value addition | Value addition |
| 32 | Others | Regular | Off | General | 1 | Anemia management through healthy regional foods | Health and nutrition |
| 33 | Others | Regular | Off | General | 1 | Demonstration of Lemon harvester to reduce drudgery | Farm machinery |
| 34 | Others | Regular | Off | General | 1 | Functional clothing to address safety and hygiene during threshing | Safety measures |
| 35 | FLD | Regular | Off | General | 1 | Engineering measures in S&WC | Soil and water conservation |
| 36 | FLD | Regular | Off | General | 1 | Moisture conservation in Mango using Micro-catchment techniques | Soil and water conservation |
| 37 | FLD | Regular | Off | General | 1 | Demonstration of Multi-Crop thresher in Ragi | Farm machinery |
| 38 | FLD | Regular | Off | General | 1 | Mechanization in ground nut | Farm machinery |
| 39 | OFT | Regular | Off | General | 1 | Drudgery reducing tools and equipments in Field crops | Farm machinery |
| 40 | FLD | Regular | Off | General | 1 | Inter cultivation and Weed management using Cycle weeder | Farm machinery |
| 41 | Others | Regular | Off | General | 1 | Demonstration of Solar powered Knapsack Sprayer in groundnut | Farm machinery |
| 42 | OFT/FLD | Regular | Off | General | 1 | Ragi Reaper- A boon for Farmer in reducing labour shortage during Harvesting of ragi | Farm machinery |
| 43 | FLD | Regular | Off | General | 1 | Demonstration of Seed Treatment in Millets and pulses | Seed treatment |
| 44 | FLD | Regular | Off | General | 1 | Demonstration of Seed Treatment in Groundnut and redgram | Seed treatment |
| 45 | OFT | Regular | Off | General | 1 | Demonstration on Preparation of Root slips in Fodder | ICM |
| 46 | FLD | Regular | Off | General | 1 | Demonstration of Soil sampling and Its Importance in Groundnut & Millets | Soil health |
| 47 | FLD | Regular | Off | General | 1 | Demonstration of Soil sampling and Its Importance in Millets | Soil health |
| 48 | FLD | Regular | Off | General | 1 | Method demonstration of nutrient application in guava eco-system | INM |
| 49 | Others | Regular | Off | General | 1 | Role of honey bees and other bees in pigeon pea | Honey bee |
| 50 | FLD | Regular | Off | General | 1 | Demonstration of HaNPV spraying for the management of Helicoverpa | IPM |
| 51 | FLD | Regular | Off | General | 1 | Demonstration of Soil sampling and Its Importance in Garden pea | IPDM |
| 52 | FLD | Regular | Off | General | 1 | Demonstration of Biofertilisers application in Mulberry | INM |
| 53 | FLD | Regular | Off | General | 1 | Safe use of pesticides in cabbage cultivation | IPM |
| 54 | FLD | Regular | Off | General | 1 | Method demonstration on herbicide application in field crops | IPDM |
| 55 | FLD | Regular | Off | General | 1 | Use of fruit fly traps in mango | IPDM |
| 56 | FLD | Regular | Off | General | 1 | Etiology of kajji bug in guava | IPDM |
| 57 | Others | Regular | Off | General | 1 | Importance of safety measures in plant protection | IPDM |
| 58 | Others | Regular | Off | General | 1 | Seed treatment method demonstration for soil and seed borne diseases and sucking pests | IPDM |

| SN | Sub Thematic Area | Skill is to impart? (Y/N) | Source of Fund(if sponsored) | Agency Name | Amount (Rs) | Others Male | Others Female | SC/ST Male | SC/ST Female |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 |
| 1 | Entrepreneurship development | Y | ICAR | - | - | 6 | 20 | 2 | 2 |
| 2 | Value addition | Y | ICAR | - | - | 8 | 18 | 1 | 3 |
| 3 | Nutrition | Y | ICAR | - | - | 12 | 22 | 4 | 6 |
| 4 | Nutrition | Y | ICAR | - | - | 10 | 20 | 2 | 3 |
| 5 | Farm Mechanization | Y | ICAR | - | - | 18 | 2 | 3 | 2 |
| 6 | Farm Mechanization | Y | ICAR | - | - | 22 | 4 | 1 | 1 |
| 7 | Soil & Water Conservation | Y | ICAR | - | - | 20 | 2 | 2 | 2 |
| 8 | Soil & Water Conservation | Y | ICAR | - | - | 22 | 4 | 3 | 2 |
| 9 | Nutrition security | N | ICAR | - | - | 18 | 4 | 3 | 2 |
| 10 | Nutrition security | N | ICAR | - | - | 12 | 18 | 3 | 2 |
| 11 | Cropping system | N | ICAR | - | - | 18 | 12 | 2 | 1 |
| 12 | Cropping system | N | ICAR | - | - | 18 | 12 | 2 | 1 |
| 13 | Cropping system | N | ICAR | - | - | 18 | 12 | 2 | 1 |
| 14 | Soil Health | N | ICAR | - | - | 18 | 12 | 2 | 1 |
| 15. | Waste recycling | Y | ICAR | - | - | 20 | 12 | 2 | 1 |
| 16. | Pest and disease management | N | ICAR | - | - | 20 | 12 | 2 | 1 |
| 17 | Cropping system | N | ICAR | - | - | 20 | 12 | 2 | 1 |
| 18 | Pest and disease management | N | ICAR | - | - | 20 | 12 | 2 | 1 |
| 19 | Cropping system | N | ICAR | - | - | 20 | 12 | 2 | 1 |
| 20 | Nutrition security | N | ICAR | - | - | 20 | 12 | 2 | 1 |
| 21 | Shelf life | N | ICAR | - | - | 20 | 12 | 2 | 1 |
| 22 | Nutrient management | N | ICAR | - | - | 20 | 12 | 2 | 1 |
| 23 | Soil and Water conservation | N | ICAR | - | - | 20 | 12 | 2 | 1 |
| 24 | Cropping system | N | ICAR | - | - | 20 | 12 | 2 | 1 |
| 25 | Value addition | Y | ICAR | - | - | 5 | 20 | 2 | 1 |
| 26 | Nutrition security | N | ICAR | - | - | 5 | 20 | 2 | 1 |
| 27 | Soil health | N | ICAR | - | - | 5 | 20 | 2 | 1 |
| 28 | Value addition | N | ICAR | - | - | 5 | 20 | 2 | 1 |
| 29 | Food and nutrition | N | ICAR | - | - | 8 | 20 | 2 | 1 |
| 30 | Health and nutrition | N | ICAR | - | - | 8 | 20 | 2 | 1 |
| 31 | Value addition | N | ICAR | - | - | 10 | 25 | 2 | 1 |
| 32 | Health and nutrition | N | ICAR | - | - | 10 | 25 | 2 | 1 |
| 33 | Farm machinery | N | ICAR | - | - | 18 | 12 | 2 | 1 |
| 34 | Safety measures | N | ICAR | - | - | 18 | 12 | 2 | 1 |
| 35 | Soil and water conservation | N | ICAR | - | - | 20 | 8 | 2 | 1 |
| 36 | Soil and water conservation | N | ICAR | - | - | 20 | 8 | 2 | 1 |
| 37 | Farm machinery | N | ICAR | - | - | 20 | 8 | 2 | 1 |
| 38 | Farm machinery | N | ICAR | - | - | 20 | 8 | 2 | 1 |
| 39 | Farm machinery | N | ICAR | - | - | 20 | 8 | 2 | 1 |
| 40 | Farm machinery | N | ICAR | - | - | 20 | 8 | 2 | 1 |
| 41 | Farm machinery | N | ICAR | - | - | 20 | 8 | 2 | 1 |
| 42 | Farm machinery | N | ICAR | - | - | 20 | 8 | 2 | 1 |
| 43 | Seed treatment | Y | ICAR | - | - | 20 | 8 | 2 | 1 |
| 44 | Seed treatment | Y | ICAR | - | - | 20 | 8 | 2 | 1 |
| 45 | Cropping system | Y | ICAR | - | - | 20 | 8 | 2 | 1 |
| 46 | Soil fertility | Y | ICAR | - | - | 20 | 8 | 2 | 1 |
| 47 | Soil health | Y | ICAR | - | - | 20 | 8 | 2 | 1 |
| 48 | Nutrient management | N | ICAR | - | - | 20 | 8 | 2 | 1 |
| 49 | Honey bee | N | ICAR | - | - | 20 | 8 | 2 | 1 |
| 50 | Pest management | N | ICAR | - | - | 20 | 8 | 2 | 1 |
| 51 | Pest and disease management | N | ICAR | - | - | 20 | 8 | 2 | 1 |
| 52 | Nutrient management | N | ICAR | - | - | 20 | 8 | 2 | 1 |
| 53 | Pest management | N | ICAR | - | - | 20 | 8 | 2 | 1 |
| 54 | Pest and disease management | N | ICAR | - | - | 20 | 8 | 2 | 1 |
| 55 | Pest and disease management | N | ICAR | - | - | 20 | 8 | 2 | 1 |
| 56 | Pest and disease management | N | ICAR | - | - | 20 | 8 | 2 | 1 |
| 57 | Pest and disease management | N | ICAR | - | - | 20 | 8 | 2 | 1 |
| 58 | Pest and disease management | N | ICAR | - | - | 20 | 8 | 2 | 1 |

D. Extension programme

| SN | Extension programme | No. of Programme | No. of Farmers/ participants | No. of Extension Officers |
| --- | --- | --- | --- | --- |
|  | Advisory over Phone | 1500 | 1500 | 300 |
|  | Bi-Monthly meeting | 6 | - | 300 |
|  | Celebration of Day | 9 | 450 | 45 |
|  | Diagnostic visit | 100 | 300 | 22 |
|  | Exhibition | 5 | 1000 | 30 |
|  | Exposure Visit | 5 | 250 | 20 |
|  | Ex-trainees Samelan | - | - | - |
|  | Extension Literature | 12 | - | - |
|  | Farmers Science conveners meeting | 2 | 50 | 10 |
|  | Farmer /Extension personnel visit to KVK | 500 | 450 | 50 |
|  | Farmers Seminar/ Workshop | 2 | 250 | 25 |
|  | Field day | 15 | 750 | 30 |
|  | Film Show | 20 | 750 | 50 |
|  | Formation of SHGs | 2 | 50 | - |
|  | Group Meeting | 25 | 225 | 55 |
|  | Kisan Ghosti | 5 | 250 | 20 |
|  | Kisan Mela | 1 | 150 | 22 |
|  | Lecture delivered as resource person | 150 | 5500 | 150 |
|  | Method demonstration | 125 | 650 | 250 |
|  | Newspaper coverage | 100 | - | - |
|  | No. of animals treated | 2 | 100 | 6 |
|  | Popular arterials | 72 | - | - |
|  | Radio talk | 20 | - | - |
|  | Scientist visit to Farmers Field | 750 | 1250 | 25 |
|  | SHC campaign | 6 | 500 | 20 |
|  | SHG meeting | 2 | 100 | 10 |
|  | Technical Reports | 52 | - | - |
|  | TV Talk | 15 | - | - |
|  | Other- Specify |  |  |  |
| Total |  | 3503 | 14525 | 1440 |

8. Activities proposed

- Mobile Advisory Services

| Message Type | Crops | Livestock | Weather | Marketing | Awareness | Other enterprise | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Text | 62 | 12 | 12 | 62 | 26 | 18 | 192 |
| Voice | 12 | 6 | 12 | 12 | 6 | 6 | 54 |
| Total | 74 | 18 | 24 | 74 | 32 | 24 | 246 |

- Seed/ Quality Planting Material

| Name of the Crop | Quantity to be Produced |  | Expected income (Rs) | Expected expenditure (Rs) | Net returns (Rs) |
| --- | --- | --- | --- | --- | --- |
|  | Seed (kg) | Planting Material (Nos) |  |  |  |
| Sunhemp – Local | 2000 | - | 1,40,000 | 60,000 | 80,000 |
| Horse gram – PHG-9 | 2000 | - | 1,20,000 | 45,000 | 75,000 |
| Ragi – ML-365 | 500 | - | 15,000 | 8,000 | 7,000 |
| Foxtail millet – DHFT-109-3 | 200 | - | 12,000 | 5,000 | 7,000 |
| Drumstick – PKM-1 | 5 | - | 10,000 | 2,000 | 8,000 |
| Pumpkin var. CO-1 | 20 | - | 24,000 | 8,000 | 16,000 |
| Grafts & saplings of fruit crops (Mango, Papaya, Sapota, Guava, lemon, tamarind, pomegranate, jamoon & Jack) | - | 15,000 | 6,00,00 | 2,50,000 | 3,50,000 |
| Drumstick seedlings – PKM-1 | - | 18,000 | 1,80,000 | 72,000 | 1,08,000 |
| Fodder slips (CO-4, CO-5, DHN-6) | - | 1,00,000 | 1,00,000 | 40,000 | 60,000 |

- Bio Products

| Name of the Bio Product | Quantity to be Produced |  | Expected income (Rs) | Expected expenditure (Rs) | Net returns (Rs) |
| --- | --- | --- | --- | --- | --- |
|  | Product (kg) | Others (Nos) |  |  |  |
| Mango Special | 2000 kgs | - | 3,00,000 | 1,80,000 | 1,20,000 |
| Banana Special | 2000 kgs | - | 3,00,000 | 1,80,000 | 1,20,000 |

- Home Care Production

| Name of Home product | Quantity to be Produced |  | Expected income (Rs) | Expected expenditure (Rs) | Net returns (Rs) |
| --- | --- | --- | --- | --- | --- |
|  | Product (kg) | Others (Nos) |  |  |  |
| Ragi malt | 50 | - | 10000 | 5000 | 5000 |
| Enriched ragi flour | 50 | - | 10000 | 5000 | 5000 |
| Arecanut plates | - | 8000 | 20000 | 12000 | 8000 |

- Livestock

| Name of Livestock | To be Produced (Nos) (Target) | Expected income (Rs) | Expected expenditure (Rs) | Net returns (Rs) |
| --- | --- | --- | --- | --- |
| Sheep | 3 | 15,000 | 6,000 | 9,000 |
| Goat | 5 | 25,000 | 10,000 | 15,000 |
| Chicks | 30 | 6,000 | 2,000 | 4,000 |
| Cattle (Milk) | 1500 | 45,000 | 27,000 | 13,000 |
| Fish | 2000 | 2,10,000 | 90,000 | 1,20,000 |

- Farm Production

| Name of Farm Produce | To be Produced |  | Expected income (Rs) | Expected expenditure (Rs) | Net returns (Rs) |
| --- | --- | --- | --- | --- | --- |
|  | Product (kg) | Others (Nos) |  |  |  |
| Coconut | - | 1,000 | 15,000 | 3,000 | 12,000 |
| Lemon | - | 1,000 | 2,000 | 600 | 1,400 |
| Mango | 3,750 | - | 1,50,000 | 35,000 | 1,15,000 |
| Cashew | 20 | - | 2,000 | 500 | 1,500 |
| Papaya | 250 | - | 2,500 | 1,200 | 1,300 |
| Jack fruit | 200 | - | 2,400 | 600 | 1,800 |
| Vegetables | - | - | 10,000 | 2,000 | 8,000 |

- Publication / Literature

| Item Name | Title | Auther/s Name | No. of circulation |
| --- | --- | --- | --- |
| Folder | Madhumeha nirvahane | Lata R. Kulkarni, Savita, S. M. & Syed Mazar Ali | 500 |
| Book let | Siridanyagala mahathva, samskarane mathu moulyavardhane | Lata R. Kulkarni, Savita, S. M., Syed Mazar Ali & Dinesh | 500 |
| Folder | Arogyavardhaka aharagalu | Lata R. Kulkarni, Savita, S. M. & Syed Mazar Ali | 500 |
| Booklet | Kushki besayadalli adhika labhakke 23ivid abele paddathigalu | Dinesh, Savita, S. M., Preethu, D. C. & Rajendraprasad | 500 |
| Folder | Bahu varshika bahu katavu mevina belegala adhunika thaligalu mathu basaya paddatigalu | Dinesh, Savita, S. M., Lata R. Kulkarni, & Syed Mazar Ali | 500 |
| Booklet | Jeevanadhare mannu | Preethu, D. C., Savith, S. M. & Dinesh, M.S. | 500 |
| Folder | Mannina nirvahane | Preethu, Savith, S. M. Dinesh, M.S. & Rajendraprasad | 500 |
| Folder | Mannu pareeksheya mahatva | Preethu, Savita, S. M. Rajendraprasad & Dinesh, M.S. | 500 |
| Folder | Elekosinalli parisara snehi peede mathu roga nirvahane | Rajendraprasad, Savita, Dinesh, M.S. & Syed Mazar Ali | 500 |
| Folder | Thogriyalli samagra bele nirvahane | Rajendraprasad, Savita, S. M., Dinesh, & Lata R. Kulkarni | 500 |
| Folder | Shenga beleyalli yanthrikarana | Syed Mazar Ali, Lata R. Kulkarni, Savita S. M., Ranganatha, Rajendra, Preethu & Dinesh | 500 |
| Folder | Meenu sakanike parichaya | Savita S. M., Lata R. Kulkarni & Ranganatha | 500 |
| Folder | Mushroom Cultivation | Savita S. M., Lata R. Kulkarni & Rajendraprasad | 500 |
| Total |  |  | 6500 |

- Electronic Media

| Media Type | Title | No. circulation | Developed by |
| --- | --- | --- | --- |
| CD | Introduction of GKVK-5 groundnut var. and its spread | 50 | KVK, Ramanagara |
| CD | Value addition to regional crops for enhanced income | 50 | KVK, Ramanagara |

- SWTL Activities

| Type | No. of samples to be analyzed | Names of the team members involved | Expected income (Rs) | Expected expenditure (Rs) | Net returns (Rs) |
| --- | --- | --- | --- | --- | --- |
| Soil | 500 | Soil Science & all Scientist | 75000 | 50000 | 25000 |
| Water | 150 | Soil Science & all Scientist | 22500 | 15000 | 7500 |
| Plant | 50 | Soil Science & all Scientist | 7500 | 5000 | 2500 |
| Others | - | - | - | - | - |

No. of SHC to be distributed: 500

- News letter

| Name | To be issue | No. of Soft copies to be issue | No. of hard copies to be issue |
| --- | --- | --- | --- |
| Krishi Chinthana | - | 42 | - |

- Technology Week

| Proposed Date | No. of agencies to be linked | Qty. Seeds supply | Qty. Planting material supply | Qty. bio products supply |
| --- | --- | --- | --- | --- |
| October 2018 | 5 | 100 kg | 1000 | 100 kg |

- Proposed Projects

| Project Name | Role of KVK | Duration | Project Outlay (Rs) | Additional Man Power to be planned |
| --- | --- | --- | --- | --- |
| Suitability of packaging materials for storage of food grains and flours at house hold levels | Project area | 1 year | 1,20,000 | - |
| Development of nutria-dense products from pearl millet for promoting self-employment | Project area | 1 year | 2,50,000 | - |

- Farmer’s Field School planned

| Thematic area | Title of the FFS | Budget proposed in Rs. | No. of farmers |
| --- | --- | --- | --- |
| Integrated Crop Management | IPDM in pole bean | 30000 | 25 |

- E-linkage

| SN | Nature of activities |  |
| --- | --- | --- |
| 1 | Is KVK has website (Y/N) | Yes |
| 2 | If NO, date of website to be develop & host | - |
| 3 | Name of the module assigned during Orientation Programme | External Funded projects |
| 4 | Plan, Progress and expected date of completion | June 2018 |

- KVK instructional farm Activities

| SN | Plot | Season | Area (ha) | Name of the crop | Expected Yield (kg) | Expected Expenditure (Rs) | Expected income (Rs) | Net returns (Rs) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | B | Kharif | 0.2 | Foxtail millet – DHFT-109-3 | 500 | 12,000 | 30,000 | 18,000 |
| 2 | B | Kharif | 0.2 | Pumpkin – CO-1 | 20 | 8,000 | 24,000 | 16,000 |

- Activities planned under Rainwater Harvesting Scheme (only to those KVKs which are already having scheme under Rain Water Harvesting)

| SN | Activities planned | Remarks if any |
| --- | --- | --- |
| - | - | - |

- Plan of other activities

| # | Proposed activities | Expected expenditure (Rs) | Expected income (Rs) | Net Returns (Rs) | Name of the team members involved |
| --- | --- | --- | --- | --- | --- |
| 1 | Hydrophonics for better nutrition among cattle’s | 10000 | 15000 | 5000 | Agron., Home Science & Farm Manager |

- Innovative Farmer’s Meet

| Particulars | Details |
| --- | --- |
| Are you planning for conducing Farm Innovators meet in your district? | No |
| If Yes likely month of the meet |  |
| Brief action plan in this regard |  |

10. Organic Farming

## Technology Assessment related to organic farming

| SN | Title | Thematic Area | Crop Category | Crop Name | Variety / Hybrid Name | Farming Situation | Problem Definition | Area (ha) | No. of Trials | Critical Inputs Provided & Total Amount (DBT) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  | 9 | 10 |
| 1 | Assessment of different compost culture in composting farm wastes | INM | - | - | - | - | Unscientific disposal of organic wastes Environmental contamination affecting Soil fertility | - | 5 | Neem coated urea, Compost bags, Compost start culture of IIHR, UASB, Waste decomposer of NCOF, Jaggery, Compost analysis charges – Rs. 32375 |

| SN | Title | Male |  | Female |  | Farmers Practice | Recommended Practice (RP) | Source of Technology (RP) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Others | SC/ST | Others | SC/ST |  |  |  |
| 1 | 2 | 11 | 12 | 13 | 14 | 15 | 16 | 17 |
| 1 | Assessment of different compost culture in composting farm wastes | 2 | 1 | 2 | - | Farm wastes + cow dung slurry | Farm wastes + Urea+ microbial culture | IIHR, Hesaraghatta UAS, Bangalore NCOF, Ghaziabad |

| SN | Title | Tech. Option1 | To1: Source of Technology | Tech. Option2 | To2: Source of Technology | Tech. Option3 | To3: Source of Technology | Tech. Option4 | To4: Source of Technology |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 |
| 1 | Assessment of different compost culture in composting farm wastes | Farm wastes + cow dung slurry | FP | Farm wastes + Urea+ microbial culture | IIHR, Hearaghatta | Farm wastes + cow dung slurry + microbial culture | UAS (B) | Farm waste + Waste decomposer | NCOF, Ghaziabad |

| SN | Title | Primary Parameter(Yield) | Primary Parameter Unit (Q/ha) | Secondary Parameter1 | Secondary Parameter Unit1 | Secondary Parameter2 | Secondary Parameter Unit2 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 26 | 27 | 28 | 29 | 30 | 31 |
| 1 | Assessment of different compost culture in composting farm wastes | Maturity indices | Ratio | Nutrient contents | % | % recovery in weight basis | % |

B. Frontline Demonstrations related to organic farming : Nil

C. Trainings related to organic farming

| SN | Training Category (OFT/ FLD/Oth) | Training Type (Regular/ Vocational/ Sponsored/ Rural Youth/ Extension ) | Training location (On/Off) | Training For (General Rural Youth/ Extension ) | Duration (Days) | Title | Thematic Area |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |
| 1 | OFT | Regular | On | General | 2 | Importance of soil health & nutrient management | Soil health |
| 2 | OFT | Regular | On | General | 2 | Agricultural waste recycling – efficient method of composting | Waste recycling |

| SN | Sub Thematic Area | Skill is to impart? (Y/N) | Source of Fund(if sponsored) | Agency Name | Amount (Rs) | Others Male | Others Female | SC/ST Male | SC/ST Female |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 |
| 1 | Soil Health | N | ICAR | - | - | 18 | 12 | 2 | 1 |
| 2 | Waste recycling | Y | ICAR | - | - | 20 | 12 | 2 | 1 |

D. Extension programme related to organic farming

| SN | Extension programme | No. of Programme | No. of Farmers/ participants | No. of Extension Officers |
| --- | --- | --- | --- | --- |
|  | Advisory over Phone | 300 | 250 | 50 |
|  | Bi-Monthly meeting | 1 | - | 50 |
|  | Celebration of Day | 2 | 150 | 20 |
|  | Diagnostic visit | 25 | 280 | 20 |
|  | Exhibition | 2 | 500 | 15 |
|  | Exposure Visit | 2 | 100 | 5 |
|  | Ex-trainees Samelan | - | - | - |
|  | Extension Literature | 5 | - | - |
|  | Farmers Science conveners meeting | 1 | 50 | 4 |
|  | Farmer /Extension personnel visit to KVK | 100 | 80 | 20 |
|  | Farmers Seminar/ Workshop | - | - | - |
|  | Field day | 1 | 50 | 5 |
|  | Film Show | 10 | 300 | 20 |
|  | Formation of SHGs | - | - | - |
|  | Group Meeting | 5 | 150 | 10 |
|  | Kisan Ghosti | 1 | 100 | 10 |
|  | Kisan Mela | 1 | 75 | 8 |
|  | Lecture delivered as resource person | 10 | 550 | 50 |
|  | Method demonstration | 6 | 180 | 20 |
|  | News paper coverage | 5 | - | - |
|  | No. of animals treated | - | - | - |
|  | Popular arterials | 6 | - | - |
|  | Radio talk | 2 | - | - |
|  | Scientist visit to Farmers Field | 18 | 35 | - |
|  | SHC campaign | - | - | - |
|  | SHG meeting | - | - | - |
|  | Technical Reports | 12 | - | - |
|  | TV Talk | 2 | - | - |
|  | Other- Specify | - | - | - |
| Total |  | 517 | 2850 | 307 |

E. Organic Certification is planned?  If Yes Details

F. Any other activity related to Organic farming. Pl specify.

11. Swachh Barat Abiyan

| Activity | Month | Details | No. of Participants/ Farmers |
| --- | --- | --- | --- |
| Swachhta pakwad | October 2018 | Awareness programmes, campaigns, shramadhan | 200 |
| Creating awareness through mass media | Every month | Articles through newspaper | - |
| Creating awareness through mass media | Every fortnight | Short messages through farmers portal | 3246 |
| Capacity building programme | May 2018 | Training progrmame to municipal workers | 35 |

12.Budget

- Revolving Fund (Rs in Lakh)

| Opening balance as on 01.04.2017 | Expenditure incurred during 2017-18 | Receipts during 2017-18 | Closing balance as on 31.01.2018 |
| --- | --- | --- | --- |
| 119541 | 512255 | 523133 | 108663 |

B. Details of budget utilization (2017-18) upto 31 January 2018

| S. No. | Particulars | Sanctioned | Released | Expenditure |
| --- | --- | --- | --- | --- |
| A. Recurring Contingencies |  |  |  |  |
| 1 | Pay & Allowances | 8260000 | 8260000 | 8153488 |
| 2 | Traveling allowances | 200000 | 200000 | 200000 |
| 3 | Contingencies |  |  |  |
| A | Stationery, telephone, postage and other expenditure on office running, publication of Newsletter and library maintenance (Purchase of News Paper & Magazines) | 300000 | 300000 | 300000 |
| B | POL, repair of vehicles, tractor and equipments | 250000 | 250000 | 250000 |
| C | Meals/refreshment for trainees (ceiling upto Rs.40/day/trainee be maintained) | 100000 | 100000 | 100000 |
| D | Training material (posters, charts, demonstration material including chemicals etc. required for training) | 50000 | 50000 | 50000 |
| E | Frontline demonstration except oilseeds and pulses (minimum of 30 demonstration in a year) | 326000 | 326000 | 326000 |
| F | On farm testing | 60000 | 60000 | 60000 |
| G | Extension Activities | 50000 | 50000 | 50000 |
| H | Training of extension functionaries | 25000 | 25000 | 25000 |
| I | FFS | 30000 | 30000 | 30000 |
| J | EDP | 30000 | 30000 | 30000 |
| K | Display Boards | 0 | 0 | 0 |
| L | Maintenance of buildings | 100000 | 100000 | 100000 |
| M | Establishment of Soil, Plant & Water Testing Laboratory | 25000 | 25000 | 25000 |
| N | Library | 5000 | 5000 | 5000 |
| TOTAL (A) |  | 9811000 | 9811000 | 9704488 |
| B. Non-Recurring Contingencies |  |  |  |  |
| 1 | Works |  |  |  |
| 2 | Equipments including SWTL & Furniture |  |  |  |
| 3 | Vehicle (Four wheeler/Two wheeler, please specify) |  |  |  |
| 4 | Library | 10000 | 10000 | 7500 |
| TOTAL (B) |  | 10000 | 10000 | 7500 |
| C. REVOLVING FUND |  |  |  |  |
| GRAND TOTAL (A+B+C) |  | 9821000 | 9821000 | 9711988 |

C. Details of Budget Estimate (2018-19) based on proposed action plan

| S. No. | Particulars | BE 2018-19 proposed |
| --- | --- | --- |
| A. Recurring Contingencies |  |  |
| 1 | Pay & Allowances | 114.50 |
| 2 | Traveling allowances | 3.00 |
| 3 | Contingencies |  |
| A | Stationery, telephone, postage and other expenditure on office running, publication of Newsletter and library maintenance (Purchase of News Paper & Magazines) | 3.50 |
| B | POL, repair of vehicles, tractor and equipments | 3.00 |
| C | Meals/refreshment for trainees (ceiling upto Rs.40/day/trainee be maintained) | 1.55 |
| D | Training material (posters, charts, demonstration material including chemicals etc. required for conducting the training) | 1.00 |
| E | Frontline demonstration except oilseeds and pulses (minimum of 30 demonstration in a year) | 3.53 |
| F | On farm testing (on need based, location specific and newly generated information in the major production systems of the area) | 1.12 |
| G | FLD under NFSM | 0.99 |
| H | Training of Extension Functionaries | 0.30 |
| I | Extension Activities | 0.50 |
| J | EDP | 0.46 |
| K | Display Boards | 0.10 |
| L | Maintenance of buildings | 1.00 |
| M | Establishment of Soil, Plant & Water Testing Laboratory | 0.50 |
| N | Library | 0.25 |
| TOTAL (A) |  | 135.30 |
| B. Non-Recurring Contingencies |  |  |
| 1 | Works |  |
| 2 | Equipment’s including SWTL & Furniture |  |
| 3 | Vehicle (Four wheeler/Two wheeler, please specify) | 0.70 |
| 4 | Library (Purchase of assets like books & journals) | 0.10 |
| TOTAL (B) |  | 0.80 |
| C. REVOLVING FUND |  |  |
| GRAND TOTAL (A+B+C) |  | 136.10 |