ZONAL PROJECT DIRECTORATE - ZONE VIII

ICAR, HEBBAL, BANGALORE

PROFORMA FOR ACTION PLAN 2016-17

GUIDELINES

(Please read this carefully without fail)

- It is mandatory to fill all the items of activities in the format. Further, additional activity/activities within the mandate which are relevant to the well being of farmers of operational villages will be encouraged.

- For the activities proposed to be continued, all the data of the previous year(s) must be presented, supported by visuals.

- In case you have already completed 2-3 years in the existing operational villages, select a new cluster villages in the district based on the need analysis through different methods and interactions with farmers and field level extension functionaries, farmers group meetings, field visits, focus on specific locations of the district etc. Conduct PRA in those clusters and identify issues/problems in crops, livestock, fisheries and allied sectors. Then prioritize the problems based on criteria like the extent, severity, importance and frequency of each problem with quantitative data.

- Relevant additional supporting information such as problem-cause diagram, ranking matrix, yield gap analysis etc must be appended for each technological intervention with the Action Plan.

- All major agricultural related activities in operational cluster villages must be reflected in the Action Plan.

- Plan of work must correspond to the prioritized problems to be addressed in selected cluster of villages. Before proposing the Action Plan, discuss in detail about the prioritized problems with factors affecting through problem-cause diagram, technological solutions available and technological interventions to be undertaken by KVK.

- The entire KVK team must be involved in the preparation of Action Plan.

- The Action Plan should include a combination of OFTs, FLDs, Training and Extension activities to address each of the identified problems.

- In the case of FLD on varietal performance, ensure that the varieties / hybrids are not older than 5 years.

- Technology interventions in animal husbandry, poultry and fisheries need additional emphasis. Respective Veterinary Universities and experienced cluster KVKs may be approached in this regard.

- Vocational trainings should be planned on the thrust area identified in the operational area. Specific vocational programmes may be conducted for para-technicians and field personnel engaged in animal husbandry activities.

- OFT / FLD proposals on fodder crops may be included under Livestock - feed and fodder management.

- The contingency budget will be linked to the number of approved FLDs/OFTs. Hence due care may be taken to propose OFTs/FLDs.

- Plan for public-private partnership to enhance the availability of seed/planting material/bio-agent etc. in the villages for speedy dissemination of technologies.

- Interact thoroughly with stakeholders (farmers, extension personnel, scientists etc) before finalizing Action Plan.

- Additional activities (other than mandated activities) if any, (such as SHM, RKVY, NYK etc) have to be incorporated in the action plan and presented for technical approval by ZPD.

- The recommendations of SAC related to technical activities should be addressed in the Action Plan without fail.

###### ZONAL PROJECT DIRECTORATE – ZONE VIII BANGALORE

###### PROFORMA FOR ACTION PLAN OF KVKs IN ZONE VIII FOR 2016-17

###### General information about the Krishi Vigyan Kendra

| 1.1 | Name and address of KVK with Phone, Fax and e-mail | : | Krishi Vigyan Kendra, Chitradurga Babbur Farm, Hiriyur-577 598, Chitradurga district, Karnataka State. Phone : 08193-289160 Fax : 08193-289160 e-mail : kvkchitradurga@gmail.com |
| --- | --- | --- | --- |
| 1.2 | Name and address of host organization | : | University of Agricultural & Horticultural Sciences, Shivamogga Savalanga Road, Navile, Shivamogga, Karnataka-Pin: 577 225 |
| 1.3 | Year of sanction | : | 2000 (NATP), 2004 to 2014 - Full-fledged under UASB Under UAHS Shivamogga, Since 01-07-2014 |
| 1.4 | Website address of KVK and date of last update |  | www.kvkchitradurga.in Last Update:26-03-2015 |

2. Details of staff as on date

|  |  |  |  | If Permanent, Please indicate |  |  | If Temporary, pl. indicate the consolidated amount paid (Rs./month) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sl. No. | Sanctioned post | Name of the incumbent | Discipline | Current Pay Band | Current Grade Pay | Date of joining |  |
| 2.1 | Programme Coordinator | - | - | 37000-67000 | 9000 | - | Vacant |
| 2.2 | SMS Soil Science & Programme Coordinator(Ic) | Dr. Sarvajna B. Salimath | Soil Science & Agril. Chemistry | 15600-39100 | 7000 | 01-09-2008 | Permanent |
| 2.3 | Subject Matter Specialist | Dr. S. Onkarappa | Crop Protection | 15600-39100 | 6000 | 17-07-2009 | Permanent |
| 2.4 | Subject Matter Specialist | Mr. Prakash Kerure | Horticulture | 15600-39100 | 6000 | 10-11-2011 | Permanent |
| 2.5 | Subject Matter Specialist | Dr. Sumana, D.A | Home Science | 15600-39100 | 6000 | 13-07-2015 | Permanent |
| 2.6 | Subject Matter Specialist | Mr. Gajendra T.H | Agri. Extension | 15600-39100 | 6000 | 6-12-2013 | Permanent |
| 2.7 | Subject Matter Specialist | Dr.RudragoudaF.Channagounda | Agronomy | 15600-39100 | 6000 | 17-10-2013 | Permanent |
| 2.8 | Programme Assistant(Lab) | Ms. B.N. Geetha Kumari | Agriculture | 9300-34800 | 4200 | 04-11-2010 | Permanent |
| 2.9 | Programme Assistant (Computer) | Miss. Kavitha P.Naik | Computer Science | 9300-34800 | 4200 | 31-11-2013 | Permanent |
| 2.10 | Farm Manager | Miss. Anitha K | Sericulture | 9300-34800 | 4200 | 10-12-2015 | Temporary |
| 2.11 | Accountant/Superintendent | Mr. D. Gurumurthy | Accountant | 9300-34800 | 4200 | 01-01-2013 | Permanent |
| 2.12 | Stenographer | Mrs. A. Rekha | Steno (Typing cum computer asst.) | 5200-20200 | 2400 | 11-1-2016 | Temporary |
| 2.13 | Driver 1 | Mr. Mehaboob Patel | Tractor driver | 5200-20200 | 2000 | 23-10-2008 | Permanent |
| 2.14 | Driver 2 | Mr. Bhadraiah S. | Jeep driver | 5200-20200 | 2400 | 14-09-2015 | Temporary |
| 2.15 | Supporting staff 1 | Mr. Basavaraju | Cook | 5200-20200 | 1800 | 22-12-2008 | Permanent |
| 2.16 | Supporting staff 2 | Mr. G.Nagaraj | Messenger | 4440-7440 | 1300 | 19-12-2015 | Temporary |

3. Details of SAC meeting conducted during 2015-16

| Sl. No | Date | Major recommendations | Status of action taken in brief | Tentative date of SAC meeting proposed during 2016-17 |
| --- | --- | --- | --- | --- |
| 3.1 | 11-08-2014 | Awareness on importance of pulses in nutritional security | Twenty Five Front Line Demonstrations were conducted during 2015-16 under NFSM (Bengal gram and Redgram) | May 2016 |
| 3.2 |  | Conduct residue analysis in Pomegranate Fruits | The residue analysis in pomegranate will be carried out during 2016-17 under Promegranate project of UAHS , Shivamogga. |  |
| 3.3 |  | FLD of proven technology need to be convincing Line depts. staff and farmers | Large scale demonstrations were conducted on ICM in Groundnut, Redgram, Onion, Hebbal Aware (HA-4) , Mango, Millets, Fodder, Cotton, Arecanut Banana, Pomegranate crops during 2014-15(19 FLD’s and 2015-16(14 FLD’s). |  |
| 3.4 |  | Emphasize on large scale production of Vermi compost. | Large scale production of Vermi Compost is being taken up in the Farm and technology being scaled up with IFSD Farmers of Hiriyur & Callakere Taluka (12 farmers). |  |
| 3.5 |  | Common training calendar may be prepared jointly by KVK and DATC Hiriyur. | The plan was prepared after discussing with ADA, DATC , Hiriyur and accordingly care was taken to avoid duplicity . Similarly action plan for 2016-17 is being shared with ADA, DATC. |  |
| 3.6 |  | KVK must limit to training programmes to those related to FLD and OFT beside need based and selected sponsored programmes. | Trainings have been conducted based on the action plan prepared for 2015-16.(Totally 56 trainings related to FLD & OFT were conducted during 2015-16) |  |
| 3.7 |  | Problems for taking up FLD/OFT should be identified through PRA of cluster villages. Work intensively in these villages for 2 to 3 years on the prioritized problems. Impact of KVK interventions should be measured in terms of extent to which these problems are minimized | New cluster villages were identified through PRA technique. Success stories were documented and impact assessment will be initiated for KVK interventions. Poster presentation were made on assessment of Onion verities for Chitrdurga district at UAS, Dharwad |  |
| 3.8 |  | Seek permission from ZPD and recruit Farm Manager on contract basis immediately. Simultaneously, initiate action to recruit on permanent. | Farm Manager on contract basis has been recruited during Dec 2015. |  |
| 3.9 |  | Popularize double cross hybrid in sericulture through demonstration | FLD on double cross hybrid in sericulture was conducted in Hariyabbe cluster during 2014-15. |  |
| 4.0 |  | Soil test based fertilizer recommendation may be taken as innovative activity | 265 Soil Health Cards have been prepared during 2015-16 for two villages for Hiriyur & Challakere . International Soil Health Day was celebrated on 5th of Dec 2015 . |  |
| 4.1 |  | Documentation and maintenance of district agriculture status and other activities | Data of agriculture status has been documented based on the reports of JDA, Chitradurga & Statistical department , Chitradurga |  |
| 4.2 |  | Characteristics of Hebbal Avare HA-4 variety need to be assessed | FLD was implemented in Baramasagara Cluster (at Hampanur village) and different parameters were assessed. Seed production of HA-4 was taken up in the KVK Farm |  |
| 4.3 |  | Conduct compressive demonstration on large scale with line department for wider spreading of the technology. | Large scale demonstrations were conducted on groundnut, Redgram, Bengalgram and Greengram in collaboration with agriculture department during 2014-15. During 2015-16 large scale demonstration were conducted in Challakere taluka. Technology was spread in collaboration with DoA, Challakere throughout the taluka . |  |
| 4.4 |  | Popularize micro credit facility of NABARD and other nationalized banks. | Through our on campus trainings farmers are sensitized about NABARD linkage for micro finance. |  |
| 4.5 |  | Sensitize farm women about scientific dairy management practices | Front Line Demonstrations on different green fodder verities were taken up in Hiriyur Tq. and seeds of CoFS -29 were given to adopted village dairy farmers of Shidlyanakote . |  |
| 4.6 |  | Create awareness on DCH castor hybrid through large scale demonstration | Large scale demonstrations were conducted in KVK contact farmer’s field during 2014-15 through IFS programme in 10 villages of Hiriyur taluka. |  |
| 4.7 |  | Intensify the onion seed production through participatory approach | Around 22 q Arka Kalyan seed was produced through participatory seed production programme at Muddapaura cluster during 2014-15. During 2015-16 seed production of Bheema Super Varity is being taken up in Hosakundure village of Hosdurga Tq. (5 Farmers ). |  |
| 4.8 |  | Demonstrations/Training about drip irrigation in onion need to be conducted | OFT on onion was conducted using raised bed cultivation through drip irrigation. A demonstration was taken up at our Farm during 2015-16. |  |
| 4.9 |  | Popularize the agricultural technologies through electronic media | Regularly sending agriculture information through SMS (Farmers Portal) and actively using mass media for technology dissemination in a wider scale. |  |

4. Capacity Building of KVK Staff

4.1. Plan of Human Resource Development of KVK personnel during 2016-17

| S. No | New Areas of Training | Institution proposed to attend | Justification |
| --- | --- | --- | --- |
| 4.1.1 | Weed management in field crops | UAS, Dharwad | Management of weeds through integrated approach |
| 4.1.2 | Mass production of Trichoderma and Pseudomonas | NBAII, Bangalore | Management of fungal and bacterial diseases in agricultural and horticultural crops |
| 4.1.3 | Water Management & Hydroponics | Mashav & Hebrew University of Jerusalem, Israel | Pomegranate cultivation needs water management technology. Fodder cultivation under Hydroponics for nutrition of animals |
| 4.1.4 | Production of bio inputs and bio agents. Gender in agriculture | NAARM Hyderabad/UAS Bangalore/IIHR Bangalore | Production of bio inputs Lab at KVK. |
| 4.1.5 | Improved Horticulture Production Technologies | IAHR, Bangalore | To know the recent research achievements in Horticultural Crops |
| 4.1.6 | Protected in Vegetable Crops | IARI, New Dheli | Recent Technology in production aspects of Capsicum , Tomato and cucumber |

4.2. Cross-learning across KVKs during 2016-17

| Sl. No | Name of the KVK proposed | Specific Learning Areas |
| --- | --- | --- |
| 4.2.1 | Within ring – Davanagere, Tumkur, Shivamogga | - Quality Seeds and Planting Materials. - Nutrient Mixture, Exposure Visits, Farmers’ Interaction - Management of Black Headed Caterpillar and Wilt in Coconut - Management of Stem Borer and Blight in Maize |
| 4.2.2 | Within the zone – a ) KVK, Thrissur, Kerala | Resource Conservation Technologies Vegetable seed production in collaboration with SHG, |
|  | b) KVK, CARD, Pattanamtitta, Kerala | Role of Processing and value addition in empowering SHG |
|  | c) KVK, Kozhikode, Kerala. | Training programmes emphasized on unemployed women and youth such as mechanized coconut climbing and fresh water fish culture. |
| 4.2.3 | Outside zone – a) KVK, Babaleshwara, Maharashtra | Extension method followed for dissemination of agricultural crops, modern farm technologies and method demonstrations, rain harvesting technology. |
|  | b) KVK, Baramati, Maharashtra | Improved Farm Technologies, Method Demonstrations and micro irrigation technology. |

5. Proposed cluster of KVKs (3 to 5 neighboring KVKs) to be formed for sharing knowledge/expertise, resources and activities

during 2016-17

| Sl.No. | Name of the KVKs included in the cluster | What do you intend to share with Cluster KVKs | What do you expect from Cluster KVKs |
| --- | --- | --- | --- |
| 5.1 | Davanagere, , Dharwad, Chamarajanagar | - INM in Banana and cotton - PHT of millets - INM in cotton - IPM in Coconut - INM in groundnut - INM in finger millet | - Fish cultivation and Dairy management - CBA formation and strengthening for effective management - Micronutrients ,Horticulture seeds/planting materials - Value addition in coconut - Cultivation of maize - Recent technology in cotton - Recent technology in groundnut production |

6. Operational areas details proposed during 2016-17

| S.No. | Major crops & enterprises being practiced in cluster villages | Prioritized problems in these crops/ enterprise | Extent of area (Ha/No.) affected by the problem in the district | Names of Cluster Villages identified for intervention | Proposed Intervention (OFT, FLD, Training, extension activity etc.)* |
| --- | --- | --- | --- | --- | --- |
| 6.1 | Foxtail millet | Low yielding varieties Susceptible to stress condition Susceptible to pest and diseases | 12,370 | Rampura and Hosadurga | OFT |
| 6.2 | Finger millet | Existing varieties are susceptible to stress condition Varieties are susceptible to neck blast Non availability of good quality fodder variety | 47,801 | Hosadurga and Dharmpura | FLD |
| 6.3 | Groundnut | Plant population Low yields and susceptible to leaf spot disease of existing varieties Imbalanced nutrient management | 1,15,000 | Parasurampura and Dharmpura | FLD |
| 6.4 | Fodder sorghum variety COFS-29 | Non availability of good quality green fodder variety Non availability of stress resistant variety | 650 | Dharmpura and Hosadurga | FLD |
| 6.5 | Red gram | Low yield, pod borer and Sterility mosaic | 4,300 | Peelapura, Bagur Hariyabbe, Eswaragere | FLD |
| 6.6 | Bengal gram | Low yield, pod borer and wilt | 14,200 | Nagenahalli, Bagur Maradihalli, Eswaragere | FLD |
| 6.7 | Coconut | Stem bleeding and wilt | 22,000 | Kanchipura, Bagur | FLD |
| 6.8 | Areca nut | Spindle bug, scales, mites and bud rot | 7,800 | Janakal, Bagur | FLD |
| 6.9 | Pomegranate | Bacterial blight, wilt, thrips, fruit sucking moths | 6,900 | T. Nagenahalli, Eswaragere | FFS |
| 6.10 | Onion | - Non availability of quality seed material - Dependency on other states - Higher seed cost | Total Area of onion around 13, 967 ha | Hosakunduru, Ramgiri , Hosadurga and Holalkere Tq | FLD, Off campus training |
| 6.11 | Watermelon | - Fruit cracking, - Imbalanced nutrient application - Wilt disease | Total Area of watermelon around 265 ha | Eshwaragere, Hiriyur Tq | FLD, Off campus training |
| 6.12 | Field bean (Avare) | - No variety suitable for all season - Low yield due to local variety - Impure and poor quality seeds | Total Area of 250 ha | Sirigere, Chitradurga Tq | FLD, Off campus training |
| 6.13 | Onion | - Low yield due to local varieties - No results of onion varieties suitable for Rabi season of Chitradurga Dist. | Total Area of onion around 13, 967 ha | Eshwaragere and KVK farm Hiriyur Tq | OFT, Off campus training |
| 6.14 | Paddy | Low yields due to salinity problem | 1500 ha area affected. | S hanumapura Molakalmur Taluk | OFT. |
| 6.15 | Banana | Low bunch yields due to imbalanced nutrient Management | 6000 ha | Katanayakanahally of Hiriyur taluka and VK Gudda. | FLD |
| 6.16 | Empowering Rural youth through Oyster mushroom cultivation | Lack of Knowledge on cultivation and marketing | - | KVK Babbur Farm Hiriyur | EDP |
| 6.17 | Value addition, branding & marketing of millets | Lack of machinery, knowledge on branding and market linkage | - | KVK Babbur Farm Hiriyur | EDP |
| 6.18 | Value addition ,branding & marketing of pulses | Lack of machinery, knowledge on branding and market linkage | - | KVK Babbur Farm Hiriyur | EDP |

* Support with problem-cause and interventions diagram

7.	Technology Assessment during 2016-17

| S. No. | Crop/ enterprise | Prioritized problem | Title of intervention | Technology options | Source of Technology | Name of critical input | Qty per trial | Cost per trial | No. of trials | Total cost for the intervention (Rs.) | Parameters to be studied | Team members |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 7.1 | Foxtail millet | - Low yielding varieties - Varieties are susceptible to stress condition - Not availability good quality fodder | Assessment of foxtail millet varieties for higher yield | T1:SIA-2644 T2 :HMT-101 | UASR UASD | Seeds Azospirillum and PSB Trichoderma ZnSo4 17:17:17 NPK | 10 kg 3 kg 4 kg 50 kg | 500 300 440 1250 | 02 | 4,980 | Germination Per cent, plant height (cm), panicle length (cm), yield (q/ha ) fodder yield (t/ha) and economics. | Dr. Rudragouda F.C & other SMS |
| 7.2 | Onion | - Low yield due to local varieties - No results of onion varieties suitable for Rabi season of Chitradurga Dist. - Poor keeping qualities like sprouts & rotting in storage - Incidence of purple blotch disease | Assessment of suitable Onion Verities for Rabi season | - Satara Gurva | Farmers Practice | Breeder Seeds | 0.5 kg of each variety | 5000 | 2 | 10,000 | - Plant height - No of Leaves - Days to 50% neck fall - Bulb diameter - Bulb colour - Bulb Yield - Incidence of pest & disease, - B: C ratio | Mr. Prakash Kerure & other SMS |
|  |  |  |  | - NHRDF red-28 | NHRDF, Nasik |  |  |  |  |  |  |  |
|  |  |  |  | - Bima Shakti/ Red | DOGR, Pune |  |  |  |  |  |  |  |
|  |  |  |  | - Arka Niketan | IIHR, Bengaluru |  |  |  |  |  |  |  |
| 7.3 | Paddy | Low yielding and fine quality paddy for salt affected soils | Assessment of paddy varieties for higher yield under saline conditions | T1. Local variety (Mulla bhatta) T2: GGV 05-01 T3: IR 30864 T4:CSR-22 T5:GNV- 10-89 | Local UASR UASB UASR UASR | ---- Seeds: Bio inputs | 2.5 kg 2.5 kg 2.5 kg 2 kg | 100 100 100 200 | 02 | 700 | Plant height Panicle length No of effective tillers. 1000 grain weight Yield/ha Days to maturity | Dr.Salimath & other SMS |

## 8.	Technology Refinement during 2016-17: Nil

9.	Frontline Demonstrations during 2016-17

| S. No. | Category | Crop/ enterprise | Prioritized problem | Technology to be demonstrated | Specify Hybrid or Variety | Name of the Hybrid or Variety | Source of Technology | Name of critical input | Qty per Demo | Cost per Demo | No. of Demo | Total cost for the Demo (Rs.) | Parameters to be studied | Team members |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 9.1 | Cereals | - | - | - | - | - | - | - | - | - | - | - | - | - |
| 9.2 | Millets | Finger millet | Existing varieties are susceptible to stress condition Varieties are susceptible to neck blast Not availability of good quality fodder | Introduction of ML-365 finger millet variety for higher yield |  | Variety - ML-365 | UASB | Seeds Bio-inputs Biofertilizer 19:19:19 fertilizer ZnSo4 17:17 :17 NPK | Seed-5 kg 3 kg 1 kg 4 kg 50kg | 2350 | 5 | 11750 | Germination per cent, plant height (cm), No. of effective tillers/ plant, No. of fingers/ear head, Test wt., Yield kg/ha and economics | Dr. Rudragouda F.C & other SMS |
| 9.3 | Oilseeds | Groundnut | Plant population Low yields and susceptible to leaf spot disease of existing varieties Imbalanced nutrient management | Integrated crop management in Groundnut | Variety | KCG-6 | UASB | Seeds Rhizobium, PSB Trichoderma Captan Chloropyriphos ZnSo4 DAP | 45 kg 3 kg 0.5 kg 1.0 lit 4 kg 50 kg | 4825 | 5 | 24125 | Germination per cent, No. of pods/plant, 100 seed wt, shelling %, yield, percentage damage due to pest and disease and economics | Dr. Rudragouda F.C, & other SMS |
| 9.4 | Pulses | Red gram | Low yield, pod borer, leaf webber and Sterility mosaic disease | Integrated Crop Management in Red gram | Variety | BRG-2 | UAS (B) | Seeds Trichoderma Rhizobium PSB Pheromone traps Lures HaNPV Dicofol 18.5EC Emamectin benzoate 5SG | 6 kg 40 g 200 g 200 g 4 No. 12 No. 300 ml 2 lit 200gm | 600 5 20 20 120 240 750 850 1400 | 25 | 1,00,125 | Per cent disease and Pest incidence, No. of pods per plant, 100 seed weight ,Yield ,economics | Dr.S. Onkarappa, & other SMS |
|  |  | Bengal gram | Low yield, pod borer and wilt | Integrated crop Management in Bengal gram | Variety | J.G.-11 | UAS (B) | Seeds Trichoderma Rhizobium PSB Pheromone traps Lures HaNPV Emamectin benzoate 5SG | 25 kg 200 g 200 g 200 g 2 No. 4 No. 200 ml 150gm | 1625 20 20 20 60 80 500 1100 | 25 | 85625 | Per cent disease and pest incidence, No. of pods per plant, 100 seed weight ,yield ,economics | Dr. S. Onkarappa, & other SMS |
| 9.5 | Commercial crops |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9.6 | Horticultural crops | Areca nut | Bud rot Incidence of scales, mites Plant nutrition | Integrated crop management in Arecanut | Local variety | Local variety | UAS (B) | Trichoderma viridae MgSO4 Dimethoate 30 EC Dicofol 18.5 EC Copper oxy chloride 75WP Phorate 10G Plastic covers | 5 kg 28kg 1 lit 2 lit 2 kg 3 kg 1 kg | 500 1680 440 900 1300 300 300 | 10 | 54200 | No. of bugs per plant, No. of scales , No. of mites per 2 sq.cm. area, Percent disease incidence Yield | Dr. S. Onkarappa, & other SMS |
|  |  | Coconut | Yield loss due to imbalanced nutrient management incidence of Red palm weevil ,mites, stem bleeding, wilt, and leaf spot disease | Integrated crop management in Coconut | Laocal variety | Arasikere tall | UAS(B) | Tichoderma viridae Pheromone trap Lure(RPW) MgSO4 Hexaconazole 5EC Mancozeb 75WP Plastic covers | 3 kg 1No. 2 No. 25 kg 1 lit 2 kg 500gm | 300 120 240 1500 650 860 150 | 10 | 38200 | No. of nuts per tree & Percent disease incidence | Dr.S. Onkarappa, & other SMS |
|  |  | Banana | Imbalanced application of major nutrients, fruit cracking, Lower bunch yields | Improved Management practices for higher yield in Banana | Local | Putta Bale | IIHR Bangalore | Arka Banana Special Bio inputs: PSB, Aszospirillium | 8 kg 1 kg 1 kg | 1600 100 100 | 10 | 18000 | Bunch yield per plant | Dr.Salimath & other SMS |
|  | Horticultural crops | Onion | - Non availability of quality seed material - Dependency on other states - Higher seed cost | Participatory Seed production in onion for self reliance | Variety | Bhima Super | DOGR, Pune | *Bhima Super Breeder Seeds *Trichoderma *PSB *Bee Hives | 1Kg 4kg 4kg 1 No. | 10,000 | 5 | 50,000 | - Germination per cent - Bulb Yield/acre in kharif - Seed yield/acre in Rabi - No of umbels per plant - Net Returns | Mr. Prakash Kerure & other SMS |
|  |  | Field Bean (Avare) | Non availability of quality seed material Use of local variety and impure seeds Mainly growing | Participatory Seed production of Hebbal Avare-4 for self reliance | Variety | HA-4 | UAS, B | *HA-4 Breeder Seeds *Rhizobium *Bee Hives | 12Kg 4Kg 1 No. | 10,000 | 5 | 50,000 | - Germination percentage - No of panicle per plant - No of pods per plant - Seeds per pod - Seed yield per acre - Net returns | Mr. Prakash Kerure & other SMS |
|  |  | Watermelon | - Fruit cracking, - Imbalanced nutrient application - Wilt disease | Integrated Crop Management in Watermelon | Hybrid | Kiran | IIHR Bangalore | Arka Vegetable Special, Bio inputs: PSB, Pseudomonas, Trichoderma | 6 kg 1.5kg 1.5kg 1.5kg | 1,500 | 12 | 18,000 | - Percent fruit cracking - Fruit set per vine, Yield/ha, Incidence of pest & diseases, B:C ratio | Mr. Prakash Kerure & other SMS |
| 9.7 | Livestock | Fodder crops | Non availability of good quality green fodder variety Non availability of stress resistant variety | Popularization of fodder sorghum variety COFS-29 in Chitradurga District | Variety | COFS -29 | TNAU | Seed Azospirillum/ PSB Trichoderma ZnSo4 | 1 kg 3 kg 2 kg | 1520 | 10 | 15200 | Green fodder yield and per cent palatability | Dr.Rudragouda F.C, & other SMS |
| 9.8 | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Empowering Rural youth through Oyster mushroom cultivation | Lack of Knowledge on cultivation and marketing | Large scale demonstration/cultivation of mushroom and marketing | Mushroom spawn production | Spawn pleurotus sajor-caju oyster mushroom | UAHS IIHR UAS(B) UAS(D) | Spawn cultivation poly bags | - | - | - | 2500 | - | Dr. D.A.Sumana & other SMS |
|  |  | Value addition on branding & marketing for millets | Lack of machinery | Branding and Value addition of millets 1.Foxtail Millet 2.Little millet |  | 1.HMT-100-1 2.Suskhema (Little Millet) | UAS(B) | Processing Unit Branding packets |  |  |  | 2 00000 10000 | - | Dr. D.A.Sumana & other SMS |
|  |  | Value addition on branding & marketing for pulses | Lack of machinery | Value addition and Branding of pulses Redgram or Turdhal | - | - | UAS(B) | Sealing machine | - | - | - | 3000 | Palatability Durability | Dr. D.A.Sumana & other SMS |
|  |  |  |  |  |  |  |  | Branding packets |  |  |  | 10000 |  |  |
|  |  |  |  |  |  |  |  | processing unit/Dhal making unit |  |  |  | 1.5 lakh |  |  |

10	Training for Farmers/ Farm Women during 2016-17(On Campus)

| S.No. | Thematic area | Crop / Enterprise | Major problem | Related field intervention (OFT/FLD)* | Training Course Title** | No. of Courses | Expected No. of participants | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 10.1 | Crop Production |  |  |  |  |  |  |  |
|  |  | Groundnut | Plant population Low yields of existing varieties Imbalanced nutrient management | FLD | Integrated crop management practices in groundnut | 1 | 30 | Dr. Rudragouda F.C & other SMS |
|  |  | Finger millet | Existing varieties are susceptible to stress condition Varieties are susceptible to neck blast Not available good quality fodde | FLD | Crop management in finger millet | 1 | 30 | Dr. Rudragouda F.C & other SMS |
| 10.2 | Horticulture Production | Onion | - Non availability of quality seed material - Dependency on other states - Higher seed cost Low yield due to local varieties - No results of onion varieties suitable for Rabi season of Chitradurga Dist. | FLD/OFT | Integrated crop management and seed production technologies in onion | 1 | 40 | Mr. Prakash Kerure & other SMS |
|  |  | Flower crops | Improper nutrition, use of local varieties, pest and diseases, no pinching operations | Other | ICM practices in flower crops | 1 | 40 | Mr. Prakash Kerure & other SMS |
|  |  | Pomegranate | Indiscriminate use of growth regulators, pesticides, improper training, pruning and bahar treatments, unscientific propagation means | Other | Pruning techniques, Propagations and other ICM practices in Pomegranate | 1 | 40 | Mr. Prakash Kerure & other SMS |
| 10.3 | Livestock Production |  | - | - | - | - | - | - |
| 10.4 | Home Science |  |  |  |  |  |  |  |
|  | Value addition in millets | Foxtail millet | Lack of machinery | EDP | Value addition in millets | 1 | 30 | Dr. D.A.Sumana & other SMS |
|  | Mushroom production | Cultivation at home level | Lack of knowledge | EDP | Increasing nutrition in diet or self employment generation | 1 | 30 | Dr. D.A.Sumana & other SMS |
| 10.5 | Plant Protection | Areca nut | Spindle bug, Scales, Leaf spot | OFT | Integrated insect pest management in areca nut | 1 | 30 | Dr.S. Onkarappa, & other SMS |
|  |  | Red gram | Pod borer, Sterility mosaic, wilt | FLD | Integrated pest and disease management in Red gram | 1 | 30 | Dr.S. Onkarappa, & other SMS |
|  |  | Bengal gram | Pod borer, wilt | FLD | Integrated pest and disease management in Bengal gram | 1 | 30 | Dr.S. Onkarappa, & other SMS |
| 10.6 | Production of Inputs at Site |  | - | - | - | - | - | - |
| 10.7 | Soil Health and Fertility |  | Micro nutrient deficiency Lack of awareness on Micro nutrient application Micro nutrient deficiency symptoms | FLD | Micro nutrient management in banana and onion | 1 | 30 | Dr. S.B. Salimath, , & other SMS |
|  |  | Soil | Soil salinity Lack of awareness on crops which are persistent salinity | FLD | Management of salt affected soil | 1 | 30 | Dr. S.B. Salimath, , & other SMS |
|  |  | Horticulture crops | Salt affected water Water budgeting | FLD | Water quality and its management for horticulture crops | 1 | 30 | Dr. S.B. Salimath, , & other SMS |
|  |  | Pomegranate | In availability of soil moisture while application of solid state nutrients | FLD | Nutrient management through fertigation in pomegranate | 1 | 30 | Dr. S.B. Salimath, , & other SMS |

* Title of intervention/title of technology, ** Training title should specify the major technology/skill to be transferred.

10. 8Training for Farmers/ Farm Women  (Off Campus)

| Sl.No. | Thematic area and the Crop/Enterprise | Training title* | No. of programmes and Duration (days) | Type of Clientele (SHGs, NYKs, School students, Women, Youth etc.) | Expected No. of participants | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- |
| 10.8.1 | Crop production | Improved Production Practices in fodder crops | 1 | Farmers/ Farm women | 30 | Dr. Rudragouda F.C & other SMS |
|  |  | ICM in groundnut | 1 | Farmers/ Farm women | 30 | Dr. Rudragouda F.C & other SMS |
|  |  | Improved production practices for higher returns in finger millet | 1 | Farmers/ Farm women | 30 | Dr. Rudragouda F.C & other SMS |
| 10.8.2 | Horticulture | Seed production technologies and certification procedures in onion | 1 | Farmers/ Farm women | 30 | Mr. Prakash Kerure & other SMS |
|  |  | Seed production technologies and certification procedures in Avare | 1 | Farmers/ Farm women | 30 | Mr. Prakash Kerure & other SMS |
|  |  | Improved production techniques in Watermelon | 1 | Farmers/ Farm women | 30 | Mr. Prakash Kerure & other SMS |
| 10.8.3 | Plant protection | Integrated disease management in Areca nut for higher yield | 1 | Farmers/ Farm women | 30 | Dr.S. Onkarappa, & other SMS |
|  |  | Integrated insect pest management in coconut | 1 | Farmers/ Farm women | 30 | Dr.S. Onkarappa, & other SMS |
|  |  | Integrated disease management in coconut | 1 | Farmers/ Farm women | 30 | Dr.S. Onkarappa, & other SMS |
| 10.8.4 | Home Science | Training on Bio-Fertilizer Technology | 1 | Farm Women | 30 | Dr. D.A.Sumana & other SMS |
|  |  | Cultivation of Oyster Mushroom | 1 | Farm Women | 30 | Dr. D.A.Sumana & other SMS |
|  |  | Vegetable garden for nutritional security of school children | 1 | School students | 50 | Dr. D.A.Sumana & other SMS |
|  |  | Value addition in finger millet | 1 | SHG | 30 | Dr. D.A.Sumana & other SMS ` |
| 10.8.5 | Soil Science | Management of salt affected soil | 1 | Farmers/ Farm women | 30 | Dr. S.B. Salimath, , & other SMS |
|  |  | Nutrient management through fertigation in pomegranate | 1 | Farmers/ Farm women | 30 | Dr. S.B. Salimath, , & other SMS |

11. Training for Rural Youth during 2016-17

| S.No. | Thematic area | Crop / Enterprise | Major problem | Related field intervention (OFT/FLD)* | Training Course Title** | No. of Courses | Expected No. of participants | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 11.1 | Crop Production | - | - | - | - | - | - | - |
| 11.2 | Horticulture Production | - | - | - | - | - | - | - |
| 11.3 | Livestock Production | - | - | - | - | - | - | - |
| 11.4 | Home Science | Enterprise | Lack of knowledge on preparation | SHG | Preparation of Puliyogre powder | 1 | 30 | Dr. Sumana D.A & other SMS |
| 11.5 | Plant Protection | Pomegranate | Lack of knowledge on use of bio agents | -- | Use of bio agents in pomegranate disease management | 1 | 25 | Dr. S. Onkarappa & other SMS |

* Title of intervention/title of technology, ** Training title should specify the major technology/skill to be transferred.

12 Training for Extension Personnel during 2016-17

| S.No. | Thematic area |  | Training Course Title** | No. of Courses | Expected No. of participants | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- |
| 12.1 | Crop Production |  | Recent Agronomic practices in kharif crops | 1 | 40 | Dr. Rudragouda F.C & other SMS |
|  |  |  | Recent Agronomic practices in Rabi crops | 1 | 40 | Dr. Rudragouda F.C & other SMS |
| 12.2 | Home Science |  | Value addition on branding & marketing for pulses | 1 | 30 | Dr. Sumana D.A & other SMS |
|  |  |  | Value addition on branding & marketing for foxtail & little millets | 1 | 30 | Dr. Sumana D.A & other SMS |
|  |  |  | Mushroom cultivation | 1 | 30 |  |
| 12.3 | Capacity Building and Group Dynamics |  |  |  |  |  |
| 12.4 | Horticulture | Protected cultivation of capsicum, tomato and other vegetable crops |  | 1 | 50 | Mr. Prakash Kerure & other SMS |
|  |  | Seed production and certification in onion |  | 1 | 50 | Mr. Prakash Kerure & other SMS |
| 12.5 | Livestock Production & Management |  |  |  |  |  |
| 12.6 | Plant Protection | Integrated management of pod borer and sterility mosaic disease in Red gram |  | 1 | 40 | Dr. S. Onkarappa & other SMS |
|  |  | Integrated management of pod borer and wilt disease in Bengal gram |  | 1 | 40 | Dr. S. Onkarappa & other SMS |
|  |  | Integrated pest and disease management in groundnut |  | 1 | 40 | Dr. S. Onkarappa & other SMS |
| 12.7 |  | Integrated insect pest and disease management in coconut |  | 1 | 40 | Dr. S. Onkarappa & other SMS |
|  |  | Integrated pest and disease management in pomegranate |  | 1 | 40 | Dr. S. Onkarappa & other SMS |
| 12.8 |  | Integrated pest and disease management in vegetables |  | 1 | 40 | Dr. S. Onkarappa & other SMS |
| 12.9 | Soil Science | Nutrient Management in Papaya |  | 1 | 40 | Dr. S.B. Salimath, , & other SMS |
|  |  | Management of salt affected soil |  | 1 | 40 | Dr. S.B. Salimath, , & other SMS |

* Title of intervention/title of technology, ** Training title should specify the major technology/skill to be transferred.

## 13 Vocational trainings during 2016-17

| Sl.No. | Thematic area and the Crop/Enterprise | Training title* | No. of programmes and Duration (days) | Type of Clientele (SHGs, NYKs, School students, Women, Youth etc.) | Expected No. of participants | Sponsoring agency if any | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 13.1 | Crop Production |  |  |  |  |  |  |
| 13.2 | Home Science | Self Employment through Mushroom cultivation, Honey production, kitchen gardening, nursery raising, value addition in fruits, | 7 | Women, Youths | 20 | - | Dr. Sumana D.A & other SMS |
|  |  | Bakery training | 7 | Women | 20 |  | Experts & other SMS |
| 13.3 | Capacity Building and Group Dynamics |  |  |  |  |  |  |
| 13.4 | Horticulture | Nursery techniques for empowerment of Rural youth | 12 | Rural youths | 40 | Dept of Hort/NGOS | Mr. Prakash Kerure & other SMS |
| 13.5 | Livestock Production & Management | Youth empowerment through Poultry, sheep, goat and dairy enterprise | 7 | Farmers | 40 | Animal Husbandry dept. collaboration | Experts & other SMS |
| 13.6 | Plant Protection | Empowering of rural youth through bee keeping | 10 | SHGs | 25 | -- | Dr.S. Onkarappa & other SMS |
| 13.7 | Sericulture | Good mulberry cultivation practices and quality cocoon production | 7 | Farmers | 30 | Sericulture Dept. collaboration | Dr D Chandrappa Miss. Anitha, , Dr Harsha & other SMS |

* Training title should specify the major technology/skill to be transferred.

## 14 Sponsored trainings during 2016-17

| Sl.No. | Thematic area and the Crop/Enterprise | Training title* | No. of programmes and Duration (days) | Type of Participants (SHGs, NYKs, School students, Women, Youth etc.) | Expected number of participants | Sponsoring agency | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 14.1 | Crop Production | Management of Cotton under Saline conditions | 2 | SHGs | 40 | IISWC, Ballari | ALL SMS |
|  |  | Integrated crop management in Paddy under saline conditions | 2 | SHGs | 40 | IISWC, Ballari | ALL SMS |
| 14.2 | Home Science | Value addition on branding & marketing for pulses | 1 | Youth | 30 | NABARD | ALL SMS |
|  |  | Value addition on branding & marketing for foxtail & little millets | 1 | Youth | 30 | NABARD | ALL SMS |
|  |  | Mushroom cultivation | 1 | Youth | 30 | NABARD | ALL SMS |
| 14.3 | Horticulture | Coconut Tree Climbing | 6 | Youth | 40 | CDB/RDPR | ALL SMS |
|  |  | Cultivation of cashew for improving the livelihoods of Chitradurga farmers. | 1 | Farmers | 30 | NABARD | ALL SMS |
| 14.4 | Livestock Production & Management | Clean Milk production and Green fodder Varieties | 2 | Women | 40 | Dairy association | ALL SMS |
| 14.5 | Plant Protection | IPDM in Cotton | 2 | Farmers | 40 | DoA | All SMS |
|  |  | IPDM in Coconut & Arecanut | 2 | Farmers | 40 | DoH | All SMS |
|  |  | IPDM in Pomegranate | 2 | Farmers | 40 | NABARD | All SMS |
| 14.6 | Farm Mechanization | Mechanization in Groundnut & Millets | 1 | Farmers | 40 | Agril Eng Department ,ZAHRS | Agril Eng Department |
| 14.7 | PHT and value addition | Value Addition in Millets , Branding & Market Linkage | 1 | SHGs | 30 | DoA | All SMS |

* Programme title should specify the major technologies/skills to be transferred /refreshed.

## 15. Extension programmes during 2016-17

| Sl. No. | Extension Programme/ Activity* | No. of programmes or activities | Expected number of participants | Names of the team members involved |
| --- | --- | --- | --- | --- |
| 15.1 | Advisory Services | 2000 | 2000 | All SMS |
| 15.2 | Diagnostic Visits | 15 | 35 | All SMS |
| 15.3 | Field Day | 11 | 1500 | All SMS |
| 15.4 | Group Discussions | 8 | 430 | All SMS |
| 15.5 | Kisan Gosthi | 5 | 350 | All SMS |
| 15.6 | Film Show | 6 | 450 | All SMS |
| 15.7 | Self -Help Groups | 3 | 400 | All SMS |
| 15.8 | Kisan Mela | 4 | 11000 | All SMS |
| 15.9 | Exhibition | 5 | 10000 | All SMS |
| 15.10 | Scientists' Visit to Farmers Field | 200 | 600 | All SMS |
| 15.11 | Plant/Soil Health/Animal Health Camps | 3 | 500 | All SMS |
| 15.12 | Farm Science Club | 3 | 750 | All SMS |
| 15.13 | Ex-Trainees Sammelan | 2 | 160 | All SMS |
| 15.14 | Farmers' Seminar/Workshop | 5 | 1200 | All SMS |
| 15.15 | Method Demonstrations | 10 | 300 | All SMS |
| 15.16 | Celebration of Important Days | 4 | 200 | All SMS |
| 15.17 | Special Day Celebration | 3 | 150 | All SMS |
| 15.18 | Exposure Visits | 10 | 200 | All SMS |
| 15.19 | Technology Week, | 1 | 250 | All SMS |
| 15.20 | Farmers Field School (FFS) | 1 | 30 | All SMS |
| 15.21 | Farm Innovators Meet | 1 | 30 | All SMS |
| 15.22 | Awareness Programs | 4 | 400 | All SMS |

## 16.Activities proposed as Knowledge and Resource Centre during 2016-17

16.1 Technological knowledge

| Sl.No. | Category | Details of technologies | Area (ha)/ Number | Names of the team members involved |
| --- | --- | --- | --- | --- |
| 16.1.1 | Technology Park/ Crop cafeteria | Millets and Fodder verities | 0.4 ha | All SMS |
| 16.1.2 | Demonstration Units | - Krishi Bhagya (Soil & Water management Unit) - Vermi Compost Unit - IFS Model - Nutritional Garden - Nursery Unit - Bee Keeping Unit - Poultry Unit - Azolla Unit - Precision Farming Unit | 1ha 2 No's 1ha 1 No's 2 No's 5 No's 1 No(100 birds) 1 No. 0.15 ha | ALL SMS |
| 16.1.3 | Lab Analytical services | Soil and water analysis | 1500 No. | ALL SMS |
| 16.1.4 | Technology Week | - Production and Value addition in Millets for Nutritional Security - Seed Production & Certification in Onion - Organic Farming - Mushroom Cultivation - IPDM in Agri and Horticultural crops - Roll of Bio- fertilizers in Agriculture | 1 No. | All SMS |

16.2 Technological Products

| Sl.No. | Category | Name of the Production Partner Agency, if any | Name of the product | Quantity (q)/ Number planned to be produced during 2016-17 | Names of the team members involved |
| --- | --- | --- | --- | --- | --- |
| 16.2.1 | Seeds | KSSCA | Millets | 15q | All SMS & Farm Manager |
|  |  | KSSCA | HA-4 Field Bean | 5q | All SMS & Farm Manager |
|  |  | IGFRI | CoFS-29 | 0.4q | All SMS & Farm Manager |
| 16.2.2 | Planting materials | - | Drum Stick (Bhagya/PKM-1) | 5,000 No. | SMS, Hort & Farm Manager |
|  |  | - | Mango- Mallika | 1000 No. | SMS, Hort & Farm Manager |

16.3 Technological Information

|  | Category | Technological capsules / Number | Names of the team members involved |
| --- | --- | --- | --- |
| 16.3.1 | Technology backstopping to line departments |  |  |
|  | Agriculture | 10 | All SMS |
|  | Horticulture | 6 | All SMS |
|  | Animal Husbandry | 2 | Experts & All SMS |
|  | Fisheries | 2 | Experts & All SMS |
|  | Agricultural Engineering | 4 | Engineering department |
|  | Sericulture | 2 | Experts & All SMS |
|  | Others, pl. specify( Bee Keeping) | 2 | Experts & All SMS |
| 16.3.2 | Literature/publication | 25 | All SMS |
| 16.3.4 | Electronic Media | 5 | All SMS |
| 16.3.5 | Kisan Mobile Advisory Services | 50 | All SMS |
| 16.3.6 | Information on centre/state sector schemes and service providers in the district. | 15 | All SMS |

## 17.Additional Activities Planned during 2016-17

| S.No. | Name of the agency / scheme | Name of activity | Technical programme with quantification | Financial outlay (Rs.) | Names of the team members involved |
| --- | --- | --- | --- | --- | --- |
| 17.1 | (SVP) Seed Village Programme at Ramagiri Cluster villages of Hosadurga and Holalkere Tq. | Certified seed production of Onion variety Bhima Super and Arka Kalyan | - Procurement of breeder seeds from source of origin - Quality bulb production during kharif through farmers participation - Rouging operation at critical crop growth stages - Maintenance of isolation distances - Seed certification through KSSCA - Imparting training programs - Filed day celebrations - Exposure visit to seed production plots | 1,00,000 | ALL SMS |
| 17.2 | RKVY | Krishi Bhagya | Continued | - | ALL SMS |
| 17.3 | RKVY | IFSD | Continued | - | ALL SMS |
| 17.4 | ICAR | Distribution of Soil Health Card | Planed | - | ALL SMS |
| 17.5 | NFSM | Cluster FLD in pluses & Millets | Planed | - | ALL SMS |
| 17.6 | NABARD | Farmers Producers Organization in Coconut ,Pomegranate & Banana | Planed | - | ALL SMS |

18.	Revolving Fund

18.1	Financial status

| Opening balance as on 01.04.2015 (Rs.in Lakh) | Expenditure incurred during 2015-16 (Rs.in Lakh) | Receipts during 2015-16 (Rs.in Lakh) | Closing balance as on 31.01.2016 (Rs.in Lakh) | Expected closing balance by 31.03.2016 (Including value of material in stock/ likely to be produced) |
| --- | --- | --- | --- | --- |
| 12.12 | 3.52 | 4.84 | 13.45 | 15.00 |

18.2 	Plan of activities under Revolving Fund

| S.No. | Proposed activities | Expected output | Anticipated income (Rs.) | Names of the team members involved |
| --- | --- | --- | --- | --- |
| 18.2.1 | Seedlings: - Production of Drum Stick | 5,000 No. | 60,000 | SMS, Hort and Farm Manager |
|  | - Production of Mango Mallika grafts | 1000No. | 50,000 | SMS ,Hort and Farm Manager |
| 18.2.2 | Soil | 1500No. | 75000 | SMS, Soil Science and Lab Technician |
| 18.2.3 | Water | 1500No. | 150000 | SMS, Soil Science and Lab Technician |
| 18.2.4 | Seed Production: - Millets | 15 q | 75,000 | SMS, Agronomy and Farm Manager |
|  | - Hebbal Avare (HA-4) | 5q | 75,000 | SMS ,Hort and Farm Manager |
|  | - Fodder (COFS-29) | 40 kg | 40000 | SMS, Agronomy and Farm Manager |

## 19.Activities of soil, water and plant testing laboratory during 2016-17

| Sl.No. | Type | No. of samples to be analyzed | Names of the team members involved |
| --- | --- | --- | --- |
| 19.1 | Soil | 1500 | SMS, Soil Science and Programme Asst. (Lab) |
| 19.2 | Water | 1500 | SMS, Soil Science and Programme Asst. (Lab) |

## 20.E-linkage during 2016-17

| S. No | Nature of activities | Likely period of completion (please set the time frame) | Remarks if any |
| --- | --- | --- | --- |
| 20.1 | Title of the technology module to be prepared | - | - |
| 20.2 | Creation and maintenance of relevant database system for KVK | - | - |

21.Activities planned under Rainwater Harvesting Scheme (only to those KVKs which are already having scheme under Rain Water Harvesting)

| S. No | Activities planned | Remarks if any |
| --- | --- | --- |
| 21.1 | Trainings on Rain Water Harvesting and Management | - |
| 21.2 | Crop Demonstration using Farm Pond Water | - |

22. Innovator Farmer’s Meet

| Sl.No. | Particulars | Details |
| --- | --- | --- |
| 22.1 | Are you planning for conducing Farm Innovators meet in your district? | Yes |
| 22.2 | If Yes likely month of the meet | November |
| 22.3 | Brief action plan in this regard | - Selection of Farmers - Documentation of activities - Farmers -Scientist interaction |

23.  Farmers Field School (FFS) planned

| S. No | Thematic area | Title of the FFS | Budget proposed in Rs. |
| --- | --- | --- | --- |
| 23.1 | Pest, Disease and Nutrient Management | ICM in Pomegranate | 30,000 |

24.Budget - Details of budget  utilization (2015-16) up to 31 January 2016

(Rs.)

| S. No. | Particulars | Sanctioned | Released | Expenditure |
| --- | --- | --- | --- | --- |
| 24.1 | Recurring Contingencies |  |  |  |
| 24.1.1 | Pay & Allowances | 80.08000 | Ist 43,34,747 IInd 21,75,000 | 5937622 |
| 24.1.2 | Traveling allowances | 1.00000 |  | 81906 |
| 24.1.3 | Contingencies |  |  |  |
| 24.1.4.1 | Stationery, telephone, postage and other expenditure on office running, publication of Newsletter and library maintenance | 1.00000 |  | 264597 |
| B | POL, repair of vehicles, tractor and equipments | 1.00000 |  | 191745 |
| C | Meals/refreshment for trainees | 0.50000 |  | 53354 |
| D | Training material | 0.25000 |  | 27611 |
| E | Frontline demonstration except oilseeds and pulses | 2.22000 |  | 166526 |
| F | On farm testing | 0.10000 |  | 2991 |
| G | Training of extension functionaries | - |  | - |
| H | Maintenance of buildings | - |  | 42335 |
| I | Establishment of Soil, Plant & Water Testing Laboratory | - |  | - |
| J | Library | 0.05000 |  | 5500 |
| K | Extension Activities | 0.50000 |  | 44310 |
| l | Farmers Field School | 0.30000 |  | 5935 |
| 24.1 | Total Recurring | - |  | - |
| 24.2 | Non-Recurring Contingencies | - |  | - |
| 24.2.1 | Works | - |  | - |
| 24.2.2 | Equipments including SWTL & Furniture | 2.00000 |  | - |
| 24.2.3 | Vehicle (Four wheeler/Two wheeler, please specify) | - |  | - |
| 24.2.4 | Library | - |  | - |
| 24.2 | Total Non Recurring | - |  | - |
| 24.3 | REVOLVING FUND | - |  | - |
| 24.4 | GRAND TOTAL (A+B+C) | 89.00000 | 6509747 | 6824432 |

25.Details of Budget Estimate (2016-17) based on proposed action plan

| S. No. | Particulars | BE 2016-17 proposed (Rs.) |
| --- | --- | --- |
| 25.1 | Recurring Contingencies |  |
| 25.1.1 | Pay & Allowances | 1,32,00,000 |
| 25.1.2 | Traveling allowances | 3,50,000 |
| 25.1.3 | Contingencies | - |
| A | Stationery, telephone, postage and other expenditure on office running, publication of Newsletter and library maintenance (Purchase of News Paper & Magazines) | 4,00,000 |
| B | POL, repair of vehicles, tractor and equipments | 3,50,000 |
| C | Meals/refreshment for trainees (ceiling upto Rs.40/day/trainee be maintained) | 1,50,000 |
| D | Training material (posters, charts, demonstration material including chemicals etc. required for conducting the training) | 1,00,000 |
| E | Frontline demonstration except oilseeds and pulses | 443325 |
| F | Entrepreneurship Development Programme | 2,74,500 |
| G | On farm testing | 15,680 |
| H | Training of extension functionaries | 25,000 |
| I | Maintenance of buildings | 2,00,000 |
| J | Establishment of Soil, Plant & Water Testing Laboratory | 2,00,000 |
| K | Farmers Field School | 30,000 |
| L | Library | 25,000 |
| 25.1 | TOTAL Recurring Contingencies | 15763505 |
| 25.2 | Non-Recurring Contingencies | - |
| 25.2.1 | Works | - |
|  | Lab Equipments | 2,00,000 |
|  | Rain water harvesting for main building & Hostel | 2,00,000 |
|  | Audio visual aids | 80,000 |
|  | Up gradation of seminar hall | 2,00,000 |
| 25.2.2 | Equipments including SWTL & Furniture | 2,00,000 |
| 25.2.3 | Vehicle (Four wheeler/Two wheeler, please specify) Sumo Gold /Sumo Grand+ | 16,00,000 |
| 25.2.4 | Library (Purchase of assets like books & journals) | 50,000 |
| 25.2 | TOTAL Non-Recurring Contingencies | 2530000 |
| 25.3 | REVOLVING FUND | - |
| 25.4 | GRAND TOTAL | 18293505 |

-------XXXXXXX-------