INDEX

| Sl. No. | Content | Page No. |
| --- | --- | --- |
|  | General information | 1 |
|  | Details of staff as on date | 2 |
|  | Details of SAC meeting | 3-4 |
|  | Human Resource Development | 5 |
|  | Cross-learning across KVKs | 6 |
|  | Proposed cluster of KVKs | 6 |
|  | Operational areas | 7-8 |
|  | Technology Assessment | 9 |
|  | Frontline Demonstrations | 10-16 |
|  | Training for Farmers/ Farm Women (On Campus) | 17-19 |
|  | Training for Farmers/ Farm Women (Off campus) | 20-22 |
|  | Training for Rural Youth | 22 |
|  | ### Training for Extension Personnel | 23 |
|  | - Vocational trainings | 24 |
|  | Sponsored trainings | 24 |
|  | - Extension programmes | 25 |
|  | Technological knowledge | 26 |
|  | Technological Products | 26 |
|  | Technological Information | 27 |
|  | Additional Activities Planned | 27 |
|  | Financial status | 28 |
|  | Plan of activities under Revolving Fund | 28 |
|  | - Activities of soil, water and plant testing laboratory | 28 |
|  | - Rainwater Harvesting Scheme | 28 |
|  | - Innovator Farmer’s Meet | 29 |
|  | - Farmers Field School (FFS) | 29 |
|  | - Budget | 30-31 |
|  | - Annexure-I Calendar of Activities | 32-40 |
|  | - Annexure-IIOn and Off Campus Training Calendar | 41 |
|  | - Annexure-III KVK Farm plan for the year 2015-16 | 42 |
|  | - Annexure-IV A. Innovative Programme | 43-44 |
|  | - Technology Week | 44 |
|  | - Village adoption for sustainable livelihood | 45 |
|  | - Innovative Farmers Meet | 46 |

###### ZONAL PROJECT DIRECTORATE – ZONE VIII BANGALORE

###### ACTION PLAN OF KVK CHITRADURGA FOR 2015-16

###### 1. General information about the Krishi Vigyan Kendra

| 1.1 | Name and address of KVK with Phone, Fax and e-mail | : | Krishi Vigyan Kendra, Chitradurga Babbur Farm, Hiriyur-577 598, Chitradurga district, Karnataka State. Phone : 08193-289160 Fax : 08193-289160 e-mail : kvkchitradurga@gmail.com |
| --- | --- | --- | --- |
| 1.2 | Name and address of host organization | : | University of Agricultural & Horticultural Sciences, Shivamogga Savalanga Road, Navile, Shivamogga, Karnataka-Pin: 577 225 |
| 1.3 | Year of sanction | : | 2000 (NATP), 2004 to 2014 - Full-fledged under UASB Under UAHS Shivamogga, Since 01-07-2014 |
| 1.4 | Website address of KVK and date of last update |  | www.kvkchitradurga.in Last Update:26-03-2015 |

2. Details of staff as on date

| Sl. No. | Sanctioned post | Name of the incumbent | Discipline | If Permanent, Please indicate |  | Date of joining | If Temporary, pl. indicate the consolidated amount paid (Rs./month) |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Current Pay Band | Current Grade Pay |  |  |
| 2.1 | Programme Coordinator | - | - | 37000-67000 | 9000 | - | Vacant |
| 2.2 | SMS Soil Science & Programme Coordinator(Ic) | Dr. Sarvajna B. Salimath | Soil Science & Agril. Chemistry | 15600-39100 | 7000 | 01-09-08 | Permanent |
| 2.3 | Subject Matter Specialist | Dr. S. Onkarappa | Crop Protection | 15600-39100 | 6000 | 17-07-09 | Permanent |
| 2.4 | Subject Matter Specialist | Mr. Prakash Kerure | Horticulture | 15600-39100 | 6000 | 10-11-11 | Permanent |
| 2.5 | Subject Matter Specialist | Smt. N. Sudharani | Home Science | 15600-39100 | 6000 | 19-10-12 | Permanent |
| 2.6 | Subject Matter Specialist | Mr. Gajendra T.H | Agri. Extension | 15600-39100 | 6000 | 6-12-13 | Permanent |
| 2.7 | Subject Matter Specialist | Dr.RudragoudaF.Channagounda | Agronomy | 15600-39100 | 6000 | 17-10-13 | Permanent |
| 2.8 | Programme Assistant(Lab) | Ms. B.N. Geetha Kumari | Agriculture | 9300-34800 | 4200 | 08-11-10 | Permanent |
| 2.9 | Programme Assistant (Computer) | Miss. Kavitha P.Naik | Computer Science | 9300-34800 | 4200 | 31-11-13 | Permanent |
| 2.10 | Farm Manager | - | - | 9300-34800 | 4200 | - | Vacant |
| 2.11 | Accountant/Superintendent | Mr. D. Gurumurthy | Superintendent (A/c) | 9300-34800 | 4200 | 01-01-13 | Permanent |
| 2.12 | Stenographer | Mrs. A. Rekha | Steno (Typing cum computer asst.) | 5200-20200 | 2400 | 19-12-12 | Temporary |
| 2.13 | Driver 1 | Mr. Mehaboob Patel | Tractor driver | 5200-20200 | 2000 | 23-10-08 | Permanent |
| 2.14 | Driver 2 | Mr. Bhadraiah S. | Jeep driver | 5200-20200 | 2400 | 01-03-13 | Temporary |
| 2.15 | Supporting staff 1 | Mr. Basavaraju | Cook | 5200-20200 | 1800 | 22-12-08 | Permanent |
| 2.16 | Supporting staff 2 | Mr. G.Nagaraj | Messenger | 4440-7440 | 1300 | 1-06-13 | Temporary |

3. Details of SAC meeting

| Sl. No | Date | Major recommendations | Status of action taken in brief | Tentative date of SAC meeting proposed during 2015-16 |
| --- | --- | --- | --- | --- |
| 3.1 | 11-8-2014 | Awareness on importance of pulses in nutritional security | Twenty Front Line Demonstrations planned for 2015-16 under NFSM (Bengal gram and Redgram) | Third week of August, 2015 Third week of August, 2015 |
|  |  | Conduct residue analysis in Pomegranate Fruits | Residue analysis is planned in FLD for 2015-16 |  |
|  |  | FLD of proven technology need to be convincing Line depts. staff and farmers | Large scale demonstrations were conducted on ICM in Groundnut, Redgram, Onion, Hebbal Aware (HA-4) , Mango, Banana, Pomegranate crops during 2014-15. |  |
|  |  | Emphasize on large scale production of Vermicompost. | Compost units of the Farm will be utilized for large scale vermicompost. |  |
|  |  | Common training calendar may be prepared jointly by KVK and DATC Hiriyur. | Discussed with ADA, DATC, Hiriyur and our plan for 2015-16 is shared with them and care will be taken to avoid duplicity. |  |
|  |  | KVK must limit to training programmes to those related to FLD and OFT beside need based and selected sponsored programmes. | Trainings planned as per the FLD and OFT |  |
|  |  | Problems for taking up FLD/OFT should be identified through PRA of cluster villages. Work intensively in these villages for 2 to 3 years on the prioritized problems. Impact of KVK interventions should be measured in terms of extent to which these problems are minimized | New cluster villages were identified through PRA technique. Success stories were documented and impact assessment will be initiated for KVK interventions. Ten abstracts sent for KVK seminar to be held at UAS Dharwad. |  |
|  |  | Seek permission from ZPD and recruit Farm Manager on contract basis immediately. Simultaneously, initiate action to recruit on permanent. | Under process |  |
|  |  | Popularize double cross hybrid in sericulture through demonstration | FLD on double cross hybrid in sericulture was conducted in Hariyabbe cluster during 2014-15. |  |
|  |  | Soil test based fertilizer recommendation may be taken as innovative activity | Village adopted for this activity and soil test based reccommandations will be made |  |
|  |  | Documentation and maintenance of district agriculture status and other activities | Last ten year data on agriculture and allied activities were collected from respective line department and documented. |  |
|  |  | Characteristics of Hebbal Avare HA-4 variety need to be assessed | FLD was implemented in Baramasagara Cluster (at Hampanur village) and different parameters were assessed. |  |
|  |  | Conduct comprehensive demonstration on large scale with line department for wider spreading of the technology. | Large scale demonstrations were conducted on groundnut, Redgram, Bengalgram and Greengram in collaboration with Agriculture Department during 2014-15. . Dr. Varaprasad Project Director, DOR, participated in the Groundnut Field day at Devarkotta. |  |
|  |  | Popularize micro credit facility of NABARD and other nationalized banks. | Through our on campus trainings farmers will be sensitized about NABARD linkage for micro finance. |  |
|  |  | Sensitize farm women about scientific dairy management practices | Front Line Demonstrations planned for 2015-16. |  |
|  |  | Create awareness on DCH castor hybrid through large scale demonstration | Large scale demonstrations were conducted in KVK contact farmer’s field during 2014-15 through IFS programme in 10 villages of Hiriyur taluka. |  |
|  |  | Intensify the onion seed production through participatory approach | Around 22 quintal seed is being produced through participatory seed production programme at Muddapaura cluster during 2014-15. Same programme through certification is being planned during 2015-16 under FLD. |  |
|  |  | Demonstrations/Training about drip irrigation in onion need to be conducted | OFT on onion was conducted using raised bed cultivation through drip irrigation. A demonstration will be taken up at our Farm during 2015-16. |  |
|  |  | Popularize the agricultural technologies through electronic media | Regularly sending agriculture information through SMS (Farmers Portal) and actively using mass media for technology dissemination in a wider scale. |  |

4. Capacity Building of KVK Staff

4.1. Plan of Human Resource Development of KVK personnel

| Sl. No | New Areas of Training | Institution proposed to attend | Justification |
| --- | --- | --- | --- |
| 4.1.1 | Weed management in field crops | UAS, Dharwad | Weed Management through integrated approach |
| 4.1.2 | Recent advances in Horticulture | IIHR, Bangalore | Precision Farming |
| 4.1.3 | Soil, Plant and Environment interaction | MASHAV University, Israel | Management of soil and water quality in relation to environmental changes |
| 4.1.4 | Post harvest technology | IICPT, Thanjavur | Food processing technology & quality analysis. |
| 4.1.5 | Advance trends in Food science and technology | ANGRU, Hyderabad | Community based Recent food science technologies |
| 4.1.6 | Recent trend in Agronomy | MANAGE, Hyderabad | Management of crops through modern technology |
| 4.1.7 | Mass production of Trichoderma and Pseudomonas | NBAII, Bangalore | Management of wilt and bacterial diseases in agricultural and horticultural crops |
| 4.1.8 | Web designing, photo shop, DTP, Data base management | GKVK, Bangalore | Updating KVK database |
| 4.1.9 | Technology Documentation and Presentation for Effective Extension | MANAGE, Hyderabad | To develop skill in effective documentation and presentation |
| 4.1.10 | Professional skills for Trainers of Extension Institutes of Agriculture and allied departments | MANAGE, Hyderabad | Improved skill development |
| 4.1.11 | New multi media management | NAARM, Hyderabad | To manage digital resource and publications |

4.2. Cross-learning across KVKs

| Sl. No | Name of the KVK proposed | Specific Learning Areas |
| --- | --- | --- |
| 4.2.1 | Within ring – Davanagere, Tumkur, Shivamogga | - Quality Seeds and Planting Materials. - Nutrient Mixture, Exposure Visits, Farmers’ Interaction - Management of Black Headed Caterpillar and Wilt in Coconut - Management of Stem Borer and Blight in Maize |
| 4.2.2 | Within the zone – a ) KVK, Thrissur, Kerala | Resource Conservation Technologies Vegetable seed production in collaboration with SHG, |
|  | b) KVK, CARD, Pattanamtitta, Kerala | Role of Processing and value addition in empowering SHG |
|  | c) KVK, Kozhikode, Kerala. | Training programmes emphasized on unemployed women and youth such as mechanized coconut climbing and fresh water fish culture. |
| 4.2.3 | Outside zone – a) KVK, Babaleshwara, Maharashtra | Extension method followed for dissemination of agricultural crops, modern farm technologies and method demonstrations, rain harvesting technology. |
|  | b) KVK, Baramati, Maharashtra | Improved Farm Technologies, Method Demonstrations and micro irrigation technology. |

5. Proposed cluster of KVKs (3 to 5 neighboring KVKs) to be formed for sharing knowledge/expertise, resources and activities

| Sl.No. | Name of the KVKs included in the cluster | What do you intend to share with Cluster KVKs | What do you expect from Cluster KVKs |
| --- | --- | --- | --- |
| 5.1 | Davanagere, Tumkur, Shivamogga | - INM in Banana and cotton - PHT of millets - INM in cotton - IPM in Coconut - INM in groundnut | - Fish cultivation and Dairy management - CBA formation and strengthening for effective management - Micronutrients ,Horticulture seeds/planting materials - Value addition in coconut - Cultivation of maize |

6. Operational areas details

| Sl.No. | Major crops & enterprises being practiced in cluster villages | Prioritized problems in these crops/ enterprise | Extent of area (ha/No.) affected by the problem in the district | Names of Cluster Villages identified for intervention | Proposed Intervention (OFT, FLD) | Trainings/ Extension activity |
| --- | --- | --- | --- | --- | --- | --- |
| 6.1 | Foxtail millet | Low yielding and susceptible to pest and diseases | 12,266 | Nayakanhatti | OFT | Trainings and field days/sharing meetings will be conducted in the FLD and OFT villages. Trainings and field days/sharing meetings will be conducted in the FLD and OFT villages |
| 6.2 | Finger millet | Non availability of high yielding and neck blast resistant varieties | 35,867 | Karehalli | FLD |  |
| 6.3 | Finger millet | Low income due to Lack of knowledge on processing , value addition and Branding | 650 | Madadkere | FLD |  |
| 6.4 | Groundnut | Old varieties Low plant population Lack of application of micronutrients | 75,000 | Talaku | FLD |  |
| 6.5 | Fodder crops | Non availability of green fodder and Imbalanced nutrition | 12,000 | Kodihalli | FLD |  |
| 6.6 | Red gram | Low yield, pod borer and leaf webber | 5,000 | Kodihalli | FLD |  |
| 6.7 | Bengal gram | Low yield, pod borer and wilt | 7,600 | Kodihalli | FLD |  |
| 6.8 | Onion | Non availability of quality seed material Dependency on other states for seed Higher seed cost | 13, 967 | Hanagal | FLD |  |
| 6.9 | Watermelon | Fruit cracking, Imbalanced nutrient application Wilt disease | 275 | Taluku | FLD |  |
| 6.10 | Chrysanthemum | Imbalanced nutrient application Wilt and leaf blight disease | 500 | Belagere | FLD |  |
| 6.11 | Pomegranate | Bacterial blight | 6,200 | Kodihally | OFT and FFS |  |
| 6.12 | Areca nut | Spindle bug, scales, mites and leaf spot | 7,500 | T. Nulenur, | FLD |  |
| 6.13 | Field bean | Mono cropping Depletion of soil fertility Weed problem | 3,500 | Sirigere | FLD |  |
| 6.14 | Integrated farming system | Mono cropping, component integration , inefficient utilization of farm resource | - | Kodihally, Sirigere, T. Nulenur | FLD |  |
| 6.15 | Terrace gardening | Crop plan for terrace gardening and recycling of waste material. | - | Sirigere | FLD |  |
| 6.16 | Dairy | Imbalanced nutrition feeding to livestock. Economic and Balanced feed for enhancing milk yield | 2,56,000 | Kodihally | FLD |  |

7. Technology Assessment

| Sl. No. | Crop/ enterprise | Prioritized problem | Title of intervention | Technology options | Source of Technology | Name of critical input | Qty per trial (kg) | Cost per trial | No. of trials | Total cost for the intervention (Rs.) | Parameters to be studied | Team members |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 7.1 | Foxtail millet | Low yielding and susceptible to pest and diseases | Assessment of foxtail millet varieties for higher yield | T1:SIA-2644 T2 :HMT-101 | UASR UASD | Seeds Biofertilizer ZnSO4 | 10 1.5 4 | 1130 | 02 | 2260 | Germination percentage, plant height (cm), panicle length, yield kg/ha and economics | Rudragouda Gajendra Salimath Onkarappa, Sudharani Prakash Kerure |

8.  Frontline Demonstrations

| Sl. No. | Category | Crop/ enterprise | Prioritized problem | Technology to be demonstrated | Specify Hybrid or Variety | Name of the Hybrid or Variety | Source of Technology | Name of critical input | Qty per Demo | Cost per Demo | No. of Demo | Total cost for the Demo (Rs.) | Parameters to be studied | Team members |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 8.1 | Millets | Finger millet | Non availability of high yielding and neck blast resistant varieties | Introduction of ML-365 finger millet variety for higher yield | Variety | ML-365 | UASB | Seeds Bio-inputs ZnSO4 | 5 kg 1.5 kg 4 kg | 640 | 05 | 3200 | Plant height (cm), No. of effective tillers/ plant, No. of finger/ear head, Yield kg/ha and economics | Rudragouda F Salimath. Gajendra, Onkarappa, Prakash Kerure Sudharani |
|  |  | Finger millet | Low income due to Lack of knowledge on processing , value addition and Branding | Branding and Market Linkages to Finger millet Value Added Products under EDP mode | Variety | GPU 28 | UASB | Packaging Material (Al standing pouch) Food Labels, Sealing Machine Electronic Food weighing scale | 2 x 200 2 x 200 1 No 1 No | 2000 2000 2500 5000 | 2 | 23,000 | Economics, Consumer preference. | Sudharani Rudragouda, Gajendra Salimath Onkarappa |
| 8.2 | Oilseeds | Groundnut | Old varieties Low plant population Lack of application of micronutrients | Integrated Crop Management in Groundnut | Variety | KCG-6 | UASB | Seeds Rhizobium, PSB Trichoderma Captan Chloropyriphos ZnSo4 | 30 kg 3 kg 0.5 kg 1.0 l 4 kg | 3415 | 5 | 17,075 | Germination percentage no. of pods/plant, 100 seed wt, shelling %, yield and B:C ratio | Rudragouda Salimath Gajendra Onkarappa, Prakash Kerure Sudharani |
| 8.3 | Pulses | Red gram | Low yield,pod borer and leaf webber | Integrated Crop Management in Red gram | Variety | BRG-2 | UAS (B) | Seeds Trichoderma Rhizobium PSB Pheromone traps Lures NPV | 6 kg 40 g 200 g 200 g 4 No. 12 No. 300 ml | 540 4 20 20 120 360 690 | 5 | 8,770 | No. of larva per plant, No. of pods per plant, Yield | Onkarappa, Sarvajna B. Salimath, Rudragouda Gajendra Sudharani |
|  |  | Bengal gram | Low yield,pod borer and wilt | Integrated crop Management in Bengal gram | Variety | J.G.-11 | UAS (B) | Seeds Trichoderma Rhizobium PSB Pheromone traps Lures NPV | 25 kg 200 g 200 g 200 g 4 No. 12 No. 200 ml | 1875 20 20 20 120 360 460 | 5 | 14375 | No. of pods per plant, No. of larva per plant, Yield | Onkarappa, Salimath Rudragouda Sudharani |
| 8.4 | Horticultural crops | Onion | Non availability of quality seed material Dependency on other states for seed, Higher seed cost | Seed Production in Onion | Variety | Bhima Super | DOGR, Pune | Bhima Super breeder Seed | 5 kg | 2000 | 5 | 10,000 | Germination percentage Bulb Yield/ ha in kharif Seed yield in rabi Net Returns | Prakash Kerure Onkarappa, Gajendra Rudragouda |
|  |  | Banana | Imbalanced application of major nutrients, fruit cracking, Lower bunch yields | Improved Management practices for higher yield in Banana | Local | Putta Bale | IIHR Bangalore | Arka Banana Special | 8 kg | 20 kg/ha | 5 | 8000 | Bunch yield per plant | Salimath Prakash Kerure Onkarappa Sudharani Gajendra Rudragouda |
|  |  | Watermelon | Fruit cracking, Imbalanced nutrient application Wilt disease | Integrated Crop Management in Watermelon | Hybrid | Kiran | IIHR Bangalore | Arka Vegetable Special, Bio inputs: PSB, Pseudomonas, Trichoderma | 6 kg Vegetable special, 1.5 kg of PSB, Pseudomonas, Trichoderma | 1,350 | 5 | 6750/- | Per cent fruit cracking fruit set per vine, Yield/ha, Incidence of pest & diseases, B:C ratio | Mr. Prakash Kerure Dr. S. Onkarappa, Mr. Gajendra T.H , Dr. Rudragouda |
|  |  | Pomegranate | Bacterial blight | Bacterial blight management in Pomegranate | Variety | Bhagava | UAS (D) | Pseudomonas fluorescens Trichoderma viridae VAM Neem cake Micronutrients Residue analysis | 4 2 2 13 0.5 | 6600 | 3 | 19800 | No. fruits per plant, Percent incidence of disease, Residue in fruits, Yield | Onkarappa,. Salimath Prakash Kerure, Gajendra and Sudharani |
|  |  | Terrace gardening | Low health status due to non- availability fresh vegetables throughout the year and high cost of vegetables. Lack of knowledge on terrace gardening. Pesticide contaminated vegetables. | Terrace gardening for Nutrition security of urban population | Variety | Arka varieties | IIHR, Bangalore | Vegetable seed kit Vegetable pres ervator (CRIDA model) Protrays Fibre pots | 3 kits 1 unit 3 10 | 300 1500 60 1500 | 3 | 10080 | Consumption of vegetables (ICMR stds) Availability of vegetables throughout the year. Nutritional status before and after | Sudharani Salimath Onkarappa Prakash kerure Gajendra Rudragouda |
|  |  | Areca nut | Spindle bug, Mites, Scales, Leaf spot | Integrated crop management in Arecanut | Local variety | Local Adike | UAS (B) | Trichoderma viridae Dimethoate 30 EC Dicofol 18.5 EC Mancozeb 75 WP | 2 kg 1.5 l. 1.0 l 1 kg | 200 600 400 400 | 5 | 8,000 | No. of bugs per plant, No. of scales per leaf, No. of mites per 2 sq.cm. area, Percent disease incidence Yield | S. Onkarappa, Prakash Kerure, . Sarvajna B. Salimath Gajendra Sudharani |
|  |  | Field bean | Mono cropping Depletion of soil fertility Weed Problem | Demonstration of Hebbal Avere-4 as an intercrop in Arecanut | Variety | Hebbal Avare-4 | UAS (B) | Seeds | 6 kg | 900 | 5 | 4500 | Pre and post harvest soil status Weed count/sq m Sole crop yield and intercrop yield Crop equivalent yield, BCR | Prakash Kerure Onkarappa Salimath Gajendra |
|  |  | Chrysanthemum | Imbalanced nutrient management. Mall formation of flower by sucking pest, bud borer and blight . | Integrated Crop Management in Chrysanthemum | Local variety | Chandani local | IIHR, Bangalore | Micronutrients: ZnSO4:10 kg/ha, Borax:2.5 kg/ha Bio-inputs: Trichoderma, PSB and Pseudomonas @ 10 Kg/ha | 4 kg ZnSO4 1 kg Borax 4 k g PSB, 4 kg Pseudomonas, 4 kg Trichoderma, | 1,600 | 5 | 8,000 | No branches/plant, no. of flower picking, flower diameter, flower yield/plant/ha, incidence of pest & diseases, B:C ratio, no mall formed flower | Prakash Kerure. Salimath . Onkarappa, Rudragouda Gajendra Sudharani |
| 8.5 | Livestock | Fodder | Non availability of green fodder Imbalanced nutrition | Technology demonstration module in fodder crops | Varieties | Lucerne COFS-29 Fodder cowpea Horse gram South African tall | TNAU | Seeds Azospirillum PSB Trichoderma | 15 kg 3 kg | 3300 | 5 | 16,500 | Fodder yield (t/ha) and Palatability | Rudragouda F.C, . S.B Salimath, Mr. Gajendra T.H . S. Onkarappa, Mr. prakash Kerur Sudharani |
|  |  | Dairy | Imbalanced nutritional management Lack of awareness on balanced feeding . | Demonstration on balanced feed formulation for cross breed cattle | Variety | - | NIANP | Improved fodder verities Concentrate feed Mineral mixture | 4000 slips 100 5 q 5 kg | 3,648 | 5 | 18,240 | Milk yield Fat content Palatability | Gajendra,T.H., Rudragouda, CF,S.B., Salimath,Onkarappa,S.,Prakash Kerure, Sudharani,S. |
| 8.6 | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | IFS | Agri-horti-silvi-pastural and apiculture | Mono cropping, inefficient utilization of farm resource | IFSD | Varieties | Varieties | UAS, Bangalore | Food crops. Vegetable Seed kit Fodder crop Horticulture Small Ruminants, Apiary, Azolla Unit, Vermi composting Unit, Bio Input | 1 | 5000 | 5 | 25,000 | Efficient Utilization of limited Resources | Gajendra,T.H., Rudragouda, Salimath, Onkarappa,S.,Prakash Kerure, Sudharani,S. |

9. Training for Farmers/ Farm Women  (On Campus)

| Sl. No. | Thematic area | Crop / Enterprise | Major problem | Related field intervention (OFT/FLD)* | Training Course Title** | No. of Courses | Expected No. of participants | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 9.1 | Crop Production | Fodder | Non availability of high yielding green fodder | FLD | High yielding green fodder varieties for increased milk yield | 1 | 20 | Rudragouda F.C Gajendra S.B Salimath S. Onkarappa, Prakash Kerure Sudharani N |
|  |  | Groundnut | Low plant population Poor pod filling Lack of application of bio inputs | FLD | Higher yield through ICM in groundnut | 1 | 20 | Rudragouda F.C Gajendra S.B Salimath S. Onkarappa, Prakash Kerure Sudharani N |
| 9.2 | Soil Science | Banana & Onion | Micro nutrient deficiency Lack of awareness on Micro nutrient application Micro nutrient deficiency symptoms | FLD | Micro nutrient management in banana and onion | 1 | 30 | Dr. S.B. Salimath, Mr. GajendraT.H. |
|  |  | Soil | Soil salinity Lack of awareness on crops which are persistent salinity | FLD | Management of salt affected soil | 1 | 30 | Dr. S.B. Salimath, Mr. GajendraT.H. |
|  |  | Horticulture crops | Salt affected water Water budgeting | FLD | Water quality and its management for horticulture crops | 1 | 30 | Dr. S.B. Salimath, Mr. GajendraT.H. |
|  |  | Pomegranate | In availability of soil moisture while application of solid state nutrients | FLD | Nutrient management through fertigation in pomegranate | 1 | 30 | Dr. S.B. Salimath, Mr. GajendraT.H. |
| 9.3 | Horticulture Production | Onion | Weed management, imbalanced nutrition, bolting and sprouting in storages | FLD | Balanced nutrition and pest/disease management for higher bulb yield | 1 | 30 | Prakash Kerure S. Onkarappa, Sarvajna B. Salimath Gajendra and Rudragouda F.C |
|  |  | Watermelon | Imbalanced nutrition, Wilt disease, Fruit Cracking | FLD | Balanced fertigation in watermelon for higher yield | 1 | 30 | Prakash Kerure S. Onkarappa, Sarvajna B. Salimath Gajendra and Rudragouda F.C |
|  |  | Pomegranate | Bacterial blight, wilt, lack of Pruning skills, indiscriminate use of pesticides | OFT | Pruning techniques and IPDM practices in Pomegranate for quality fruits production | 1 | 30 | Prakash Kerure S. Onkarappa, Sarvajna B. Salimath Gajendra |
| 9.4 | Plant Protection | Red gram | Pod borer, Sterility mosaic, wilt | FLD | Integrated pest and disease management in Red gram for higher yield | 1 | 30 | S. Onkarappa Sarvajna B. Salimath Rudragouda F.C Sudharani N. |
|  |  | Bengal gram | Pod borer, wilt | FLD | Integrated pest and disease management in Bengal gram | 1 | 30 | S. Onkarappa Sarvajna B. Salimath Rudragouda F.C Gajendra Sudharani N. |
|  |  | Pomegranate | Bacterial blight, wilt, thrips, fruit borer | OFT | Bacterial disease management for quality fruits production | 1 | 30 | S. Onkarappa Sarvajna B. Salimath Prakash Kerure Gajendra T.H. Sudharani N. |
|  |  | Areca nut | Spindle bug, Scales, Leaf spot | FLD | Integrated management of pest and diseases in Areca nut for higher nut yield | 1 | 30 | S. Onkarappa Sarvajna B. Salimath Prkash Kerure Gajendra T.H. Sudharani N. |
| 9.5 | Home Science | Finger millet | Low income due to lack of knowledge on Value addition, branding | FLD | Higher income through value addition of millet | 1 | 30 | Sudharani N. Rudragouda F.C Sarvajna B. Salimath S. Onkarappa Gajendra T.H. Sudharani N. |
|  |  | Terrace gardening | Low health status due to non- availability fresh vegetables throughout the year and high cost of vegetables. Lack of knowledge on terrace gardening. Pesticide contaminated vegetables. | FLD | Terrace gardening for nutrition security | 1 | 30 | Sudharani N. Sarvajna B. Salimath S. Onkarappa Prakash Kerure Rudragouda F.C Gajendra T.H. |
| 9.6 | Capacity building | Major agricultural crops | low demand on traditional crops | FLD | Market led Production System | 1 | 30 | Gajendra,T.H. S.B. Salimath Rudragouda CF Onkarappa,S Prakash Kerure Sudharani N. |
|  |  | Dairy | Dairying is treated as subsidiary occupation | FL1D | Commercial dairy farming | 1 | 30 | Gajendra,T.H. S.B., Salimath Rudragouda, CF Onkarappa,S Prakash Kerure Sudharani, N |
|  |  | IFSD | Small and Marginal land holdings | FLD | Livelihood security through IFS | 1 | 30 | Gajendra,T.H., Rudragouda, CF. S.B. Salimath, Onkarappa,S, Prakash Kerure, Sudharani,S |
|  |  | Red gram, Pomegranate, Chilli, Paddy and Cotton | lack of awareness on ICT tools | FLD | Access To Advanced Market information through Web Based Extension Channels | 1 | 30 | Gajendra,T.H., Rudragouda, CF. S.B., Salimath, Onkarappa,S, Prakash Kerure, Sudharani,S |

10. 9. Training for Farmers/ Farm Women  (Off Campus)

| Sl.No. | Thematic area and the Crop/Enterprise | Training title* | No. of programmes and Duration (days) | Type of Clientele (SHGs, NYKs, School students, Women, Youth etc.) | Expected No. of participants | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- |
| 10.1 | Crop production | Improved agronomic practices for fodder production | 1 | Farmers/ Farm women | 30 | Dr. Rudragouda F.C , Mr. Gajendra T. H Dr. S. Onkarappa |
|  |  | Integrated crop management in groundnut | 1 | Farmers/ Farm women | 30 | Dr. Rudragouda F.C , Mr. Gajendra T. H Dr. S. Onkarappa, Dr S.B.Salimath |
|  |  | Improved production practices in finger millet production | 1 | Farmers/ Farm women | 30 | Dr. Rudragouda F.C , Mr. Gajendra T. H Dr. S. Onkarappa |
| 10.2 | Soil Science | ICM in banana and onion | 1 | Farmers/ Farm women | 30 | Dr. S.B. Salimath, Mr. GajendraT.H. |
|  |  | Management of salt affected soil | 1 | Farmers/ Farm women | 30 | Dr. S.B. Salimath, Mr. GajendraT.H. |
|  |  | Nutrient management through fertigation in pomegranate | 1 | Farmers/ Farm women | 30 | Dr. S.B. Salimath, Mr. GajendraT.H. |
| 10.3 | Horticulture | Improved onion cultivation practices | 1 | Farmers/ Farm women | 30 | Mr. Prakash Kerure, Mr. Gajendra,T.H., Dr. Onkarappa,S |
|  |  | Seed production techniques in onion | 1 | Farmers/ Farm women | 30 | Mr. Prakash Kerure, Mr. Gajendra,T.H., Dr. Onkarappa,S |
|  |  | Improved production techniques in pomegranate | 1 | Farmers/ Farm women | 30 | Mr. Prakash Kerure, Mr. Gajendra,T.H., Dr. Onkarappa,S |
|  |  | Cropping system in Arecanut | 1 | Farmers/ Farm women | 30 | Mr. Prakash Kerure, Mr. Gajendra,T.H., Dr. Onkarappa,S |
|  |  | Improved production technology in watermelon | 1 | Farmers/ Farm women | 30 | Mr. Prakash Kerure, Gajendra,T.H., Dr. Onkarappa,S |
| 10.4 | Plant protection | Integrated Management of pod borer in Redgram | 1 | Farmers/ Farm women | 30 | Dr. Onkarappa,S Mr. Gajendra,T.H., |
|  |  | Management of spindle bug in Arecanut | 1 | Farmers/ Farm women | 30 | Dr. Onkarappa,S Mr. Gajendra,T.H., |
|  |  | Management of diseases in Groundnut | 1 | Farmers/ Farm women | 30 | Dr. Onkarappa,S Mr. Gajendra,T.H., |
|  |  | Preparation of NSKE for pest management | 1 | Farmers/ Farm women | 30 | Dr. Onkarappa,S Mr. Gajendra,T.H., |
|  |  | Management of diseases in Banana | 1 | Farmers/ Farm women | 30 | Dr. Onkarappa,S Mr. Gajendra,T.H., |
| 10.5 | Home Science | Management of Diabetes through diet | 1 | Women | 30 | Sudharani & Gajendra |
|  |  | Processing and value addition in millets | 1 | SHG | 30 | Sudharani & Gajendra |
|  |  | Processing and value fruits and vegetables | 1 | Women | 30 | Sudharani & Gajendra |
|  |  | Role of terrace gardening | 1 | Women | 30 | Sudharani & Gajendra |
| 10.6 | Capacity Building | Integrated Farming System Development | 1 | Farmers | 30 | Mr. Gajendra,T.H.,Dr. Rudragouda, CF. Dr. S.B., Salimath, Dr. Onkarappa,S, Mr. Prakash Kerure, |
|  |  | lack of awareness on ICT tools Access To Advanced Market information through Web Based Extension Channels | 1 | Farmers | 30 | Mr. Gajendra,T.H., Dr. Rudragouda, CF. Dr. S.B., Salimath, Dr. Onkarappa,S, Mr. Prakash Kerure, Mrs. Sudharani,S |

11. Training for Rural Youth

| Sl.No. | Thematic area | Crop / Enterprise | Major problem | Related field intervention (OFT/FLD)* | Training Course Title** | No. of Courses | Expected No. of participants | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 11.1 | Horticulture Production | Onion | Non-availability of quality seeds, | FLD | Seed production aspects in onion for higher income/returns | 1 | 30 | Mr. Prakash Kerure Dr.S.Onkarappa Dr. Sarvajna B. Salimath Mr. GajendraT.H |
| 11.2 | Plant Protection | Pomegranate | Bacterial blight, wilt, fruit borer | OFT | Bio inputs in quality fruit production | 1 | 30 | Dr. S. Onkarappa Dr. Sarvajna B. Salimath Mr. Prakash Kerure Mr. GajendraT.H Mrs. Sudharani N. |
| 11.3 | Home science | Mushroom cultivation | Low awareness | FLD | Mushroom cultivation for self employment generation | 1 | 30 | Mrs. Sudharani N. Mr. GajendraT.H Dr. Sarvajna B. Salimath Dr. S. Onkarappa Dr. Rudragouda CF Mr. Prakash Kerure |
| 11.4 | Capacity building | Bee Keeping | Low awareness | FLD | Apiculture as subsidiary activity | 1 | 30 | Mr. GajendraT.H Dr. Rudragouda CF Dr. Sarvajna B. Salimath Dr. S. Onkarappa Mr. Prakash Kerure Mrs. Sudharani N. |

12 Training for Extension Personnel

| Sl.No. | Thematic area | Training Course Title** | No. of Courses | Expected No. of participants | Names of the team members involved |
| --- | --- | --- | --- | --- | --- |
| 12.1 | Crop Production | Recent Agronomic practices in Finger millet production | 1 | 40 | Dr. Rudragouda F.C , Mr. Gajendra T. H Dr. S.B Salimath , Dr. S. Onkarappa Mr Prakash Kerur , Mrs. Sudharani N. |
| 12.2 | Soil Science | Micro nutrient management in banana and onion | 1 | 40 | Dr. S.B. Salimath, Mr. GajendraT.H. Dr. S. Onkarappa Mr Prakash Kerur , Mrs Sudharani N. |
|  |  | Management of salt affected soil | 1 | 40 | Dr. S.B. Salimath, Mr. GajendraT.H. Dr. S. Onkarappa Mr Prakash Kerur , Mrs Sudharani N. |
|  |  | Water quality and its management for horticulture crops | 1 | 40 | Dr. S.B. Salimath, Mr. GajendraT.H. Dr. S. Onkarappa Mr Prakash Kerur , Mrs Sudharani N. |
|  |  | Nutrient management through fertigation in pomegranate | 1 | 40 | Dr. S.B. Salimath, Mr. GajendraT.H. Dr. S. Onkarappa Mr Prakash Kerur , Mrs Sudharani N. |
| 12.3 | Agricultural Extension | Information Communication Technology and Programme Planning and Management | 1 | 25 | Mr.Gajendra,T.H., Dr. Rudragouda, CF. Dr.S.B., Salimath, Dr. S.Onkarappa,S Mr. Prakash Kerure, Mrs.Sudharani,S |
| 12.4 | Horticulture | Protected cultivation of capsicum under shade nets for quality production | 1 | 50 | Mr. Prakash Kerure, Dr.S.B., Salimath, Dr. S.Onkarappa,S, Dr. Rudragouda, CF. Mrs. Sudharani,N. Mr. Gajendra T.H. |
| 12.5 | Plant Protection | Integrated pest and disease management in agricultural crops | 1 | 40 | Dr. S.Onkarappa,S., Dr.S.B., Salimath, Dr. Rudragouda, CF., Mr. Gajendra T.H. Mrs. Sudharani,N. |
|  |  | Integrated pest and disease management in horticultural crops | 1 | 40 | Dr. S.Onkarappa,S, Dr.S.B., Salimath, Mr. Prakash Kerure Mr. Gajendra T.H. Mrs. Sudharani,N. |
| 12.6 | Home Science | Nutrition education with special reference to mother | 1 | 25 | Mrs. Sudharani,N. Mr. Gajendra T.H. Dr.S.B., Salimath Dr. S.Onkarappa,S Dr. Rudragouda, Mr. Prakash Kerure |

## 13 Vocational trainings

| Sl.No. | Thematic area and the Crop/Enterprise | Training title* | No. of programmes and Duration (days) | Type of Clientele (SHGs, NYKs, School students, Women, Youth etc.) | Expected No. of participants | Sponsoring agency if any | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 13.1 | Horticulture | Skill development in Horticulture for self employment | 12 | Rural youths | 40 | Dept of Hort/NGOS | Prakash, SB, Salimat, S. Onkarappa, Rudragouda, Sudharani, Gajendra |
| 13.2 | Home science | Bakery training for self employment generation | 7 | SHG and rural youths | 20 | - | Sudharani, Gajendra, Salimath, Onkarappa Rudragouda, Prakash kerure |

## 14 Sponsored trainings

| Sl.No. | Thematic area and the Crop/Enterprise | Training title* | No. of programmes and Duration (days) | Type of Participants (SHGs, NYKs, School students, Women, Youth etc.) | Expected number of participants | Sponsoring agency | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 14.1 | Farm Mechanization | Friends of coconut tree | 5 | Rural youths | 100 | CDB/RDPR ZP | ALL SMS |

## 15. Extension programmes

| Sl. No. | Extension Programme/ Activity* | No. of programmes or activities | Expected number of participants | Names of the team members involved |
| --- | --- | --- | --- | --- |
| 15.1 | Advisory Services | 50 | 25000 | All SMS |
| 15.2 | Diagnostic Visits | 08 | 24 | All SMS |
| 15.3 | Field Day | 17 | 950 | All SMS |
| 15.4 | Group Discussions | 29 | 800 | All SMS |
| 15.5 | Kisan Gosthi | 10 | 450 | All SMS |
| 15.6 | Film Show | 10 | 500 | All SMS |
| 15.7 | Self -Help Groups | 5 | 150 | All SMS |
| 15.8 | Kisan Mela | 3 | 15000 | All SMS |
| 15.9 | Exhibition | 6 | 500000 | All SMS |
| 15.10 | Scientists' Visit to Farmers Field | 50 | 150 | All SMS |
| 15.11 | Plant/Soil Health/Animal Health Camps | 2 | 160 | All SMS |
| 15.12 | Farm Science Club | 5 | 65 | All SMS |
| 15.13 | Ex-Trainees Sammelan | 10 | 450 | All SMS |
| 15.14 | Farmers' Seminar/Workshop | 6 | 1000 | All SMS |
| 15.15 | Method Demonstrations | 28 | 900 | All SMS |
| 15.16 | Celebration of Important Days | 5 | 650 | All SMS |
| 15.17 | Special Day Celebration | 5 | 700 | All SMS |
| 15.18 | Exposure Visits | 12 | 400 | All SMS |
| 15.19 | Technology Week, | 1 | 250 | All SMS |
| 15.20 | Farmers Field School (FFS) | 1 | 25 | All SMS |
| 15.21 | Farm Innovators Meet | 1 | 25 | All SMS |
| 15.22 | Awareness Programs | 2 | 500 | All SMS |

## 16.	Activities proposed as Knowledge and Resource Centre

16.1 Technological knowledge

| Sl. No. | Category | Details of technologies | Area (ha)/ Number | Names of the team members involved |
| --- | --- | --- | --- | --- |
| 16.1.1 | Technology Park/ Crop cafeteria | Onion varieties demonstrations, Fodder block | 0.4 ha | ALL SMS |
| 16.1.2 | Demonstration Units | Vermi-Composting | 2 units | ALL SMS |
|  |  | Azolla unit | 5 units | ALL SMS |
|  |  | Piggery unit | 1 unit | ALL SMS |
| 16.1.3 | Lab Analytical services | Soil and water analysis | 1000 No. | ALL SMS |
| 16.1.4 | Technology Week | Soil and water management | 1 No. | All SMS |

16.2 Technological Products

| Sl. No. | Category | Name of the Production Partner Agency | Name of the product | Quantity (q)/ Number | Names of the team members involved |
| --- | --- | --- | --- | --- | --- |
| 16.2.1 | Seeds | Farmers participatory | Bhima Super Onion variety (CS) | 10 q | All SMS |
| Planting materials |  |  |  |  |  |
| 16.2.2 | Grafts | KVK | Sapota (Cricket ball) | 1000 No. | All SMS |
| 16.2.3 | Seedlings | KVK | Drumstick and lime | 2500 No. | All SMS |
| 16.2.4 | Bio-agent | NHM | Pseudomonas | 15 q | ALL SMS & SRF |
|  |  | NHM | Trichoderma | 5 q | ALL SMS & SRF |

16.3 Technological Information

| Sl. No. | Category | Technological capsules / Number | Names of the team members involved |
| --- | --- | --- | --- |
| 16.3.1 | Technology backstopping to line departments |  |  |
|  | Agriculture | 10 | ALL SMS |
|  | Horticulture | 6 | ALL SMS |
|  | Animal Husbany | 2 | ALL SMS |
|  | Fisheries | 2 | ALL SMS |
|  | Agricultural Engineering | 4 | ALL SMS |
|  | Sericulture | 1 | ALL SMS |
|  | Others, pl. specify |  |  |
| 16.3.2 | Literature/publication | 50 | ALL SMS |
| 16.3.4 | Electronic Media | 5 | ALL SMS |
| 16.3.5 | Kisan Mobile Advisory Services | 12000 | ALL SMS |
| 16.3.6 | Information on centre/state sector schemes and service providers in the district. | 15 | ALL SMS |

## 17.	Additional Activities Planned

| Sl. No. | Name of the agency / scheme | Name of activity | Technical programme with quantification | Financial outlay (lakh) | Names of the team members involved |
| --- | --- | --- | --- | --- | --- |
| 17.1 | RKVY | Creating awareness on Gum guar production through study tours | Project proposed to RKVY, GOK | 10.50 | ALL SMS |
| 17.2 | IWST Bangalore | Tree based farming system | Seminar | 00.12 | ALL SMS |
| 17.3 | RKVY | IFSD | Under progress | 11.00 | ALL SMS |
| 17.4 | RKVY | Krishi Bhagya | Initiated | 02.50 | ALL SMS |
| 17.5 | ICAR | Preparation of village Soil Fertility Maps and Fertiliser Recommendation | Planned | 00.20 | ALL SMS |

18.	Revolving Fund

18.1	Financial status

| Opening balance as on 01.04.2014 (Rs.in Lakh) | Expenditure incurred during 2014-15 (Rs.in Lakh) | Receipts during 2014-15 (Rs.in Lakh) | Closing balance as on 31.01.2015 (Rs.in Lakh) | Expected closing balance by 31.03.2015 (Including value of material in stock/ likely to be produced) |
| --- | --- | --- | --- | --- |
| 11,11,430 | 5,30,029 | 5,88,837 | 11,70,230 | 12,85,000 |

18.2 	Plan of activities under Revolving Fund

| Sl.No. | Proposed activities | Expected output | Anticipated income (Rs.) | Names of the team members involved |
| --- | --- | --- | --- | --- |
| 18.2.1 | Production of Sapota grafts (Cricket Ball) | 1000 | 50,000 | ALL SMS |
| 18.2.2 | Piggery –Piglets | 10 |  | SMS (Home Science) & Programme Co-ordinator |

## 19.	Activities of soil, water and plant testing laboratory

| Sl.No. | Type | No. of samples to be analyzed | Names of the team members to be involved |
| --- | --- | --- | --- |
| 19.1 | Soil | 2000 | All SMS and Lab Technician |
| 19.2 | Water | 2000 | All SMS and Lab Technician |

21.  Activities planned under Rainwater Harvesting Scheme (only to those KVKs which are already having

scheme under Rain Water Harvesting)

| Sl. No | Activities planned | Remarks if any |
| --- | --- | --- |
| 21.1 | Trainings on rain water harvesting | - |

22.	Innovator Farmer’s Meet

| Sl. No. | Particulars | Details |
| --- | --- | --- |
| 22.1 | Are you planning for conducing Farm Innovators meet in your district? | Yes |
| 22.2 | If Yes likely month of the meet | December |
| 22.3 | Brief action plan in this regard | - Identification and Documentation of outstanding Innovations - Farmer to farmer interaction - Farmers to scientists interaction - Assistance to patent - Identifying and Creating social Identity to the innovators - Involvement of them in Extension Activities - Technology dissemination through print and electronic media |

23.	Farmers Field School (FFS) planned

| S. No | Thematic area | Title of the FFS | Budget proposed in Rs. |
| --- | --- | --- | --- |
| 23.1 | Nutrient Management and Plant Protection | Nutriment management and Plant Protection in Pomegranate | 20,000 |

24. Budget - Details of budget utilization (2014-15) up to 31 January 2015

| Sl. No. | Particulars | Sanctioned (Rs.) | Released | Expenditure (Rs.) |
| --- | --- | --- | --- | --- |
| 24.1 | Recurring Contingencies |  |  |  |
| 24.1.1 | Pay & Allowances | 65,00000 |  | 61,56,215 |
| 24.1.2 | Traveling allowances | 62,000 |  | 73,793 |
| 24.1.3 | Contingencies |  |  |  |
| 24.1.4.1 | Stationery, telephone, postage and other expenditure on office running, publication of Newsletter and library maintenance | 35,000 |  | 2,74,708 |
| B | POL, repair of vehicles, tractor and equipments | 40,000 |  | 1,60,653 |
| C | Meals/refreshment for trainees | 20,000 |  | 41,183 |
| D | Training material | 20,000 |  | 25,825 |
| E | Frontline demonstration except oilseeds and pulses | 2,00000 |  | 1,89,335 |
| F | On farm testing | 35,000 |  | 19,737 |
| G | Training of extension functionaries | 10,000 |  | 11,347 |
| H | Maintenance of buildings | 10,000 |  | 31,762 |
| I | Establishment of Soil, Plant & Water Testing Laboratory | - |  | - |
| J | Library | - |  | 4923 |
| K | IFS | 10,000 |  | 17,586 |
| L | Extension activities | 10,000 |  | 48,600 |
| M | FFS | 10,000 |  | 14,075 |
| 24.1 | Total Recurring | 6962000 |  | 7069742 |
| 24.2 | NRC | 0 |  | 0 |
| 24.2.1 | Works | 0 |  | 0 |
| 24.2.2 | Equipments including SWTL & Furniture | - |  | - |
| 24.2.3 | Vehicle (Four wheeler/Two wheeler, please specify) | - |  | - |
| 24.2.4 | Library | - |  | - |
| 24.2 | Total Non Recurring | - |  | - |
| 24.3 | REVOLVING FUND | - |  | - |
| 24.4 | GRAND TOTAL (A+B+C) | 6962000 |  | 7069742 |

25. Details of Budget Estimate (2015-16) based on proposed action plan

| S. No. | Particulars | BE 2015-16 proposed (Rs.) |
| --- | --- | --- |
| 25.1 | Recurring Contingencies | 0 |
| 25.1.1 | Pay & Allowances | 1,03,50,000 |
| 25.1.2 | Traveling allowances | 2,75,000 |
| 25.1.3 | Contingencies | 0 |
| A | Stationery, telephone, postage and other expenditure on office running, publication of Newsletter and library maintenance (Purchase of News Paper & Magazines) | 4,50,000 |
| B | POL, repair of vehicles, tractor and equipments | 3,75,000 |
| C | Meals/refreshment for trainees (ceiling up to Rs.75 for on campus and Rs. 40/- for off campus/trainee be maintained) | 2,50,000 |
| D | Training material (posters, charts, demonstration material including chemicals etc. required for conducting the training) | 2,00,000 |
| E | Frontline demonstration except oilseeds and pulses (minimum of 30 demonstration in a year) | 1,40,090 |
| F | On farm testing (on need based, location specific and newly generated information in the major production systems of the area) | 2,260 |
| G | Training of extension functionaries | 50,000 |
| H | Maintenance of buildings | 2,75,000 |
| I | Establishment of Soil, Plant & Water Testing Laboratory | 0 |
| J | Library | 20,000 |
| K | IFS | 25,000 |
| L | Extension activities | 1,45,000 |
|  | Entrepreneurship development programme | 23,000 |
| M | FFS | 50,000 |
| 25.1 | TOTAL Recurring Contingencies | 1,26,30,350 |
| 25.2 | Non-Recurring Contingencies |  |
| 25.2.1 | Works (Staff Quarters) | 2,04,50,000 |
| 25.2.2 | Equipments including SWTL & Furniture | 6,00,000 |
| 25.2.3 | Vehicle (Four wheeler: Jeep) | 14,00,000 |
| 25.2.4 | Library (Purchase of assets like books & journals) | 1,00,000 |
| 25.2 | TOTAL Non-Recurring Contingencies | 2,25,50,000 |
| 25.3 | REVOLVING FUND | - |
| 25.4 | GRAND TOTAL | 3,51,80,350 |

Annexure-I

Calendar of Activities for FLD/OFT

| Sl No | OFT/FLD | Months |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | April | May |  | June | July | August | Sept | Oct | Nov | Dec | Jan | Feb | March |
| 1 | Agronomy |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1) | Assessment of Foxtail millet varieties for higher yield |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Orientation |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Agreement |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Distribution of critical inputs (seeds) |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Soil sampling |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Sowing |  |  |  | X | X |  |  |  |  |  |  |  |  |
|  | Fertilizer application |  |  |  |  | X | X |  |  |  |  |  |  |  |
|  | Observation on growth parameters |  |  |  |  |  |  | X | X |  |  |  |  |  |
|  | Observation on yield and yield parameters |  |  |  |  |  |  |  | X |  |  |  |  |  |
|  | Observation on pest and disease |  |  |  |  |  |  |  | X |  |  |  |  |  |
|  | Sharing meeting |  |  |  |  |  |  | X |  |  |  |  |  |  |
| 2) | Introduction of ML-365 finger millet variety for higher yield |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Orientation |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Agreement |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Distribution of critical inputs (seeds) |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Soil sampling |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Sowing |  |  |  | X | X |  |  |  |  |  |  |  |  |
|  | Fertilizer application |  |  |  |  | X | X |  |  |  |  |  |  |  |
|  | Observation on growth parameters |  |  |  |  |  |  | X |  |  |  |  |  |  |
|  | Observation on yield and yield parameters |  |  |  |  |  |  |  | X |  |  |  |  |  |
|  | Observation on pest and disease |  |  |  |  |  |  |  | X |  |  |  |  |  |
|  | Field day |  |  |  |  |  |  |  | X |  |  |  |  |  |
| 3) | Integrated Crop Management in Groundnut |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Orientation |  | X |  |  |  |  |  |  |  |  |  |  |  |
|  | Agreement |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Distribution of critical inputs (seeds) |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Soil sampling |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Sowing |  |  |  | X | X |  |  |  |  |  |  |  |  |
|  | Fertilizer application |  |  |  |  | X |  |  |  |  |  |  |  |  |
|  | Observation on growth parameters |  |  |  |  |  |  |  | X |  |  |  |  |  |
|  | Observation on yield and yield parameters |  |  |  |  |  |  |  | X |  |  |  |  |  |
|  | Observation on pest and disease |  |  |  |  |  |  |  | X |  |  |  |  |  |
|  | Field day |  |  |  |  |  |  |  | X |  |  |  |  |  |
| 4) | Technology demonstration module in fodder crops |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Orientation |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Agreement |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Distribution of critical inputs (seeds) |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Soil sampling |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Sowing |  |  |  | X | X |  |  |  |  |  |  |  |  |
|  | Fertilizer application |  |  |  |  | X |  |  |  |  |  |  |  |  |
|  | Green fodder yield (Cuttings) |  |  |  |  |  |  | X |  | X |  | X |  |  |
|  | Palatability (%) |  |  |  |  |  |  | X |  | X |  | X |  |  |
|  | Field day |  |  |  |  |  |  | X |  |  |  |  |  |  |
| 2 | Soil Science |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1) | Improved Management practices for higher yield in Banana |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Orientation |  | X |  |  |  |  |  |  |  |  |  |  |  |
|  | Agreement |  | X |  |  |  |  |  |  |  |  |  |  |  |
|  | Distribution of critical inputs |  |  |  | X |  |  | X |  |  |  |  |  |  |
|  | Soil sampling |  | X |  |  |  |  |  |  |  |  |  |  |  |
|  | Sowing |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Fertilizer application |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Observation on growth parameters |  |  |  |  | X | X | X | X | X | X | X | X | X |
|  | Observation on pest and disease |  |  |  |  | X | X | X | X | X | X | X | X | X |
|  | Observation on yield and yield parameters |  |  |  |  |  |  |  |  |  | X |  |  |  |
|  | Field day |  |  |  |  |  |  |  |  |  | X |  |  |  |
| 3 | Plant protection |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1) | Integrated crop management in Redgram |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Orientation |  | X |  |  |  |  |  |  |  |  |  |  |  |
|  | Agreement |  | X |  |  |  |  |  |  |  |  |  |  |  |
|  | Distribution of critical inputs |  |  |  | X |  |  | X |  |  |  |  |  |  |
|  | Soil sampling |  | X |  |  |  |  |  |  |  |  |  |  |  |
|  | Sowing |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Fertilizer application |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Observation on growth parameters |  |  |  |  | X | X | X | X | X | X | X |  |  |
|  | Observation on pest and disease |  |  |  |  | X | X | X | X | X | X | X |  |  |
|  | Observation on yield and yield parameters |  |  |  |  |  |  |  |  |  | X |  |  |  |
|  | Field day |  |  |  |  |  |  |  |  |  | X |  |  |  |
| 2) | Integrated crop management in Bengalgram |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Orientation |  |  |  |  |  |  | X |  |  |  |  |  |  |
|  | Agreement |  |  |  |  |  |  | X |  |  |  |  |  |  |
|  | Distribution of critical inputs (seeds) |  |  |  |  |  |  |  | X |  |  |  |  |  |
|  | Soil sampling |  |  |  |  |  |  | X |  |  |  |  |  |  |
|  | Sowing |  |  |  |  |  |  |  | X |  |  |  |  |  |
|  | Fertilizer application |  |  |  |  |  |  |  | X |  |  |  |  |  |
|  | Observation on growth parameters |  |  |  |  |  |  |  |  |  | X |  |  |  |
|  | Observation on yield and yield parameters |  |  |  |  |  |  |  |  |  |  | X |  |  |
|  | Observation on pest and disease |  |  |  |  |  |  |  |  | X | X |  |  |  |
|  | Field day |  |  |  |  |  |  |  |  |  |  | X |  |  |
| 3) | Integrated Crop Management in Arecanut |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Orientation | X |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Agreement | X |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Distribution of critical inputs (seeds) |  | X |  |  |  |  |  |  |  |  |  |  |  |
|  | Soil sampling | X |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Fertilizer application |  |  |  | X |  |  |  | X |  |  |  |  |  |
|  | Observation on growth parameters |  |  |  |  |  | X |  |  |  |  |  |  |  |
|  | Observation on pest and disease | X | X |  |  |  | X |  |  | X |  |  |  |  |
|  | Observation on yield and yield parameters |  |  |  |  |  |  | X | X |  |  |  |  |  |
|  | Field day |  |  |  |  |  |  | X |  |  |  |  |  |  |
| 4) | Integrated management of Bacterial blight in Pomegranate |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Orientation |  |  |  |  | X | X | X | X | X | X |  |  |  |
|  | Agreement |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Distribution of critical inputs |  |  |  |  |  |  |  |  | X |  |  |  |  |
|  | Soil sampling |  |  |  |  | X |  |  |  |  |  |  |  |  |
|  | Pruning |  |  |  |  |  | X | X | X | X | X | X |  |  |
|  | Fertilizer application |  |  |  |  |  | X | X | X | X | X | X |  |  |
|  | Observation on growth parameters |  |  |  |  | X | X | X | X | X | X | X |  |  |
|  | Observation on pest and disease |  |  |  | X | X | X | X | X | X | X | X |  |  |
|  | Observation on yield and yield parameters |  |  |  |  |  | X |  |  |  |  | X |  |  |
|  | Field day |  |  |  |  |  |  |  |  |  |  | X |  |  |
| 4 | Horticulture |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1) | Farmers Participatory Seed Production in Onion |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Orientation |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Agreement |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Distribution of inputs (seeds) |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Soil sampling |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Nursery raising |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Nursery observations |  |  |  | X | X |  |  |  |  |  |  |  |  |
|  | Transplanting/planting of seed tuber |  |  |  |  |  | X |  |  | X |  |  |  |  |
|  | Fertilizer application |  |  |  |  |  | X | X |  | X | X | X |  |  |
|  | Observation on growth parameter |  |  |  |  |  |  | X | X |  |  |  |  |  |
|  | Observation on pest and disease |  |  |  |  | X | X | X | X |  | X | X |  |  |
|  | Harvesting bulb/umbel |  |  |  |  |  |  |  | X |  |  |  | X |  |
|  | Observation on Yield parameter |  |  |  |  |  |  |  | X |  |  |  |  |  |
|  | Field day |  |  |  |  |  |  | X |  |  |  |  |  |  |
|  | Selection of seed tuber |  |  |  |  |  |  |  | X |  |  |  |  |  |
|  | Packaging and Storage |  |  |  |  |  |  |  |  |  |  |  |  | X |
| 2) | Integrated crop management in Chrysanthemum |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Orientation |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Agreement |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Soil sampling |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Distribution of inputs |  |  |  |  | X |  |  |  |  |  |  |  |  |
|  | Fertilizer application |  |  |  |  | X |  |  |  |  |  |  |  |  |
|  | Observation on growth parameter |  |  |  |  | X | X | X |  |  |  |  |  |  |
|  | Observation on pest and disease |  |  |  | X | X | X | X | X |  |  |  |  |  |
|  | Harvesting |  |  |  |  |  | X | X | X |  |  |  |  |  |
|  | Observation on Yield parameter |  |  |  |  |  |  | X | X |  |  |  |  |  |
|  | Field day |  |  |  |  |  | X |  |  |  |  |  |  |  |
|  | Marketing and value addition studies |  |  |  |  |  |  | X | X |  |  |  |  |  |
| 3) | Demonstration of Field Bean (HA-4) intercrop in Arecanut |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Orientation |  |  |  |  |  |  | X |  |  |  |  |  |  |
|  | Agreement |  |  |  |  |  |  | X |  |  |  |  |  |  |
|  | Soil sampling |  |  |  |  |  |  | X |  |  |  |  |  |  |
|  | Distribution of inputs (Seeds) |  |  |  |  |  |  | X |  |  |  |  |  |  |
|  | Sowing |  |  |  |  |  |  | X |  |  |  |  |  |  |
|  | Fertilizer application |  |  |  |  |  |  | X | X |  |  |  |  |  |
|  | Observation on growth parameter |  |  |  |  |  |  |  |  | X | X |  |  |  |
|  | Weed counts |  |  |  |  |  |  |  | X | X | X |  |  |  |
|  | Observation on pest and disease |  |  |  |  |  |  |  |  | X | X | X |  |  |
|  | Harvesting |  |  |  |  |  |  |  |  |  | X | X |  |  |
|  | Observation on Yield parameter |  |  |  |  |  |  |  |  |  | X | X |  |  |
|  | Field day |  |  |  |  |  |  |  |  |  | X |  |  |  |
|  | Marketing |  |  |  |  |  |  |  |  |  | X | X |  |  |
|  | Soil Sampling after crop harvest |  |  |  |  |  |  |  |  |  |  | X |  |  |
| 4) | Integrated crop management in Watermelon |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Orientation |  |  |  |  |  |  |  |  | X |  |  |  |  |
|  | Agreement |  |  |  |  |  |  |  |  | X |  |  |  |  |
|  | Soil sampling |  |  |  |  |  |  |  |  | X |  |  |  |  |
|  | Distribution of inputs (Seeds) |  |  |  |  |  |  |  |  | X |  |  |  |  |
|  | Sowing |  |  |  |  |  |  |  |  | X |  |  |  |  |
|  | Fertilizer application |  |  |  |  |  |  |  |  | X | X |  |  |  |
|  | Observation on growth parameter |  |  |  |  |  |  |  |  |  |  | X | X |  |
|  | Observation on pest and disease |  |  |  |  |  |  |  |  |  | X | X | X | X |
|  | Harvesting |  |  |  |  |  |  |  |  |  |  |  | X | X |
|  | Observation on Yield parameter |  |  |  |  |  |  |  |  |  |  |  | X | X |
|  | Field day |  |  |  |  |  |  |  |  |  |  |  | X |  |
|  | Marketing studies |  |  |  |  |  |  |  |  |  |  |  | X | X |
| 5 | Home Science |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Branding and Market Linkages to Finger millet Value Added Products under EDP mode |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Orientation and selection of SHG | - |  | - | X |  |  |  |  |  |  |  |  |  |
|  | Sharing meeting to brief the activities |  |  |  |  | X |  |  |  |  |  |  |  |  |
|  | Training on skill demonstration of value added products |  |  |  |  |  | X |  |  |  |  |  |  |  |
|  | Nutritional labeling |  |  |  |  |  |  | X |  |  |  |  |  |  |
|  | Packing and labeling techniques |  |  |  |  |  |  |  | X |  |  |  |  |  |
|  | Branding and certification |  |  |  |  |  |  |  |  | X |  |  |  |  |
|  | Marketing linkage |  |  |  |  |  |  |  |  |  | X |  |  |  |
|  | Consumer preference |  |  |  |  |  |  |  |  |  |  | X | X | X |
|  | Economics |  |  |  |  |  |  |  |  |  |  | X | X | X |
|  | Experience sharing meeting |  |  |  |  |  |  |  |  |  |  | X | X | X |
|  | Terrace gardening for Nutrition security of urban population |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | On campus training |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Selection of the interested beneficiaries |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Consumption of vegetables (ICMR stds)- survey Nutritional status before intervention |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Distribution of the critical inputs |  |  |  |  | X |  |  |  |  |  |  |  |  |
|  | Availability of vegetables in seasons |  |  |  |  |  | X | X | X | X | X | X | X | X |
|  | Nutritional status after intervention |  |  |  |  |  |  |  |  | X | X | X | X | X |
|  | Experience sharing meeting |  |  |  |  |  |  |  |  |  |  | X | X | X |
| 6 | Agriculture Extension |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Demonstration on balanced feed formulation for cross breed cattle |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Orientation and selection farmers |  |  | X |  |  |  |  |  |  |  |  |  |  |
|  | Off campus training |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Distribution of inputs |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Sowing of fodder seeds |  |  |  |  | X |  |  |  |  |  |  |  |  |
|  | Orientation on FLD |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Input distribution (Remaining) |  |  |  |  |  | X |  |  |  |  |  |  |  |
|  | Balanced feeding |  |  |  |  |  | X |  |  |  |  |  |  |  |
|  | Recording Observation |  |  |  |  |  | X | X |  |  |  |  |  |  |
|  | Economics |  |  |  |  |  |  |  | X |  |  |  |  |  |
|  | Impact Assessment |  |  |  |  |  |  |  | X |  |  |  |  |  |
|  | Field day |  |  |  |  |  |  |  | X |  |  |  |  |  |
|  | Integrated Farming System Demonstration |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Orientation and baseline data collection |  |  | X |  |  |  |  |  |  |  |  |  |  |
|  | Off campus training |  |  |  | X |  |  |  |  |  |  |  |  |  |
|  | Distribution of inputs |  |  |  |  | X |  |  |  |  |  |  |  |  |
|  | Sowing |  |  |  |  | X |  |  |  |  |  |  |  |  |
|  | Off campus training on FLD |  |  |  |  |  | X |  |  |  |  |  |  |  |
|  | Input distribution |  |  |  |  |  | X |  |  |  |  |  |  |  |
|  | On campus training |  |  |  |  |  |  | X |  |  |  |  |  |  |
|  | Recording Observation |  |  |  |  |  |  |  | X | X |  |  |  |  |
|  | Economics |  |  |  |  |  |  |  |  | X |  |  |  |  |
|  | Impact Assessment |  |  |  |  |  |  |  |  | X |  |  |  |  |
|  | Field day |  |  |  |  |  |  |  |  |  |  |  |  |  |

Annexure-II

II. On & Off Campus Training Calendar (Farmers, Extension Personnel, Vocational)

| Months | Agronomy |  |  | Soil Science |  |  | Horticulture |  |  | Plant Protection |  |  | Home Science |  |  | Agril. Extension |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| April-15 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 |
| May |  |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  | 2 |  |  |
| June |  |  |  | 1 |  |  |  |  |  | 1 | 1 |  |  |  |  | 2 |  |  |
| July |  |  |  |  | 1 | 1 | 1 | 1 |  | 1 |  | 1 | 2 |  |  | 1 |  |  |
| August |  |  |  | 1 |  |  | 1 |  |  | 1 |  |  | - | 1 | 1 | 2 |  | 1 |
| September |  |  |  |  | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 |  |  |  | 2 |  |
| October | 2 | 1 |  | 1 |  |  |  |  |  | 1 |  |  | 1 | 1 |  |  |  |  |
| November |  | 2 | 1 |  |  | 1 | 1 | 1 |  |  | 1 |  |  |  |  |  |  |  |
| December |  |  |  | 1 |  |  |  |  |  | 1 |  |  |  | 1 |  |  |  |  |
| January-16 |  |  |  |  | 1 | 1 | 1 | 1 |  |  | 1 |  |  |  |  |  |  |  |
| February |  |  |  |  |  |  |  |  |  |  | 1 |  |  | 1 |  |  |  |  |
| March |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |  |

Training code details:   1=On campus, 2=Off campus  3=Extension Functionaries

Annexure-III

- KVK Farm plan for the year 2015-16

| Sl. No. | Particulars | Area (ha) | Institution involved |
| --- | --- | --- | --- |
| 1 | Integrated Farming System (Agri-Horti-Silvi-Pastoral and Animal Husbandry) | 1 | KVK |
| 2 | Seed production (BRG-2, JG-11) | 4 | KVK and ZAHRS |
| 3 | Horti-forestry (Curry leaf+ Teak+ Mango) | 2 | KVK |
| 4 | Rain water harvesting | 1 | KVK |
| 5 | Chilli seed production | 3 | KVK and ZAHRS |
| 6 | Demo plots (onion raised bed, Castor, Safflower, Chickpea and Millets) | 7 | KVK and ZAHRS |
| 7 | Nursery ( Sapota Grafts, Drumstick, Citrus (lemon) and Curry leaf seedlings | 1 | KVK and ZAHRS |
| 8 | Infrastructure ( Administrative building, Farmers Hostel, Ware house and Quarters) | 1 | KVK |
| Total Area |  | 20 |  |

Annexure-IV

- Innovative Programme:  Quality Pomegranate Production through Cluster Approach (PPP mode)

Activity Schedule

- Problems:

Lack of knowledge on

- Production aspects (nutrient management, Pest and disease management)

- Market dynamics

- Quality control

- Consumer needs

Lack of community approach in marketing and input procurement

Lack of awareness on Govt. facilities

- Process:

No of Clusters: 2

- Meeting with APEDA , Farmers, KVK and Line Depts

- Formation of clusters in Hiriyur and Hosadurga Taluka

- Orientation about the benefits of linkage

- Formation of Task Force involving Farmer Representatives, KVK, Line Depts. APEDA and Marketing Agency

- Linkage of APEDA for establishment of Pack house, Cold Storage, export and marketing agencies

- KVK to provide technical inputs on production aspects based on ecology of the clusters

- Plan for individual farmers

- Monthly meetings for review of activities

- Trainings by KVK and experts on quality production, packing and marketing

- Study tours to Pomegranate areas of Maharashtra

- Linkage for inputs and planting materials

- Grading and marketing

- Marketing through Federation

- Expected outcome:

- Individual Farmer’s interaction with scientists and experts enable them to acquire skills in Pomegranate Production

- Enable to farmers interact freely about their problems and will provide a platform for quick solution

- Would be able to reduce the cost of production

- Through community approach in adoption of control measures for disease and pests, it will help to control the diseases on large scale.

- Better Price through Market linkages

- Can take quick decisions on management of crop due to timely advisory services of KVK

- Helps to meet the supply on regular basis based on the consumer needs.

- Advisory: Through Phone messages, Leaflets, CD, Trainings, Study tours

- Financial Assistance : APEDA

- Technology Week: Sustainable Crop Production for Livelihood Security

Activity Schedule

- Onion seed production ( Field visit: Paramenahalli)

- Soil and water management for horticulture crops (Field visit: Devarkotta and eshwargere )

- Value addition in millets (Field visit: Hosdurga)

- Animal nutrition through Balanced feed (Field visit: Hariyabbe )

Recycling of farm residues and composting (Field visit: Vaddikere)

- Pomegranate production (Field visit: Hoovinahole/ kodihalli)

Village adoption for sustainable resource management

- Transfer of Agriculture Technology

- Demonstrations on IFS

- Post harvest and Value addition

- Water Management

- Wasteland management

- Land use systems

- Animal health

- Children and women health

- Awareness on Farm Mechanization to school children

- Front Line Demonstrations proposed for 2015-16 under NFSM

| Sl.No | Name of the Crop | Variety | Technology | Village/Taluk | No of demo plots | Budget per demo(Rs.) | Total (Rs.) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Redgram | BRG-2 | Integrated Crop Management | Taluku , Challakere | 10 | 3000 | 30000 |
| 2 | Bengal gram | JG -11 | Integrated Crop Management | Ghananayakanahally, Hiriyur | 10 | 3000 | 30000 |
| 3 | Millets | ML-365 | Introduction of variety and ICM | Karehally Hosadurga | 10 | 2000 | 20000 |
| 4 | Cotton | Bt Cotton | Integrated Crop Management and sodic soil management | Pampapura, Holalkare | 10 | 2800 | 28000 |
| Total |  |  |  |  | 40 |  | 1,08,000 |

- Innovative Farmers Meet

General Details:

      - Coverage Area: Chitradurga District

      - Farmers Type: Innovative Farmers

      - Expected Number: 25

      - Month of Meet: May

      - Budget : Rs. 25,000

Plan of activities:

    - Identification and Documentation of outstanding Innovations  made by farmers

    - Farmer to farmer interaction

    - Farmers to scientists interaction

    - Assistance to patent

    - Identifying and Creating social Identity to the innovators

    - Involvement of them in Extension Activities

    - Technology dissemination through print and electronic media

Abstract of Budget Details during the year 2015-16

| SL.No. |  | OFT,FLD and FFS | Budget | Remarks |
| --- | --- | --- | --- | --- |
| I. On farm testing |  |  |  |  |
| 1 |  | Assessment of foxtail millet varieties for higher yield | 2,260 |  |
| Total |  |  | 2,260 |  |
| II. Front line demonstration |  |  |  |  |
|  |  | Introduction of ML-365 finger millet variety for higher yield | 3,200 |  |
|  |  | Integrated Crop Management in Groundnut | 17,075 |  |
|  |  | Technology demonstration module in fodder crops | 16,500 |  |
|  |  | Farmers Participatory Seed Production in Onion | 10,000 |  |
|  |  | Integrated crop management in Watermelon | 6,750 |  |
|  |  | Terrace gardening for Nutrition security of urban population | 10,080 |  |
|  |  | Improved Management practices for higher yield in Banana | 8,000 |  |
|  |  | Integrated Crop Management in Red gram | 8,770 |  |
|  |  | Bacterial blight Management in Pomegranate | 6,600 |  |
|  |  | Integrated crop Management in Bengal gram | 14,375 |  |
|  |  | Integrated crop management in Arecanut | 8,000 |  |
|  |  | Demonstration on balanced feed formulation for cross breed cattle | 18,240 |  |
|  |  | Integrated Crop Management in Chrysanthemum | 4,500 |  |
|  |  | Demonstration of Hebbal Avere-4 as an intercrop in Arecanut | 8,000 |  |
| Total |  |  | 1,40,090 |  |
|  |  | Integrated Farming System Demonstration | 25,000 |  |
|  |  | Branding and Market Linkages to Finger millet Value Added Products under EDP mode | 23,000 |  |
| c) | FFS |  | 50,000 |  |
| Total |  |  | 98,000 |  |
| Total |  |  | 2,40,350 |  |