ICAR-ATARI, ZONE-XI, HEBBAL, BANGALORE

PROFORMA FOR ACTION PLAN 2019-20

GUIDELINES

(Please read carefully before preparing action plan)

- It is mandatory to fill all the items of activities in the format. Further, additional activity/activities within the mandate which are relevant to increase income of farmers in the operational villages will be encouraged.

- For the activities proposed to be continued, all the data of the previous year(s) must be presented, supported by visuals.

- Please finalize the Doubling Farmers Income (DFI) document of the district first before taking up the action plan for 2019-20. Select villages and the technologies/interventions identified for DFI as the basis for Action Plan 2019-20.

- Integrate all the ongoing major schemes like CFLDs, Seed Hub, NICRA, ARYA, Sujala, ASCI skill training, KKA etc as well as sponsored projects such as state/central sector projects, host organization activities and other agencies in the selected villages.

- Villages where ongoing projects are implemented may be considered on priority as cluster villages (operational) for KVK action plan.

- Household as a whole need to be emphasized with possible interventions to achieve significant increase in income within a short period of time. KVK can plan to cover all households in a phased manner.

- Benchmark (baseline) data on extent of technology adoption, yield, cost and income must be clearly documented for the farm families covered so that the impact can be easily monitored and recorded after KVK interventions.

- Decide on the number of households to be covered in each village based on schemes implemented and budget available.

- Plan to involve all sections of the community and households (women, youth, SC/ST etc).

- Action plan should include a combination of OFTs, FLDs, training and extension activities to achieve higher productivity/income.

- Entire KVK team must be involved in the preparation of action plan for combination of interventions.

- In the case of FLDs on varietal performance, ensure that the varieties / hybrids are not older than 10 years.

- Vocational trainings, EDPs and Market interventions should be planned for value-chain oriented activities of the major crops/commodities.

- Recommendations of SAC related to technical activities should be addressed in the action plan.

ICAR-ATARI, ZONE –XI, HEBBAL, BENGALURU

###### PROFORMA FOR ACTION PLAN OF KVKs IN ZONE XI FOR 2019-20

###### 1. General information about the Krishi Vigyan Kendra

| 1.1 | Name and address of KVK with phone, fax and e-mail ID | : | ICAR- Krishi Vigyan Kendra, Chitradurga Babbur Farm, Hiriyur-577 598, Chitradurga district, Karnataka State. Phone : 08193-289160 Fax : 08193-289160 E-mail : kvkchitradurgahyr@gmail.com kvk.Chitradurga@icar.gov.in Website: kvkchitradurga.com |
| --- | --- | --- | --- |
| 1.2 | Name and address of host organization | : | University of Agricultural and Horticultural Sciences, Shivamogga Savalanga Road, Navile, Shivamogga, Karnataka-Pin: 577 225 |
| 1.3 | Year of sanction | : | 2000 (NATP), 2004 to 2014 - Full-fledged under UASB Under UAHS Shivamogga, Since 01-07-2014 |
| 1.4 | Website address of KVK and date of last update |  | Website: kvkchitradurga.com, mid of December |

2. Details of staff as on date

| Sl. No. | Sanctioned post | Name of the incumbent | Discipline | If permanent, please indicate |  | Date of joining | If temporary, pl. indicate the consolidated amount paid (Rs./month) |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Current pay band | Current grade pay |  |  |
| 2.1 | Senior Scientist & Head/PC | Vacant |  |  |  |  | - |
| 2.2 | Subject Matter Specialist | Dr. S. Onkarappa | Crop Protection | 79800-217000 | 8000 | 17-7-2009 | - |
| 2.3 | Subject Matter Specialist | Dr. Amaresh Kumar K | Agriculture Extension | 131400-2171000 | 9000 | 31-3-2018 | - |
| 2.4 | Subject Matter Specialist | Dr. ParashuramChandravanshi | Soil Science | 131400-2171000 | 9000 | 26-3-2018 | - |
| 2.5 | Subject Matter Specialist | Dr. PrakashKerure | Horticulture | 68900-205500 | 7000 | 10-11-2011 | - |
| 2.6 | Subject Matter Specialist | Dr. Rudragouda F. Channagouda | Agronomy | 68900-205500 | 7000 | 17-10-2013 | - |
| 2.7 | Subject Matter Specialist | Vacant | Home Science | - | - |  |  |
|  | Programme Assistant (Lab Assistant) | Mrs. GeethaKumari, B.N. | Agriculture | 9300-34800 | 4600 | 08-11-2010 | - |
| 2.8 | Programme Assistant (Computer Programmer) | Miss. Kavitha P. Naik | Computer Science | 9300-34800 | 4600 | 30-11-2013 | - |
| 2.9 | Programme Assistant (Farm Manager) | Mr. Rudramuni T | Farm Manager | 9300-34800 | 4600 | 14-5-2019 | - |
| 2.10 | Accountant/Superintendent | Mr. D. Gurumurthy | Accounts & Administration | 37900-70850 | - | 01-01-2013 | - |
| 2.11 | Stenographer | Vacant |  |  |  |  | - |
| 2.12 | Driver 1 | Mr. Mehaboob Patel | Tractor driver | 30350-58250 | - | 23-10-2008 | - |
| 2.13 | Driver 2 | Mr. Hariprasad S. | Driver (LMV) | 21400-42000 |  | 14-11-2018 | - |
| 2.14 | Supporting staff 1 | Mrs. Nagamma | Messenger | 17000-28900 | - | 24-11-2016 | -- |
| 2.15 | Supporting staff 2 | Vacant |  |  |  |  | - |

3. Details of SAC meeting conducted during 2019-20

| Date | Number of Participants | Salient Recommendations | Action taken | Remarks, if any |
| --- | --- | --- | --- | --- |
| 1-7-2019 | 18 | Advised to select more number of farmers to take up planting of forest plants in the waste lands with the help of forest departments. | - Planting of 150 ( drumstick, hebbevu, honge ) trees in the KVK farm. - 1500 dryland horticulture plants (Mango , Custard apple and tamarind ) in farmers field at Halgondanahally, vaderahally , Gopanahally villages of Challakere tq. - Mango-200 No. fig -100, tamarind-200, lime -50, Jack fruit -50 , Sapota- 50, Custard apple-50 , Ber-50, Jamun-50 planted at adopted village of Chitradurga Dist. |  |
|  |  | Enhance more numbers of beneficiaries for bee keeping with the help of concerned departments | Ten Bee hives were distributed to beneficiaries of Chitradurga district through DoH under National Horticulture Mission in collaboration with KVK |  |
|  |  | Explore alternative variety for Groundnut TMV-2 and large scale demonstration to be conducted . | Conducted OFT on groundnut varieties DGRMB-24, 32 and TAG 34A at Bommanakunte, Challakere taluk in 6 farmers fields |  |
|  |  | Minimize flood irrigation and relay on drip irrigation and other moisture conserving technologies in order to mitigate water crises through training / Abhiyana programmes | - Models on drip and fertigation , trench cum bunding, farm pond developed at KVK field . - Created awareness programmes on adaption of microirrigation through krishi abhiyan , Jal shakthi abhiyana , trainings and farmers scientist interactions . Programmes; No. of Programmes; No. Participants. Krishi abhiyan; 6; 281. Jal shakthi abhiyana; 25; 2159. Trainings; 6; 166. Farmers scientist interactions; 4; 120. - Under guidance of KVK , Prograssive farmer Shri. Sanmukappa , Myadana hole , Hiriyur Tq. adopted drip irrigation for 1 ha in collaboration with DoH |  |
|  |  | More and more numbers of radio and TV programs to be broad casted on the burning issues like soil and water conservation, pest and diseases , contingent crop plan and live stocks. | - Radio programmes details as follows Date; Topic; Station Name. 24.06.2019; Pest management in Onion, Groundnut Arecanut ,Redgram and Banana.; AIR, Chitradurga. 6.7.2019; Drought mitigation measures in Chitradurga district. 9.7.2019; Phone in programme alternate crops for late Kharif. 9-7-2019; Improved production techniques for kharif crops. 10-7-2019; Live phone in programme. 13.7.2019; Role of Integrated farming system sustainable agriculture. 20.8.2019; Management of army worm in maize. 11.9.2019; Jala shakthi abhiyana programme. 19.9.2019; Integrated pest and disease management in arecanut. 19.9.2019; Importance of soil and water testing. - TV programmes details as follows Date; Topic; Station Name. 5.10.2019; Integrated management of insect pests in arecanut; DD Chandana. 5.10.2019; Integrated pest and disease management in Bengalgram. 5.10.2019; Onion seed production. 5.10.2019; ICM in of Bhima Super Onion variety. 5.10.2019; Importance of fodder Sorghum variety COFS-31. 5.10.2019; Improved production practices for cultivation of Finger millet Variety ML-365. 12-11-2019; Drumstick cultivation for dry powder production. |  |
|  |  | Number of farmers exposure visit may be increased to update the knowledge on new innovative technologies in Agriculture , Horticulture and IFS . | Date; Purpose; Place. 24-5-2019; Interaction with high power committee; UAHS, Shivamogga. 9-13, September,2019; ICM in practices in pomegranate; Visited to NRCP at Solapura. 6-11-2019; Field day at UAHS, Shivamogga; UAHS, Shivamogga. 22-08-2019; Training programme on management of Fall army worm in maize; KVK , Davangere. |  |
|  |  | Farmers –scientist interaction programme may be increased. | Following Farmers –Scientist interaction programmes were conducted Date; No. Participants; Place. 22-07-2019; 7; KVK. 09-09-2019; 8; KVK. 04-10-2019; 7; KVK. 30-11-2019; 7; Chillahally. 13-12-2019; 15; Chillahally. 7.11.2019; 10; Ramajogihalli, Challakere taluk. 16-05-2019; 50; Imangal. 18-05-2019; 5; Dharmapura. 16-05-2019; 65; Imangala. 18-05-2019; 51; Dharmpura. 01-06-2019; 67; Chitradurga. |  |
|  |  | Awareness on nutritional security through organizing nutri garden demonstrations at village level to overcome the problem of malnutrition and anemia in rural women and children. | - Twenty demonstration were conducted on nutria garden at Shidlayyanakote , Hiriyur Tq. - Ten demonstration were conducted on nutria cereals at Gopanahally , Challakere Tq. - Model nutri garden is established at nursery at KVK - Following trainings were conducted Date; Topic; No of Participants. 28-05-2019; ICM in little millet; 36. 17-07-2019; ICM in millets; 43. 20-08-2019; Nutri garden importance; 24. 19-09-2019; Improved production practices in finger millet variety ML-365; 19. 27-09-2019; ICM in finger millet; 37. 19-06-2019; ICM in little millet; 16. 14-08-2019; Enhance finger millt production through ICM approaches; 35. 16-08-2019; Improved production practices in finger millet; 20. 17-08-2019; ICM in finger millet; 17. 20-11-2019; Demonstration of Nutrient garden techniques and its importance; 16. Total; 263. |  |
|  |  | Mass production of Bio-agents (Trichoderma and Pseudomonas) should be initiated in collaboration with Microbiologist , ZAHRS, Hiriyur | 200 kg of Trichoderma was produced initiated in collaboration with Microbiologist , ZAHRS, Hiriyur |  |
|  |  | More number of research papers /popular articles /folders /news letters are to be published. | Particulars; Number. Research papers- National; 5. Technical reports; 5. Popular articles – Local language; 10. Extension literature; 7. TOTAL; 27. |  |
|  |  | Popularization of drought tolerant date palm and cashew in the district . | Under the technical support of KVK , SKDRDP, Hiriyur Planted 6000 cashew plants at Chillahally , Hariyabbe , Kundalagara of Hiriyur Tq. |  |
|  |  | Evaluation of OFT may be simultaneously taken up in the farmers and KVK field and then include the proven technology in POP and same may be disseminated on large scale. | OFT on sesamum was conducted at KVK farm Variety : DS-5 and local Area: 1 acre |  |
|  |  | Hydroponics and Fodder seed production may be increased in order to overcome fodder crisis. | - Hydroponic demonstration conducted in Gananayanahalli, Hemadal of Hiriyur Tq. , Doddarangayyanahatti of Hosdurga Tq. and Halgondanahalli of Challakere Tq. - Established low and high-tech hydrophonic model in collaboration with ZAHRS , Babbur farm at campus . - Awareness was created by training programme Date; Place; No. of Participants. 16-8-2019; KVK; 20. 17-8-2019; KVK; 17. 2-12-2019; KVK; 26. 21-12-2019; KVK; 49. - Produced 150 kg seeds of fodder sorghum variety COFS-31 at KVK farm. - Nearly 560 kg seeds of fodder sorghum variety COFS-31 produced by farmers under the guidance of KVK |  |
|  |  | Large scale demonstration on onion seed production may be taken up as farmers participatory. | - Large scale demonstration on onion (Arka Kalyan & Bhima Super ) seed production through farmers participatory were conducted in ten farmers field at Hosakundur, Hosdurga Tq. , Mayasandra & Suguru villages of Hiriyur Tq. , |  |
|  |  | Establishment of millets processing unit | - University has completed tender process for procurement of Millet processing unit . |  |

4. Details of operational areas proposed during 2019-20 (Please refer to the implementation plan of DFI)

| Clusters | Major crops & enterprises being practiced in cluster villages | Prioritized problems in these crops/ enterprise that limit yield and income | Extent of area (ha/No.) affected by the problem in the village | Proposed intervention (OFT, FLD, Training, extension activity etc.)* |
| --- | --- | --- | --- | --- |
| Cluster A Parashurampura |  |  |  |  |
| Halagondanahalli | Groundnut | - Less plant population (30-35 kg seeds/acre) - Imbalanced nutrition (farmers apply only 1 bag DAP) - Leaf minor, root grub, bud necrosis and leaf spot problem | 18,415 | FLD on ICM in groundnut and training |
| Halagondanahalli | Finger millet | - Non availability of high yielding varieties - Neck blast, lodging and suscebality to drought - Imbalanced nutrition | 560 | FLD on ICM in finger millet and training |
| Halagondanahalli | Groundnut | - Lack of knowledge on Nano fertilizer and its usage - Less fertilizer use efficiency | - | OFT, Training |
| Bomberahalli | Onion | - Low yield due to local variety - Imbalanced nutrition - Incidence of thrips and purple blotch disease | 7,520 | FLD, Training |
| Hligondanahalli | Onion | - Low yield due to local variety - Imbalanced nutrition - Incidence of thrips and purple blotch disease | 2,220 (Rabi) | FLD, Training |
| Haligondanahalii | Mango | - Low yield due to imbalance nutrient management - Flower and fruit drop - Incidence of powdery mildew , hopper and fruit flies | 1250 | FLD, Training |
| Haligondanahalii | Watermelon | - Low yield due to local varieties - Incidence of watermelon bud necrosis virus | 150 | OFT, Training |
| Haligondanahalii | Arecanut | - Imbalanced nutrition, button shedding and nut splitting | 15400 | FLD, Training |
| Haligondanahalli | Red gram | - Leaf Webber and Pod borer - Pigeonpea sterility mosaic disease | 8,700 | FLD and training |
| Cluster B Hosadurga |  |  |  |  |
| Kangavalli | Bengal gram | - Pod borer and wilt | 6,450 | FLD and training |
| Madadakere | Banana | - Low bunch yield due to imbalanced application of major and micro nutrients | 2520 | FLD and training |
| ClusterC - Dharamapura |  |  |  |  |
| Hemadhala | Bhendi | - Low yield due to local varieties - Incidence of Yellow vein mosaic virus and hoppers | 75 | FLD, Training |
| Shidalinakote | Redgram | - Sterility mosaic and wilt problem - Imbalance nutrition | 2512 | OFT, Training |
| Shidalinakote | Greengram | - Yellow Mosaic disease - Imbalanced application of fertilizers | 1200 ha | FLD and training |
| Alur | - | - Improper disposal of Arecanut husk - Lack of knowledge about composting methods | 2700 | OFT and training |
| Cluster D - Bharamasagara |  |  |  |  |
| Haleudhara | Avare | - Low yield due to poor nutrient uptake under moisture stress | 500 | FLD and training |

5. Technology assessment during 2020-21

| Sl.No. | Crop/ enterprise | Prioritized problem | Title of intervention | Technology options | Source of technology | Name of critical input | Qty per trial (q) | Cost per trial (Rs.) | No. of trials | Total cost (Rs.) | Parameters to be studied | Team members |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5.1 | Groundnut | Lack of knowledge on Nano fertilizer and its usage - Less fertilizer use efficiency | Assessment of Nano fertilizer (N & Zn) on growth and yield of groundnut | T1 : 1 bag DAP (50 kg per acre) + 2 bag gypsum (100 kg per acre) at the time of sowing and no top dressing with fertilizers. T2 : 10:20:10 NPK per acre (50% N : 100% P : 50 % K as basal and remaining 50 % N and 50 % K will be applied as top dressing at 30 DAS) + Zinc Sulphate 4 kg/acre + Borax 2 kg/acre + 200 kg gypsum per acre at 30 DAS. T3 : 05:20:10 NPK per acre (50% N : 100% P : 50 % K as basal and 50 % K will be applied as top dressing at 30 DAS) + N & Zn Nano fertilizer foliar spray @ 4ml /lit each at 30 DAS and 55 DAS Borax 2 kg/acre + 200 kg gypsum per acre at 30 DAS. | Farmer’s Practice UASB IFFCO-NBRC, Gujarath | Complex fertilizers | 100 kg | 2500 | 03 | 8520 | Germination percentage, No. of pods/plant, test weight , shelling per cent , yield and economics | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi |
|  |  |  |  |  |  | Zinc sulphate | 4 kg | 400 |  |  |  |  |
|  |  |  |  |  |  | Borax | 4 kg | 440 |  |  |  |  |
|  |  |  |  |  |  | Gypsum | 200 kg | 500 |  |  |  |  |
|  |  |  |  |  |  | Soil analysis | 1 + 3 | 600 |  |  |  |  |
|  |  |  |  |  |  | N based nano fertilizer | 1 lit | 450 |  |  |  |  |
|  |  |  |  |  |  | Zn based nano fertilizer | 1 lit | 450 |  |  |  |  |

| 5.2 | Redgram | - Sterility mosaic and wilt problem - Imbalance nutrition | Assessment of redgram varieties for higher yield | T1:BRG-2(Farmers practice ) T2:BSMR-736 T3:BRG -5 | UASB UASR UASB | Seeds Rhizobium PSB Trichoderma ZnSO4 | 20kg 3kg 12kg | 4000 | 2 | 8000 | Germination percentage, plant height (cm), No. of pods/plant), yield (q/ha ) ,economics , % disease incidence. | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5.3 | Watermelon | - Low yield due to local varieties - Incidence of watermelon bud necrosis virus | Assessment of Watermelon hybrids for higher yield | T1 : NS 295 T2 : Arka Akash T3 : Arka Muthu | Farmers practice(Namadhari seeds ) IIHR, Bengaluru IIHR, Bengaluru | Seeds | 0.3 kg each variety | 12500 | 2 | 25000 | Vine length (cm), No of fruits per plant (No.), Fruit weight (kg), Yield per ha, incidence of WBNV (%) and economics | Scientist (Hort) Scientist (PP) Scientist (Agr), Scientist (Soil Science) |
| 5.4 | - | - Improper disposal of arecanut husk - Lack of knowledge about composting methods | Evaluation of performance of different compost cultures to decompose Arecanut husk | TO1: Disposal of arecanut husk on roads TO2: Composting of Arecanut husk by using compost culture @3 kg/ton TO3: Composting of Arecanut husk by using waste decomposer @100ml/ton TO4: Composting of Arecanut husk by using compost culture @ 4kg/ton | Farmers practice UAS(D) NCOF, New Delhi UAHS, Shivamogga Farmer’s practice | Compost culture waste decomposer compost culture | 3 kgs 200ml 4kg | 300 300 300 | 3 | 2700 | No. of days taken to compost | Scientist (Soil Science), Scientist (Plant protection), Scientist (Hort), Scientist (Agronomy) |

6. Frontline demonstrations during 2020-21

| Sl. No. | Category | Crop/ enterprise | Prioritized problem | Technology to be demonstrated | Name of variety | Name of hybrid | Source of technology | Name of critical input | Qty per demo (q) | Cost per demo (Rs.) | No. of demos | Total cost for the demo (Rs.) | Parameters to be studied | Team members |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 6.1 | Cereals |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.2 | Millets | Finger millet | - Non availability of high yielding varieties - Neck blast, lodging and suscebality to drought Imbalance nutrition | - Demonstration of variety ML-365 - Seed treatment with Biofertilizers- Azospirillum and PSB,@ 4 g/kg Biofungicide -Trichoderma @ 4 g/kg - FYM: 3 t/acre - RDF : 20:15:16 kgNPK /acre, - Micronutrients (ZnSO4 5 kg/acre +Borax @ 4 kg/acre) - Foliar spray 19:19:19 @ 40 DAS - Spray with Imidachloprid 17.8 EC @ 0.5 ml/lit water - Spraying of Carbendazim @ 1g/lit of water | ML-365 |  | UAS(B) | Seed, Azospirillum, PSB, Trichoderma, ZnSO4, Foliar spray of 19:19:19 | 20 kg 3 kg 4 kg 2 kg | 1760 | 5 | 8800 | Germination percentage, plant height (cm), No. of tillers/ plant ,Yield Kg/ha and economics Disease incidence | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi |
| 6.3 | Oilseeds | Groundnut | - Less plant population (30-35 kg seeds/acre) - Imbalanced nutrition - Leaf minor, root grub, bud necrosis and leaf spot | 1. Demonstration of seed cum fertilizer drill 2. Seed treated with Rhizobium & PSB , Biofungicide- Trichoderma @4 g/kg 3. Use of micronutrients (4 kg ZnSo4 ) 4. RDF-10:20:10 kg NPK+ 3 t FYM/ acre + 200 kg gypsum/acre 5. 19:19:19 fertilizer (5g/l ) sprayed at 35 DAS 6. Foliar spray of 0.1% borax at flower initiation 7.Seeds treated with Chlorpyriphos 20 EC @ 10 ml per kg seeds 8. Spray with Imidachloprid 17.8 EC @ 0.5 ml/l water 9. Spraying of Hexaconozole @ ml/l of water 10. Growing of high stature crops as barriers in all along the crop | TMV-2 | - | UAHS(S) | Pods, Rhizobium, PSB, Trichoderma, , ZnSO4 ,Borax | 60 kg 3 kg 4 kg 1 l | 4930 | 10 | 49300 | Germination percentage, no. of plants/m2 , no. of pods/plant, test weight , shelling per cent , yield, incidence of pest and disease and economics | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi |
| 6.4 | Pulses | Greengram | - Yellow Mosaic disease - Imbalance nutrition | - Demonstration of variety- KKM-3 - Seed treatment with Rhizobium , PSB @ 4 g/kg seeds - Trichoderma @ 4 g/kg seeds - FYM : 3 t/acre - RDF : 5: 10:10 NPK kg, 4 kg ZnSo4 /acre - Foliar spray 19:19:19 @ 35 & 45 DAS - Spray with Imidachloprid 17.8 EC @ 0.5 ml/lit water - Spraying of Carbendazim @ 1g/lit of water - Spraying of Quinolphos 25 EC @ 2 ml/lit of water | KKM-3 | - | UAHS (S) | Seed, Rhizobium , PSB, Trichoderma, Foliar spray of 19:19:19 | 15 kg 3 kg 2 | 2090 | 5 | 10450 | Germination percentage, plant height, no. of pods per plant, test weight, per cent disease incidence, yield and economics | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi |
|  |  | Redgram | - Low yield due to pod borer and leaf webber incidence - Pigeon pea sterility mosaic and wilt disease | - Variety BRG-5 - FYM –7.5 t/ha, N:P:K 25:50:25, Sulphur- 20 kg, ZnSO4 –15 kg/ha, Pulse Magic 10g/l foliar spray - Trichoderma – 5 g/kg seeds, Rhizobium – 500 g/ha, PSB –500g/ha. - Pheromone traps – 10 Nos. / ha , HaNPV – 300 LE/ha. - Use of Bird perches - Dicofol 18.5 EC – 2.5 ml/l, Emamectin benzoate 5 SG – 0.3 g/l | BGR-5 | - | UAS(B) | Seeds, Trichoderma, Rhizobium, PSB, Pheromone traps, lures HaNPV Pulse Magic | 6 kg 1 kg 200 g 200 g 5 Nos. 4 kg | 2010 | 10 | 20100 | Per cent disease and pest incidence, no. of pods per plant, 100 seed weight , yield and economics | Dr. Onkarappa , Dr. Rudragouda, Dr Prakash kerure , Dr. Jyothi |
|  |  | Bengalgram | - Low yield due to pod borer and wilt disease | - FYM – 7.5 t /ha, N:P:K 12.5:25:25, - Foliar spray 19:19:19 – 2g/l - Trichoderma – 5 gm/kg seeds, Rhizobium – 500 g/ha, PSB – 500 g/ha. - Pheromone traps – 10 Nos., HaNPV – 300 LE/ha. - Bengal gram : Coriander -6:1 - Use of Bird perches - Emamectin benzoate 5SG – 0.3g/l | JAKI -9218 | - | UAS(B) | Seeds, Trichoderma, Rhizobium, PSB, Pheromone traps, lures HaNPV Chickpea special | 25 kg 1 kg 200 g 200 g 5 Nos. 2 kg | 2770 | 10 | 27700 | Per cent disease and pest incidence, No. of pods per plant, 100 seed weight , yield and economics | Dr. Onkarappa , Dr. Rudragouda, Dr Prakash kerure , Dr. Jyothi |
|  |  | Avare | - Low yield due to poor nutrient uptake under moisture stress in rainfed condition | - FYM – 7.5 t ha-1 - Seed treatment- Rhizobium@ 500g/ha & PSB @ 500 g/ha - RDF - 25:50:25 NPK kg ha-1+ Foliar application of Arka vegetable special (2 g litr-1) - Dimethote 30EC-1.75ml/l - Melathion 5D-25kg/ha - Carbendazim -50WP- 500 g/ha | HA-4 | - | UAS – Bangalore and IIHR, Bangalore | Seeds Arka vegetable special Soil and water analysis | 10 kg 4 kg 1+1 No. | 2,810 | 10 | 28,100 | Plant height, no. of branches/plant, no. pod / plant, Seed yield and economics, soil analysis (Soil pH, EC, organic carbon, Available nitrogen, phosphorus, potassium and micronutrients viz., Cu, Fe, Mn, Zn and B) and water analysis (water pH, EC, Exchangeable Na, Ca+Mg, chlorides, bicarbonates, SAR and RSC). | Dr. Jyothi T.V., Dr. Onkarappa , Dr. Rudragouda, Dr Prakash kerure |
| 6.5 | Commercial crops | - | - | -- | - | - | - | - | - | - | - | - | - | - |
| 6.6 | Horticultural crops | - | - | - | - | - | - | - | - | - | - | - | - | - |
| a | Vegetable crops | Onion | - Low yield due to local variety - Imbalanced nutrition - Incidence of thrips and purple blotch disease | - Bhima Super Variety - Soil test based (RDF=125:75:125kg NPK/ha) application and spraying of Arka Vegetable Special @ 2g /l - Seed treatment with Trichoderma @ 4 g /kg - Use of yellow sticky traps for management of thrips@10 No. / ha - Growing of high stature crops as barriers in all along the crop | Bhima Super | - | DOGR, Pune | Bhima Super Seeds | 4 kg | 8000 | 5 | 40000 | Yield (t/ha), bulb diameter (cm), bulb color, days to 50% neck fall, incidence of thrips & purple blotch and economics | Scientist (Hort) Scientist (PP) Scientist (Agr), Scientist (Soil Science) |
|  |  | Onion | - Low yield due to local variety - Imbalanced nutrition - Incidence of thrips and purple blotch disease | - Bhima Shakti Variety - Soil test based (RDF=125:75:125kg NPK/ha) application and spraying of Arka Vegetable Special @ 2g /l - Seed treatment with Trichoderma @ 4 g /kg - Use of yellow sticky traps for management of thrips@10 No. / ha - Growing of high stature crops as barriers in all along the crop | Bhima Shakti | - | DOGR, Pune | Bhima Shakti Seeds | 4 kg | 6000 | 5 | 30000 | Yield (t/ha), bulb diameter (cm), bulb color, days to 50% neck fall, incidence of thrips & purple blotch and economics | Scientist (Hort) Scientist (PP) Scientist (Agr), Scientist (Soil Science) |
|  |  | Bhendi | - Low Yield - Incidence of yellow vein mosaic virus - Incidence of fruit borer and hoppers disease | - Demonstration of Arka Nikhita hybrid - Soil test based (RDF=125:75:63kg NPK/ha) application and - spraying of Arka Vegetable Special @ 2g /l - Use of yellow sticky traps for management of sucking pest @ 8-10 No. / ha - Growing of high stature crops as barriers in all along the crop | - | Arka Nikhita | IIHR, Bengaluru | Seeds | 3kg | 7000 | 5 | 35000 | Yield (t/ha), No of pods per plant, pod color, % incidence of YVMV, % incidence of sucking pest, % incidence of pod borer and economics | Scientist (Hort) Scientist (PP) Scientist (Agr), Scientist (Soil Science) |
| b | Fruit crops | Mango | - Low yield due to imbalance nutrient management - Flower and fruit drop - Incidence of powdery mildew, hopper and fruit flies | - Application of RDF (730:180:680 g NPK/Plant) - Foliar application of Arka Mango Special @ 5 g/l (First Spray: Jun-Jul ,Second Spray: Oct-Nov,Third Spray: Dec-Jan, Fourth Spray: Feb-Mar ) - Demo of IIHR mango fruit fly trap for control of fruit flies@1 for 5 plants - Spraying of hexaconoazol@ 1 ml/l for Powdery mildew and imidachloprid @ 0.5 ml/l for hoppers | Alphanso | - | ICAR-IIHR Bengaluru | Arka Mango Special Mango fruit flies trap | 8kg 4 No. | 3,500 | 12 | 42,000 | No of fruits per plant, fruit yield per plant, incidence of hopper, fruit flies, powdery mildew and economics | Scientist (Hort) Scientist (PP) Scientist (Agr) Scientist (Soil Science) |
|  |  | Banana | - Low bunch yield due to imbalanced application of major and micro nutrients | - FYM: 5kg/plant - RDF: 175:105:220 g N:P2O5:K2O / plant - Split application of major nutrients once in 35 days - (5 times) - Micronutrients foliar application (Arka banana special @ 0.5 %) - Green manuring crop – Sesbania - Dimethoate 30EC- 1.7ml/l - Phorate 10G- 5g/l - Carbendazim – 1g/l - Propiconazole – 1ml/l | Putta bale | - | UHS, Bagalkot and IIHR, Bangalore | Sesbania seeds Trichoderma Arka Banana Special Soil and water analysis | 5 kg 2 kg 8 kg 1+1 | 500 240 1,400 250 | 10 | 23,900 | No. of nuts drop per palm, yield, economics, soil analysis (Soil pH, EC, organic carbon, Available nitrogen, phosphorus, potassium and micronutrients viz., Cu, Fe, Mn, Zn and B) and water analysis (water pH, EC, Exchangeable Na, Ca+Mg, chlorides, bicarbonates, SAR and RSC). | Dr. Jyothi T.V., Dr. Onkarappa , Dr. Rudragouda, Dr Prakash kerure |
| c | Plantation crops | Arecanut | - Imbalanced nutrition - nut dropping and nut splitting | - FYM – 20 kg/plant, 100:40:140 g N:P2O5:K2O / plant - Soil test based recommendation - MgSO4 - 100 g/plant, Borax - 20 g/plant, ZnSO4 - 40 g/plant - Trichoderma - 50 g/plant - Dimethoate 30 EC 1.7ml/l, Copper oxy chloride 50WP- 3g/l , Dicofol 18.5 EC- 2.5 ml/l. | Local | - | UHS, Bagalkot | Sesbania seeds Trichoderma MgSO4 Soil and water analysis | 5kg 2 kg 25 kg 1+1 | 500 240 550 250 | 10 | 15,400 | No. of nuts drop per palm, yield, economics, soil analysis (Soil pH, EC, organic carbon, Available nitrogen, phosphorus, potassium and micronutrients viz., Cu, Fe, Mn, Zn and B) and water analysis (water pH, EC, Exchangeable Na, Ca+Mg, chlorides, bicarbonates, SAR and RSC). | Dr. Jyothi T.V., Dr. Onkarappa , Dr. Rudragouda, Dr Prakash kerure |
| 6.7 | Livestock | - | - | - | - | - | - | - | - | - | - | - | - | - |
| 6.8 | Fisheries | - | - | - | - | - | - | - | - | - | - | - | - | - |
| 6.9 | Others(EDP) | - | - | - | - | - | - | - | - | - | - | - | - | - |

7. Training for farmers/ farm women during 2020-21

| Sl.No. | Thematic area and the crop/ enterprise | Crop / Enterprise | Related field intervention (OFT/FLD) | Training title | No. of courses | Expected No. of participants | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 7.1 | Crop production | Sesamum | OFT | Agro techniques for sesamum productin | 1 | 20 | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi |
|  |  | Finger millet | FLD | ICM finger millet | 1 | 30 | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi |
|  |  | Greengram | FLD | Recent production techniques in greengram production | 1 | 30 | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi |
|  |  | Groundnut | FLD | Crop management practices in groundnut Production | 1 | 30 | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi |
|  |  | Greengram | FLD | Improved production practices for Greengram | 1 | 30 | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi |
|  |  | Groundnut | FLD | Enhance grounndut productivity through ICM practices | 1 | 30 | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi |
|  |  | Sesamum | OFT | Integrated crop management in sesame | 1 | 30 | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi |
|  |  | Finger millet | FLD | INM in finger millet millet | 1 | 30 | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi |
| 7.2 | Horticulture production | Onion | FLD | Integrated crop management and seed production technologies in onion | 3 | 90 | Dr Prakash kerure, Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi |
|  |  | Watermelon | OFT | Integrated crop management in watermelon | 1 | 30 | Dr Prakash kerure, Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi |
|  |  | Bhendi | FLD | ICM in bhendi | 1 | 30 | Dr Prakash kerure, Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi |
|  |  | Mango | FLD | Integrated crop management in Mango | 2 | 60 | Dr Prakash kerure, Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi |
|  |  | Coconut | Other | ICM and Cropping systems in Coconut | 1 | 30 | Dr Prakash kerure, Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi |
|  |  | Onion | Others | Seed production in Onion | 1 | 30 | Dr Prakash kerure, Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi |
|  |  | Pomegranate | Others | Propagation and pruning techniques in pomegranate | 1 | 30 | Dr Prakash kerure, Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi |
|  |  | Avare | FLD | Integrated Nutrient management in Avare | 1 | 30 | Dr. Jyothi T.V., Dr. Onkarappa , Dr Prakash Kerure, Dr. Rudragouda |
| 7.3 | Livestock production | - | - | - | - | - | - |
| 7.4 | Home Science | - | - | - | - | - | - |
| 7.5 | Plant protection |  |  |  |  |  |  |
|  |  | Red gram | FLD | Integrated pest and disease management in Red gram | 1 | 30 | Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda, Dr. Jyothi |
|  |  | Bengal gram | FLD | Integrated pest and disease management in Bengal gram | 1 | 30 | Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda, Dr. Jyothi |
|  |  | Coconut | Others | Integrated management of diseases in coconut | 1 | 30 | Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda, Dr. Jyothi |
|  |  | Pomegranate | Others | Integrated management of pest and diseases in Pomegranate | 1 | 30 | Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda, Dr. Jyothi |
|  |  | Pomegranate | Others | Integrated pest management in pomegranate | 1 | 30 | Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda, Dr. Jyothi |
|  |  | Banana | FLD | Integrated management of wilt disease in Banana | 1 | 30 | Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda, Dr. Jyothi |
|  |  | Coconut & Arecanut | FLD | Root feeding techniques in Coconut & Arecanut | 1 | 30 | Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda, Dr. Jyothi |
|  |  | Chrysanthemum | Others | Integrated disease management in Chrysanthemum | 1 | 30 | Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda, Dr. Jyothi |
| 7.6 | Production of inputs at site | - | - | - | - | - | - |
| 7.7 | Soil health and fertility | Plantation crops | Others | Importance of soil and water quality in plantation crops cultivation | 1 | 40 | Dr. Jyothi T.V..,Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda |
|  |  |  | others | Enriching compost with macronutrients in plantation crops | 1 | 30 | Dr. Jyothi T.V..,Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda |
|  |  | Crops | Others | Maintenance of soil fertility by using green manuring crops | 1 | 30 | Dr. Jyothi T.V..,Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda |
|  |  | Soil and water | Others | Management of soil and water resources for sustainable agriculture | 1 | 40 | Dr. Jyothi T.V..,Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda |
|  |  | Soil and water | Others | Water conservation practices to maintain soil moisture in dryland farming | 1 | 30 | Dr. Jyothi T.V..,Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda |
|  |  | Micronutrient | Others | Enriching vermicompost with micronutrients in plantation crops | 1 | 40 | Dr. Jyothi T.V..,Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda |
|  |  | Nutrients | Others | Foliar application of nutrients in pulses | 1 | 20 | Dr. Jyothi T.V..,Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda |
|  |  |  | Others | Use of farm calculators in field crops and plantation crops | 1 | 40 | Dr. Jyothi T.V..,Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda |
|  |  | Arecanut | FLD | Management of problematic soils in arecanut gardens | 1 | 40 | Dr. Jyothi T.V..,Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda |
|  |  | Fruit crops | FLD | Recycling of farm wastes as a source of organic manure in fruit crops | 1 | 40 | Dr. Jyothi T.V..,Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda |
| 7.8 | PHT and value addition | - | - | - | - | - | - |
| 7.9 | Capacity building/ group dynamics | - | - | - | - | - | - |
| 7.10 | Farm mechanization | - | - | - | - | - | - |
| 7.11 | Fisheries production technologies | - | - | - | - | - | - |
| 7.12 | Mushroom production | - | - | - | - | - | - |
| 7.13 | Agro forestry | - | - | - | - | - | - |
| 7.14 | Bee keeping | - | - | - | - | - | - |
| 7.15 | Sericulture | - | - | - | - | - | - |
| 7.16 | Others, pl. specify | - | - | - | - | - | - |

8. Training for rural youth during 2020-21

| Sl.No. | Thematic area and the crop/ enterprise | Crop / Enterprise | Related field intervention (EDP/Skill development etc) | Training title | No. of courses | Expected No. of participants | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 8.1 | Crop production | Groundnut | - | Recent production practices in groundnut | 1 | 30 | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi |
| 8.2 | Horticulture production |  |  |  |  |  |  |
|  |  | Vegetables | - | Nursery production techniques for vegetables | 1 | 30 | Dr Prakash kerure, Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi |
| 8.3 | Livestock production |  |  |  |  |  |  |
| 8.4 | Home Science |  |  |  |  |  |  |
| 8.5 | Plant protection | Pomegranate | - | Integrated crop management in Pomegranate | 1 | 30 | Dr. Onkarappa ,Dr Prakash kerure, Dr. Rudragouda, Dr. Jyothi |
| 8.6 | Production of inputs at site |  |  |  |  |  |  |
| 8.7 | Soil health and fertility |  | - | Micronutrients management in salt affected soils | 1 | 30 | Dr. Jyothi T.V.., Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda |
|  |  |  | - | Organic farming for sustained soil health | 1 | 30 | Dr. Jyothi T.V.., Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda |
| 8.8 | PHT and value addition | - | - | - | - | - | - |
| 8.9 | Capacity building/ group dynamics | - | - | - | - | - | - |
| 8.10 | Farm mechanization | - | - | - | - | - | - |
| 8.11 | Fisheries production technologies | - | - | - | - | - | - |
| 8.12 | Mushroom production | - | - | - | - | - | - |
| 8.13 | Agro forestry | - | - | - | - | - | - |
| 8.14 | Bee keeping | - | - | - | - | - | - |
| 8.15 | Sericulture | - | - | - | - | - | - |
| 8.16 | Others, pl. specify | - | - | - | - | - | - |

### 9. Training for extension personnel during 2020-21

| Sl.No. | Thematic area and the crop/ enterprise | Training title | No. of courses | Expected No. of participants | Names of the team members involved |
| --- | --- | --- | --- | --- | --- |
| 9.1 | Crop production | Recent Agronomic practices in Groundnut and Redgram | 1 | 50 | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi |
|  |  | Recent Agronomic practices in Chickpea and summer groundnut | 1 | 50 | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi |
| 9.2 | Home Science | - | - | - | - |
| 9.3 | Capacity building and group dynamics |  |  |  |  |
| 9.4 | Horticulture | Protected cultivation of capsicum, tomato and other vegetable crops | 1 | 65 | Dr Prakash kerure, Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi |
| 9.5 | Soil science | Soil, water and plant analysis for nutrient management in agriculture | 1 | 50 | Dr. Jyothi T.V.., Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda |
|  |  | Use of farm calculators in increasing nutrient use efficiency | 1 | 50 | Dr. Jyothi T.V.., Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda |
|  |  | Application of amendments as a source of gypsum in dryland farming | 1 | 50 | Dr. Jyothi T.V.., Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda |
| 9.6 | Livestock production and management | - | - | - | - |
| 9.7 | Plant protection | IPDM in Redgram and Groundnut crops | 1 | 50 | Dr. Onkarappa ,Dr Prakash kerure, Dr. Rudragouda, Dr. Jyothi |
| 9.8 |  | IPDM in Arecanut and Coconut crops | 1 | 50 |  |
| 9.9 | Farm mechanization | - | - | - | - |
| 9.10 | PHT and value addition | - | - | - | - |
| 9.11 | Production of inputs at site | - | - | - | - |
| 9.12 | Sericulture | - | - | - | - |
| 9.13 | Fisheries | - | - | - | - |
| 9.14 | Other, pl. specify | - | - | - | - |
| 9.15 |  | - | - | - | - |

## 10. Vocational trainings during 2020-21

| Sl.No. | Thematic area and the crop/ enterprise | Training title | No. of programmes | Duration (days) | Expected No. of participants | Sponsoring agency, if any | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 10.1 | Crop production |  |  |  |  |  |  |
| 10.2 | Home Science |  |  |  |  |  |  |
| 10.3 | Capacity building and group Dynamics |  |  |  |  |  |  |
| 10.4 | Horticulture | Nursery production techniques and protected cultivation of horticulture crops | 1 | 21 | 20 | DoH | Dr Prakash kerure, Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi |
| 10.5 | Livestock production and management |  |  |  |  |  |  |
| 10.6 | Plant protection | Bee keeping for rural youths | 1 | 3 | 25 | Nil | Dr. Onkarappa ,Dr Prakash kerure, Dr. Rudragouda, Dr. Jyothi |
| 10.7 | Farm mechanization | - | - | - | - | - | - |
| 10.8 | PHT and value addition | - | - | - | - | - | - |
| 10.9 | Production of inputs at site | - | - | - | - | - | - |
| 10.10 | Sericulture | - | - | - | - | - | - |
| 10.11 | Fisheries | - | - | - | - | - | - |
| 10.12 | Other, pl. specify | - | - | - | - | - | - |

## 11. Sponsored trainings during 2020-21

| Sl.No. | Thematic area and the crop/ enterprise | Training title | No. of programmes | Duration (days) | Expected number of participants | Sponsoring agency | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 11.1 | Crop production | - | - | - | - | - | - |
| 11.2 | Home Science | - | - | - | - | - | - |
| 11.3 | Capacity building and group Dynamics | - | - | - | - | - | - |
| 11.4 | Horticulture | Integrated crop management in Coconut | 4 | 1 | 120 | CDB, Cochin, Kerala | Dr Prakash kerure, Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi |
| 11.5 | Livestock production and management | - | - | - | - | - | - |
| 11.6 | Plant protection | - | - | - | - | - | - |
| 11.7 | Farm mechanization | - | - | - | - | - | - |
| 11.8 | PHT and value addition | - | - | - | - | - | - |
| 11.9 | Production of inputs at site | - | - | - | - | - | - |
| 11.10 | Sericulture | - | - | - | - | - | - |
| 11.11 | Fisheries | - | - | - | - | - | - |
| 11.12 | Others, pl. specify | - | - | - | - | - | - |

## 12. Extension activities during 2020-21

| Sl. No. | Extension activity | No. of activities | Targeted numberof participants | Names of the team members involved |
| --- | --- | --- | --- | --- |
| 12.1 | Advisory services | 2500 | 2500 | All Scientists and staff |
| 12.2 | Diagnostic visits | 12 | 80 |  |
| 12.3 | Field days | 10 | 600 |  |
| 12.4 | Group discussions | 15 | 350 |  |
| 12.5 | Kisan gosthies | 4 | 250 |  |
| 12.6 | Film shows | 10 | 400 |  |
| 12.7 | Self -Help Groups (SHGs) meetings | 3 | 50 |  |
| 12.8 | Kisan Melas | 3 | 350 |  |
| 12.9 | Exhibitions | 7 | >100000 |  |
| 12.10 | Scientists' visit to farmers fields | 190 | 400 |  |
| 12.11 | Plant/soil health/animal health camps | 3 | 60 |  |
| 12.12 | Farm science club meetings | - | - |  |
| 12.13 | Ex-trainees sammelans (Meetings) | 1 | 60 |  |
| 12.14 | Farmers' seminars/workshops | 2 | 200 |  |
| 12.15 | Method demonstrations | 15 | 400 |  |
| 12.16 | Celebration of important days | 3 | 200 |  |
| 12.17 | Special day celebrations | 5 | 300 |  |
| 12.18 | Exposure visits | 8 | 130 |  |
| 12.19 | Technology week celebration | 1 | 300 |  |
| 12.20 | Farmers Field School (FFS) | - | - |  |
| 12.21 | Farm innovators meet | 1 | 30 |  |
| 12.22 | Awareness programmes | 4 | 300 |  |
| 12.23 | Pre-kharif campaign | 3 | 250 |  |
| 12.24 | Pre-rabi/summer campaign | 3 | 250 |  |
| 12.25 | Others, pl. specify |  |  |  |

## 13. Activities proposed as knowledge and resource center during 2020-21

13.1 Technological knowledge

| Sl. No. | Category | Details of technologies | Area (ha) | Number | Names of the team members involved |
| --- | --- | --- | --- | --- | --- |
| 13.1.1 | Technology park/ crop cafeteria | Fodder unit | 20 gunta | - | All Scientists , Farm manager & Staff |
| 13.1.2 | Demonstration units | Drum stick | 10 gunta | - |  |
|  |  | Establishment of Mango mother block | 10 gunta | - |  |
|  |  | Jasmine Mother block | 10 gunta | - |  |
|  |  | Kitchen garden | 10 gunta | - |  |
|  |  | Vermicompost unit | 96sqm | - |  |
|  |  | Green manure seed production unit | 20 gunta |  |  |
| 13.1.3 | Lab analytical services | Soil and water samples analysis | - | - | Scientist (SS) |
| 13.1.4 | Technology week | Recent production techniques in agri. & horticulture crops | - | - | All Scientists , Farm manager & Staff |
| 13.1.5 | Others, Pl. specify |  |  |  |  |

13.2 Technological products

| Sl. No. | Category | Name of the production partner agency, if any | Name of the product | Quantity planned to be produced during 2020-21 (q) | Number planned to be produced during 2019-20 | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- |
| 13.2.1 | Seeds | Nil | Greengram KKM-3 | 10 q | - | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi and Mr. Rudramuni |
|  |  | Nil | Redgram (BRG-5) | 20 q | - | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi and Mr. Rudramuni |
|  |  | Nil | Chickpea (JG-11) | 15 q | - | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi and Mr. Rudramuni |
|  |  |  | Onion (Arka Kalyan) | 1.5 |  | Dr Prakash kerure, Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi and Mr. Rudramuni |
| 13.2.2 | Planting material | - | Drum stick (PKM-1) | - | 1000 | Dr Prakash kerure, Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi and Mr. Rudramuni |
|  |  |  | Lime (Balaji Local ) | - | 1000 | Dr Prakash kerure, Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi and Mr. Rudramuni |
|  |  |  | Arecanut (Local) | - | 5000 | Dr Prakash kerure, Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi and Mr. Rudramuni |
|  |  |  | Coconut ( Arsikere tall ) | - | 3000 | Dr Prakash kerure, Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi and Mr. Rudramuni |
|  |  |  | Mango |  | 2000 | Dr Prakash kerure, Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi and Mr. Rudramuni |
|  |  |  | Tamarind |  | 750 | Dr Prakash kerure, Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi and Mr. Rudramuni |
|  |  |  | Jamun |  | 1000 | Dr Prakash kerure, Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi and Mr. Rudramuni |
| 13.2.3 | Bio-products | - | - | - | - | - |
| 13.2.4 | Livestock strains | - | Chicks (Swarna dhara, Giriraja and Nati) | - | 200 | Dr Prakash kerure, Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi and Mr. Rudramuni |
| 13.2.5 | Fish fingerlings | - | - | - | - | - |
| 13.2.6 | Any other, pl specify | - | - | - | - | - |

13.3 Technological information

| Sl. No | Category | Technological capsules/lectures/number | Names of the team members involved |
| --- | --- | --- | --- |
| 13.3.1 | Technology backstopping to line departments |  |  |
|  | - Agriculture | 32 | All Scientists and staff |
|  | - Horticulture | 13 |  |
|  | - Animal Husbandry | 3 |  |
|  | - Fisheries | - |  |
|  | - Agricultural Engineering | 10 |  |
|  | - Sericulture | 3 |  |
|  | - Others, pl. specify | - |  |
| 13.3.2 | Literature/publication | 15 |  |
| 13.3.3 | Electronic media | 6 |  |
| 13.3.4 | Kisan mobile advisory services | 30 | All Scientists & Prg Assistant (Computer) |
| 13.3.5 | Information on centre/state sector schemes and service providers in the district (Data may be collected from different agencies). | 6 | All Scientists & Prg Assistant (Computer) |

## 14. Additional activities planned during 2020-21

| Sl. No. | Name of the agency / scheme | Name of activity | Technical programme with quantification | Financial outlay (Rs.) | Names of the team members involved |
| --- | --- | --- | --- | --- | --- |
| - | - | - | - | - | - |

15. Revolving fund

15.1 Financial status of revolving fund

| Opening balance as on 01.04.2018 (Rs.in Lakh) | Expenditure incurred during 2018-19 (Rs.in Lakh) | Receipts during 2018-19 (Rs.in Lakh) | Closing balance as on 31.01.2019 (Rs.in Lakh) | Expected closing balance by 31.03.2019 (Including value of material in stock/ likely to be produced) |
| --- | --- | --- | --- | --- |
| 9.99 | 9.50 | 8.26 | 8.54 | 10.20 |

## 15.2 Plan of activities under revolving fund 2020-21

| Sl. No. | Proposed activities | Expected output | Anticipated income (Rs.) | Names of the team members involved |
| --- | --- | --- | --- | --- |
|  | Seed production |  |  |  |
| 1 | Greengram KKM-3 | 10q | 32000 | All Scientist & Farm Manager |
|  | Redgram (BRG-5) | 20 q | 36000 |  |
|  | Chickpea (JG-11) | 15 q | 28000 |  |
|  | Onion (Arka Kalyan) | 1.5q | 65000 |  |
| 2 | Planting materials |  |  |  |
|  | Drum stick (PKM-1) | 1000 | 10000 |  |
|  | Lime (Balaji Local ) | 1000 | 6000 |  |
|  | Arecanut (Local) | 5000 | 75000 |  |
|  | Coconut ( Arsikere tall ) | 3000 | 80000 |  |
|  | Mango | 2000 | 50000 |  |
|  | Tamarind | 750 | 8000 |  |
|  | Jamun | 1000 | 12000 |  |

## 16. Activities of soil, water and plant testing laboratory during 2020-21

| Sl.No. | Type of samples | No. of samples to be analyzed | Names of the team members involved |
| --- | --- | --- | --- |
| 16.1 | Soil test using analytical lab | 1500 | Dr. Jyothi T.V. |
| 16.2 | Soil test using mobile analysis kit | - | - |
| 16.3 | Water | 1500 | Dr. Jyothi T.V. |
| 16.4 | Plant | - | - |
| 16.5 | Others, pl. specify | - | - |

## 17. E-linkage during 2020-21

| Sl. No | Nature of activities | Likely period of completion (please set the time frame) | Remarks if any |
| --- | --- | --- | --- |
| 17.1 | Title of the technology module to be prepared | - | - |
| 17.2 | Creation and maintenance of relevant database system for KVK | 6 months | - |
| 17.3 | Any other (Please specify) | - | - |

18. Activities planned under rainwater harvesting scheme (only to those KVKs which are already having scheme under rain water harvesting)

| Sl. No | Activities planned | Remarks if any |
| --- | --- | --- |
| - | - | - |

19. Farmers Field School (FFS) planned

| Thematic area | Title of the FFS | Budget proposed in Rs. |
| --- | --- | --- |
| ICM | Integrated Crop Management in Onion | 60,000 |

20. Integrated Farming System (IFS) planned

| Description of model(s) | No. of models/units | Budget proposed in Rs. |
| --- | --- | --- |
| - | - | - |

21. Details of budget utilization 2019-20

(Rs.)

| Sl.No. | Particulars | Sanctioned | Released | Expenditure |
| --- | --- | --- | --- | --- |
| 21.1 | (A). REVENUE (Recurring Contingencies) |  | 1st Installment |  |
| 21.1.1 | Pay & Allowances | 11500000 | Rs. 3488000 | 11308277 |
| 21.1.2 | Traveling allowances | 200000 |  | 200000 |
| 21.1.3 | Contingencies |  |  |  |
| 21.1.3.a | Stationery, telephone, postage and other expenditure | 310000 | 2nd Installment Rs. 872083 | 306151 |
| 21.1.3.b | POL, repair of vehicles, tractor and equipment’s | 260000 | Rs. 227000 | 257740 |
| 21.1.3.c | Food/refreshment for farmers/extension personnel @ Rs.150/person/day | 100000 |  | 92477 |
| 21.1.3.d | Training material (need based materials and equipment’s for conducting the training) | 35000 | 3rd Installment | 31400 |
| 21.1.3.e | Frontline demonstrations | 260000 | Rs. 1744166 | 181560 |
| 21.1.3.f | On farm testing (OFTs)/Technology Assessment | 30000 | 4th Installment | 20023 |
| 21.1.3.g | Integrated Farming System (IFS) (Min. 5 Units) | - | Rs. 1821168 | - |
| 21.1.3.h | Training of extension functionaries | 25000 | 5th Installment | - |
| 21.1.3.i | Extension activities/services | 25000 | Rs. 227000 | 23455 |
| 21.1.3.j | Farmers' Field School | - | 6th Installment | - |
| 21.1.3.k | EDP (2 Nos.) / Innovative activities | - | Rs. 958333 | - |
| 21.1.3.l | Soil & water testing & issue of soil health cards | 25000 |  | 24690 |
| 21.1.3.m | Maintenance of building | 25000 |  | 24360 |
| 21.1.3.n | Farmers Conclave, KVK Conference | - |  | - |
| 21.1.3.o | Nutri Garden | 25000 |  | 20300 |
| 21.1.3.p | Library (Purchase of Journals, Periodicals, News Papers& Magazines) | 3000 |  | 2672 |
|  | Total Recurring | 12823000 |  | 12493105 |
| 21.2 | (B). CAPITAL (Non-Recurring Contingencies) |  |  |  |
| 21.2.1 | Equipment& Furniture | 0 |  | 0 |
| 21.2.2 | Works | 0 |  | 0 |
| 21.2.3 | Vehicle | 0 |  | 0 |
| 21.2.3 a | Four wheeler (replacement) | 0 |  | 0 |
| 21.2.4 | Library | 0 |  | 0 |
|  | Total Non Recurring | 0 |  | 0 |
| 21.3 | (C). REVOLVING FUND | 0 |  | 0 |
|  | GRAND TOTAL (A+B+C) | 12823000 | 9337750 | 12493105 |

22. Details of Budget Estimate based on proposed action plan(2020-21)

| Sl.No. | Particulars | BE 2020-21 proposed (Rs.) |
| --- | --- | --- |
| 1 | (A). REVENUE (Recurring Contingencies) |  |
| 1.1 | Pay & Allowances | 13240000 |
| 1.2 | Traveling allowances | 350000 |
| 2 | Contingencies | - |
| 2.1 | Stationery, telephone, postage and other expenditure on office running, publication of Newsletter | 610000 |
| 2.2 | POL, repair of vehicles, tractor and equipments | 450000 |
| 2.3 | Food/refreshment for farmers / extension personnel @ Rs.150/person/day | 175000 |
| 2.4 | Training material (need based materials and equipments for conducting the training) | 100000 |
| 2.5 | Frontline demonstrations | 295780 |
| 2.6 | On farm testing (OFTs)/Technology Assessment | 91470 |
| 2.7 | EDP | 130000 |
| 2.8 | Training of extension functionaries | 50000 |
| 2.9 | Extension activities/services | 75000 |
| 2.10 | Soil &water testing & issue of soil health cards | 50000 |
| 2.11 | Maintenance of building | 150000 |
| 2.12 | Library (Purchase of Journals, Periodicals, News Papers& Magazines) | 15000 |
| 2.13 | FFS | 60000 |
|  | Total Recurring (A) | 15782250 |
| 3 | (B). CAPITAL (Non-Recurring Contingencies) |  |
| 3.1 | Equipment & Furniture | 200000 |
| 3.2 | Works: |  |
|  | 1. Bore well, electricity connection & pipeline works | 200000 |
|  | 2. Shed for implementation of millet processing unit | 500000 |
| 3.3 | Vehicle | 0 |
| 3.4 | Four wheeler (replacement) | 0 |
| 3.5 | Library | 0 |
|  | Total Non Recurring (B) | 900000 |
|  | Grand Total (A + B) | 16682250 |

-:O:-