ICAR-ATARI, ZONE-XI, BENGALURU

PROFORMA FOR ACTION PLAN 2021-22

GUIDELINES

(Please read carefully before preparing action plan)

- It is mandatory to fill all the items of activities in the format. Further, additional activities within the mandate which are relevant to increase income of farmers in the operational villages will be encouraged.

- For the activities proposed to be continued, all the data of the previous year(s) must be presented, supported by visuals.

- Integrate all the ongoing major schemes like CFLDs, Seed Hub, NICRA, ARYA, Sujala, ASCI skill training, KKA etc as well as sponsored projects such as state/central sector projects, host organization activities and other agencies in the selected DFI villages.

- Villages where ongoing projects are implemented may be considered on priority as cluster villages (operational) for KVK action plan.

- Household as a whole need to be emphasized with possible interventions to achieve significant increase in income within a short period of time. KVK can plan to cover all households in a phased manner.

- Decide on the number of households to be covered in each village based on schemes implemented and budget available.

- Plan to involve all sections of the community and households (women, youth, SC/ST etc).

- Action plan should include a combination of OFTs, FLDs, training and extension activities to achieve higher productivity/income.

- Entire KVK team must be involved in the preparation of action plan for combination of interventions.

- In the case of FLDs on varietal performance, ensure that the varieties / hybrids are not older than 10 years.

- Vocational trainings, EDPs and Market interventions should be planned for value-chain oriented activities of the major crops/commodities.

- Recommendations of SAC related to technical activities should be addressed in the action plan.

ICAR-ATARI, ZONE –XI, BENGALURU

###### PROFORMA FOR ACTION PLAN OF KVKs IN ATARI, ZONE XI FOR 2021-22

###### 1. General information about the Krishi Vigyan Kendra

| 1.1 | Name and address of KVK with phone, fax and e-mail ID | : | ICAR- Krishi Vigyan Kendra, Chitradurga Babbur Farm, Hiriyur-577 598, Chitradurga district, Karnataka State. Mobile: 9480838201 E-mail : kvkchitradurgahyr@gmail.com kvk.Chitradurga@icar.gov.in |
| --- | --- | --- | --- |
| 1.2 | Name and address of host organization | : | University of Agricultural and Horticultural Sciences, Shivamogga Savalanga Road, Navile, Shivamogga, Karnataka-Pin: 577 225 |
| 1.3 | Year of sanction | : | 2000 (NATP), 2004 to 2014 - Full-fledged under UASB Under UAHS Shivamogga, Since 01-07-2014 |
| 1.4 | Website address of KVK and date of last update |  | https://kvkct.uahs.edu.in/ updated 1st June 2021 |

2. Details of staff as on date

| Sl. No. | Sanctioned post | Name of the incumbent | Discipline | If permanent, please indicate |  | Date of joining | If temporary, pl. indicate the consolidated amount paid (Rs./month) |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Current pay band | Current pay |  |  |
| 2.1 | Senior Scientist & Head/PC | Vacant | - | - | - | - | - |
| 2.2 | Subject Matter Specialist | Dr. S. Onkarappa | Crop Protection | 79800-217000 | 98200 | 17-07-2009 | - |
| 2.3 | Subject Matter Specialist | Dr. Amaresh Kumar K | Agriculture Extension | 131400-217000 | 143600 | 31-3-2018 | - |
| 2.4 | Subject Matter Specialist | Dr. Parashuram Chandravanshi | Soil Science | 131400-217000 | 139400 | 26-3-2018 | - |
| 2.5 | Subject Matter Specialist | Dr. Prakash Kerure | Horticulture | 68900-205500 | 77600 | 10-11-2011 | - |
| 2.6 | Subject Matter Specialist | Dr. Rudragouda F. Channagouda | Agronomy | 68900-205500 | 82300 | 17-10-2013 | - |
| 2.7 | Subject Matter Specialist | Vacant | Home Science | - | - | - | - |
| 2.8 | Programme Assistant (Lab Assistant) | Mrs. Geetha Kumari, B.N. | Agriculture | 44900-142400 | 52000 | 08-11-2010 | - |
| 2.9 | Programme Assistant (Computer Programmer) | Mrs. Kavitha P. Naik | Computer Science | 44900-142400 | 47600 | 30-11-2013 | - |
| 2.10 | Programme Assistant (Farm Manager) | Mr. Rudramuni T | Farm Manager | 44900-142400 | 52000 | 14-5-2019 | - |
| 2.11 | Accountant/Superintendent | Mr. D. Gurumurthy | Accounts & Administration | 37900-70850 | 40900 | 01-01-2013 | - |
| 2.12 | Stenographer | Vacant | - | - | - | - | - |
| 2.13 | Driver 1 | Mr. Mehaboob Patel | Tractor driver | 30350-58250 | 35150 | 23-10-2008 | - |
| 2.14 | Driver 2 | Mr. Hariprasad | LMV | 21400-42000 | 22400 | 14-11-2018 | - |
| 2.15 | Supporting staff 1 | Mrs. Nagamma | Messenger | 17000-28900 | 18600 | 24-11-2016 | -- |
| 2.16 | Supporting staff 2 | Vacant | - | - | - | - | - |

3. Details of SAC meeting conducted during 2020-21

| Date | Major recommendations | Status of action taken in brief | Reasons for no actions, if any |
| --- | --- | --- | --- |
| 16-12-2020 | Increase seed production activities in onion through farmers’ participatory programme. | Onion seed production through farmers’ participatory programme has been initiated since from 2016 further area will be increased | - |
|  | Promote the hydroponic fodder production technologies among the farmers. | This technology will be promoted through establishment of fodder hydroponic unit at KVK, ZAHRS, campus and technology disseminated through training programmes started since last 3 years | - |
|  | Demonstration on kitchen garden should be arranged to overcome the problem of anemia and mal nutrition in rural area. | Special programme on “Demonstration of nutrigarden among farm families” for 50 farmers have been taken up from 2019-2020 & 2020-21 | - |
|  | Document and publish the success stories of progressive farmers. | Success stories of progressive farmers will be published during 2021-22 | - |
|  | Promotion of dry land horticultural crops | Cashew is promoted as dry land horticulture crop in Hariyabbe and Chillahalli villages of Hiriyur Tq. since 2019. | - |
|  | Make fodder sorghum var. COFS-31 seeds availability through seed production. | 180 Kg seeds of fodder sorghum var. COFS-31 were produced in KVK. Due to encouragement by KVK, farmers themself produced around 300 kg fodder seeds | - |
|  | Encourage women self help groups in preparation of value added products on perishable commodities during market glut. | It will be initiated during 2021-22 | - |
|  | Progressive farmers may be involved as resource person in training programmes at KVK to share their experience with farmers/trainees | Progressive farmers were involved as resource person in training programmes at KVK to share their experience with farmers/trainees during 2018-19.Also we are planning to implement the same during 2021-22 | - |
|  | More number of field days must be organized to share the technologies of FLD . | During 2020-21 ,15 field days for 660 farmers were conducted on different crops | - |
|  | Each scientist should give 10 radio programmes under Negila Miditha Scheme (AIR). | During 2020-21 ,15 radio programmes were given by Scientist of KVK , Chitradurga and number of programme will be increased during 2021-22 | - |
|  | Arrange exposure visit to Gonikoppal KVK with selected FPO farmers to know the success of FPO activities. | It will be initiated during 2021-22 | - |
|  | Skill development training programme should be organized for unemployed rural youths. | It will be initiated during 2021-22 | - |
|  | Create awareness on New Form Acts 2020-21. | - 5 Awareness programmes on New Form Acts were conducted during 2020-21 - We have uploaded video in KVK website and Whatsapp group on New Farm Act in local language | - |
|  | The technology which is suitable, economically viable must be demonstrated in the farmer’s field. | It will be initiated during 2021-22 | - |
|  | Impact of FLD and OFT should be documented which were conducted in the farmer’s field. | Impact of FLD and OFT is documented regularly | - |
|  | Rechecking of VSL soil sample values through KVK lab. | It will be initiated during 2021-22 | - |
|  | Financial assistant will be provide by Dept. of Agriculture to study the soil health management. | It will be initiated during 2021-22 | - |
|  | Develop and publish production and protection practices in onion and arrange field day on successful onion growing farmer field. | Regularly FLD and OFT on Onion production have been conducted by KVK in farmers field and production technology was shared in the websites and media. Field days were conducted with involvement of line department officials | - |
|  | Make availability of grafted jamun, hybrid coconut, tissue culture banana at KVK nursery. | 500 grafted Jamun , 4000 coconut plants were produced during 2020-21. | - |
|  | To conduct studies on performance of SF-4 over V-1 and their impact on silk worms and share the technology to Dept. of Sericulture | It will be initiated during 2021-22 | - |
|  | Promotion of value-added products in groundnut through SHG’s | It will be initiated during 2021-22 | - |
|  | Popularize micro credit facility of NABARD to the farmers | It will be initiated during 2021-22 | - |
|  | Ensure the availability of Trichoderma and other Bio inputs. | Trichoderma and other Bio inputs has been supplied to the farmers through OFRC, Shivamogga | - |
|  | Awareness among the farmers on integrated farming system. | Awareness among the farmers on integrated farming system was implement through the IFS project by selecting 12 farmers in the district during2016-17 to 2018-19 . Further training programmes will be conducted during 2021-22. | - |
|  | Encourage farmers on dairy farming | Dairy farming is being encouraged by providing fodder sorghum var. COFS-31 seeds to the farmers and advising them to grow fodder trees. Two training programmes were conducted for veterinary officers and farmers regarding silage making and improved fodder production technology | - |

4. Details of operational areas proposed during 2021-22

| Clusters | Major crops & enterprises being practiced in cluster villages |  | Prioritized problems in these crops/ enterprise that limit yield and income | Extent of area (ha/No.) affected by the problem in the village | Proposed intervention (OFT, FLD, Training, extension activity etc.)* |
| --- | --- | --- | --- | --- | --- |
| Cluster A - Parashurampura |  |  |  |  |  |
| Halagondanahalli | Groundnut | - Less seed rate(30-35 kg seeds/acre) - Imbalanced nutrition (farmers apply only 1 bag DAP) - Leaf minor, root grub, bud necrosis and leaf spot problem |  | 200 | FLD on ICM in groundnut and training |
| Halagondanahalli | Finger millet | - Low yield - Neck blast, lodging and susceptibility to drought - Imbalanced nutrition |  | 32 | FLD on ICM in finger millet and training |
| Gopinahalli | Redgram | - Sterility mosaic and wilt problem - Imbalance nutrition |  | 280 | OFT, Training |
| Haligondanahalii | Mango | - Low yield due to imbalance nutrient management - Flower and fruit drop - Incidence of powdery mildew , hopper and fruit flies |  | 25 | FLD, Training |
| Haligondanahally | Arecanut | - Imbalanced nutrition, button shedding and nut splitting |  | 9 | FLD on INM in Arecanut and Training |
| Haligondanahally | Banana | - Low bunch yield due to imbalanced application of major and micro nutrients |  | 15 | FLD on INM in Banana and training |
| Haligondanahally | Red gram | - Leaf Webber and Pod borer - Pigeonpea sterility mosaic disease and wilt disease |  | 140 | FLD and training |
| Purlahalli | Watermelon | - Low yield due to local varieties - Incidence of watermelon bud necrosis virus |  | 10 | OFT, Training |
| Vidapanakunte | Onion | - Low yield - Imbalanced nutrition - Incidence of thrips and purple blotch disease |  | 75 | FLD and training |
| Cluster B- Hosadurga |  |  |  |  |  |
| Kachapura | Greengram |  | - Yellow Mosaic disease - Imbalanced application of fertilizers | 28 | FLD and training |
| Kangavalli | Bengal gram |  | - Pod borer and wilt | 64 | FLD and training |
| Cluster C - Dharamapura |  |  |  |  |  |
| Shydlainakote | Maize |  | - Nano fertilizer is a new technology yet to be spread to the farming community - Less fertilizer use efficiency | 20 | OFT, Training |
| Kanajanahalli | Onion |  | - Low yield due imbalanced nutrition - Uneven bulb size - bulb splitting, rotting | 55 | OFT, Training |
| Burudukunte | Onion |  | - Low yield - Imbalanced nutrition - Incidence of bulb rot and purple blotch disease | 27 | FLD and training |
| Eshwaragere | Mulberry |  | - Lower leaf yield due to imbalanced use of fertilizers | 6 | FLD on nutrient management in Mulberry and training |
| Cluster D - Hiriyur |  |  |  |  |  |
| Alur | Arecanut husk |  | - Improper disposal of arecanut husk - High lignin content - Lack of awareness on composting methods | 48 | OFT, Training |

5. Technology assessment during 2021-22

| Sl.No. | Crop/ enterprise | Prioritized problem | Title of intervention | Technology options | Source of technology | Name of critical input | Qty per trial (q) | Cost per trial (Rs.) | No. of trials | Total cost (Rs.) | Parameters to be studied | Team members |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5.1 | maize | - Nano fertilizer is a new technology yet to be spread to the farming community - Less fertilizer use efficiency | Assessment of Nano fertilizer (N & Zn) on growth and yield of maize | T1 :Basal dose of Application -fertilizers 50 kg DAP and 25 kg MOP :Top dressing with urea- 50 kg urea per acre at 40 DAS | Farmer’s Practice | Zinc sulphate | 4 kg | 400 | 3 | 16,500 | Yield q/ha, Plant height (cm) No of rows /cob, Cob weight ( g) and Benefit cost ratio | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi |
|  |  |  |  |  |  | Soil analysis | 3 | 600 |  |  |  |  |
|  |  |  |  |  |  | N based nano fertilizer | 1 l | 450 |  |  |  |  |
|  |  |  |  | T2 : 40:20:10 kg N, P2O5 ,K2O per acre (50 % N . 100 % P2O5 and 100 % K20 as a basal and 25 % N at 30 DAS and 25% N at 50 DAS + Zinc Sulphate 4 kg/acre as basal | UAHS (S) |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Zn based nano fertilizer | 1 l | 450 |  |  |  |  |
|  |  |  |  |  |  | Complex fertilizer | 100 kg | 3600 |  |  |  |  |
|  |  |  |  | T3 : 20:20:10 kg N, P2O5 ,K2O per acre (50 % N . 100 % P2O5 and 100 % K20 as a basal + 50 % N (4 ml/l) and Zn (2ml/l of water) through Nano fertilizer spray in two times at 30 DAS and 50 DAS | IFFCO-NBRC, Gujarath |  |  |  |  |  |  |  |
| 5.2 | Redgram | Sterility mosaic and wilt problem | Assessment of Redgram varieties for sterility mosaic virus | T1:BRG-2 | UAS (B) | Seeds Rhizobium PSB Trichoderma ZnSO4 | 20 kg 3 kg 12 kg | 2200 360 1440 | 2 | 8000 | Germination percentage, plant height (cm), No. of pods/plant), yield (q/ha ) ,economics , % disease incidence. | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi |
|  |  |  |  | T2:BSMR-736 | UAS (R) |  |  |  |  |  |  |  |
|  |  |  |  | T3:BRG -5 | UAS (B) |  |  |  |  |  |  |  |
| 5.3 | onion | - Low yield due imbalanced nutrition - Uneven bulb size - bulb splitting, rotting | Assessment of Sulphur applications in Kharif onion production for higher yield | T1 : Urea @ 125 kg , DAP@ 125 kg, 10:26:26 @125 kg | Farmers practice | Zinc sulphate | 4 | 500 | 2 | 5200 | Yield per plot and yield per ha, avg. bulb weight, bulb diameter (cm), incidence of thrips & purple blotch and economics | Dr Prakash kerure ,Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi |
|  |  |  |  |  |  | Borax | 4 | 1500 |  |  |  |  |
|  |  |  |  | T2 : 125:75:125kg NPK/ha + 20 kg Sulpher /ha , FYM @ 15 kg/ha (Full of PKS and 1/3 of N need to be applied at the time of transplanting and remaining 2/3 of N in two equal splits at 30 and 45 DAT.), Zinc sulphate @ 10 Kg/ha, Borax@10 kg/ha, 19:19:19 @ 5g/ liter at 30,45 and 60 DAT | DOGR, Pune | Sulpher | 6 | 600 |  |  |  |  |
|  |  |  |  | T3 : 125:75:125kg NPK/ha + 30 kg Sulpher /ha ,FYM @ 20 t/ha + 5 kg/ha of Azatobactor + 5 kg/ha of PSB, 19:19:19 @ 10g/ liter at 15,30 and 45DAT | NHRDF, Delhi |  |  |  |  |  |  |  |
| 5.4 | Watermelon | - Low yield due to local varieties - Incidence of watermelon bud necrosis virus | Assessment of Watermelon hybrids for higher yield | T1 : NS 295 | Farmers practice | Seeds | 0.6kg (each variety) | 12500 | 3 | 25,000 | Vine length (cm), No of fruits per plant (No.), Fruit weight (kg), Yield per ha, incidence of WBNV (%) and economics | Dr Prakash kerure ,Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi |
|  |  |  |  | T2 : Arka Muthu | IIHR, Bangaluru |  |  |  |  |  |  |  |
|  |  |  |  | T3 : Arka Akash | IIHR, Bengaluru |  |  |  |  |  |  |  |
| 5.5 | - | - Improper disposal of arecanut husk - High lignin content - Lack of awareness on composting methods | Assessment of different compost cultures to decompose arecanut husk | TO1 -Composting arecanut husk by using compost culture @ 2 kg/tonne | UAS, Dharwad | Compost culture | 2 kg | 800 | 3 | 3,400 | Number of days to compost (No.), C:N ratio | Dr. Jyothi T.V., Dr. Onkarappa , Dr. Rudragouda, Dr Prakash kerure |
|  |  |  |  | TO2 -Composting the arecanut husk by using compost culture @ 20 litres/tonne | NCOF, New Delhi | Waste decomposer | 20 litres | 600 |  |  |  |  |
|  |  |  |  | TO3 -Composting the arecanut husk by using compost culture @ 4 kg/tonne | UAHS, Shivamogga | Compost culture | 4 kg | 2000 |  |  |  |  |

6. Frontline demonstrations during 2021-22

| Sl. No. | Category | Crop/ enterprise | Prioritized problem | Technology to be demonstrated | Name of variety | Name of hybrid | Source of technology | Name of critical input | Qty per demo (q) | Cost per demo (Rs.) | No. of demos | Total cost for the demo (Rs.) | Parameters to be studied | Team members |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 6.1 | Cereals | Maize | Low yield due to fall armyworm | - Spacing of 60x30cm for maize - Seed treatment with Azospirillium , Trichoderma and PSB @ 500 g/ha - FYM : 7.5 t/ha, RDF : 100: 50:25 kg N, P2O5 ,K2O (50 % N . 100 % P2O5 and 100 % K20 as a basal and 25 % N at 30 DAS and 25% N at 50 DAS) + Zinc Sulphate 10 kg/ha as basal - Installation of pheromone traps @ 12 nos. per ha for Fall armyworm (Spodoptera frugiperda) 8 days after sowing - Spraying of Chlorantraniliprole 18.5 SC @ 0.4 ml/l of water Spraying of Mancozeb75WP @ 2.5g/l of water for leaf spot | - | - | UAHS(S) | Trichoderma | 1 kg | 120 | 10 | 11,600 | Yield q/ha, No. of moths/trap, percent incidence, No. of larva/plant, Plant height (cm) No of rows /cob, Cob weight ( g) and Benefit cost ratio | Dr. Onkarappa , Dr. Rudragouda, Dr Prakash kerure , Dr. Jyothi |
|  |  |  |  |  |  |  |  | Azospirillium | 1 kg | 120 |  |  |  |  |
|  |  |  |  |  |  |  |  | PSB | 1 kg | 120 |  |  |  |  |
|  |  |  |  |  |  |  |  | Pheromone traps, lures | 5 traps & 10 lures | 800 |  |  |  |  |
| 6.2 | Millets | Finger millet | - Low yield - Aphids , Neck blast and lodging - Imbalance nutrition (50 kg urea) | - Demonstration of variety ML-365 - Seed treatment with Biofertilizers- Azospirillum and PSB,@ 4 g/kg Biofungicide -Trichoderma @ 4 g/kg - FYM: 3 t/acre - RDF : 20:15:16 kg N, P2O5 ,K2O /acre, - Micronutrients (ZnSO4 5 kg/acre +Borax @ 4 kg/acre) - Foliar spray 19:19:19 @ 40 DAS - Spray with Imidachloprid 17.8 SL @ 0.5 ml/lit water - Spraying of Carbendazim 50 WP @ 1g/lit of water | ML-365 | - | UAHS (S) | Seed | 10 | 600 | 10 | 16,900 | Germination percentage, plant height (cm), No. of tillers/ plant, No. of fingers/ear head, % disease incidence, yield kg/ha and economics | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi |
|  |  |  |  |  |  |  |  | Azospirillum PSB Trichoderma | 3 | 330 |  |  |  |  |
|  |  |  |  |  |  |  |  | 19:19:19 | 4 | 440 |  |  |  |  |
|  |  |  |  |  |  |  |  | ZnSO4 | 4 | 320 |  |  |  |  |
| 6.3 | Oilseeds | Groundnut | - Less seed rate (30-35 kg seeds/acre) - Imbalanced nutrition (50kg DAP) - Root grub, bud necrosis and leaf spot | - Demonstration of seed cum fertilizer drill - Seed treated with Rhizobium & PSB , Biofungicide- Trichoderma @4 g/kg - Use of micronutrients (4 kg ZnSo4 ) - RDF-10:20:10 kg N, P2O5 ,K2O + 3 t FYM/ acre + 200 kg gypsum/acre - 19:19:19 fertilizer (10g/l ) sprayed at 35 DAS - Foliar spray of 0.1% borax at flower initiation - Seeds treated with Chlorpyriphos 20 EC @ 10 ml per kg seeds - Spray with Imidachloprid 17.8 SL @ 0.5 ml/l water - Spraying of Hexaconozole 5 SC @ ml/l of water - Growing of high stature crops as barriers in all along the crop |  | - | UAHS (S) | Pods | 60 | 4200 | 10 | 54,000 | Germination percentage, no. of plants/m2 , no. of pods/plant, test weight , shelling per cent , yield, % incidence of pest and disease and economics | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi |
|  |  |  |  |  |  |  |  | Rhizobium PSB Trichoderma | 3 | 330 |  |  |  |  |
|  |  |  |  |  |  |  |  | ZnSO4 | 4 | 320 |  |  |  |  |
|  |  |  |  |  |  |  |  | Boron | 1 | 110 |  |  |  |  |
|  |  |  |  |  |  |  |  | 19:19:19 | 4 | 440 |  |  |  |  |
| 6.4 | Pulses | Greengram | - Yellow mosaic disease - Imbalanced nutrition (25 kg DAP) | - Demonstration of variety- KKM-3 - Seed treatment with Rhizobium , PSB @ 4 g/kg seeds - Trichoderma @ 4 g/kg seeds - FYM : 3 t/acre - RDF : 5: 10:10 kg N, P2O5 ,K2O , 4 kg ZnSo4 /acre - Foliar spray 19:19:19 @ 1 % during 35 & 45 DAS - Spray with Imidachloprid 17.8 EC @ 0.5 ml/lit water - Spraying of Carbendazim @ 1g/lit of water | KKM-3 | - | UAHS (S) | Seed | 8kg | 2000 | 5 | 13,850 | Germination percentage, plant height, no. of pods per plant, test weight, per cent disease incidence, yield and economics | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi |
|  |  |  |  |  |  |  |  | Rhizobium PSB Trichoderma | 3kg | 330 |  |  |  |  |
|  |  |  |  |  |  |  |  | 19:19:19 | 4kg | 440 |  |  |  |  |
|  |  | Redgram | - Low yield due to pod borer and leaf webber - Pigeon pea sterility mosaic and wilt disease | - Introduction of new variety BRG-5 - FYM –7.5 t/ha, N:P:K 25:50:25, Sulphur- 20 kg, ZnSO4 –15 kg/ha, Pulse Magic 10g/l foliar spray - Trichoderma – 5 g/kg seeds, Rhizobium – 500 g/ha, PSB –500g/ha. - Pheromone traps – 10 Nos. / ha , HaNPV – 500 LE/ha, NSKE – 4% - Use of Bird perches - Dicofol 18.5 EC – 2.5 ml/l, Emamectin benzoate 5 SG – 0.3 g/l | BRG-5 | - | UAHS (S) | Seeds | 6 kg | 522 | 10 | 20,720 | Per cent disease and pest incidence, no. of pods per plant, 100 seed weight , yield and economics | Dr. Onkarappa , Dr. Rudragouda, Dr Prakash kerure , Dr. Jyothi |
|  |  |  |  |  |  |  |  | Trichoderma | 1 kg | 120 |  |  |  |  |
|  |  |  |  |  |  |  |  | Rhizobium | 200 g | 25 |  |  |  |  |
|  |  |  |  |  |  |  |  | PSB | 200 g | 25 |  |  |  |  |
|  |  |  |  |  |  |  |  | Pheromone traps, lures | 5 Nos. | 340 |  |  |  |  |
|  |  |  |  |  |  |  |  | Pulse Magic | 4 kg | 1040 |  |  |  |  |
|  |  | Bengalgram | - Low yield due to pod borer and wilt disease | - Variety: JAKI-9218 - FYM – 7.5 t /ha, N:P:K 12.5:25:25, - Foliar spray 19:19:19 – 2g/l, Chickpea special 10g/l - Trichoderma – 5 g/kg seeds, Rhizobium – 500 g/ha, PSB – 500 g/ha. - Pheromone traps – 5 No.s/ha HaNPV – 250 LE/ha. - Bengal gram : Coriander(Arka Isha)-6:1 - Use of Bird perches - Emamectin benzoate 5SG – 0.3g/l | JAKI-9218 | - | UAHS (S) | Seeds | 25 kg | 1,800 | 10 | 28300 | per cent disease and pest incidence, No. of pods per plant, 100 seed weight , yield and economics. | Dr. Onkarappa , Dr. Rudragouda, Dr Prakash kerure , Dr. Jyothi |
|  |  |  |  |  |  |  |  | Trichoderma | 1 kg | 120 |  |  |  |  |
|  |  |  |  |  |  |  |  | Rhizobium | 200 g | 25 |  |  |  |  |
|  |  |  |  |  |  |  |  | PSB | 200 g | 25 |  |  |  |  |
|  |  |  |  |  |  |  |  | Pheromone traps, lures | 5 Nos. | 340 |  |  |  |  |
|  |  |  |  |  |  |  |  | Chickpea special | 2 kg | 520 |  |  |  |  |
| 6.5 | Commercial crops | - | - | - | - | - | - | - | - | - | - | - | - | - |
| 6.6 | Horticultural crops | - | - | - | - | - | - | - | - | - | - | - | - | - |
| a | Vegetables | Onion | - Low yield - Imbalanced nutrition - Incidence of thrips and purple blotch disease | - Ddemonstration of Bhima Super Variety - Soil test based (RDF=125:75:125kg NPK/ha) application and spraying of Arka Vegetable Special @ 2g /l - Seed treatment with Trichoderma @ 4 g /kg - Use of yellow sticky traps for management of thrips@10 No. / ha - Growing of high stature crops as barriers in all along the crop - MMancozeb 75 WP @ 2g/l for Purple blotch and Acetamiprid 20 SP @ 0.2g/l for Thrips managements | Bhima Super | - | UAHS Shivamogga and IIHR, Bengaluru | Bhima Super Seeds Bioinputs (Trichoderma and PSB) | 3.5kg 10 kg | 8,750 | 5 | 43,750 | Yield (t/ha), days to 50% neck fall, incidence purple blotch, bub rot (%) and economics | Dr Prakash kerure ,Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi |
|  |  | Onion | - Low yield - Imbalanced nutrition - Incidence of bulb rot and purple blotch disease | - Demonstration of Bhima Shakti Variety - Soil test based (RDF=125:75:125kg NPK/ha) application and spraying of Arka Vegetable Special @ 2g /l - Seed treatment with Trichoderma @ 4 g /kg - Use of yellow sticky traps for management of thrips@10 No. / ha - Growing of high stature crops as barriers in all along the crop - Mancozeb 75 WP @ 2 g/l for Purple blotch and Acetamiprid 20 SP @ 0.2g/l for thrips management | Bhima Shakti | - | UAHS Shivamogga and IIHR, Bengaluru | Bhima Shakti Seeds Bioinputs (Trichoderma and PSB) | 3.5kg 10 kg | 8,750 | 5 | 43,750 | Yield (t/ha), bulb diameter (cm), bulb color, days to 50% neck fall, incidence of thrips & purple blotch and economics | Dr Prakash kerure ,Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi |
| b | Fruit crops | Mango | - Incidence of powdery mildew, hopper and fruit flies - Flower and fruit drop - Low yield due to imbalance nutrition | - Application of RDF (730:180:680 g NPK/Plant) - Foliar application of Arka Mango Special @ 5 g/l (First Spray: Jun-Jul, Second Spray: Oct-Nov, Third Spray: Dec-Jan, Fourth Spray: Feb-Mar ) - HHexaconazole 5 EC @ 1 ml/l for powdery mildew and Aecetamiprid 20 SP @ 0.2 g/l for hoppers | Alphanso | - | ICAR-IIHR Bengaluru | Arka Mango Special | 8 kg | 2,500 | 12 | 36,000 | No of fruits per plant, fruit yield per plant, incidence of hopper, fruit flies, powdery mildew and economics | Dr Prakash kerure ,Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi |
|  |  |  |  |  |  |  |  | Yellow sticky traps | 10kg | 500 |  |  |  |  |
|  |  | Banana | - Low bunch yield due to imbalanced application of major and micro nutrients | FYM: 5 kg/plant, RDF: 175:105:220 g N:P2O5:K2O / plant Split application of major nutrients once in 35 days (5 times) Micronutrients foliar application (Arka banana special @ 0.5 %), Green manuring crop – Dhaincha Dimethoate 30EC- 1.7ml/l, Phorate 10G- 5g/l, Carbendazim – 1g/l, Propiconazole – 1ml/l | Putta bale | - | UHS, Bagalkot and IIHR, Bangalore | Dhaincha seeds | 5kg | 500 | 10 | 23,900 | Bunch weight, no. of fruits per bunch , yield and economics, soil analysis (Soil pH, EC, organic carbon, available nitrogen, phosphorus, potassium and micronutrients viz., Cu, Fe, Mn and Zn ) and water analysis (water pH, EC, exchangeable Na, Ca + Mg, chlorides, bicarbonates, SAR and RSC). | Dr. Jyothi T.V., Dr. Onkarappa , Dr. Rudragouda, Dr Prakash kerure |
|  |  |  |  |  |  |  |  | Trichoderma | 2kg | 240 |  |  |  |  |
|  |  |  |  |  |  |  |  | Arka Banana Special | 8kg | 1400 |  |  |  |  |
|  |  |  |  |  |  |  |  | Soil and water analysis | 1+1 | 250 |  |  |  |  |
| c | Plantation crops | Arecanut | Imbalanced nutrition, button shedding and nut splitting | FYM – 20 kg/plant, Soil test based recommendation RDF- 100:40:140 g N:P2O5:K2O / plant , Borax - 20 g/plant, ZnSO4 - 40 g/plant, Trichoderma - 50 g/plant Dimethoate 30 EC 1.7 ml/l, Copper oxy chloride 50WP- 3g/l , Dicofol 18.5 EC- 2.5 ml/l. | Bheemasamudra Local | - | UAHS (S) | Dhaincha seeds | 5kg | 500 | 10 | 15,400 | No. of nuts drop per palm, yield, economics, soil analysis (Soil pH, EC, organic carbon, available nitrogen, phosphorus, potassium and micronutrients viz., Cu, Fe, Mn, Zn and B) and water analysis (water pH, EC, exchangeable Na, Ca + Mg, chlorides, bicarbonates, SAR and RSC). | Dr. Jyothi T.V., Dr. Onkarappa , Dr. Rudragouda, Dr Prakash kerure |
|  |  |  |  |  |  |  |  | Trichoderma | 2kg | 240 |  |  |  |  |
|  |  |  |  |  |  |  |  | ZnSO4 | 25 kg | 480 |  |  |  |  |
|  |  |  |  |  |  |  |  | Soil and water analysis | 1+1 | 250 |  |  |  |  |
| 6.7 | Livestock | - | - | - | - | - | - | - | - | - | - | - | - | - |
| 6.8 | Fisheries | - | - | - | - | - | - | - | - | - | - | - | - | - |
| 6.9 | Others | - | - | - | - | - | - | - | - | - | - | - | - | - |
|  |  | Mulberry | Lower leaf yield due to imbalanced use of fertilizers | FYM - 20-25 tonnes/ha/year RDF - 350:140:140 kg N:P2O5:K2O/ha/year in five splits equal doses Dr. Soil – Apply @ 62.5 litres for 1st crop; 25 litres each for 2nd crop and 3rd crop ; 12.5 litres per crop is enough from 4th crop onwards (per ha) Apply Dr. Soil through drip irrigation | V-1 | - | UAS, Bangalore, Central Sericultural Research and Training Institute (CSRTI), Mysuru, Central silk board, Ministry of textiles , Mysuru and M/s Microbi Agrotech Pvt. Ltd., Bengaluru | Trichoderma | 2 | 240 | 10 | 35,700 | Number of shoots per plant, Number of leaves per shoot , Leaf yield (t/ha) | Dr. Jyothi T.V., Dr. Onkarappa , Dr. Rudragouda, Dr Prakash kerure |
|  |  |  |  |  |  |  |  | Soil and water analysis | 1+1 | 250 |  |  |  |  |
|  |  |  |  |  |  |  |  | Dr. Soil | 7 litres | 3,080 |  |  |  |  |

7. Training for farmers/ farm women during 2021-22

| Sl.No. | Thematic area and the crop/ enterprise | Crop / Enterprise | Related field intervention (OFT/FLD) | Training title | No. of courses | Expected No. of participants | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 7.1 | Crop production | Maize | OFT | Importance of nano fertilizer on Maize | 1 | 25 | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi T.V. |
|  |  | Finger millet | FLD | Agro techniques for finger millet | 1 | 25 | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi T.V. |
|  |  | Groundnut | FLD | ICM in groundnut | 1 | 25 | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi |
|  |  | Greengram | FLD | Recent production techniques in greengram production | 1 | 25 | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi T.V. |
|  |  | Redgram | OFT | ICM in Redgram | 1 | 25 | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi T.V. |
|  |  | Greengram | FLD | Improved production practices for Greengram | 1 | 30 | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi T.V. |
|  |  | Groundnut | FLD | Water management in groundnut | 1 | 30 | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi T.V. |
|  |  | Groundnut | FLD | Integrated weed management in groundnut | 1 | 30 | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi T.V. |
|  |  | Finger millet | FLD | INM in Finger millet | 1 | 30 | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi T.V. |
| 7.2 | Horticulture production | Onion | FLD | Integrated crop management in onion | 1 | 25 | Dr Prakash kerure, Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi T.V. |
|  |  | Onion | Other | Seed production technologies in onion | 1 | 25 | Dr Prakash kerure, Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi |
|  |  | Coconut | Other | ICM and Cropping systems in Coconut | 1 | 25 | Dr Prakash kerure, Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi T.V. |
|  |  | Mango | FLD | ICM in Mango | 1 | 25 | Dr Prakash kerure, Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi T.V. |
|  |  | Bhendi | Other | ICM in Vegetables (Bhendi and watermelon) | 1 | 30 | Dr Prakash kerure, Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi T.V. |
|  |  | Onion | FLD/OFT | Integrated crop management in Onion | 1 | 30 | Dr Prakash kerure, Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi T.V. |
|  |  | Coconut and Arecanut | Other | Inter cropping systems in Coconut and Arecanut | 1 | 30 | Dr Prakash kerure, Dr. Rudragouda, Dr. Onkarappa Dr. Jyothi T.V. |
|  |  | Mango | FLD | ICM in Mango | 1 | 30 | Dr Prakash kerure, Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi T.V. |
|  |  | Onion | Other | Seed production techniques in Onion | 1 | 30 | Dr Prakash kerure, Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi T.V. |
|  |  | Pomegranate | Other | Crop regulations in Pomegranate | 1 | 30 | Dr Prakash kerure, Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi T.V. |
| 7.3 | Livestock production | - | - | - | - | - | - |
| 7.4 | Home Science | - | - | - | - | - | - |
| 7.5 | Plant protection | Red gram | FLD | Integrated pest and disease management in Red gram | 1 | 25 | Dr. Onkarappa ,Dr Prakash kerure, Dr. Rudragouda, Dr. Jyothi T.V. |
|  |  | Bengal gram | FLD | Integrated pest and disease management in Bengal gram | 1 | 25 | Dr. Onkarappa ,Dr Prakash kerure, Dr. Rudragouda, Dr. Jyothi T.V. |
|  |  | Coconut | Other | Integrated management of diseases in coconut | 1 | 25 | Dr. Onkarappa ,Dr Prakash kerure, Dr. Rudragouda, Dr. Jyothi T.V. |
|  |  | Pomegranate | Other | Integrated management of pest and diseases in Pomegranate | 1 | 25 | Dr. Onkarappa ,Dr Prakash kerure, Dr. Rudragouda, Dr. Jyothi T.V. |
|  |  | Pomegranate | Other | Integrated pest management in pomegranate | 1 | 30 | Dr. Onkarappa ,Dr Prakash kerure, Dr. Rudragouda, Dr. Jyothi T.V. |
|  |  | Banana | FLD | Integrated management of wilt disease in Banana | 1 | 30 | Dr. Onkarappa ,Dr Prakash kerure, Dr. Rudragouda, Dr. Jyothi T.V. |
|  |  | Coconut & Arecanut | others | Root feeding techniques in Coconut & Arecanut | 1 | 30 | Dr. Onkarappa ,Dr Prakash kerure, Dr. Rudragouda, Dr. Jyothi T.V. |
|  |  | Chrysanthemum | others | Integrated disease management in Chrysanthemum | 1 | 30 | Dr. Onkarappa ,Dr Prakash kerure, Dr. Rudragouda, Dr. Jyothi T.V. |
| 7.6 | Production of inputs at site | - | - | - | - | - | - |
| 7.7 | Soil health and fertility | Plantation crops | others | Importance of soil and water quality in plantation crops | 1 | 25 | Dr. Jyothi T.V.., Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda |
|  |  | - | others | Importance of balanced use of fertilizers | 1 | 25 | Dr. Jyothi T.V.., Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda |
|  |  | Banana | FLD | Integrated nutrient management in Banana | 1 | 25 | Dr. Jyothi T.V.., Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda |
|  |  | - | others | Soil and water conservation practices in farm fields | 1 | 25 | Dr. Jyothi T.V.., Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda |
|  |  | Plantation crops | others | Enriching vermicompost with micronutrients in plantation crops | 1 | 30 | Dr. Jyothi T.V.., Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda |
|  |  | Vegetables | Others | Foliar application of nutrients in vegetable crops | 1 | 30 | Dr. Jyothi T.V.., Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda |
|  |  | Banana | FLD | Recent nutrient management technologies in Banana | 1 | 30 | Dr. Jyothi T.V.., Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda |
|  |  | Horticulture crops | others | Management of problematic soils in horticulture crops | 1 | 30 | Dr. Jyothi T.V.., Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda |
|  |  | Plantation crops | others | Recycling of crop residues as a source of organic manure in plantation crops | 1 | 30 | Dr. Jyothi T.V.., Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda |
| 7.8 | PHT and value addition | - | - | - | - | - | - |
| 7.9 | Capacity building/ group dynamics | - | - | - | - | - | - |
| 7.10 | Farm mechanization | - | - | - | - | - | - |
| 7.11 | Fisheries production technologies | - | - | - | - | - | - |
| 7.12 | Mushroom production | - | - | - | - | - | - |
| 7.13 | Agro forestry | - | - | - | - | - | - |
| 7.14 | Bee keeping | - | - | - | - | - | - |
| 7.15 | Sericulture | - | - | - | - | - | - |
| 7.16 | Others, pl. specify | - | - | - | - | - | - |

8. Training for rural youth during 2021-22

| Sl.No. | Thematic area and the crop/ enterprise | Crop / Enterprise | Related field intervention (EDP/Skill development etc) | Training title | No. of courses | Expected No. of participants | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 8.1 | Crop production | Groundnut | - | Recent production practices in groundnut | 1 | 30 | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi |
| 8.2 | Horticulture production | vegetables | - | Nursery production techniques for vegetables | 1 | 30 | Dr Prakash kerure, Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi |
| 8.3 | Livestock production |  | - |  |  |  |  |
| 8.4 | Home Science |  | - |  |  |  |  |
| 8.5 | Plant protection | Pomegranate | - | Integrated crop management in Pomegranate | 1 | 30 | Dr. Onkarappa ,Dr Prakash kerure, Dr. Rudragouda, Dr. Jyothi |
| 8.6 | Production of inputs at site |  | - |  |  |  |  |
| 8.7 | Soil health and fertility | - | - | Use of water soluble fertilizers and principles | 1 | 30 | Dr. Jyothi T.V.., Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda |
|  |  | plantation crops | - | Use of farm calculators in field crops and plantation crops | 1 | 30 | Dr. Jyothi T.V.., Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda |
|  |  | - | - | Micronutrients management in problematic soils | 1 | 30 | Dr. Jyothi T.V.., Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda |
|  |  | - | - | Organic farming – principles and practices | 1 | 30 | Dr. Jyothi T.V.., Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda - |
| 8.8 | PHT and value addition | - | - | - | - | - | - |
| 8.9 | Capacity building/ group dynamics | - | - | - | - | - | - |
| 8.10 | Farm mechanization | - | - | - | - | - | - |
| 8.11 | Fisheries production technologies | - | - | - | - | - | - |
|  |  | - | - | - | - | - | - |
| 8.12 | Mushroom production | - | - | - | - | - | - |
| 8.13 | Agro forestry | - | - | - | - | - | - |
| 8.14 | Bee keeping | - | - | - | - | - | - |
| 8.15 | Sericulture | - | - | - | - | - | - |
| 8.16 | Others, pl. specify |  |  |  |  |  |  |

### 9. Training for extension personnel during 2021-22

| Sl.No. | Thematic area and the crop/ enterprise | Training title | No. of courses | Expected No. of participants | Names of the team members involved |
| --- | --- | --- | --- | --- | --- |
| 9.1 | Crop production | Recent production techniques in groundnut, cotton and maize | 1 | 30 | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi |
|  |  | Recent production techniques in Chickpea | 1 | 30 | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi |
| 9.2 | Soil health and fertility | Soil and plant analysis for nutrient management in Banana | 1 | 30 | Dr. Jyothi T.V.., Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda |
|  |  | Soil, water and plant analysis for nutrient management in agriculture crops | 1 | 30 | Dr. Jyothi T.V.., Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda |
|  |  | Soil test based fertilizer recommendation by using farm calculators | 1 | 30 | Dr. Jyothi T.V.., Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda |
|  |  | Application of gypsum as a source of amendments in dryland farming | 1 | 30 | Dr. Jyothi T.V.., Dr. Onkarappa , Dr Prakash kerure, Dr. Rudragouda |
| 9.3 | Home Science | - | - | - | - |
| 9.4 | Capacity building and group dynamics | - | - | - | - |
| 9.5 | Horticulture | Protected cultivation of capsicum, tomato and other vegetable crops |  |  | Dr Prakash kerure, Dr. Rudragouda, Dr. Onkarappa , Dr. Jyothi |
| 9.6 | Livestock production and management | - | - | - | - |
| 9.7 | Plant protection | IPDM in Redgram and Groundnut crops | 1 | 30 | Dr. Onkarappa ,Dr Prakash kerure, Dr. Rudragouda, Dr. Jyothi |
|  |  | IPDM in Arecanut and Coconut crops | 1 | 30 | Dr. Onkarappa ,Dr Prakash kerure, Dr. Rudragouda, Dr. Jyothi |
| 9.8 | Farm mechanization | - | - | - | - |
| 9.9 | PHT and value addition | - | - | - | - |
| 9.10 | Production of inputs at site | - | - | - | - |
| 9.11 | Sericulture | - | - | - | - |
| 9.12 | Fisheries | - | - | - | - |
| 9.13 | Other, pl. specify | - | - | - | - |

## 10. Vocational trainings during 2021-22

| Sl.No. | Thematic area and the crop/ enterprise | Training title | No. of programmes | Duration (days) | Expected No. of participants | Sponsoring agency, if any | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 10.1 | Crop production | Vermicompost production | 1 | 2 | 15 | - | Dr. Rudragouda, Dr. Onkarappa , Dr Prakash kerure , Dr. Jyothi |
| 10.2 | Home Science | - | - | - | - | - | - |
| 10.3 | Capacity building and group Dynamics | - | - | - | - | - | - |
| 10.4 | Horticulture | Skill development and self employment generation activities in horticulture for rural youths | 1 | 21 | 25 | DoH | Dr Prakash kerure,Dr. Onkarappa , Dr. Rudragouda, Dr. Jyothi |
| 10.5 | Livestock production and management | - | - | - | - | - | - |
| 10.6 | Plant protection | Bee keeping for rural youths | 1 | 3 | 25 | - | Dr. Onkarappa ,Dr Prakash kerure, Dr. Rudragouda, Dr. Jyothi |
| 10.7 | Farm mechanization | - | - | - | - | - | - |
| 10.8 | PHT and value addition | - | - | - | - | - | - |
| 10.9 | Production of inputs at site | - | - | - | - | - | - |
| 10.10 | Sericulture | - | - | - | - | - | - |
| 10.11 | Fisheries | - | - | - | - | - | - |
| 10.12 | Other, pl. specify | - | - | - | - | - | - |

## 11. Sponsored trainings during 2021-22

| Sl.No. | Thematic area and the crop/ enterprise | Training title | No. of programmes | Duration (days) | Expected number of participants | Sponsoring agency | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 11.1 | Crop production | - | - | - | - | - | - |
| 11.2 | Home Science | - | - | - | - | - | - |
| 11.3 | Capacity building and group Dynamics | - | - | - | - | - | - |
| 11.4 | Horticulture | - | - | - | - | - | - |
| 11.5 | Livestock production and management | - | - | - | - | - | - |
| 11.6 | Plant protection | - | - | - | - | - | - |
| 11.7 | Farm mechanization | - | - | - | - | - | - |
| 11.8 | PHT and value addition | - | - | - | - | - | - |
| 11.9 | Production of inputs at site | - | - | - | - | - | - |
| 11.10 | Sericulture | - | - | - | - | - | - |
| 11.11 | Fisheries | - | - | - | - | - | - |
| 11.12 | Others, pl. specify | - | - | - | - | - | - |

## 12. Extension activities during 2021-22

| Sl. No. | Extension activity | No. of activities | Targeted number of participants | Names of the team members involved |
| --- | --- | --- | --- | --- |
| 12.1 | Advisory services | 2000 | 2000 | All Scientist & staff |
| 12.2 | Diagnostic visits | 10 | 70 |  |
| 12.3 | Field days | 12 | 800 |  |
| 12.4 | Group discussions | 15 | 350 |  |
| 12.5 | Kisan gosthies | 3 | 250 |  |
| 12.6 | Film shows | 15 | 600 |  |
| 12.7 | Self -Help Groups (SHGs) meetings | 3 | 50 |  |
| 12.8 | Kisan Melas | 2 | 350 |  |
| 12.9 | Exhibitions | 6 | >100000 |  |
| 12.10 | Scientists' visit to farmers fields | 180 | 500 |  |
| 12.11 | Plant/soil health/animal health camps | 3 | 60 |  |
| 12.12 | Farm science club meetings | - | - |  |
| 12.13 | Ex-trainees sammelans (Meetings) | 1 | 60 |  |
| 12.14 | Farmers' seminars/workshops | 2 | 200 |  |
| 12.15 | Method demonstrations | 15 | 400 |  |
| 12.16 | Celebration of important days | 6 | 400 |  |
| 12.17 | Special day celebrations | 5 | 400 |  |
| 12.18 | Exposure visits | 5 | 100 |  |
| 12.19 | Technology week celebration | 1 | 300 |  |
| 12.20 | Farmers Field School (FFS) | 1 | 30 |  |
| 12.21 | Farm innovators meet | 1 | 30 |  |
| 12.22 | Awareness programmes | 4 | 400 |  |
| 12.23 | Pre-kharif campaign | 3 | 250 |  |
| 12.24 | Pre-rabi/summer campaign | 3 | 250 |  |
| 12.25 | Others, pl. specify | - | - |  |

## 13. Activities proposed as knowledge and resource centre during 2021-22

13.1 Technological knowledge

| Sl. No. | Category | Details of technologies | Area (ha) | Number | Names of the team members involved |
| --- | --- | --- | --- | --- | --- |
| 13.1.1 | Technology park/ crop cafeteria | Pulses , vegetables , fruit crops Fodder varieties and green manure ,coconut nursery | 1 | 1 | Farm manager & Scientists |
| 13.1.2 | Demonstration units | Farm Pond | 21x21x4 m | 1 | Farm manager & Scientists |
|  |  | Dry land horticulture | 0.8 | 1 | Farm manager & Scientists |
|  |  | Nursery | 650 sq.m. | 1 | Farm manager & Scientists |
|  |  | Bee Keeping | - | 3 | Farm manager & Scientists |
|  |  | Poultry | - | 250 | Farm manager & Scientists |
|  |  | Farm machinery | - | - | Farm manager & Scientists |
|  |  | Establishment of Mango mother block | 10 gunta | 1 | Farm manager & Scientists |
|  |  | Vermicompost | 96sqm | 1 | Farm manager & Scientists |
| 13.1.3 | Lab analytical services | Soil and water samples analysis | - | 1 | Scientist (SS) |
| 13.1.4 | Technology week | Improved technologies in agri and horticultural crops | - | 200 participants | Dr. Onkarappa ,Dr Prakash kerure, Dr. Rudragouda, Dr. Jyothi |
| 13.1.5 | Others, Pl. specify | - | - | - | - |

13.2 Technological products

| Sl. No. | Category | Name of the production partner agency, if any | Name of the product | Quantity planned to be produced during 2021-22 (q) | Number planned to be produced during 2021-22 | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- |
| 13.2.1 | Seeds | - | Fodder sorghum | 2 | - | Farm manager & Scientists |
|  |  | - | Napier | - | 10,000 stem cuttings | Farm manager & Scientists |
|  |  | - | Green manure | 1 | - | Farm manager & Scientists |
|  |  | - | Groundnut | 0.5 | - | Farm manager & Scientists |
|  |  | - | Redgram | 0.5 | - | Farm manager & Scientists |
|  |  | - | Greengram | 0.25 | - | Farm manager & Scientists |
| 13.2.2 | Planting material | - | Coconut ( Arsikere tall ) | - | 5000 | Farm manager & Scientists |
|  |  | - | Arecanut (Local) | - | 5000 | Farm manager & Scientists |
|  |  | - | Drum stick (PKM-1) | - | 3000 | Farm manager & Scientists |
|  |  | - | Lime (Balaji Local) | - | 1000 | Farm manager & Scientists |
|  |  | - | Jamun (Grafts) | - | 1000 | Farm manager & Scientists |
|  |  | - | Mango (Grafts) | - | 1000 | Farm manager & Scientists |
|  |  | - | Curry leaf | - | 1000 | Farm manager & Scientists |
|  |  | - | Tamarind (Grafts) | - | 1000 | Farm manager & Scientists |
|  |  | - | Mahaghani | - | 1000 | Farm manager & Scientists |
|  |  | - | Red Sandal | - | 1000 | Farm manager & Scientists |
|  |  | - | Teak | - | 1000 | Farm manager & Scientists |
|  |  | - | Hebbevu | - | 1000 | Farm manager & Scientists |
| 13.2.3 | Bio-products | - |  | - |  |  |
| 13.2.4 | Livestock strains | - | Giriraja | - | 200 | Farm manager & Scientists |
|  |  | - | Swardhara | - | 200 | Farm manager & Scientists |
|  |  | - | Local | - | 100 | Farm manager & Scientists |
| 13.2.5 | Fish fingerlings | - | - | - | - | - |
| 13.2.6 | Any other, pl specify | - | - | - | - | - |

13.3 Technological information

| Sl. No | Category | Technological capsules/lectures/number | Names of the team members involved |
| --- | --- | --- | --- |
| 13.3.1 | Technology backstopping to line departments |  |  |
|  | - Agriculture | 28 | All Scientists and staff |
|  | - Horticulture | 11 |  |
|  | - Animal Husbandry | 3 |  |
|  | - Fisheries | - |  |
|  | - Agricultural Engineering | 8 |  |
|  | - Sericulture | 3 |  |
|  | - Others, pl. specify | - |  |
| 13.3.2 | Literature/publication | 10 |  |
| 13.3.3 | Electronic media | 6 |  |
| 13.3.4 | Kisan mobile advisory services | 30 | All Scientists & Prg Assistant (Computer) |
| 13.3.5 | Information on centre/state sector schemes and service providers in the district (Data may be collected from different agencies). | 5 | All Scientists & Prg Assistant (Computer) |

## 14. Additional activities planned during 2021-22

| Sl. No. | Name of the agency / scheme | Name of activity | Technical programme with quantification | Financial outlay (Rs.) | Names of the team members involved |
| --- | --- | --- | --- | --- | --- |
|  | - | - | - | - | - |

15. Revolving fund

15.1 Financial status of revolving fund

| Opening balance as on 01.04.2020 (Rs.in Lakh) | Expenditure incurred during 2020-21 (Rs.in Lakh) | Receipts during 2020-21 (Rs. in Lakh) | Closing balance as on 31.01.2021 (Rs. in Lakh) | Expected closing balance by 31.03.2021 (Including value of material in stock/ likely to be produced) |
| --- | --- | --- | --- | --- |
| 6.57 | 4.95 | 10.39 | 12.01 | 13.50 |

15.2 Plan of activities under revolving fund

| Sl. No. | Proposed activities | Expected output | Anticipated income (Rs.) | Names of the team members involved |
| --- | --- | --- | --- | --- |
|  | Fodder sorghum | 2q | 1,30,000 | Farm manager & Scientists |
|  | Napier | 10,000 stem cuttings | 20,000 | Farm manager & Scientists |
|  | Green manure | 1q | 8,000 | Farm manager & Scientists |
|  | Groundnut | 0.5q | 2,500 | Farm manager & Scientists |
|  | Redgram | 0.5q | 2,000 | Farm manager & Scientists |
|  | Greengram | 0.25q | 1,400 | Farm manager & Scientists |
|  | Coconut ( Arsikere tall ) | 5000 No’s | 1,00,000 | Farm manager & Scientists |
|  | Arecanut (Local) | 5000 No’s | 87,000 | Farm manager & Scientists |
|  | Drum stick (PKM-1) | 3000 No’s | 30,000 | Farm manager & Scientists |
|  | Lime (Balaji Local) | 1000 No’s | 4,500 | Farm manager & Scientists |
|  | Jamun (Grafts) | 1000 No’s | 25,000 | Farm manager & Scientists |
|  | Mango (Grafts) | 1000 No’s | 21,000 | Farm manager & Scientists |
|  | Curry leaf | 1000 No’s | 4,500 | Farm manager & Scientists |
|  | Tamarind (Grafts) | 1000 No’s | 14,000 | Farm manager & Scientists |
|  | Mahaghani | 1000 No’s | 4,500 | Farm manager & Scientists |
|  | Red Sandal | 1000 No’s | 3,000 | Farm manager & Scientists |
|  | Teak | 1000 No’s | 4,000 | Farm manager & Scientists |
|  | Hebbevu | 1000 No’s | 2,000 | Farm manager & Scientists |
|  | Giriraja | 200 No’s | 40,000 | Farm manager & Scientists |
|  | Swardhara | 200 No’s | 40,000 | Farm manager & Scientists |
|  | Local | 100 No’s | 18,000 | Farm manager & Scientists |

## 16. Activities of soil, water and plant testing laboratory during 2021-22

| Sl.No. | Type of samples | No. of samples to be analyzed | Names of the team members involved |
| --- | --- | --- | --- |
| 16.1 | Soil test using analytical lab | 1200 | Dr. Jyothi T. V. |
| 16.2 | Soil test using mobile analysis kit | - | - |
| 16.3 | Water | 1200 | Dr. Jyothi T.V. |
| 16.4 | Plant | - | - |
| 16.5 | Others, pl. specify | - | - |

## 17. E-linkage during 2021-22

| Sl. No | Nature of activities | Likely period of completion (please set the time frame) | Remarks if any |
| --- | --- | --- | --- |
| 17.1 | Title of the technology module to be prepared | - | - |
| 17.2 | Creation and maintenance of relevant database system for KVK | 6 months | - |
| 17.3 | Any other (Please specify) | - | - |

18. Activities planned under rainwater harvesting scheme (only to those KVKs which are already having scheme under rain water harvesting)

| Sl. No | Activities planned | Remarks if any |
| --- | --- | --- |
| - | - | - |

19. Farmers Field School (FFS) planned

| Thematic area | Title of the FFS | Budget proposed in Rs. |
| --- | --- | --- |
| ICM | Virtual Farmers School- ICM in Pomegranate | 50,000 |

20. Integrated Farming System (IFS) planned

| Description of model(s) | No. of models/units | Budget proposed in Rs. |
| --- | --- | --- |
| - | - | - |

21. Details of budget utilization (2020-21) upto 31 January 2021

(Rs.)

| Sl.No. | Particulars | Sanctioned | Released | Expenditure |
| --- | --- | --- | --- | --- |
| 21.1 | (A). REVENUE (Recurring Contingencies) |  |  |  |
| 21.1.1 | Pay & Allowances | 12100000 | 8503269 | 10252337 |
| 21.1.2 | Traveling allowances | 150000 |  | 84316 |
| 21.1.3 | Contingencies | - |  | - |
| 21.1.3.a | Stationery, telephone, postage and other expenditure on office running, publication of Newsletter | 275000 |  | 238007 |
| 21.1.3.b | POL, repair of vehicles, tractor and equipments | 225000 |  | 220391 |
| 21.1.3.c | Food/refreshment for farmers/extension personnel @ Rs.150/person/day | 100000 |  | 39205 |
| 21.1.3.d | Training material (need based materials and equipments for conducting the training) | 35000 |  | 26600 |
| 21.1.3.e | Frontline demonstrations | 293000 |  | 243685 |
| 21.1.3.f | On farm testing (OFTs)/Technology Assessment | 45000 |  | 15200 |
| 21.1.3.g | Integrated Farming System (IFS) (Min. 5 Units) | 0 |  | 0 |
| 21.1.3.h | Training of extension functionaries | 0 |  | 0 |
| 21.1.3.i | Extension activities/services | 25000 |  | 13425 |
| 21.1.3.j | Farmers' Field School | 0 |  | 0 |
| 21.1.3.k | EDP (2 Nos.) / Innovative activities | 0 |  |  |
| 21.1.3.l | Soil & water testing & issue of soil health cards | 25000 |  | 12500 |
| 21.1.3.m | Maintenance of building | 25000 |  | 19681 |
| 21.1.3.n | Farmers Conclave, KVK Conference | 25000 |  | 23552 |
| 21.1.3.o | Video production | 0 |  | 0 |
| 21.1.3.p | Library (Purchase of Journals, Periodicals, News Papers& Magazines) | 25000 |  | 24135 |
|  | Total Recurring | 5000 |  | 3276 |
| 21.2 | (B). CAPITAL (Non-Recurring Contingencies) | 13353000 |  | 11216310 |
| 21.2.1 | Equipments& Furniture | 0 |  | 0 |
| 21.2.2 | Works | 0 |  | 0 |
| 21.2.3 | Vehicle | 0 |  | 0 |
| 21.2.3 a | Four wheeler (replacement) | 0 |  | 0 |
| 21.2.4 | Library | 0 |  | 0 |
|  | Total Non Recurring | 0 |  | 0 |
| 21.3 | (C). REVOLVING FUND | 0 |  | 0 |
|  | GRAND TOTAL (A+B+C) | 13353000 | 8503269 | 11216310 |

22. Details of Budget Estimate based on proposed action plan (2021-22)

| Sl.No. | Particulars | BE 2021-22 proposed (Rs.) |
| --- | --- | --- |
| 22.1 | (A). REVENUE (Recurring Contingencies) |  |
| 21.1.1 | Pay & Allowances | 17600000 |
| 22.1.2 | Traveling allowances | 450000 |
| 22.1.3 | Contingencies |  |
| 22.1.3.a | Stationery, telephone, postage and other expenditure on office running, publication of Newsletter | 500000 |
| 22.1.3.b | POL, repair of vehicles, tractor and equipments | 450000 |
| 22.1.3.c | Food/refreshment for farmers / extension personnel @ Rs.150/person/day | 200000 |
| 22.1.3.d | Training material (need based materials and equipments for conducting the training) | 150000 |
| 22.1.3.e | Frontline demonstrations | 350000 |
| 22.1.3.f | On farm testing (OFTs)/Technology Assessment | 60000 |
| 22.1.3.g | Integrated Farming System (IFS) (Min. 5 Units) | 250000 |
| 22.1.3.h | Training of extension functionaries | 100000 |
| 22.1.3.i | Extension activities/services | 150000 |
| 22.1.3.j | Virtual Farmers' Field School | 50000 |
| 22.1.3.k | Special programme on Farmers participatory onion seed production for self reliance | 50000 |
| 22.1.3.l | Soil & water testing & issue of soil health cards | 50000 |
| 22.1.3.m | Maintenance of building (Repair & Renovation) | 200000 |
| 22.1.3.n | Library (Purchase of Journals, Periodicals, News Papers& Magazines) | 25000 |
| 22.1.3.o | Others, pl. specify Video Production | 100000 |
|  | Total Recurring (A) | 20735000 |
| 22.2 | (B). CAPITAL (Non-Recurring Contingencies) |  |
| 22.2.1 | Equipment’s& Furniture | 500000 |
| 22.2.2 | Works | 1000000 |
| 22.2.3 | Vehicle | - |
| 22.2.3.a | Four wheeler (replacement) | - |
| 22.2.4 | Library | 25000 |
|  | Total Non Recurring (B) | 1525000 |
|  | Grand Total (A + B) | 22260000 |

-:O:-