ACTION PLAN OF KVK GADAG

FOR THE YEAR 2011-12

Presented at

ACTION PLAN MEETING

(3rd – 4th March, 2011)

Venue

Zonal Project Directorate

ICAR, Zone VIII, Bangalore

`

Prepared by

K.H.PATIL KRISHI VIGYAN KENDRA

Hulkoti-582 205   Dist : GADAG, Karnataka State

Website : www.khpkvk.org

e-mail : kvkhulkoti@gmail.com

Contents

| Sl. No. | PARTICULARS | PAGE NO. |
| --- | --- | --- |
| 1 | Details of KVK | 1-5 |
| 2 | Plan of work for 2011-12 and thrust areas | 5-15 |
| 3 | Abstracts of interventions proposed | 15-20 |
| 4 | Target set for interventions | 20-21 |
| 5 | Plan for On Farm Testings | 22-29 |
| 6 | Plan of Front Line Demonstrations | 30-39 |
| 7 | Plan for training programme |  |
|  | Training programme for farmers / farmwomen Extension functionaries | 40-42 |
|  | Training for rural youths | 42 |
|  | Training programme for Extension personnel | 43 |
|  | Vocational training for young farmers | 44 |
|  | Sponsored trainings | 44 |
| 8 | Extension programme planned | 45-47 |
| 9 | Details of print and electronic media | 48 |
| 10 | Collaborative programmes planned | 48 |
| 11 | Financial & Physical status of revolving fund and plan for utilization | 48-49 |
| 12 | Status of KVK farm and demonstration units | 49 |
| 13 | Production & supply of inputs, linkage with ATMA/NHM | 50 |
| 14 | Activities of soil, water and plant testing | 51 |
| 15 | Details of budget | 51-53 |
| 16 | Target for E-linkage | 53 |
| 17 | Farmers’ Field School activities planned | 54 |

###### ACTION PLAN (2011-12)

OF

###### K.H. PATIL KRISHI VIGYAN KENDRA, HULKOTI, GADAG DISTRICT

###### General information about the Krishi Vigyan Kendra

| 1. | Name and address of KVK with Phone, Fax and e-mail | : | K.H. Patil Krishi Vigyan Kendra Hulkoti – 582205 Dist.: Gadag Phone : (08372) 289606 Fax : (08372) 289474 E-mail : khpatil_kvk_hulkoti@yahoo.com kvkhulkoti@gmail.com |
| --- | --- | --- | --- |
| 2. | Name and address of host organization with Phone, Fax and e-mail | : | Agricultural Science Foundation Hulkoti – 582205 District: Gadag Phone : (08372) 289069 Fax : (08372) 289474 E-mail : asf_hulkoti@yahoo.co.in |
| 3. | Name of the Programme Coordinator Residence Phone Number/ Mobile No. | : | Dr. L.G.Hiregoudar Phone (R) : (08372) 289772 (M) : 09448358772 |
| 4. | Year of sanction | : | 1985 |
| 5. | Year of start of activities | : | 1985 |
| 6. | Major farming systems/enterprises | : | A) Field crop based Farming systems (i) Chilli + Onion + Cotton, Onion + Chilli (ii) Groundnut – Rabi jowar/ Wheat (iii) Greengram – Sunflower / Rabi jowar/ Wheat /Bengalgram (iv) Maize – Bengalgram / Wheat (Irrigated) (v) Kharif jowar + Tur (vi) Bt Cotton B) Horticulture based Farming systems (i) Vegetable Crops (Irrigated condition) (ii) Flower crops (irrigated) (iii) Mango (mainly dryland) C) Major Enterprises (i) Dairy farming (ii) Sheep rearing (iii) Goat rearing |
| 7. | Name of agro-climatic zone | : | Northern Dry Zone (Region – 2) comprising of Gadag, Ron, Naragund and Mundaragi blocks Semi transitional Zone -8 comprising of Shirahatti block |
| 8. | Soil type | : | Deep black to medium black soils, red sandy soil and red clay soils |
| 9. | Annual rainfall (mm) | : | 612 mm |

- Staff Strength as on 01-02-2011:

|  | Programme Coordinator | Subject Matter Specialists | Programme Assistant | Administrative Staff | Auxiliary Staff | Supporting Staff | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sanctioned | 1 | 6 | 3 | 2 | 2 | 2 | 16 |
| Filled | 1 | 6 | 3 | 2 | 2 | 2 | 16 |
| Vacant | 0 | 0 | 0 | 0 | 0 | 0 | 0 |

III. Details of staff as on 01-02-2011

| Sl. No. | Sanctioned post | Name of the incumbent | Discipline | Existing Pay scale | Number in which directly associated in the proposed programmes | Date of joining | Permanent / Temporary |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | No. of technologies to be assessed / refined | FLDs | Training Programmes | Extension Programmes |  |  |
| 1. | Programme Coordinator | Dr. L.G. Hiregoudar | Crop Physiology | 16400-22400 | 1 | 1 | 13 | - | 05.09.1992 | Permanent |
| 2. | Subject Matter Specialist | Mr. S.K.Mudlapur | Plant Protection | 10000-15200 | 2 | 4 | 35 | - | 26.09.1994 | Permanent |
| 3. | Subject Matter Specialist | Mr. S.H.Adapur | Ag. extension | 10000-15200 | - | - | 08 | 51 | 23.06.1995 | Permanent |
| 4. | Subject Matter Specialist | Smt. S.S.Rayanagoudar | Home Science | 10000-15200 | 2 | 4 | 33 | - | 26.06.1995 | Permanent |
| 5 | Subject Matter Specialist | Mr. V.D.Vaikunthe | Agronomy | 10000-15200 | 2 | 8 | 23 | - | 01.07.1995 | Permanent |
| 6 | Subject Matter Specialist | Mr. K.T.Patil | Horticulture | 10000-15200 | - | 2 | 18 | - | 01.07.1995 | Permanent |
| 7 | Subject Matter Specialist | Mr. N.H.Bhandi | Soil Science | 8000-13500 | - | 3 | 27 | - | 01.06.2005 | Permanent |
| 8 | Programme Assistant | Mr. B.M.Murgod | Animal Husbandry | 5500-9000 | 1 | 5 | 27 | - | 25.06.2007 | Permanent |
| 9 | Farm Manager | Mr. Suresh L. Halemani | - | 5500-9000 | Total | 8 | 27 | 184 | 51 | 01.02.2011 | Permanent |
|  |  |  |  |  | NOT APPLICABLE |  |  |
| 10 | Computer Programmer | Smt. L.S.Asuti | - | 5500-9000 |  | 01.06.2005 | Permanent |
| 11 | Accountant/ Superintendent | Mr. M.B. Jakkanagoudar | - | 5500-9000 |  | 25.06.2007 | Permanent |
| 12 | Stenographer | Smt. M.Halappanavar | - | 4000-6000 |  | 01.01.2011 | Permanent |
| 13 | Driver 1 | Mr. N.L. Hadapad | - | 3200-4900 |  | 03.09.1992 | Permanent |
| 14 | Driver 2 | Mr. G.D. Madivalar | - | 3200-4900 |  | 20.07.1995 | Permanent |
| 15 | Supporting staff 1 | Mr. S.B. Kotabagi | - | 3050-4590 |  | 18.07.1985 | Permanent |
| 16 | Supporting staff 2 | Mr. V.R. Navalli | - | 3050-4590 |  | 20.07.1993 | Permanent |

IV.. Plan of Human Resource Development of KVK personnel during 2011-12

| Sl. No | Discipline | Area of training required | Institution where training is offered | Organization | Justification | Highlight on Future programmes to be planned after training | Approximate duration (days) | Training fee (Rs.) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Home Science | (i) Preliminary processing & value addition of pulses | CIPHET Ludhiana | ICAR | Farmers are selling whole pulses at cheaper rate. So to promote value addition training is required | Value addition in pulses mainly greengram & bengalgram | One week | - |
|  |  | (ii) Branding and licensing of food products | Any relevant institution | - | For branding and sale of SHG products as our KVK had constructed marketing building | For establishing KVK Mall at KVK premises for the sale of SHG products | 3-4 days | - |
| 2 | Ag. Extension | (i) Promotion of commodity interest groups | Manage, Hyderabad | MoA, GoI | To promote Mango grower commodity groups | Establishment of Mango grower commodity groups | 5 days | 6000 |
|  |  | (ii) Farm mechanization extension | Manage, Hyderabad | MoA, GoI | To initiate farm mechanisation | To organize training programmes & demosntrations on farm mechanisation | 5 days | 6000 |
| 3 | Horticulture | Hitech production technology in vegetable fruits & flower crops | IIHR, Bangalore NRC, Onion & Garlic, Pune NRC, Lucknow | ICAR ICAR ICAR | To know the latest technology developed & varieties released To know the latest technology developed & varieties released To know the latest technology developed & varieties released | Seed production, training & demonstration Seed production, training & demonstration Seed production, training & demonstration | 7 days | 25000 |
|  |  | Cashew fruit & nut processing | NRC, Puttur | ICAR | To know technology of cashew processing | Training & demonstration | 5 days |  |
| 4 | Agronomy | (i)Sugarcane production | SBI, Coimbatore | ICAR | Sugarcane area is increasing | Imparting training to farmers | 5 days | 5000 |
|  |  | (ii) Chemical weed management | UAS, Dharwad | Agriculture University | Labour problem for weeding | Imparting the training to farmers | 3 days | 3000 |
| 5 | Plant protection | (i) IPM in Horticulture crop | IIHR, Bangalore or NCIPM, Delhi | ICAR | To know the latest IPM technologies | Imparting training to farmers | 6 days | 7000 |
|  |  | (ii) IPM in Sugarcane | SBI, Coimbatore | ICAR | Sugar cane area is increasing | Imparting training to farmers | 5 days | 5000 |
| 6 | Farm manager | (i)Protective cultivation | ICAR | ICAR | Required to implement in the farm | Strengthening KVK Demo. Unit | 6 days | - |
|  |  | (ii) Seed production & certification | IIHR, Bangalore/ UAS, Dharwad | ICAR/ Agriculture University | To take up seed production activities more efficiently | Taking up seed production on large scale | 4 days | - |

V. Infrastructure

i) Land

| Total Area (ha) | Area Cultivated (ha) | Area occupied by buildings and roads (ha) | Area with demonstration units (ha) |
| --- | --- | --- | --- |
| 20 | 20 | 1.5 | 0.5 |

ii) Buildings

| Admin. Building | Trainees Hostel | Staff Quarters | Demonstration Unit |
| --- | --- | --- | --- |
| Plinth area (m2) | Cost (Rs. in lakhs) | Year | Plinth area (m2) | Cost (Rs. in lakhs) | Year | Plinth area (m2) | Cost (Rs. in lakhs) | Year | No. | Plinth area (m2) | Cost (Rs. in lakhs) |
| 800 | 33.46 | 1996 | 550 | 17.26 | 1997 | 400 | 45.00 | 2006 | Dairy, sheep & goat | 150 | 6.63 |
|  |  |  |  |  |  |  |  |  | Vermicompost | 350 | 5.30 |
|  |  |  |  |  |  |  |  |  | Nursery | 150 | 3.00 |

iii) Vehicles

| Type of vehicle | Model | Actual cost (Rs.) | Total kms. Run | Present status |
| --- | --- | --- | --- | --- |
| Bolero SLX | 2009 | 6.90 | 26304 Kms | Good |
| Mahindra Tractor | 2003 | 5.00 | 64303 hours | Good |
| Motor cycle | 2005 | 0.40 | 77829 Kms | Good |
| Motor cycle | 2009 | 0.50 | 8043 Kms | Good |

- Equipments and AV aids

| Sl. No. | Name of Equipments | Date of purchase | Cost (Rs.in lakhs) | Present status |
| --- | --- | --- | --- | --- |
| 1 | Computer | 2003 | 1.25 | Good |
| 2 | Camera | 1998 | 0.14 | Good |
| 3 | Television | 1999 | 0.28 | Good |
| 4 | Amplifier | 1998 | 0.15 | Good |
| 5 | Fax | 2004 | 0.25 | Good |
| 6 | OHP | 2004 | 0.25 | Good |
| 7 | Hipro lab model gin machine | 2006 | 0.70 | Good |
| 8 | Seed delinting machine | 2006 | 0.18 | Good |
| 9 | Cotton seed sorter | 2007 | 0.50 | Good |
| 10 | Seed treatment drum | 2007 | 0.40 | Good |
| 11 | Lap top Computer | 2007 | 0.54 | Good |
| 12 | LCD | 2007 | 0.56 | Good |
| 13 | Ceramic black board | 2007 | 0.12 | Good |
| 14 | Rotavator | 2008 | 0.92 | Good |
| 15 | Rotary weeder | 2009 | 3.90 | Good |
| 16 | Laser guided land leveler | 2011 | 3.90 | Good |
| 17 | Power tiller | 2011 | 2.72 | Good |
| 18 | Lab equipments for dairy and goatery | 2011 | 0.50 | Good |
| 19 | Generator | 2011 | 1.00 | Good |

VI. Details of SAC meeting conducted during 2010-11

| Sl. No | Date | Major recommendations of SACs which are to be implemented during 2010-11 |
| --- | --- | --- |
| 01 | 25-06-2010 | Give feed back of farmers about technologies demonstrated under FLD |
|  |  | Organise programme on market led extension |
|  |  | Arrange Farmers-Scientist interaction |
|  |  | Facilitate farmers interview with AIR & TV |
|  |  | Develop technology leaders in lead crops & other enterprises |
|  |  | Give more thrust on pulse production |
|  |  | Procurement of seeds produced in FLDs need to be taken |
|  |  | Oraganise training on health, hygiene and nutrition for Anganawadi workers |
| 02 | 04-12-2010 | To test Kadiri-6 and ICGV-91114 varieties of bunch groundnut in Shirahatti block during next Kharif season. |
|  |  | To address problems faced by sericulture farmers through technology assessment and refinement or Frontline Demonstrations |
|  |  | To organize more number of trainings to farmers of Malaprabha command area. |
|  |  | To maintain database of KVK activities |
|  |  | To conduct radio lessons to farmers on Field School through AIR Dharwad |
|  |  | To organize more number of Income Generation Programmes to Women SHG members |

VII. Planning of SAC during 2011-12

| Sl. No | Date planned for conducting SAC meeting during 2011-12 |
| --- | --- |
| 01 | 31-05-2011 |
| 02 | 04-11-2011 |

VIII. Plan of Work for 2011-12

1.  Operational areas details for 2011-12

| Sl. No. | Taluk | Blocks/groups of villages | Major crops & enterprises being practiced | Major problems identified | Identified thrust areas | Existing / New Please State without fail | If existing from which year Please state |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Gadag | Asundi cluster (Comprising of Asundi, Kurthkoti & Mallasamudra ) | Greengram Bunch groundout | Moisture stress Non-availability of quality seeds Incidence of pod borer Incidence of powdery mildew Incidence of storage pest Less market price Moisture stress Incidence of weeds Non-availability of quality seeds Poor shelling percentage Collar rot incidence Drudgery in hand shelling of Groundnut Lack of knowledge on improved practices | Moisture conservation practices Seed production activities Pod borer management Powdery mildew Management of stored grain pest Value addition through grading Moisture conservation practices Chemical Weed Management Seed production Integrated Nutrient Management Management of collar rot Promotion of Groundnut Decorticator Knowledge dissemination through FRC | Existing Existing Existing | 2010-11 2010-11 2010-11 |
|  |  |  | Bt. Cotton | Dropping of squares of tender bolls and leaf reddening Incidence of sucking pest Lack of knowledge on Bt. Cotton cultivation | Integrated Nutrient Management Integrated Pest Management Knowledge dissemination through FRC | Existing | 2010-11 |
|  |  |  | Onion | High incidence of purple blotch Incidence of thrips Bulb Rot High incidence of weeds | Varietal Introduction Thrips management Integrated Nutrient Management and assessment of resistant variety Seed rate, spacing and chemical weed management | Existing | 2010-11 |
|  |  |  | Chilli | High incidence of Murda High incidence of Anthracnose Lack of knowledge on selection of pods for seed purpose | Integrated pest management Anthracnose management Knowledge dissemination through FRC & training | Existing | 2010-11 |
|  |  |  | Rabi Jowar | Moisture stress | Assessment of short duration variety & seed priming | Existing | 2010-11 |
|  |  |  | Brinjal | Incidence of Red Spider mite Incidence of shoot and fruit borer Lack of storage facilities at house hold level | Management of Red Spider mite Integrated Pest Management Promotion of Zero Energy Cool Chamber | Existing | 2010-11 |
|  |  |  | Tomato | Incidence of leaf curl | Leaf curl management | Existing | 2010-11 |
|  |  |  | Livestock enterprises Buffalo rearing | Feeding of dry fodder leading to low milk production Worm infestation | Animal nutrition Deworming | Existing | 2010-11 |
|  |  |  | C.B. Cows | Tick infestation Lack of knowledge on feed management Delayed inter calving period | Tick management Training Nutrition management |  |  |
|  |  |  | Sheep | Incidence of Endoparasites | Parasite management |  |  |
|  |  | Lakkundi cluster (comprising of Lakkundi, Papanashi and Sambhapur) | Chrysanthemum | Incidence of leaf spot Non opening of buds High fluctuating price Lack of knowledge on cultivation practices | Leaf spot management Integrated Nutrient Management Introduction of Aster crop Knowledge dissemination | New | - |
|  |  | Hulkoti cluster (comprising of Hulkoti &Hosalli) | Mango | Incidence of mango hopper & fruit fly Incidence of powdery mildew Incidence of red spider mite | Management of mango hopper & fruit fly Management of powdery mildew Management of red spider mite | Existing | 2010-11 |
|  |  | Soratur cluster (comprising of Soratur, Shirunja & Yalishirunja) | All crops | Lack of knowledge & non-availability of inputs at right time | Knowledge dissemination and supply of inputs through Farm Resource Centre (FRC) established by KVK | New | - |
|  |  | Mulgund cluster (comprising of Mulagund, Harthi, Kanavi) | All crops | Lack of knowledge & non-availability of inputs at right time | Knowledge dissemination and supply of inputs through Farm Resource Centre (FRC) established by KVK Development of master trainer in lead crops and enterprises | New | - |
| 2 | Shirahatti | Bannikoppa cluster (comprising of Bannikoppa, Suganhalli, Hadagali & Muradi villages) | Onion | Incidence of purple blotch Low productivity of local variety Incidence of weeds Bulb rotting Non-availability of quality seeds | Varietal Introduction and purple blotch management Varietal Introduction Chemical weed management INM Seed production | Existing | 2010-11 |
|  |  |  | Bt. Cotton | Dropping of squares of tender bolls and leaf reddening Incidence of sucking pest Lack of knowledge on Bt. Cotton cultivation | Integrated Nutrient Management Integrated Pest Management Knowledge dissemination | Existing | 2010-11 |
|  |  |  | Greengram | Pod shattering Incidence of pod borer Incidence of powdery mildew | Introduction of S-4 variety Management of pod borer Management of powdery mildew | Existing | 2010-11 |
|  |  |  | Little millet | Low productivity due to cultivation of local variety | Introduction of improved variety | Existing | 2010-11 |
|  |  |  | Foxtail millet | Low productivity due to cultivation of local variety | Introduction of improved variety | Existing | 2010-11 |
|  |  |  | Value addition | Lack of awareness on importance of millets in diet No value addition | Awareness on importance of millets in diet Value addition in millets | Existing | 2010-11 |
|  |  |  | Rabi Jowar | Moisture stress | Seed priming and introduction of short duration variety | Existing | 2010-11 |
|  |  |  | Drudgery | Drudgery in cooking | Introduction of envirofit chulha | Existing | 2010-11 |
|  |  |  | Livestock Enterprises Buffalo Sheep Employment | Feeding of dry fodder Worm infestation Endoparasite Incidence of Enterotoximea disease Lack of employment opportunities | Enrichment of dry fodder Deworming Endoparasite management E.T. management Dairy farming, poultry farming | Existing | 2010-11 |
| 3 | Mundaragi | JantliShirur cluster (Comprising of Jantlishirur, Shingatarayanakeri, Petalur & Ramenhalli | Greengram | Moisture stress Poor seed replacement ratio High incidence of pod borer | Moisture conservation practices Seed production and supply of quality seeds Management of pod borer | Existing | 2010-11 |
|  |  |  | Maize | Soil salinity Lack of knowledge on improved technologies | Reclamation of saline soils Dissemination of knowledge | Existing | 2010-11 |
|  |  |  | Bt. Cotton | Dropping of squares of tender bolls and leaf reddening Incidence of sucking pest Lack of knowledge on Bt. Cotton cultivation | Integrated Nutrient Management Integrated Pest Management Knowledge dissemination | Existing | 2010-11 |
|  |  |  | Onion | High incidence of purple blotch Non availability quality seeds Incidence of weeds | Introduction of Arka Kalyan variety & purple blotch management Seed production Chemical weed management | Existing | 2010-11 |
|  |  |  | Groundnut | Low productivity due to local variety Poor shelling percentage Incidence of leaf minor Incidence of leaf spot Non-availability of labour for groundnut shelling | Introduction of new varieties INM Leaf minor management Leaf spot management Introduction of groundnut decorticator | Existing | 2010-11 |
|  |  |  | Rabi Jowar | Moisture stress | Seed priming & introduction of early duration variety | Existing | 2010-11 |
|  |  |  | Health Hygiene | Lack of awareness on balanced diet, Health and Hygiene | Awareness on balanced diet, nutrition and nutrition garden | Existing | 2010-11 |
|  |  |  | Livestock Enterprises Buffaloe | Foot and mouth disease Imbalanced nutrition Worm infestation in milking animals | Foot and mouth disease management Balanced nutrition Deworming | Existing | 2010-11 |
|  |  |  | Sheep | Incidence of Interotoximea | Management of E.T. | Existing | 2010-11 |
| 4 | Naragund | Banahatti cluster (Comprising of Banhatti, Mooganur, Kurlageri) | Maize | Incidence of stem borer Incidence of Army worm Incidence of leaf blight | Management of stem borer Management of Army worm Management of leaf blight | Existing | 2010-11 |
|  |  |  | Bt. Cotton | Incidence of Angular leafspot Incidence of black arm Dropping of squares of tendar bolls and leaf reddening Incidence of sucking pest Lack of knowledge on Bt. Cotton cultivation | Disease management Disease management Integrated Nutrient Management Integrated Pest Management Knowledge dissemination | Existing | 2010-11 |
|  |  |  | Bengalgram | Incidence of wilt Incidence of pod borer | Introduction of new variety IPM | Existing | 2010-11 |
|  |  |  | Drudgery | Drudgery in weeding & inter cultivation | Introduction of twin wheel hoe weedier | Existing | 2010-11 |
|  |  |  |  | Drudgery in harvesting of bengalgram | Introduction of hand gloves | New | - |
|  |  |  | Wheat | Low productivity due to local variety High incidence of weed Drudgery in harvesting of wheat | Introduction of new variety Chemical weed management Introduction of improved sickle | Existing | 2010-11 |
|  |  |  | Sunflower | Poor seed setting Incidence of powdery mildew Incidence of leaf eating caterpillar | INM Management of powdery mildew Management of leaf eating caterpillar | Existing | 2010-11 |
|  |  |  | Livestock enterprises Buffaloe | Low production of milk | Deworming | Existing | 2010-11 |
|  |  |  | Drudgery | Incidence of stored grain pest Drudgery in cooking | Pest management Introduction of envirofit chulla | Existing | 2010-11 |
|  |  |  | Health | Lack of awareness on health hygienie & nutrition | Awareness on health hygienie & | Existing | 2010-11 |
| 5 | Ron | Jakkali Cluster (Comprising of Jakkali, Maranabasari and Bhudihal Village) | Green gram | Non-availability of quality seeds Incidence of Pod borer and leaf defoliator Incidence of powdery mildew | Seed production Pod borer & caterpillar Management Powdery mildew Management | New | - |
|  |  |  | Spreading groundnut | Imbalanced nutrition Incidence of root grub Incidence of collar rot Incidence of leaf minor | INM Root grub management Collar rot management Leaf minor management | New | - |
|  |  |  | Onion | Non-availability of quality seeds Incidence of purple blotch Imbalanced nutrition Weed problem | Seed production Purple blotch management INM Weed management | New | - |
|  |  |  | Chilli | Non-availability of quality and pure seeds Incidence of murda complex Incidence of powdery mildew | Seed production Murda complex management Powdery mildew management | New | - |
|  |  |  | Desi Cotton | Non-availability of quality seeds | Seed production | New | - |
|  |  |  | Bengal gram | Incidence of wilt and rust Incidence of Pod borer | Wilt and rust management Pod borer management | New | - |
|  |  |  | Rabi Jowar | Low productivity of Maladandi variety Moisture stress | Variety replacement Seed priming | New | - |
|  |  |  | Livestock Enterprises Mitch animals | Imbalanced nutrition Incidence of ticks | Nutrition management Management of ticks | New | - |
|  |  |  | Sheep | Incidence of worms | Deworming | New | - |
|  |  |  | All Crops | Lack of knowledge on improved practices and non-availability of extension worker | Development of master trainers | New | - |
|  |  | Hirehal cluster comprising of 23 villages, (650 farmers registered for Grameena suvidha Kendra) | Lead crops & enterprises | Lack of knowledge on improved practices and non- availability of quality seeds | Kharif campaign Rabi Campaign Supply of improved seeds Supply of literature | New | - |

2. Details of thrust areas under which interventions are planned for 2011-12

- Crops

| Thrust areas | Crops to be covered | Interventions planned |
| --- | --- | --- |
| Moisture conservation practices | Greengram | Refinement of resource conservation technology, Kharif campains on Compartment bunding, Training, Supply of literature, TV coverage and Video shows |
|  | Groundnut | Refinement of resource conservation technology, FLD on pair row method of sowing, Kharif campain, compartment bunding, training, Supply of literature, TV coverage and Video shows |
|  | Rabi Jowar | Refinement of resource conservation technology, Training and Supply of literature |
| Soil reclamation | Maize | Soil testing, Soil amendments with Gypsum, Training and Supply of Literature |
| Integrated Nutrient Management | (i) Groundnut | Application of boron, soil testing, FLD on INM, Training, supply of micronutrient and biofertiliser, supply of literature and field day |
|  | (ii) Sunflower | Soil testing, FLD on INM, Training, Field day, Mobile message and Literature |
|  | (iii) Chrysanthemum | Assessment of application of growth regulators (GA) for early bud opening, FLD on INM, Trainings, Seminars, Literature and TV coverage |
| Integrated Crop Management | (i) Bt. Cotton | Soil testing, FLD on production technology, Training, Literature, Field day, Mobile message and TV coverage |
|  | (ii) Greengram | Soil testing, FLD on selection-4 variety along with ICM, Training, Field day, Supply of literature, Mobile message and Supply of seeds |
|  | (iii) Bengalgram | Soil testing, FLD on JG-11 variety along with ICM, Training, Field day, Supply of literature, Mobile message, TV coverage and Supply of seeds |
|  | (iv) Groundnut | Soil testing, FLD on GPBD-4, TAG-24 variety along with ICM, Training, Field day, Supply of literature, Mobile message, Supply of seeds and TV coverage |
|  | (v) Desi cotton | Soil testing, FLD on DDHC-11 variety along with ICM, Training, Field day, Supply of literature, Mobile message, Supply of seeds and TV coverage |
|  | (vi) Brinjal | FLD on IPM, Training, Supply of literature, Mobile message and TV coverage |
| Weed Management | (i) Onion | FLD on weed management, Method Demonstration, Training, Supply of literature and Mobile message |
|  | (ii) Groundnut | FLD on weed management, method demonstration, Training, Supply of literature and Mobile message |
| Assessment of variety | (i) Groundnut | Assessment of kadiri-6 and ICGV-91114 for drought tolerance, Training, Field day and Farmers meeting |
|  | (ii) Onion | Assessment of resistant synth-6 variety for bulb rotting, Training, Supply of literature, TV & Radio coverage |
| Introduction of varieties | (i) Little millet | FLD on GPU-28, Training, Field day and Supply of literature |
|  | (ii) Foxtail millet | FLD on HMT-1, Training, Field day and Supply of literature |
|  | (iii) Rabi Jowar | FLD on CSV-22 & Anuradha, Training, Field day and Supply of literature |
|  | (iv) Wheat | FLD on UAS-304, Training, Field day and Supply of literature |
| Disease management | (i) Chilli | Assessment of Arka Meghana for powdery mildew resistant and Training |
|  | (ii) Onion | FLD on Arka Kalyan for purple blotch management, FLD on foliar spray for the management of purple blotch and Training |
|  | (iii) Chilli | Mango thrips and mite |
|  |  | Assessment of difenconazole for Anthracnose management |
| Introduction of alternate crops | (i) Aster | FLD on Aster crop introduction, Supply of literature and Field day |
|  | Fruit crops | Training on Dry Land Horticulture, Exposure visits, Supply of literature and Farm advisory service |
| Seed Production | Greengram, Groundnut, Onion, Desi Cotton, Bengalgram, Rabi Jowar & Vegetables | KVK-Farmers’ partnership mode on seed production |
| Dissemination of knowledge | All crops | Farm Resource Centres, Kharif & Rabi Campaign, Developing Master Trainers. Monthly news letter, Extension bulletin, Mobile message, Field school, Technology Week and Exhibitions. |

B. Livestock, poultry, fisheries

| Thrust areas | Livestock/ poultry / fisheries to be covered | Interventions planned |
| --- | --- | --- |
| Animal Nutrition | Buffaloe | FLD on Enrichment of Dry Fodder, supply of literature and Animal Health Camp |
|  | Cross Bred cows | FLD on fodder crop cultivation, training, supply of literature, field day and TV & radio coverage |
| Ecto-Endo parasite management | Buffaloe and Sheep | FLD on Ecto-Endo parasite management, training, Health camp, Literature and Mobile message services |
| Tick management | Cross bred cows | On Farm Testing, Training and Awareness Camps |
| Self Employment | Dairy units, Sheep & goat rearing units | Vocational training and Bank linkages through SGSY |

C. Others

| Thrust areas | Interventions planned |
| --- | --- |
| Management of stored grain pest | Assessment of management of stored grain pest and Training on stored grain pest |
| Drudgery reduction (Farm) | FLD on Groundnut decorticator, improved sickle and twin wheel hoe weeder |
| Drudgery reduction (Cooking) | FLD on Envirofit chulla |
| Health & hygiene | Training |
| Nutrition | Training on Terrace gardening |
| Value addition | Training |

## 3.1. Abstract of Interventions Proposed Based On the Identified Problems during 2011-12

| Crop/ Enterprise | Thrust area | Identified Problem | Planned Interventions |
| --- | --- | --- | --- |
|  |  |  | Title of technology to be assessed under OFT | Title of technology to be refined under OFT | Title of FLD | Title of the Training | Type of Extension activities | Details of technological products produced and supplied (specify name of product, variety, breed etc.) |
| Greengram | Sustainable production | Abiotic stress | - | Refinement of in-situ moisture conservation technology | - | Sustainable production of greengram | Field day, Demonstrations & campaigns | - |
|  | ICM | Low productivity due to pod shattering, powdery mildew and pod borer | - | - | ICM in S-4 variety | ICM | FRC activity, field day, literature & mobile messages | S-4 variety of greengram |
|  | Seed production | Non-availability of quality seeds | - | - | - | Seed production | Literature& FRC activities | S-4 variety of greengram |
|  |  | Labour problem for weeding | - | - | Introduction of TWH weeder | Drudgery reducing equipments | Literature& method demonstrations | Supply of TWH weeder |
|  | Management of stored grain pest | Incidence of pulse beetle | Assessment of management of incidence of grain storage pests in pulses at house hold level | - | - | 1. Manage ment of stored grain pest 2. Prepar ation of neem baits | Literature & method demonstrations | Neem baits, plastic bottles & cotton cloth bags |
| Bunch groundnut | Assessment of variety | Abiotic stress | Assessment of Kadiri-6 & ICGV-91114 for drought tolerance | - | - | ICM | Exhibition,Field day, literature & campaigns | K-6 & ICGV-91114 variety |
|  | Introduction of GPBD-4 with ICM | Low productivity due to cultivating local variety, imbalanced nutrition, leaf minor & root grub incidence | - | - | ICM | ICM | Field days, literature, seed production, mobile massages & campaigns | GPBD-4 & TAG-24 variety |
|  | Collar rot management | Collar rot | Assessment of seed treatment with vitawax & trichoderma for collar rot management | - | - | Collar rot management | Mobile message& Literature | - |
|  | Drudgery | Drudgery in hand shelling of Groundnuts | - | - |  | Drudgery reducing equipments- Groundnut Decorticator | Exhibition | Groundnut decorticator |
|  | Chemical weed management | Weed problem | - | - | Chemical weed management | Weed management | Literature, field day & demonstrations | - |
| Onion Chilli | ICM & introduction of Arka Kalyan | Low productivity due to purple blotch, sucking pest & weed | Assessment of Quizalfop ethyl for chemical weed management in onion | - | ICM in Arka Kalyan | ICM | Demonstrations, Field day, Literature, Mobile message& campaign | Arka Kalyan variety |
|  | Seed production | Non -availability of seeds | - | - | - | Seed production | Literature | Arka Kalyan variety |
|  | Disease management | Anthracnose | Assessment of difenconozole for management of anthracnose | - | - | Anthracnose | - | - |
|  | Pure seed | Non -availability of quality seeds | - | - | - | Training on selection of pods for seed purpose | Literature | - |
|  | Murda complex management | Murda complex | Assessment of integrated approach for management of murda complex | - | - | Murda complex management | Field day, literature | - |
| Bt. Cotton | Knowledge dissemination | Lack of knowledge on Bt. Cotton cultivation | - | - | ICM in Bt. Cotton | Training on production technology | Literature, FRC activities & Mobile message | - |
| Desi cotton | ICM | Moisture stress, low productivity & non- availability of quality seed | - | - | ICM in DDHC-11 variety | ICM | Demonstrations, Field day & literature campaign | Seed production of DDHC-11 |
|  | Drudgery | Drudgery in plucking and storage of plucked cotton | Assessment of cotton bag for plucking and storage of plucked cotton | - | - | Drudgery reducing equipments | Method demonstration | Cotton bags |
| Bengalgram | Management of wilt and pod borer | Incidence of wilt and pod borer | - | - | Introduction of JG-11 variety with ICM | ICM | Field day, literature, seed production & mobile message | JG-11 seeds |
|  | Drudgery | Drudgery and increased cost in weeding and inter cultivation | - | - | Demonstration of twin wheel hoe weeder | Drudgery reducing equipments | Literature | Twin wheel hoe weeder |
|  |  | Drudgery in harvesting of bengalgram | - | - | Demonstration of hand gloves for harvesting of bengalgram | Drudgery reducing equipments | Exhibition of hand gloves during field day | Hand gloves |
| Rabi Jowar | - | Moisture stress, low productivity of M 35-1 variety | Assessment of Anuradha variety in shallow soil for high productivity |  | Seed priming & introduction of CSV-22 | ICM | Field day, seed production, mobile message & demonstration | CSV-22 seeds |
| Maize | Soil reclamation | Soil sodicity | - | - | Soil reclamation | Soil fertility management | Literature & field day | - |
|  | INM | Imbalanced nutrition | - | - | INM | INM | Literature& mobile messages | - |
| Wheat | Varietal introduction | Low productivity of Nirmal variety due to rust incidence | - | - | Introduction of UAS-304 for rust resistance | Disease management | Field day & mobile messages | - |
|  | Weed management | Weed problem | - | - | Chemical weed management | Weed management | Field day & mobile messages | - |
|  | Drudgery | Increased drudgery in harvesting wheat | - | - |  | Drudgery reducing equipments | Exhibition, Demonstration & literature | Improved sickle |
| Brinjal | Pest management | Shoot & fruit borer and red spider mite | - | - | IPM in Brinjal | Pest management | Field day & literature | - |
| Tomato | Disease management | Leaf curl | - | - | Foliar spray of imida cloprid | Disease management | Field day & mobile messages | - |
| Chrysanthemum | Growth regulator | Non opening of buds, imbalance nutrition & leaf spot disease | - | - | Application of GA for early bud opening & INM | INM | Field day, literature & method demonstrations | - |
|  |  |  | - | - | Leaf spot management through foliar spray of propiconozole | Disease management | Field day, literature & mobile message | - |
| Aster | Introduction of Aster crop | Fluctuating prices of Chrysanthemum |  |  | Introduction of Aster crop | Training | Field day, literature, mobile message |  |
| Foxtail millet | Introduction of new variety | Low productivity of local variety (Hurupal) | - | - | Introduction of HMT-1 variety | ICM | Field day, seed production | HMT-1 |
|  | Value addition | Lack of awareness on importance of potential grains in diet | - | - |  | Importance of potential grains in diet and value addition | Exhibition & literature | - |
| Mulberry | Pest management | Sucking pest | - | - | Sucking pest management through release of predators | Pest management | Literature | - |
| Mango | Pest management | Mango hopper & fruit fly | - | - | Menace of mango hopper & fruit fly | Pest management | Literature& mobile message | - |
| Wheat & Jowar | Fortification of wheat products with soya | Lack of knowledge and utility of soys in daily diet as it is a high valued biological protein |  | - | Fortification of wheat chapatti and jowar roti with soya | Awareness on health nutrition with high valued biological protein | Exhibition | - |
| Envirofit chullha | Fuel saving and drudgery reducing equipments | To reduce drudgery in cooking | - | - | Demonstration of envirofit chullha | Fuel saving devices | Exhibition & Literature | Envirofit chullha |
| Buffaloes | Animal nutrition | Feeding of low quality & quantity of dry fodder | - | - | Enrichment of dry fodder | Importance of animal nutrition | Animal health cams &, literature | Salt & Jaggery |
| CB Cows | Animal nutrition | Delayed heat, low milk yield & less fat % in milk in post calving dairy cross bred cows | Assessment of supplementation of bypass fat in post calving dairy cows | - | Promotion of Napier fodder variety | Importance of fodder crop | Field day & literature | Hybrid napier grass Perennial Sorghum Ginuea grass |
| Buffalo | Endoparasite management | Low quantity of milk production | - | - | Oral administration of bolus fenbendazole | Awareness of deworming to milking animals | Health camp, literature & mobile message | Bolus fenbendazole-3gm |
| Sheep | Ecto-Endo parasites management | Low weight & low quality & quantity hair texture | - | - | Oral administration of closental suspension | Control of Ecto-Endo parasites | Literature& mobile message | Closantel liquid @ 1 ml/10 kg body weight |
| Livestock | Animal Nutrition | Non-availability of green fodder | - | - | Demonstration of Fodder Bank | Importance of green fodder in animal nutrition | Literature | Grass slips & seeds |

3.2. Target set for number of interventions to be implemented during 2011-12

| S. No | Particulars of intervention | Target number / Quantity |
| --- | --- | --- |
| 01 | On Farm Trial | 125 (8 crops/enterprises) |
| 02 | Front Line Demonstration | 461(27 crops/enterprises) |
| 03 | Training Programmes |  |
|  | Farmers and farm women | 104 |
|  | Rural Youth | 13 |
|  | Extension personnel | 17 |
|  | Sponsored programmes | 39 |
|  | Vocational Programmes | 11 |
| 04 | Extension Programmes |  |
|  | Field Day | 6 |
|  | Kisan Mela | 1 |
|  | Kisan Ghosthi | 3 |
|  | Exhibition | 4 |
|  | Film Show | 50 |
|  | Method Demonstrations | 50 |
|  | Seminars | 3 |
|  | Workshop | 2 |
|  | Group meetings | 30 |
|  | Lectures delivered | 15 |
|  | Newspaper coverage | 15 |
|  | Radio coverage | 5 |
|  | TV coverage | 10 |
|  | Radio Programmes | 10 |
|  | TV Programmes | 10 |
|  | Publications | 5 |
|  | Popular articles | 10 |
|  | Extension Literature | 5 |
|  | Advisory Services | 100 |
|  | Scientific visit to farmers’ fields | 250 |
|  | Farmers’ visits to KVK | 30 batches |
|  | Diagnostic visits | 10 |
|  | Field visits | 100 |
|  | Exposure visits | 5 |
|  | Ex-trainees meet | 5 |
|  | Agriculture Camps | 2 |
|  | Clinic day | - |
|  | Soil health Camp | 5 |
|  | Animal Health Camp | 5 |
|  | Agri mobile clinic | - |
|  | Soil test campaigns | 10 |
|  | Farm Science Club Conveners meet | - |
|  | Self Help Group Conveners meetings | 20 |
|  | Mahila Mandals Conveners meetings | - |
|  | Special Day celebrations | 2 |
|  | Awareness campaigns | 5 |
|  | Others (Pl. specify) | - |
| 05 | Production and supply of seed materials |  |
|  | 1) Cereals | 25 Qtl |
|  | ii) Oilseeds | 20 Qtl |
|  | iii) Pulses | 20 Qtl |
|  | iv) Vegetables | 1 Qtl |
|  | v) Flower crops | 2 Kg |
|  | vi) Others (Specify) | - |
|  | Production and supply of Planting materials |  |
|  | Fruits | 2000 |
|  | Spices | - |
|  | Vegetables | 50000 |
|  | Forest species | 5000 |
|  | Ornamental crops | - |
|  | Plantation crops | - |
|  | Others | - |
|  | Production and supply of bio-products |  |
|  | Bio agents | - |
|  | Bio fertilizers | 10 Qtl |
|  | Bio pesticides | 1 Qtl |
|  | Production and supply of livestock material |  |
|  | Sheep | 10 |
|  | Poultry birds | - |
|  | Goat | 10 |
|  | Fisheries | - |
|  | Others (Specify) | - |
| 06 | Number of soil samples to be analyzed | 600 |
| 07 | Number of water samples to be analyzed | 200 |

## 4.   Plan of Technology Assessment and Refinement for 2011-12

Assessment : 1

| a) | Title of technology assessed | : | Assessment of Kadari-6 and ICGV-91114 groundnut varieties for drought tolerance |
| --- | --- | --- | --- |
| b) | No. of Trials | : | 9 |
| c) | Problem Definition | : | Erratic rainfall & long dry spells result in low productivity in existing varieties of groundnut |
| d) | Production system and thematic area | : | Medium & big farmers production system under rainfed situation and varietal assessment |

e) Details of the technologies with budget for critical inputs

| Technology Options | Details of the technology assessed | Area in ha. | Year of release of the Technology Option | Source of the technology | Major Parameter of assessment | Other Parameters | Critical Inputs for Technology |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) |
| 1) Farmer’s practice | Usage of local variety (TMV-2) | 0.4 | 1970 | TNAU, Coimbatore | No. of pods/plant Pod yield/ha |  | NIL |
| 2) Recommen-ded practice | GPBD-4 variety | 0.4 | 2003 | UAS, Dharwad | No. of pods/plant Pod yield/ha | - | GPBD-4 (Pods) | 0.75 Qt | 2625 | 2625 |
| 3) Assessment proposed | Kadari-6 | 0.4 | 2008 | ARS,Kadiri under ANGRAU, Hyderabad | No.of pods/plant Pod yield/ha | - | Kadari-6 (pods) | 0.75 Qt | 3000 | 3000 |
|  | ICGV-91114 | 0.4 | 2008 | ICRISAT, Hyderabad | No. of pods/plant Pod yield/ha |  | ICGV-91114 | 0.75 Qt | 3000 | 3000 |
| Total | 8625 |

f)   Cost per trial : Rs.8625

g)  Total cost for the assessment :  Rs.39000

Assessment : 2

| a) | Title of technology assessed | : | Assessment of Vitawax for collar rot management in Bunch Groundnut |
| --- | --- | --- | --- |
| b) | No. of Trials | : | 30 |
| c) | Problem Definition | : | Incidence of collar rot disease is affecting the groundnut productivity. The disease occurs immediately after germination of crop and it will continue throughout the crop season. The yield loss is about 25-40% |
| d) | Production system and thematic area | : | Medium and big farm production system under rainfed situation & Disease management |

e) Details of the technologies with budget for critical inputs

| Technology Options | Details of the technology assessed | Area in ha. | Year of release of the Technology Option | Source of the technology | Major Parameter of assessment | Other Parameters | Critical Inputs for Technology |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) |
| 1) Farmer’s practice | Seed treatment with Captan @ 2.5 gm | 0.2 | - | - | % of disease index Yield | No. of plant die in sqmt area | NIL |
| 2) Recomm-ended practice | Seed treatment with Trichoderma @ 4 gm/Kg seed | 0.4 |  | UAS, Dharwad | % of disease index Yield | No. of plant dia in sqmt area | Trichoderma | 200 gm | 40 | 250 |
| 3) Assessm-ent proposed | Seed treatment with Vitawax @ 3 gms | 0.4 |  | DOR, Hyderabad | % of disease index Yield | No. of plant die in sqmt area | Vitawax | 150 gm | 210 |  |
| Total | 250 |

f)   Cost per trial : Rs.250

g)  Total cost for the assessment : Rs. 7500

Assessment :  3

| a) | Title of technology assessed | : | Assessment of Anuradha variety for increasing productivity of rabi sorghum in shallow soils |
| --- | --- | --- | --- |
| b) | No. of Trials | : | 25 |
| c) | Problem Definition | : | Yields are very low in shallow soils |
| d) | Production system and thematic area | : | Rainfed production system & Varietal assessment |

e) Details of the technologies with budget for critical inputs

| Technology Options | Details of the technology assessed | Area in ha. | Year of release of the Technology Option | Source of the technology | Major Parameter of assessment | Other Parameters | Critical Inputs for Technology |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) |
| 1) Farmer’s practice | Un purified M 35-1 variety seeds | 0.4 |  |  | Grain yield/ha Fodder yield/ha | Height of the plant Duration Organoleptic evaluation of roti | NIL |
| 2) Recommen-ded practice | M 35-1 (Pure seeds) | 0.4 |  | UAS, Dharwad | Grain yield/ha Fodder yield/ha | Height of the plant Duration Organoleptic evaluation of roti | M 35-1 variety seeds | 3 Kg | 75 | 75 |
| 3) Assessment proposed | Anuradha | 0.4 | 2009 | MPKV-Rahuri, Maharastra | Grain yield/ha Fodder yield/ha | Height of the plant Duration Organoleptic evaluation of roti | Anuradha variety seeds | 3 Kg | 120 | 120 |
| Total | 195 |

f)   Cost per trial : Rs.195

g)  Total cost for the assessment : Rs. 4875

Assessment : 4

| a) | Title of technology assessed | : | Assessment of management of grain storage pest incidence in pulses at household level |
| --- | --- | --- | --- |
| b) | No. of Trials | : | 15 |
| c) | Problem Definition | : | In the identified cluster of villages, more than 90% of farmwomen face the problem of incidence of pulse beetle in stored grains. The recommended practice of using Aluminium phosphide is not practical for storage of pulses in smaller quantities at household level. Moreover the usage of chemical pesticides may pose health hazards to humanbeings |
| d) | Production system and thematic area | : | Greengram production system and Grain storage. |

e) Details of the technologies with budget for critical inputs

| Technology Options | Details of the technology assessed | Area in ha. | Year of release of the Technology Option | Source of the technology | Major Parameter of assessment | Other Parameters | Critical Inputs for Technology |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) |
| 1) Farmer’s practice | 1) No treatment | - | - |  |  |  | NIL |
| 2) Recomm-ended practice | Aluminium Phosphide @ 2-3 tablets/ton (Not relevant at household level) |  |  |  |  |  |  |  |  |  |
| 3) Assessm-ent proposed | 1) Preparation of neem baits from a mixture of neem leaves (50 gms), ginger powder (30 gms) & sweet flag ( 5-10 gms)/Kg of pulses 2) Chilli flakes @ 15-20 gms/Kg of pulses 3) Boric powder@5-10 gms/Kg of pulses 4) Oil smearing @ 5% |  | 2002 | CIKS, Chennai (Centre for Indian Knowledge Systems) and UAS, Dharwad | No. of insects/ 100 gms | Cost incurred for storage | Ginger powder | 4 Kg | 450 | 1800 |
|  |  |  |  |  |  |  | Sweet flag | 3 Kg | 250 | 750 |
|  |  |  |  |  |  |  | Labour charges for neem bait preparation | 15 | 1500 | 1500 |
|  |  |  |  |  |  |  | Chilli flakes | 3 Kg | 150 | 450 |
|  |  |  |  |  |  |  | Boric powder | 1.5 Kg | 600 | 1500 |
|  |  |  |  |  |  |  | Edible Oil | 6 Kg | 80 | 480 |
|  |  |  |  |  |  |  | Cotton bags | 90 | 30 | 2700 |
| Total | 9180 |

f)   Cost per trial: Rs.612

g)  Total cost for the assessment: Rs.9180

Assessment : 5

| a) | Title of technology assessed | : | Assessment of Cotton bags for storage of plucked cotton |
| --- | --- | --- | --- |
| b) | No. of Trials | : | 5 |
| c) | Problem Definition | : | Farmwomen keep the plucked cotton in old clothes which is tied to their waist. This causes increased load and drudgery to farmwomen. |
| d) | Production system and thematic area | : | Small and big production system & Drudgery Reduction |

e) Details of the technologies with budget for critical inputs

| Technology Options | Details of the technology assessed | Area in ha. | Year of release of the Technology Option | Source of the technology | Major Parameter of assessment | Other Parameters | Critical Inputs for Technology |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) |
| 1) Farmer’s practice | Old clothes | 0.5 | - |  |  |  | NIL |
| 2) Assessme- nt proposed | Cotton bags | 0.5 |  | - | Total quantity of plucked cotton stored in cotton cot bag Drudgery as felt by farmwomen | Suitability Acceptance | Cottonbags Model1 Model2 Model3 | 5 5 5 | 200 200 200 | 1000 1000 1000 |
| Total | 3000 |

f)   Cost per trial : Rs.600

g)  Total cost for the assessment : Rs. 3000

Assessment : 6

| a) | Title of technology assessed | : | Assessment of Spray of Difenconazole for management of Anthracnose in chilli |
| --- | --- | --- | --- |
| b) | No. of Trials | : | 12 |
| c) | Problem Definition | : | The disease appears on ripened fruit stalk and spread along with the stem and in severe cases cause die back symptom on the chilli plant. The fruit with many spot drop-off pre-maturely, resulting in the crop loss up to 30-45% |
| d) | Production system and thematic area | : | Medium and big farm production system under rainfed situation & Disease management |

e) Details of the technologies with budget for critical inputs

| Technology Options | Details of the technology assessed | Area in ha. | Year of release of the Technology Option | Source of the technology | Major Parameter of assessment | Other Parameters | Critical Inputs for Technology |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) |
| 1) Farmer’s practice | Spraying Dithane M-45 @ 2 gm/lit | 0.2 | - | - | % of disease index Yield | Quantity of disease affected chilli pods | NIL |
| 2) Recomm-ended practice | Spraying COC(Copper Oxy Chloride @ 3 gms/lit or Mancozeb @ 2 gm /lit (two times spray) | 0.2 |  | UAS, Dharwad | % of disease index Yield | Quantity of disease affected chilli pods | Copper Oxy Chloride (COC) | 500 gm | 243 | 938 |
| 3) Assessm-ent proposed | Spraying of Difenconazole @ 1 ml/lit with Trichoderma Viridae @ 3 gm/lit (two times spray) | 0.2 |  | UAS, Dharwad & TNAU, Coimbatore | % of disease index Yield | Quantity of disease affected chilli pods | Difenconazole & Trichoderma | 250 ml 500 gm | 620 75 |  |
| Total | 938 |

f)   Cost per trial in Rs. : Rs.938

g)  Total cost for the assessment in Rs.: 11256

Assessment : 7

| a) | Title of technology assessed | : | Assessment of Quizalfop ethyl for chemical weed management in onion |
| --- | --- | --- | --- |
| b) | No. of Trials | : | 9 |
| c) | Problem Definition | : | The major constraints in onion cultivation is increased weed competition, that is leading to drastic reduction in yield & quality. |
| d) | Production system and thematic area | : | Rainfed & weed management |

e) Details of the technologies with budget for critical inputs

| Technology Options | Details of the technology assessed | Area in ha. | Year of release of the Technology Option | Source of the technology | Major Parameter of assessment | Other Parameters | Critical Inputs for Technology |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) |
| 1) Farmer’s practice | Manual weeding | - |  |  |  |  | NIL |
| 2) Recommended practice | Spray of Pendimethaline @ 4 ml/lit as a pre emergent weedicide | 1.2 | 1998 | UAS, Dharwad |  | - | Pendimethline | 1 ltr | 500 | 500 |
| 3) Assessment proposed | Spray of Pendimethaline @ 4 ml/lit as a pre emergent & Quizalfop ethyl @ 1 ml/lit as a post emergent | 1.2 | 2004 | Agriculture University, Bihar | % of weed control B.C Ratio Bulb yield | - | Pendimethline Quizalfop ethyl | 1 ltr 1 ltr | 500 1400 | 500 1400 |
| Total | 2400 |

f)   Cost per trial : Rs.2400

g)  Total cost for the assessment : Rs. 21600

Assessment : 8

| a) | Title of technology assessed | : | Assessment of supplementation of bypass fat in post calving dairy cows |
| --- | --- | --- | --- |
| b) | No. of Trials | : | 10 |
| c) | Problem Definition | : | Delayed heat, low milk yield & less fat % in milk in post calving dairy cross bred cows. |
| d) | Production system and thematic area | : | Nutritional management in milking cross bred cows |

e) Details of the technologies with budget for critical inputs

| Technology Options | Details of the technology assessed | Area in ha. | Year of release of the Technology Option | Source of the technology | Major Parameter of assessment | Other Parameters | Critical Inputs for Technology |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) |
| 1) Farmer’s practice | Feeding dry fodder, green fodder, groundnut cake & boosa | - | - |  |  |  | NIL |
| 2) Recomm-ended practice | Feeding dry fodder, green fodder, concentrated feed @ 1 Kg/2.5 lit of milk production & Mineral mixture 50 gm/day | 25 |  | KVAFSU, Bidar | Period for induced (No. of open days) Milk production/day Fat % |  | Mineral mixture | 3 Kg | 140 | 420 |
| 3) Assessm-ent proposed | Feeding dry fodder, green fodder, concentrated feed @ 1 Kg/2.5 lit of milk production & Mineral mixture 50 gm/day & by pass fat 150 gm/day/cow for three months period | 25 |  | NIANP, Bangalore | Heat period (No. of open days) Milk production/day Fat % |  | Mineral mixture By pass fat | 3 Kg 9 Kg | 140 60 | 420 540 |
| Total | 1380 |

f)   Cost per trial : Rs.1380

g)  Total cost for the assessment : Rs.13800

5. Frontline Demonstrations

| Category | Problem identified | Thematic area | Current status of yield q/ ha / number / litres/unit / kg/unit | Technology to be demonstrated | Source | Year of release | Local check | Area in ha / No. of units / animals /birds | No. of demonstrations | Critical inputs to be provided per demonstrations | Total cost for all demonstrations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | District average | Potential | Farmers |  |  |  |  |  |  | Name & Quantity (kg/ha) or number/unit | Cost (Rs./ha) or Rs./unit |  |
| Oilseeds |
| Groundnut (Summer-Bunch type) (Ron block) | Low productivity due to use of local variety | ICM in TAG-24 | 12 | 22-25 | 15-16 | Demonstration of TAG-24 variety Seed treatment with Bio-fertiliser Seed treatment with Trichoderma | UAS Dharwad | 1991-92 | *Local variety (TMV-2) Nil Nil | 2 | 5 | TAG-24 (pods)-250 Kg Rhizobium @ 2.5 Kg/ha PSB @2.5 Kg/ha Trichoderma @ 1 Kg/ha | 8750 100 100 150 | 18200 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | 9100 |  |
| Groundnut (Bunch type) | Incidence of root grub (Ron & Shirahatti block) | Management of root grub |  |  |  | Seed treatment with Chlorpyriphos (6.25 ml/Kg seed) | DOR, Hyderabad |  | - | 6 | 15 | Chloropyriphos – 1 lit/ha | 210 | 1260 |
|  | High incidence of weed problem (Gadag block) | Chemical weed management |  |  |  | Pre-emergence application of Pendimethalin @ 1 Kg/ha | UAS, Dharwad |  | By interculture & hand weeding | 2 | 5 | Pendimethalin @ 1 Kg/ha | 630 | 1260 |
| Pulses |
| Greengram | Moisture stress Pod shattering | ICM in Greengram | 3.18 | 8-10 | 5-6 | Moisture conservation practices Demonstration of Selection-4 variety Usage of biofertiliser | UAS, Dharwad | 2002-03 | Nil Usage of local seeds (China moong) Nil | 10 | 25 | Seeds Selection-4 @ 12.5 Kg/ha Biofertiliser Rhizobium @ 500 gm/ha PSB @ 500 gm/ha Trichoderma @ 100 gm/ha | 1055 | 10550 |
| Bengalgram | Incidence of wilt | ICM | 10 | 20-25 | 16-18 | Demonstration of JG-11 variety Seed treatment with trichoderma Usage of biofertiliser | UAS, Dharwad | 2007 | Usage of local seeds (Annigeri-1) Nil Nil | 8 | 20 | Seeds (JG-11) @ 62.5 Kg/ha Trichoderma @ 375 gm/ha Carboxin @ 60 gm/ha Rhizobium @ 1 Kg/ha PSB@1 Kg/ha | 2680 | 21440 |
| Cereals & millets |
| Foxtail millet | Low productivity due to cultivation of local variety | Introduction of HMT-1 variety & value addition |  | 18-20 | 10-20 | Demonstration of HMT-1 variety | UAS, Dharwad | 2004-05 | Usage of local seeds | 10 | 25 | Seeds (HMT-1) @ 10 Kg/ha | 400 | 4000 |
| Rabi jowar | Lack of high yielding variety for deep black soils | Introduction of CSV-22 variety | 5.75 | 14-15 | 8-10 | Demonstration of CSV-22 variety | UAS, Dharwad | 2009 | Usage of local seeds | 10 | 25 | Seeds (CSV-22) @8 Kg/ha | 240 | 2400 |
| Wheat | * Low yield due to incidence of wilt disease * High incidence of weed problem (Wheat, Irrigated) | ICM in UAS-304 | 10.50 | 30-35 | 24-25 | *Demonstration of UAS-304 variety *Post emergence application of 2,4-D, 80 W.P @ 2.5 kg/ha | UAS, Dharwad | 2010 | Usage of DWR-162 & local seeds By hand weeding | 2 | 5 | Seeds (UAS-304) @ 150 Kg/ha 2.4-5 80 WP @ 2.5 Kg/ha | 6625 | 13250 |
| Maize | Low yield due to imbalanced nutrition Incidence of turcicum leaf blight | ICM |  | 60-65 | 45-50 | Application of ZnSo4 & FeSo4 Management of turcicum leaf blight | UAS, Dharwad |  | Nil Nil | 5 | 10 | ZnSo4 @ 25 Kg/ha FeSo4 @ 25 Kg/ha DiethaneM-45 @ 750 gm/ha | 2088 | 10440 |
| Maize | Low yield due to sodic soils | Reclamation of problematic soil |  | 60-65 | 30-35 | Compartment bunding Application of Gypsum, vermicompost & biofertilisers | UAS, Dharwad |  | Nil | 2 | 5 | Gypsum @ 2.5 ton/ha Vermicompost @ 5 Qtls/ha PSB @5 Kg/ha Azospirillum @ 5 Kg/ha | 10900 | 21800 |
| Vegetables |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Onion | High incidence of purple blotch in onion Sulphur deficiency reduces yield & keeping quality Incidence of thrips and purple blotch in onion | ICM | 2.4 ton/ha | 14 ton/ha | 2.4 ton/ha | Introduction of purple blotch tolerant variety Arka Kalyan Sulphur management in onion Foliar spray of Lamda Cylhothrin and @ 0.75 ml/lit Difenconazole @ 1 ml/lit | IIHR | 1990 | Use of local variety - Dimethoate | 12 | 12 | Seeds @ 1 Kg/ha Sulphur @ 50 Kg/ha Lamda Cylhothrin @ 350 ml/ha Difenconazole @350 ml/ha | 600 1000 175 1365 | 37680 |
| Brinjal | Incidence of shoot & fruit borer Incidence of Red spider mite | IPM in Brinjal | 178 | 460 | 300 | Foliar spray of Carbosulfan @ 2 ml/lit Foliar spray of Dicofol @ 2.5 ml/lit | UAS, Dharwad |  | Monocrotophos | 1.2 | 3 | Carbosulfan @ 750 ml/ha Dicofol @750 ml/ha Water traps @ 8 No./ha Lucin lures @ 24 No./ha | 420 330 360 288 | 1680 |
| Tomato | Incidence of leaf curl | Management of leaf curl disease | 75 | 180 | 120 | Foliar spray of Clothridian (Dentaf) @ 0.1 ml/lit @ 35 & 50 DAT | UAS, Dharwad |  | Monocrotophos | 1.2 | 3 | Clothridin @ 75 ml/ha | 1059 | 1272 |
| Flowers |
| Chrysanthemum | Low yield Low quality of flower Low yield due to late opening of buds Incidence of leaf spot | Integrated Crop Management | 10.10 ton/ha | 18 ton/ha | 10.50 ton/ha | Application of 100:150:100 NPK/ha Foliar spray of water soluble NPK 19:19:19 fertlisers Spray of Micronutrients Spray of GA @ 100 pm two times after nipping & after 30 days interval of 1st spray Foliar spray of Propiconozole @ 1 ml/lit | IIHR, Bangalore & UAS, Dharwad | - | Application of 100 Kg 19;19:19 /Ha No spray Carbendizem | 4 | 10 | Water soluble NPK 19:19:19 @ 2 Kg/ha Micronutrient mixture @ 300 ml 5 gm G.A/ha Propiconazole@ 500 ml/ha | 100 1000 50 672 | 7288 |
| Aster | Low prices in Chrysanthemum | Introduction of variety | New crop | 2.0 ton | - | Introduction of Aster variety – Kamini | IIHR | 1994 | - | 1 | 10 | 650 gm seeds/ha | 6500 | 6500 |
| Ornamental |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Anthrurium |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Fruit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Spices and condiments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Black pepper |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cotton |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Bt. Cotton | Dropping of squares, tender bolls & leaf reddening Incidence of sucking pest Incidence of alterneria leaf spot | ICM |  | 25-30 q/ha | 20-22 q/ha | Spray of MgSo4 & Potassium nitrate & NAA Spray of Imidacloprid Spray of Hexaconazole | UAS, Dharwad |  | Nil | 5 | 5 | MgSo4@1.25 Kg/ha Potassium nitrate@2Kg/ha NAA@200 ml/ha Imidacloprid@150 ml/ha Hexaconazole@250 ml/ha | 985 | 4925 |
| Desi Cotton | Moisture stress Low productivity due to local variety | ICM | 2.75 q/ha | 8-10 q/ha | 4-5 q/ha | Compartment budning Demonstration of DDHC-11 variety | UAS, Dharwad | 2001-02 | Nil Usage of local seeds (Jayadhar) Nil | 20 | 50 | Seeds (DDHC-11)-10 Kg | 400 | 8000 |
| Other Fibre crops |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Commercial |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sugarcane |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Medicinal and aromatic |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Plantation crops |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Coconut |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Fodder crops | Non cultivation of perennial green grass | Nutritional management | - | - | - | Introduction of improved varieties perennial fodder crops for establishing Fodder Banks | IGFRI, RRS, Dharwad & TNAU, Coimbatore | 1996 | - | 1 ha | 10 | Hybrid Napier (CO-4) slips Fodder Sorghum @ 600 gm seeds Stylo santhes Hemata 200 gm Lucerna seeds 300 gm Rhodes grass 560 slips | 15000 | 15000 |
| Dairy |
| Cross bred cows | Tick infestation | Management of Ecto parasites |  |  |  | Management of Ecto parasite with 1% Flumethrin | KVAFSU, Bidar | - | - | 25 | 25 | 1% Flumethrin @ 50 ml/animal | 75/ animal | 1875 |
| Buffaloe | Low milk production | Management of Endo parasite | 4.5 liters/ day | 8 liters/ day | 5 liters/ day | Management of Endo parasite in milking buffaloe | KVAFSU, Bidar |  |  | 75 buffaloes | 75 | Fenbendazole-3 gm per animal | 50/tablet | 3750 |
| Buffaloe | Wastage of dry fodder during eating | Reduction in milk production | 4.5 liters/ day | 8 liters/ day | 5 liters/ day | Enrichment of dry fodder | KVAFSU, Bidar |  |  | 45 buffaloes | 45 | Salt @ 6 Kg/animal Jaggery @6 Kg/animal | 10/Kg 35/Kg | 12150 |
| Sheep | Reduced body weight and die due to severe worm infestation | Management of Endo parasite |  |  |  | Management of Endo Parasite with Closantel suspension | KVAFSU, Bidar |  |  | 300 sheeps | 15 | Closantel suspension 3 ml/ sheep | 10/ sheep | 3000 |
| Goat |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Poultry |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Layers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Broilers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Piggery |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Rabbitry |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Duckery |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Common carps |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mussels |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ornamental fishes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Oyster mushroom |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Button mushroom |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Vermicompost |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sericulture |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mulberry | Incidence of sucking pest | Management of sucking pest |  |  |  | Foliar spray of DDVP 76 EC @ 2 ml/lit | UAS, Dharwad |  | - | 3 | 3 | DDVP 76 EC @ 100 ml/ha | 520 | 1560 |
| Apiculture |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Drudgery in hoeing and intercultivation | - | - |  |  | Twin wheel hoe weeder | CIAE, Bhopal |  |  |  | 10 | 10 | 1000 | 10000 |
|  | Drudgery in harvesting of bengalgram | Drudgery reduction |  |  |  | Hand gloves | - | - | - | - | 20 | Hand gloves-20 | 150 | 3000 |
| Others (specify) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Fuel saving devices | Drudgery in cooking and collecting firewood | Drudgery |  |  |  | Envirofit chulha | Colarado State University’s Engines and Energy Conversion Laboratory | 2007 |  |  | 15 | 5 | 1500 | 7500 |
| Value addition | Lack of awareness on fortification of soyabean with wheat & jowar | Value addition | - | - | - | Fortification of soyabean with wheat & jowar | UAS, Dharwad & UAS, Bangalore | - | - | - | 10 | Soyabean–10 Kg Urad dal & other ingredients-5 Kg | 50 150 | 2000 |

6. Training Programmes

6.1. Plan of training programmes for Farmers/ Farm Women during 2011-12

| Crop / Enterprise | Major problem | Identified Thrust Area | Training Course Title | No. of Courses | Skill to be transferred |
| --- | --- | --- | --- | --- | --- |
| Greengram | Abiotic stress | In-situ soil moisture conservation | In-situ soil moisture conservation practice | 02 | In-situ soil moisture conservation method |
|  | Low productivity due to powdery mildew and pod borer | Management of powdery mildew & pod borer | Management of pod borer and powdery mildew | 02 | Identification of disease, pod borer and chemicals for control |
|  | Low productivity of local variety | Introduction of S-4 variety | ICM in S-4 variety | 02 | Identification of morphological characteristics of S-4 variety |
|  | Storage pest | Grain storage | Grain storage management | 05 | Identification of storage pest & control measurers |
|  | Labour problem for weeding and inter cultivation | Drudgery | Drudgery reducing equipments –Twin Wheel Hoe Weeder | 04 | Skills in operation |
| Bengalgram | Incidence of wilt | Introduction of JG-11 variety along with ICM | ICM | 02 | Identification of wilt and varietal characters of JG-11 variety |
|  | Incidence of pod borer | IPM | IPM | 02 | Identification of pest & IPM Package |
| Groundnut | Abiotic stress | Moisture conservation | In-situ moisture conservation | 02 | Moisture conservation methods |
|  | Imbalanced nutrition | ICM and introduction of GPBD- 4 & TAG-24 varieties | ICM | 04 | Identification of characters of varieties |
|  | Low productivity of local variety |  |  |  |  |
|  | Incidence of leaf minor | Leaf minor management | Leaf minor management | 02 | Identification of disease and chemicals for control |
|  | Weed problem | Weed management | Chemical management | 03 | Identification of weeds & control methods |
| Sunflower | Imbalanced nutrition | Balanced nutrition | INM | 02 | Symptoms of deficiency & quantity and method of application of nutrients |
|  | Powdery mildew | Management of powdery mildew | ICM | 02 | Identification of disease and it’s management |
| Hybrid Cotton | Lack of Knowledge on production technology | ICM | ICM in Bt. Cotton | 05 | Identification of ICM practices |
| Desi Cotton | Low productivity of Jayadhar and imbalanced nutrition | Introduction of DDHC-11 variety | ICM | 02 | Identification of characteristics of DDHC-11 |
| Maize | Problematic soils and Improper irrigation | Soil & Water management | Soil fertility and irrigation management | 02 | Methods of soil fertility management & irrigation |
|  | Imbalanced nutrition | INM | INM in Maize | 02 | Deficiency symptoms & nutrient application |
| Rabi Jowar | Moisture stress | Moisture conservation | Soil moisture conservation practices and seed priming | 03 | Methods of soil moisture conservation practices and seed treatment with CaCl2 |
|  | Low productivity of Maladandi (M35-1)variety | Introduction of CSV-22 variety | ICM in CSV-22 | 02 | Morphological characteristics of CSV-22 variety |
| Wheat | Low productivity of local variety | Introduction of improved variety | ICM | 01 | Morphological characteristics of variety |
|  | Drudgery in harvesting of stalks | Improved Sickles | Harvesting of Wheat stalks with improved sickle | 01 | Method of harvesting |
| Onion | Poor quality of bulb | Introduction of Arka Kalyan variety | ICM in Onion | 02 | Characteristics of Arka Kalyan variety |
|  | Weed problem | Weed management | Chemical weed management | 05 |  |
| Chilli | Anthracnose disease | Management of anthracnose | Management of anthracnose | 02 | Identification of disease and methods of control |
|  | Poor quality seeds | Training | Seed production | 02 |  |
|  | Murda complex | Murda complex management | Murda complex management | 02 | Identification of disease and chemicals for control |
|  | Poor quality of dry Chilli | Post harvest management | PHT in Chilli | 02 | Identification of PHT technology |
| Mango | Incidence of hoppers & powdery mildew | Management of disease & pest | Management of hoppers and powdery mildew | 02 | Identification of disease and chemicals for control |
| Tomato | Leaf curl incidence | Management of disease & pest | Leaf curl management | 01 | Chemical & its dosage |
| Brinjal | Shoot & fruit borer | Management of shoot & fruit borer | Management of shoot & fruit borer | 01 | Identification of symptoms, pest and chemicals for control |
| Chrysanthemum | Imbalanced nutrition | INM | INM | 01 | Dosage &method of application of nutrients |
| Aster | Introduction of Aster crop | Introduction of Aster crop | ICM | 01 | Relevant skills in production technology |
| Dairy Enterprises | Imbalanced nutrition | Nutrient management Fodder cultivation | Nutrient management | 04 | Type and methods of preparation of nutrients |
|  | Worm Infestation | Management of worms | Ecto and endo parasite management | 02 | Identification of ecto & endo parasites |
|  | Ticks | Pest management | Tick management | 03 | - |
| Sheep | Worm | Deworming | Deworming | 03 | - |
| Poultry | Low productivity of eggs in local breeds | Introduction of Swarnadhara breed | Rearing of improved breed | 02 | Identification of breed characteristics |
| Fuel saving devices | Drudgery & non availability of fuels | Fuel efficiency & to reduce drudgery | Drudgery reducing tools | 03 | Operation of envirofit chulha |
| Human nutrition | Nutrition deficiency | Nutrition | Balanced diet | 03 | Deficiency symptoms |
| Farm implements | Drudgery in weeding | Drudgery reduction | Drudgery reduction equipments | 02 | Operation of weeder & Sickle |
| Storage | Storage pests | Grain storage | Grain Storage | 05 | Preparation of Neembaits |
| Value addition | Lack of awareness | Value addition | Importance of potential grains in diet and value addition | 01 | Preparation of Value added products |

6.2. Plan of training programmes for Rural Youth during 2011-12

| Crop / Enterprise | Major problem | Identified Thrust Area | Training Course Title* | No. of Courses | Skill to be transferred |
| --- | --- | --- | --- | --- | --- |
| Greengram | Lack of knowledge on ICM practice | ICM | ICM | 2 | Relevant skills on ICM |
| Groundnut | -do- | ICM | ICM | 2 | ” |
| Bt. Cotton | -do- | Pest management | IPM | 2 | “ |
| Onion | -do- | ICM | ICM | 2 | ” |
| Chrysanthemum | -do- | ICM | ICM | 2 | ” |
| Dairy animals | Imbalanced nutrition | Nutrition | Azolla cultivation | 2 | ” |
| Amla | Lack of knowledge | Value addition | Value addition in amla | 1 | Value addition skills |

### 6.3.  Plan for training programmes for Extension Personnel during 2011-12

| Crop / Enterprise | Identified Thrust Area | Organization | Training Course Title | No. of Courses | Skill to be transferred |
| --- | --- | --- | --- | --- | --- |
| In-situ soil moisture conservation | Moisture stress management | Karnataka State Department of Agriculture | In-situ soil moisture conservation practices | 02 | Methods of In-situ soil moisture conservation practices |
| Groundnut | Enhancement of productivity | Karnataka State Department of Agriculture | Integrated Crop Management Practices | 02 | Relevant skills based on the need assessment |
| Bt Cotton | Integrated Crop Management | Karnataka State Department of Agriculture | ICM | 01 |  |
| Maize | Soil fertility management | Karnataka State Department of Agriculture | Soil fertility management | 01 |  |
| Onion + Chilli | Post harvest technology | Karnataka State Department of Agriculture | Post harvest management in Onion and Chilli | 01 | Skills in post harvest management |
| Nutrition | Health | Department of Women & Child Welfare | Importance of Balanced diet, Nutrition, Health, Hygiene and Deficiency diseases | 03 | Layout of Kitchen Garden |
| Drudgery | Drudgery reduction | Department of Women & Child Welfare | Drudgery reducing equipments | 05 | Demonstration of drudgery reducing equipments |
| High value Horticulture crop | Protected cultivation of high value crop with flower and vegetable | State Department of Horticulture | Cultivation of high value Horticulture crop under protected condition | 01 | Layout, planting and fertigation method |
| Bio- Pesticides | Preparation & usage of bio-pesticides to crops | Karnataka State Department of Agriculture | Preparation and usage of bio-pesticides | 01 | Method demonstration on preparation of Neem & Pongamia paste |

## 6.4. Plan of vocational training programmes for Young Farmers during 2011-12.

| Crop / Enterprise | Identified Thrust Area | Training title* | No. of programmes | Duration (days) | Skill to be transferred |
| --- | --- | --- | --- | --- | --- |
| Dairy | Self Employment | Scientific dairy farming | 03 | 05 | Dairy management skills |
| Terrace gardening | Self Employment | Gardening Techniques | 01 | 05 | Gardening Skills |
| Entrepreneurship | EDP Skills | EDP in Agriculture | 03 | 05 | Skills in Production, Processing and Marketing of agriculture produce |
| Value addition | Food processing | EDP & Food processing | 01 | 10 | Preparation of value added products and instant mixes |
| Vermicompost Technology | Usage and preparation of vermicompost | Vermicompost production technology and usage | 02 | 05 | Preparation of bed Value addition to vermicompost |
| Bio-pesticides | Preparation of Bio-pesticides | Preparation and usage of Bio- pesticides | 01 | 05 | Preparation methods & schedule of usage |

## 6.5. Plan for sponsored training programme during 2011-12

| Crop/ Enterprise | Identified Thrust Area | Sponsored Organization | Training course title* | No. of Courses | Sponsored Agency | Skill to be transferred |
| --- | --- | --- | --- | --- | --- | --- |
| Soil | Soil fertility management | KSDA (Agriculture Department) | Soil fertility management | 3 | -- | Relevant skills will be transferred based on need assessment |
| All crops | Soil moisture conservation | Watershed Development Department | In-situ soil moisture conservation | 3 | -- |  |
| Oil seeds | ICM | KSDA | ICM | 3 | -- |  |
| Pulses | ICM | KSDA | ICM | 2 | -- |  |
| Soil, Water & Crop Management | Water Management | CADA | Soil, Water & crop management in command area | 10 | -- |  |
| Dairy Enterprises | To increase Milk production | Zilla Panchayat | Management of milch animals | 8 | -- |  |
| Fruits & vegetables | Processing | State Department of Horticulture | Fruit and vegetable processing | 2 | -- |  |
| Lead crops & enterprise | Development of master training | NABARD | - | 5 | -- |  |
| Amla | Awareness & importance | IIHR Bangalore & Medicinal Plant Board | Training on cultivation of medicinally important crop and value addition | 3 | -- |  |

7. Extension programmes planned for 2011-12

| Month | Block & village | Extension programme* | Its relation to KVK activities (Tables 2 to 6)** | Expected category of participants | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 |
| April | Gadag Asundi Hulkoti Kurthkoti Mallasamudra Lakkundi Mundargi Jantli Shirur Shingataraynkeri Peta Alur Ramenahalli Shirahatti Bannikoppa Suganahalli Hadagali | Soil sample collection & testing Kharif campaign Method demonstration on Groundnut Decorticator Method demonstration in compartment bunding Farmers meeting Seminar on Kharif crops Field school on soil & water conservation | Front Line Demonstration Training programme Front Line Demonstration On-farm testing | 1000 |  |
| May | Ron Jakkali Maranabasari Budhihal Naragund Banahatti Kurlageri Mooganur | Soil sample collection & testing Kharif campaign Soil and water conservation campaigns Farmers meeting Seminar on soil salinity management | Training programme Front line demonstration | 1000 |  |
| June | Gadag Kurthkoti Asundi Mulagund Soratur | Farmers meeting at FRC | Training & supply of seed FLD | 300 150 |  |
|  | Hulkoti | Orchard layout | Training | 50 |  |
|  | All the identified villages | Method demonstration on Groundnut Decorticator | FLD Training | 200 |  |
|  | Ron Jakkali Maranabasari Budhihal | Animal health camps Seminar on animal nutrition | FLD Training | 200 |  |
|  | Shirahatti Bannikoppa Muradi | Demonstration of weeders | FLD | 100 |  |
| July | Ron Jakkali | Radio programme on ICM in greengram, bengalgram and groundnut | FLD and training | 25 |  |
|  | Shirahatti Bannikoppa | Weeder demonstration Demonstration on chemical weed management in onion | Training FLD | 150 100 |  |
| August | Ron Jakkali | Field day on Greengram | FLD | 200 |  |
|  | Mundaragi Jantlishirur | Demonstration on Azolla Deworming camp for sheep & goat | Training FLD | 50 50 |  |
| September | Shirahatti Bannikoppa | Field Day on Greengram | FLD | 200 |  |
|  | Ron Jakkali | Demonstration on machine harvesting of Greengram | Training | 200 |  |
|  | All the villages | Technology week celebration | Mandated activity | 1500 |  |
|  | Gadag Kurthakoti Mulagund Asundi Soratur | Farmers meeting at FRCs | - | 400 |  |
| October | All the identified villages | Rabi Campaign World Food Day Celebration Demonstration of envirofit chulha | Training FLD | 1000 |  |
|  |  | Method demonstration on the preparation of neem baits | OFT | 300 |  |
|  | Gadag Lakkundi | Field Day on Aster & Chrysanthemum | FLD | 200 |  |
| November | Shirahatti Bannikoppa | Field Day on Onion | FLD | 150 |  |
|  | Gadag Kurthakoti | Field Day on Chilli | OFT | 150 |  |
|  | Ron Bannikoppa Jakkali | Field day on Groundnut | FLD | 150 |  |
| December | Ron Jakkali | Women in Agriculture day | Celebration | 150 |  |
|  | Shirahatti Bannikoppa | Exhibition of value added products of foxtail millet Field day on maize | FLD | 150 |  |
|  | All the villages | Seminar on PHT in onion & chilli | Training | 200 |  |
| January | Ron Jakkali | Field day in Bengalgram | FLD | 150 |  |
|  | All the villages | Technology Week Celebration Exhibition Animal health camp | Mandated activities Training | 1500 200 |  |
| February | Ron Jakkali | Field day on Desi cotton Rabi jowar | FLD | 300 |  |
|  | Shirahatti Bannikoppa | Demonstration on Improved Sickle | FLD | 100 |  |
|  | All the villages | Method demonstration in cot bags | OFT | 200 |  |
| March | Naragund Banahatti | Field day on wheat Method demonstration of improved sickle | FLD FLD | 100 50 |  |
|  | Shirahatti Bannikoppa | Field day on summer Groundnut | FLD | 150 |  |

8.  Details of print & electronic media coverage planned for 2011-12

| Sl. No. | Nature of literature/publications and no. of copies | Proposed title of the publication |
| --- | --- | --- |
| 1 | Leaflet – 2000 | Importance of value addition in Amla |
|  | Leaflet – 2000 | Drudgery reduction equipments |
| 2 | Leaflet – 5000 | In-situ soil moisture conservation practices |
| 3 | Leaflet – 3000 | Production technology in Onion |
| 4 | Leaflet – 3000 | Chrysanthemum cultivation |
| 5 | Handouts-5000 | Management of pest and disease in Groundnut, Bengalgram, Greengram, Chilli and Mango |
| 6 | Handouts-5000 | Production technology in Groundnut, Sunflower, Cotton, Rabi Jowar, Wheat, Maize |
| 7 | Handouts-2000 | Animal nutrition |
| Sl. No. | Nature of media coverage | Proposed title of the programme to be telecasted/ broadcast |
| 1 | Radio talk | Dry land agronomic practices |
| 2 | Radio talk | INM in Oilseeds |
| 3 | Radio talk | ICM in Bt Cotton |
| 4 | Radio talk | Quality bulb production in Onion |
| 5 | Radio talk | Soil fertility management |
| 6 | Television | PHT in onion & chilli |
| 7 | Television | Murdha complex management in Chilli |
| 8 | Mobile message -500 | Relevant information on technology, weather and market |

9.  Nature of collaborative activities planned for 2011-12

| Thrust area | Collaborative Organizations | Nature of activities | No. of Activities |
| --- | --- | --- | --- |
| Development of master trainers | NABARD | Training | 03 |
| ICM in Oilseeds, Pulses and Cotton | Karnataka State Department of Agriculture | Training | 10 |
| Strengthening of Farm Resource Centres | Deshpande Foundation, USA | Resource Centre for disseminating of knowledge & supply of inputs & services | 01 |
| Transfer of technology | Karnataka State Department of Agriculture | Implementation of Field School | 01 |
| Self Employment | Zilla Panchayat, SGSY Programme | Training | 10 |
| Soil and Water Conservation | District Watershed Development Department | Training | 10 |
| Soil, crop & water management | CADA, Belgaum | Training | 15 |
| ICM in lead crops | Grameena Suvidha Kendra | Training | 05 |

10.  Financial status of revolving fund and plan for its utilization

| Opening balance as on 01.04.2010 (Rs.in Lakh) | Expenditure incurred during 2010-11 (Rs.in Lakh) | Receipts during 2010-11 (Rs.in Lakh) | Closing balance as on 31.01.2011 (Rs.in Lakh) | Proposed expenditure during 2011-12 (Rs.in Lakh) | Purpose | Expected production (Tonnes / Lakh Numbers/) | Proposed receipts during 2011-12 (Rs.in Lakh) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.25 | 11.89 | 14.27 | 5.63 | 14.00 |  |  | 20.00 |

- Physical status of revolving fund and plan for its utilization

| Opening stock position of materials* as on 01.04.2010 (Tonnes / Lakh Numbers/) | Quantity produced during 2010-11 (Tonnes / Lakh Numbers/) | Quantity sold during 2010-11 (Tonnes / Lakh Numbers/) | Closing stock position as on 31.01.2011 (Tonnes / Lakh Numbers/) | Expected production during 2011-12 (Tonnes / Lakh Numbers/) | Expected number of farmers to be benefited |
| --- | --- | --- | --- | --- | --- |
| Vermicompost:0.06 | 30.0 | 28.6 | 1.50 | 40.0 | 16 |
| Earthworms: 0.05 | 0.125 | 0.125 | Nil | 0.13 | 50 |
| Amla products:0.05 | 0.050 | 0.040 | 0.015 | 0.060 | - |
| Cotton | 1.50 | 1.50 | Nil | 2.0 | 135 |
| Groundnut | 1.0 | 1.0 | Nil | 1.50 | 10 |
| Greengram | 1.80 | 1.80 | Nil | 2.0 | 175 |
| Rabi Jowar | 2.40 | 2.40 | Nil | 2.0 | 120 |
| Onion | 0.50 | 0.50 | Nil | 1.5 | 180 |
| Wheat | 2.30 | 2.30 | Nil | 0.5 | 12 |
| Ridge gourd | 0.025 | 0.025 | Nil | 0.1 | 40 |
| Mango Seedlings | 4000 (nos) | 4000 (nos) | Nil | - | - |
| Amla Seedlings | - | - | Nil | 25000 (Nos) | 250 |
| Subscription to Kannada News Letter | 55000 copies | 55000 | Nil | 60000 copies | 5000 |

## 12.  Status of KVK farm and Demonstration units

| No. of blocks | Area | Source of irrigation | Season | Crop/enterprise/demonstration units | Size (no. of units/area) | Expected output |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Quantity | Value (Rs.in lakh) |
| 01 | 20 ha | Bore well as protective irrigation for about 4 ha land | Kharif Rabi Perennial | Green gram Groundnut Onion + chilli Chilli Tomato Rabi Jowar Cotton Bengalgram Simroubha Amla Guava Mango Mixed Orchard Vermicompost and earthworms production units | 3.10 1.80 1.60 - 0.40 1.50 4.00 1.00 0.40 1.00 1.20 0.80 1.20 100’ X 40’ | 15 Qt 18 Qt 65 Qt 8 Qt 40 Qt 15 Qt 30 Qt 10 Qt 3 Qt 10 Qt 45 Qt 2 Qt - 50 tons | 60,000 45,000 32,500 40,000 20,000 15,000 75,000 22,000 1,500 20,000 22,500 80,000 Yet to yield 1,25,000 |
| Total | 5,58,500 |

13.  Are there any activities planned for production and supply (Either buy back or directly farmer to farmer) of seeds/ planting material/ Bio-agents etc. in villages (other than KVK farm) so that public private partnership is utilized. Please give details in the following format

| Sl. No | Seeds/Planting material /Bio-agent | Name of the public-private partnership arranged | Quantity of output expected (Qtl) |
| --- | --- | --- | --- |
| 1 | Greengram | KVK identified JLG/SHG members | 30 |
| 2 | Bengalgram | KVK identified JLG/SHG members | 30 |
| 3 | Groundnut | KVK identified JLG/SHG members | 40 |
| 4 | Onion seed production | KVK identified JLG/SHG members | 20 |

14. What is the extent of cultivable wasteland in your district? Are there any specific activities planned to be implemented in these wastelands by the KVK during 2011-12. Please give details.

Cultivable wasteland in Gadag district is very less.  Hence no activities are proposed

15. National Horticulture Mission (NHM) is being implemented through out the country. You are requested plan for implementing some of the activities envisaged in NHM in your district in collaboration with district head of department of horticulture. Please give details of any such plans for 2011-12

National Horticulture Mission is being implemented in Gadag district from 2009-10.   During 2011-12, KVK has planned to organize training programmes for NHM assisted farmers in collaboration with State Department of Horticulture.  Apart from training, KVK has planned farm advisory services for farmers covered under National Horticulture Mission.

16. Whether SREP under ATMA is prepared and implemented & functioning in your district?

YES

If yes, what type of coordination and collaboration does your KVK is proposed to have during 2011-12?

| Sl. No | Name of activity / Programes | No. of programmes | Crops / Enterprise | Extent of coverage* |
| --- | --- | --- | --- | --- |
|  |  |  |  | No. of farmers | Area (ha) |
| 1 | Field School | 2 | Onion, Greengram | 50 | 5 |
| 2 | Training | 10 | Bt. Cotton, Onion, Groundnut, Bengalgram | 300 | - |
| 3 | Exhibition | 1 | - | - | - |

*if relevant

17. What type of Scientist-Farmer linkages are proposed by your KVK for 2010-11?

KVK has established Farm Resource Centres in 5 villages for speedy technology dissemination.  These centres act as a platform for scientist-farmer linkage.    Apart from this, KVK has network of farmer groups and field school programmes which facilitate for scientist-farmer linkage. In Ron block, KVK proposes linkage with 625 farmers in collaboration with  Grameena Suvidha Kendra.

Mobile based farm advisory, weather and marketing services are already being rendered to the farmers.  A total of 800 farmers have got registered for the SMS service.

18. Activities of soil, water and plant testing laboratory

| Year of establishment | Expenditure Rs.(lakhs) | No. of soil samples planned to be analyzed and reported | No. of water samples planned to be analyzed and reported | No. of Plant Samples planned to be analyzed and reported | Remarks if any |
| --- | --- | --- | --- | --- | --- |
| 2005-06 | 11.88 | 600 | 200 | 150 | - |

19. Details of budget  utilization (2010-11) upto February 2011

| S. No. | Particulars | Sanctioned | Released | Expenditure |
| --- | --- | --- | --- | --- |
| A. Recurring Contingencies |
| 1 | Pay & Allowances | 5800000.00 | 5800000.00 | 5181438.00 |
| 2 | Traveling allowances | 125000.00 | 125000.00 | 124850.00 |
| 3 | Contingencies |
| A | Stationery, telephone, postage and other expenditure on office running, publication of Newsletter and library maintenance (Purchase of News Paper & Magazines) | 250000.00 | 250000.00 | 206153.00 |
| B | POL, repair of vehicles, tractor and equipments | 220000.00 | 220000.00 | 163853.00 |
| C | Meals/refreshment for trainees (ceiling upto Rs.40/day/trainee be maintained) | 100000.00 | 100000.00 | 99980.00 |
| D | Training material (posters, charts, demonstration material including chemicals etc. required for conducting the training) | 80000.00 | 80000.00 | 38913.00 |
| E | Frontline demonstration except oilseeds and pulses (minimum of 30 demonstration in a year) | 175000.00 | 175000.00 | 172485.00 |
| F | On farm testing (on need based, location specific and newly generated information in the major production systems of the area) | 75000.00 | 75000.00 | 73736.00 |
| G | Training of extension functionaries | 25000.00 | 25000.00 | 25020.00 |
| H | Maintenance of buildings | 25000.00 | 25000.00 | 24981.00 |
| I | Extension Activities | 25000.00 | 25000.00 | 21213.00 |
| J | Library | 5000.00 | 5000.00 | 4857.00 |
| K | Farmers’ Field School | 25000.00 | 25000.00 | 20408.00 |
| L | Special programme on FLD | 95000.00 | 95000.00 | 95143.00 |
| TOTAL (A) | 6525000.00 | 6525000.00 | 6087483.00 |
| B. Non-Recurring Contingencies |
| 1 | Works |  |  |  |
|  | a) Demo unit | 300000.00 | 300000.00 | 300000.00 |
|  | b) Vehicle and implement shed | 200000.00 | 200000.00 | 200000.00 |
|  | c) Irrigation system | 300000.00 | 300000.00 | 300000.00 |
|  | d) Storage godown | 300000.00 | 300000.00 | 300000.00 |
|  | e) Threshing and drying yard | 200000.00 | 200000.00 | 200000.00 |
|  | f) Fencing cum compound wall | 800000.00 | 800000.00 | 800000.00 |
|  | g) Road formation | 500000.00 | 500000.00 | 500000.00 |
|  | h) Borewell | 300000.00 | 300000.00 | 0.00 |
|  | i) Repair & renovation | 300000.00 | 300000.00 | 300000.00 |
| 2 | Equipments including SWTL & Furniture |  |  |  |
|  | a) Laser guided land leveler | 500000.00 | 500000.00 | 0.00 |
|  | b) Power Tiller | 150000.00 | 150000.00 | 0.00 |
|  | c) Earthworm rearing stand | 30000.00 | 30000.00 | 0.00 |
|  | d) Lab equipments for dairy and goatery | 50000.00 | 50000.00 | 0.00 |
|  | e) Generator | 100000.00 | 100000.00 | 100000.00 |
|  | f) Furniture & furnishing | 200000.00 | 200000.00 | 0.00 |
|  | g) EPABX system | 50000.00 | 50000.00 | 0.00 |
|  | h) Plant health diagnostic facility | 100000.00 | 100000.00 | 0.00 |
| 3 | Library | 10000.00 | 10000.00 | 0.00 |
| TOTAL (B) | 5290000.00 | 5290000.00 | 3272000.00 |
| C. REVOLVING FUND |  |  |  |
| GRAND TOTAL (A+B+C) | 12315000.00 | 12315000.00 | 9525030.00 |

20. Details of Budget Estimate (2011-12) - ICAR KVKs alone may consider Pay and       Allowances based on VI Pay Commission Orders from ICAR, for rest of the KVKs please estimate based on the existing norms, since ICAR is yet to take decision in this regard.

| Sl. No. | Name of the Head | Amount (Rs. In lakhs) |
| --- | --- | --- |
| Recurring Items |
| I | Pay & Allowances |  | 69.75 |
| II | Travelling Allowances |  | 3.50 |
| III | Contingencies |  | 18.30 |
|  | Stationery and Office Expenses | 3.00 |  |
|  | POL | 3.00 |  |
|  | Meals/Refreshments for Trainees | 2.00 |  |
|  | Training Materials | 2.00 |  |
|  | FLD (Excluding Oilseeds & Pulses) | 3.90 |  |
|  | On Farm Testing | 1.65 |  |
|  | Extension Functionaries Training | 0.50 |  |
|  | Library maintenance | 0.25 |  |
|  | Building maintenance | 0.50 |  |
|  | FFS | 0.25 |  |
|  | Extension Activities | 1.00 |  |
|  | Maintenance of STL | 0.25 |  |
| Total (A) | 88.00 |
| B) Non-Recurring Items |
| I | Special programme (IFS) |  | 10.00 |
| II | Equipments (Atomic Specto Photo Meter) |  | 6.00 |
| Total (B) | 16.00 |
| Grand total (A+B) | 107.55 |

21. Targets for E-linkage activities for 2011-12

| S. No | Nature of activities | Likely period of completion (please set the time frame) | Remarks if any |
| --- | --- | --- | --- |
| 01 | Creation of web-site | Already created |  |
| 02 | Title of the technology module to be prepared | Greengram – October 2011 | Need training on preparation of technology module |
| 03 | Creation and maintenance of relevant database system for KVK |  |  |
|  | OFT | January 2012 |  |
|  | FLD | January 2012 |  |
|  | Training database | Already maintained |  |
|  | Seeds & planting material | Already maintained |  |
|  | Extension activities | Already maintained |  |
|  | Database of farmers visiting to our KVK | June 2011 |  |
|  | District database | Already maintained |  |
|  | Database of soil test | January 2012 |  |
| 04 | Any other (Please specify) |  |  |

22. Activities planned under Rainwater Harvesting Scheme during 2011-12 (only to those KVKs which are already having scheme under Rain Water Harvesting)

| S. No | Activities planned during 2011-12 | Remarks if any |
| --- | --- | --- |
| 1 | Training to farmers & farmwomen -500 No. | - |
| 2 | Demonstration - 5 No. | - |
| 3 | Seminars 1 No. | - |

23. Publication of success story / case study planned for 2011-12

| S. No | Title of success stories | Proposed date for finalization of documentation* | Title of the case study* | Proposed date for finalization of documentation* |
| --- | --- | --- | --- | --- |
| 1 | A success story on Aster cultivation | 31st May 2011 | Dry land horticulture | 31st May, 2011 |
| 2 | A success story on Vermicelli enterprise | 31st May 2011 | Soil and water conservation | 31st May, 2011 |

24. Technology Week

| Particulars | Details |
| --- | --- |
| Period of Technology Week Observed during 2010-11 | September and January |
| Period of Technology Week planned during 2011-12 | January (1 day seminar on Kharif crops will be organized in the month of June and 1 day seminar on rabi crops will be organized in the month of September. During the seminar technological products will be sold to the farmers. Weeklong technology celebration will be held in the month of January) |
| No. of demonstrations planned to be conducted in KVK Campus to show to the farmers during Technology Week | 30 |
| Other activities / Programmes planned in connection with Technology Week | Exhibitions, Farm visit, Farmers interaction with SMSs. |

25. Innovative Farmer’s Meet

| Particulars | Details |
| --- | --- |
| Are you planning for conducing Farm Innovators meet in your district? | Yes |
| If Yes likely month of the meet | January 2012 |
| Brief action plan in this regard | It will be submitted latter |

26. Progressive Farmers List

| Particulars | Details |
| --- | --- |
| Number of Progressive Farmers address and all details planned to be collected and documented during 2011-12* | 500 |
| Likely Date and Month of completion of this work (on or before 30th June 2011) | 30th June, 2011 |

27. Farmer’s Field School planned during 2011-12

| S. No | Thematic area | Title of the FFS | Budget proposed in Rs. |
| --- | --- | --- | --- |
| 1 | Integrated Crop Management | ICM in Onion | 25,000.00 |

28. Please give details of activities planned, other than those listed above.

----------XXXXXXX---------------