`

ACTION PLAN OF KVK, GADAG

Prepared by

K.H.PATIL KRISHI VIGYAN KENDRA

Hulkoti-582 205   Dist : GADAG, Karnataka State

Website : www.khpkvk.org

e-mail : kvkhulkoti@gmail.com

Contents

| Sl. No. | PARTICULARS | PAGE NO. |
| --- | --- | --- |
| 1 | Details of KVK | 1-4 |
| 2 | Plan of work for 2009-10 and thrust areas | 5-16 |
| 3 | Abstracts of interventions proposed | 17-23 |
| 4 | Target set for interventions | 24-25 |
| 5 | Plan for On Farm Testings | 26-55 |
| 6 | Plan of Front Line Demonstrations |  |
|  | - Other than Oil seeds, Pulses and Cotton | 56-60 |
|  | - FLD on Oilseeds | 61-62 |
|  | - FLD on Pulses | 63-64 |
|  | - FLD on Cotton | 65-66 |
| 7 | Plan for training programme |  |
|  | - Extension functionaries | 67 |
|  | - Vocational training for rural youths | 68 |
|  | - Training programme for farmers / farmwomen | 69-71 |
|  | - Sponsored trainings | 72 |
| 8 | Extension programme planned | 73-74 |
| 9 | Details of print and electronic media | 75 |
| 10 | Collaborative programmes planned | 75 |
| 11 | Physical status of revolving fund and plan for utilization | 76 |
| 12 | Status of KVK farm and demonstration units | 77 |
| 13 | Activities of soil, water and plant testing | 78 |
| 14 | Details of budget | 79-80 |
| 15 | Target for E-linkage | 81 |
| 16 | Farmers’ Field School activities planned | 82-83 |

###### ACTION PLAN   (2010-11)

OF

###### K.H. PATIL KRISHI VIGYAN KENDRA, HULKOTI, GADAG DISTRICT

###### GENERAL INFORMATION ABOUT THE KRISHI VIGYAN KENDRA, GADAG

| 1. | Name and address of KVK with Phone, Fax and e-mail | : | K.H. Patil Krishi Vigyan Kendra Hulkoti – 582205 Dist.: Gadag Phone : (08372) 289606 Fax : (08372) 289474 E-mail : khpatil_kvk_hulkoti@yahoo.com kvkhulkoti@gmail.com |
| --- | --- | --- | --- |
| 2. | Name and address of host organization with Phone, Fax and e-mail | : | Agricultural Science Foundation Hulkoti – 582205 District: Gadag Phone : (08372) 289069 Fax : (08372) 289474 E-mail : asf_hulkoti@yahoo.co.in |
| 3. | Name of the Programme Coordinator Residence Phone Number/ Mobile No. | : | Dr. L.G.Hiregoudar Phone (R) : (08372) 289772 (M) : 09448358772 |
| 4. | Year of sanction | : | 1985 |
| 5. | Year of start of activities | : | 1985 |
| 6. | Major farming systems/enterprises | : | A) Field crop based Farming systems (i) Chilli + Onion + Cotton, Onion + Chilli (ii) Groundnut – Rabi jowar/wheat (iii) Greengram – Sunflower / Rabi jowar / wheat /Bengalgram (iv) Maize – Bengalgram / wheat (Irrigated) (v) Kharif jowar + Tur (vi) Bt Cotton B) Horticulture based Farming systems (i) Vegetable Crops (Irrigated condition) (ii) Flower crops (irrigated) (iii) Mango (mainly dryland) C) Major Enterprises (i) Dairy farming (ii) Sheep rearing (iii) Goat rearing |
| 7. | Name of agro-climatic zone | : | - Northern Dry Zone (Region – 2) comprising of Gadag, Ron, Naragund and Mundaragi blocks - Semi transitional Zone -8 comprising of Shirhatti block |
| 8. | Soil type | : | Deep black to medium black soils, red sandy soil and red clay soils |
| 9. | Annual rainfall (mm) | : | 612 mm |

- Staff Strength as on 01-03-2010:

|  | Programme Coordinator | Subject Matter Specialists | Programme Assistant | Administrative Staff | Auxiliary Staff | Supporting Staff | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| #### Sanctioned | 1 | 6 | 3 | 2 | 2 | 2 | 16 |
| Filled | 1 | 6 | 2 | 2 | 2 | 2 | 15 |

11.  Details of staff as on 01-03-2010:

| Sl. No. | Sanctioned post | Name of the incumbent | Discipline | Pay scale | Date of joining | Permanent/ Temporary |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Programme Coordinator | Dr. L.G. Hiregoudar | Programme Coordinator | 16400-22400 | 05.09.1992 | Permanent |
| 2. | Subject Matter Specialist | Mr. S.K.Mudlapur | SMS (Plant Protection) | 10000-15200 | 26.09.1994 | Permanent |
| 3. | Subject Matter Specialist | Mr. S.H.Adapur | SMS (Ag. extension) | 10000-15200 | 23.06.1995 | Permanent |
| 4. | Subject Matter Specialist | Smt. S.S.Rayanagoudar | SMS (Home Science) | 10000-15200 | 26.06.1995 | Permanent |
| 5 | Subject Matter Specialist | Mr. V.D.Vaikunthe | SMS (Agronomy) | 10000-15200 | 01.07.1995 | Permanent |
| 6 | Subject Matter Specialist | Mr. K.T.Patil | SMS (Horticulture) | 10000-15200 | 01.07.1995 | Permanent |
| 7 | Subject Matter Specialist | Mr. N.H.Bhandi | SMS (Soil Science) | 8000-13500 | 01.06.2005 | Permanent |
| 8 | Programme Assistant | Dr. B.M. Muragod | Programme Assistant (Animal Husbandry) | 5500-9000 | 25.06.2007 | Permanent |
| 9 | Computer Programmer | Smt. L.C. Koravanavar | Programme Assistant (Computer Programmer) | 5500-9000 | 01.06.2005 | Permanent |
| 10 | Farm Manager | Mr. Suresh Halemani | Programme Assistant (Farm manager) | 5500-9000 | 01.02.2009 | Temporary |
| 11 | Accountant/ Superintendent | Mr. M.B. Jakkanagoudar | Accountant/ Superintendent | 5500-9000 | 25.06.2007 | Permanent |
| 12 | Stenographer | Mr. Manju D. | Stenographer | 4000-6000 | 11.06.2007 | Permanent |
| 13 | Driver | Mr. N.L. Hadapad | Driver | 3200-4900 | 03.09.1992 | Permanent |
| 14 | Driver | Mr. G.D. Madivalar | Driver | 3200-4900 | 20.07.1995 | Permanent |
| 15 | Supporting staff | Mr. S.B. Kotabagi | Clerk cum Fieldman | 3050-4590 | 18.07.1985 | Permanent |
| 16 | Supporting staff | Mr. V.R. Navalli | Village Work Attendant | 3050-4590 | 20.07.1993 | Permanent |

12. Plan of Human Resource Development of KVK personnel during 2010-11

| Sl. No | Discipline | Area of training required | Institution where training is offered | Approximate duration (days) | Training fee (Rs.) |
| --- | --- | --- | --- | --- | --- |
| 1. | Home Science | Value Addition | CFTRI, Mysore | 10 | 15,000/- |
| 2. | Horticulture | Green House Management | UAS, Dharwad | 05 | - |
| 3. | Agronomy | Integrated Farming System | UAS, Dharwad | 05 | - |
| 4. | Extension | Market led Extension | MANAGE, Hyderabad | 05 | - |

13.  Infrastructure:

i) Land

| Total Area (ha) | Area Cultivated (ha) | Area occupied by buildings and roads (ha) | Area with demonstration units (ha) |
| --- | --- | --- | --- |
| 20 | 20 | 1.5 | 0.5 |

ii) Buildings

| Admn. Building |  |  | Trainees Hostel |  |  | ###### Staff Quarters |  |  | Demonstration Unit |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Plinth area (m2) | Cost (Rs. in lakhs) | Year | Plinth area (m2) | Cost (Rs. in lakhs) | Year | Plinth area (m2) | Cost (Rs. in lakhs) | Year | No. | Plinth area (m2) | Cost (Rs. in lakhs) |
| 800 | 33.46 | 1996 | 550 | 17.26 | 1997 | 400 | 45.00 | 2006 | Dairy, sheep & goat | 150 | 6.63 |
|  |  |  |  |  |  |  |  |  | Vermicompost | 350 | 5.30 |
|  |  |  |  |  |  |  |  |  | Nursery | 150 | 3.00 |

iii) Vehicles

| Type of vehicle | Model | Actual cost (Rs.) | Total kms. Run | Present status |
| --- | --- | --- | --- | --- |
| Bolero SLX | 2009 | 6.90 | 24966 Kms | Good |
| Mahindra Tractor | 2003 | 5.00 | 1045 hours | Good |
| Motor cycle | 2005 | 0.40 | 77829 Kms | Good |
| Motor cycle | 2009 | 0.50 | 8043 Kms | Good |

- Equipments and AV aids

| Sl. No. | Name of Equipments | Date of purchase | Cost (Rs. in lakhs) | Present status |
| --- | --- | --- | --- | --- |
| 1 | Computer | 2003 | 1.25 | Good |
| 2 | Camera | 1998 | 0.14 | Good |
| 3 | Television | 1999 | 0.28 | Good |
| 4 | Amplifier | 1998 | 0.15 | Good |
| 5 | Fax | 2004 | 0.25 | Good |
| 6 | OHP | 2004 | 0.25 | Good |
| 7 | Hipro lab model gin machine | 2006 | 0.70 | Good |
| 8 | Seed delinting machine | 2006 | 0.18 | Good |
| 9 | Cotton seed sorter | 2007 | 0.50 | Good |
| 10 | Seed treatment drum | 2007 | 0.40 | Good |
| 11 | Lap top Computer | 2007 | 0.54 | Good |
| 12 | LCD | 2007 | 0.56 | Good |
| 13 | Ceramic black board | 2007 | 0.12 | Good |
| 14 | Rotavator | 2008 | 0.92 | Good |
| 15 | Rotary weeder | 2009 | 0.90 | Good |

14. Details of SAC meeting conducted during 2009-10

| Sl. No | Date | Major recommendations of SACs which are to be implemented during 2010-11 |
| --- | --- | --- |
| 1. | 14-07-2009 | - To demonstrate TAG-26 Groundnut variety under FLD - To introduce Bidari breed of Goat, Kenguri breed of Sheep and Swarnadhara breed of Poultry in Gadag district - To organize training in green house technology |
| 2. | 02-01-2010 | - Implement IFS model in one village and make it model for other farmers with assistance from UAS, Dharwad - Enhance quantity of improved seeds - Develop precision farming model in KVK farm - Strengthen livestock activities of KVK - Provide technical back-up for NABARD Special Programme in 5 village of Ron block - Impart trainings to VVV Club Members - To set up packing facilities for SHG products |

15. Plan of Work for 2010-11

Profile of Gadag District

1)  Major farming systems/enterprises

| S. No | Farming system/enterprise |
| --- | --- |
| Rainfed situation |  |
| 1 | Agricultural crops + Dairy enterprises |
| 2 | Agricultural crops + Horticultural crops |
| 3 | Agriculture + Horticulture + Dairy enterprise |
| 4 | Agriculture + Dairy enterprise |
| Irrigated situation |  |
| 1 | Agriculture + Dairy |
| 2 | Dairy enterprise |

2)  Description of Agro-climatic Zone & major agro ecological situations

| S. No | Agro-climatic Zone | Characteristics |
| --- | --- | --- |
| 1 | Northern Dry Zone-3 and Region-2 of the state | This zone comprises of Gadag, Ron, Mundaragi and Naragund blocks. Rainfall ranges from 450-600 mm with 30-35 rainy days mainly from June – September months. Maximum temperature range from 36-400 c. This zone is drought prone. Kharif crops grown: Greengram, Groundnut, Onion + Chilli, Sunflower, Maize Rabi crops grown: Bengalgram, Desi cotton, rabi jowar, wheat, sunflower |
| 2 | Zone -8 | This zone comprises of Shirahatti block. Average rainfall is 619 mm. Gets rainfall from both South-West and North-East mansoons. Kharif crops grown: Green gram, Jowar, Bt cotton, Groundnut, Sunflower, Millets, Maize, Onion, Chilli Rabi crops grown: Rabi jowar, Sunflower, Desi cotton, Bengal gram, Wheat |

3)  Soil types

| Sl. No | Soil type | Characteristics | Area in ha |
| --- | --- | --- | --- |
| 1 | Deep clay soil | More water holding capacity with low infiltration rate of water & clay content is more than 35 percent | 274285 |
| 2 | Medium deep black soils | Moderate water holding capacity with high runoff and less infiltration | 12000 |
| 3 | Red clay soil | Medium water holding capacity and moderately drained soils. Clay content is less than 25 percent | 27000 |
| 4 | Red gravely clay soils | Less water holding capacity. High infiltration rate and less runoff | 67500 |
| 5 | Red gravely loam soils | Moderately deep & well drained soils | 12500 |
| Total |  |  | 393285 |

4) Area, Production and Productivity of major crops cultivated in the district (2008-09)

| S. No | Crop | Area (ha) | Production (Metric tons) | Productivity (kg /ha) |
| --- | --- | --- | --- | --- |
| 1 | Greengram | 30228 | 6186 | 202 |
| 2 | Bengal gram | 44808 | 35846 | 804 |
| 3 | Groundnut (Kharif) | 36356 | 21814 | 610 |
| 4 | Sunflower (Rainfed) | 56424 | 22570 | 400 |
| 5 | Sunflower (Irrigated) | 5401 | 6481 | 1208 |
| 6 | Desi cotton | 40341 | 10678 bales | 152 |
| 7 | Onion | 26353 | 19560 | 15000 |
| 8 | Red chilli | 15605 | 19560 | 900 |
| 9 | Maize | 12512 | 2318 | 2000 |
| 10 | Rabi jowar | 63050 | 98810 | 700 |

Source: Office of Joint Director of Agriculture, Gadag

5) Weather data (January 2009- December 2009)

| Month | Rainfall (mm) | Temperature 0 C |  | Relative Humidity (%) |
| --- | --- | --- | --- | --- |
|  |  | Maximum | Minimum |  |
| January | 0 | 30.8 | 14.8 | 48 |
| February | 0 | 31.0 | 18.9 | 49 |
| March | 13.1 | 36.4 | 20.8 | 57 |
| April | 48.1 | 38.4 | 22.1 | 44 |
| May | 56.4 | 37.5 | 21.0 | 43 |
| June | 140.9 | 33.4 | 22.3 | 61 |
| July | 59.8 | 33.2 | 19.9 | 71 |
| August | 66.9 | 29.8 | 20.1 | 69 |
| September | 155.7 | 28.3 | 19.2 | 61 |
| October | 162.6 | 29.8 | 18.9 | 57 |
| November | 24.4 | 30.0 | 15.0 | 60 |
| December | 75.6 | 28.0 | 12.0 | 54 |
| Total | 804.2 |  |  |  |

Source: District Statistical Office

6) Production and Productivity of Livestock, Poultry, Fisheries etc. in the district

| Category | Population | Production | Productivity |
| --- | --- | --- | --- |
| Cattle |  |  |  |
| Crossbred | 15418 | 49950 L. milk/day | 5.22 Kg/day |
| Indigenous | 158588 | 45014 L/day | 2.40 Kg/day |
| Buffalo | 80234 | 64088 L/day | 2.80 Kg/day |
| Sheep |  |  |  |
| Crossbred |  |  |  |
| Indigenous | 313459 | 158 tons(Meat) | 15 Kg/animal |
| Goats | 172411 | 134 tons(Meat) | 16 Kg/animal |
| Poultry birds (egg production) | 158656 | 72 lakh/year | 100 per year |

Source: District Statistical Office

GADAG DISTRICT MAP SHOWING PROPOSED VILLAGES FOR

KVK INTERVENTIONS

Asundi

Binkadakatti

Mallasamudra

Hulkoti

Hosalli

Kanavi

Hosur

Totaganti

Nai Mallapur

Bachalapur

Mallapur

Petalur

Ramenahalli

Jantli-Shirur

Churchihal

Shingatarayankere

Magadi

Bannikoppa

Sugenahalli

Tarikoppa

Madalli

Yetnalli

Kurlageri

Banahatti

Muganur

Hadli

Gangapur

Surkod

TABLE 1:  OPERATIONAL AREA DETAILS FOR 2010-11

| Sl. No. | Taluk | Blocks/ groups of villages | Major crops & enterprises being practiced | Major problems identified | Identified thrust areas |
| --- | --- | --- | --- | --- | --- |
| 1. | Gadag | Asundi Cluster (Comprising of Asundi, Mallasamudra and Binkadakatti) Hulkoti Cluster (Hulkoti and Hosalli) | - Greengram | - Abiotic Stress | - Integrated Crop Management - Seed Production - Pulse beetle management |
|  |  |  |  | - Poor seed replacement ratio |  |
|  |  |  |  | - Powdery mildew & yellow vein mosaic disease |  |
|  |  |  |  | - Incidence of pulse beetle |  |
|  |  |  | - Bunch Groundnut | - Abiotic stress | - Introduction of drought tolerant variety - ICM - Seed production |
|  |  |  |  | - Leaf spot disease |  |
|  |  |  |  | - Imbalanced nutrition |  |
|  |  |  |  | - Incidence of leaf minor |  |
|  |  |  |  | - Incidence of collar rot |  |
|  |  |  |  | - Poor seed replacement ratio |  |
|  |  |  | - Onion | - Improper sowing method | - ICM and introduction of Arka Kalyan variety - Seed production |
|  |  |  |  | - Poor keeping quality |  |
|  |  |  |  | - High incidence of purple blotch |  |
|  |  |  |  | - Imbalanced nutrition |  |
|  |  |  |  | - Non availability of quality seeds |  |
|  |  |  | - Chilli | - Abiotic stress | - ICM - Post harvest management - Murda complex management - Anthracnose management |
|  |  |  |  | - Murda complex |  |
|  |  |  |  | - High incidence of anthracnose |  |
|  |  |  |  | - Imbalanced nutrition |  |
|  |  |  |  | - Improper post harvest management |  |
|  |  |  |  | - Improper harvesting of fruit for seed purpose |  |
|  |  |  | - Bt Cotton | - Imbalanced nutrition | - ICM - Organizing campaigns |
|  |  |  |  | - Lack of knowledge on production technology |  |
|  |  |  |  | - High incidence of sucking pest |  |
|  |  |  | - Brinjal | - High incidence of shoot and fruit borer | - Management of shoot & fruit borer |
|  |  |  | - Ridge gourd | - Cultivation of local variety | - Introduction of Arka Sujata and Arka Sumit |
|  |  |  | - Chrysanthemum | - Imbalanced nutrition | - INM - Pinching - Introduction of Aster crop |
|  |  |  |  | - Fluctuation in prices |  |
|  |  |  | - Rabi Jowar | - Abiotic stress | - Spacing management - Seed priming - Preparation of jowar flakes |
|  |  |  |  | - Lack of value addition |  |
|  |  |  | - Mango | - High incidence of mango hopper & fruit fly | - Management of hopper, powdery mildew & fruit fly - Orchard management - Post harvest management - Management of nutrition |
|  |  |  |  | - Incidence of powdery mildew |  |
|  |  |  |  | - Improper orchard management |  |
|  |  |  |  | - Improper post harvest management |  |
|  |  |  |  | - Improper nutrition |  |
|  |  |  | - Dairy animals | - Improper nutrition | - Nutrition management |
|  |  |  | - Calf | - Incidence of worms | - Deworming |
|  |  |  | - Goat | - Low productivity of milk in local breed | - Introduction of Bidari breed |
|  |  |  | - Sheep | - Low productivity of meat & wool in local breed | - Introduction of Ramboullete breed |
|  |  |  | - Employment | - Lack of subsidiary occupations | - Vocational trainings |
|  |  |  | - Poor utilization of resources | - Improper irrigation & fertigation in Bt. Cotton, Brinjal, Tomato | - Introduction of precision farming practice |
|  |  |  | - Extension services | - Lack of Extension Services | - Establishment of resource centres with assistance from host Institution |
|  |  | Kanavi, Hosur, Shirunja, Yelishirunja, Harti & Hosalli | - Greengram, Groundnut, Bt. Cotton, Onion and Flowers | - Lack of intime advisory services | - Kharif campaigns |
|  |  |  | - Self employment | - Lack of self employment opportunities | - Vocational trainings in gardening |
| 2. | Shirahatti | Bannikoppa Cluster (Comprising of Bannikoppa, Tarikoppa, Sugnahall & Hadagali) | - Soil and water conservation | - Low soil fertility due to high erosion | - Soil & Water Conservation and promotion of Vermicompost for resource management |
|  |  |  | - Greengram | - Moisture stress | - Abiotic stress management - Introduction of selection-4 variety - ICM - Introduction of Twin Wheel Hoe Weeder - Pulse beetle management at household storage level |
|  |  |  |  | - Seed shattering |  |
|  |  |  |  | - Incidence of pod borer & leaf eating catter piller |  |
|  |  |  |  | - Incidence of powdery mildew |  |
|  |  |  |  | - Labour problem for weeding |  |
|  |  |  |  | - Incidence of pulse beetle |  |
|  |  |  | - Bunch Groundnut | - Abiotic stress | - In-situ soil moisture conservation practices - Introduction of GPBD-4 & TAG-24 variety - ICM - Collar rot management - Seed production |
|  |  |  |  | - Low productivity of local variety |  |
|  |  |  |  | - Imbalanced nutrition |  |
|  |  |  |  | - High incidence of leaf minor & collar rot |  |
|  |  |  |  | - Poor seed replacement |  |
|  |  |  | - Sunflower | - Imbalanced nutrition | - ICM - Spacing management |
|  |  |  |  | - Abiotic stress |  |
|  |  |  |  | - Incidence of leaf eating cater piller |  |
|  |  |  |  | - Incidence of powdery mildew & leaf spot |  |
|  |  |  |  | - Drudgery in earhead cutting | - Usage of cotton hand gloves for earhead cutting |
|  |  |  | - Bt. Cotton | - Lack of knowledge on production technology | - ICM - Spacing management - Promotion of intercropping system in Bt. Cotton |
|  |  |  |  | - Lack of intercropping systems |  |
|  |  |  | - Onion | - Low productivity due to imbalanced nutrition | - Introduction of Arka Kalyan - ICM - Chemical weeding |
|  |  |  |  | - Labour problem for weeding |  |
|  |  |  |  | - Incidence of purple blotch |  |
|  |  |  | - Chilli | - Non availability of quality seed | - Seed production - Murda complex & powdery mildew management - INM |
|  |  |  |  | - Murda complex |  |
|  |  |  |  | - Powdery mildew |  |
|  |  |  |  | - Imbalanced nutrition |  |
|  |  |  | - Rabi Jowar | - Moisture stress | - In-situ soil moisture conservation - Spacing management - Seed priming - Promotion of jowar flakes |
|  |  |  |  | - Lack of value addition |  |
|  |  |  | - Desi Cotton | - Moisture stress | - In-situ soil moisture conservation - Seed production of DDHC-11 variety - ICM |
|  |  |  |  | - Non availability of quality seeds |  |
|  |  |  | - Crop diversification | - Lack of crop diversification | - Promotion of fruit crops under dryland |
|  |  |  | - Self employment | - Lack of self-employment | - Vocational trainings on vermicompost, dairy, sheep & goat rearing |
|  |  |  | - Dairy animals | - Low production of milk due to poor nutrition | - Promotion of balanced nutrition through Azolla feeding |
|  |  |  | - Sheep | - Low of productivity of wool and meat | - Introduction of Ramboulette breed - Deworming |
|  |  |  |  | - Infestation of worms |  |
|  |  |  | - Poultry birds | - Low egg productivity | - Introduction of Swarnadhara breed birds |
|  |  |  | - Drudgery in cooking | - Drudgery in cooking & collecting firewood | - Promotion of Envirofit Chulha |
|  |  |  |  | - Drudgery in cutting of Jowar stalks | - Promotion of improved sickle |
|  |  | Magadi, Yetnalli, Madolli, Keralli & Parasapur | - Greengram, Spreading Groundnut, Chilli and Rabi Jowar | - Abiotic stress | - Kharif & rabi campaign - Seed production |
|  |  |  |  | - Non availability of improved seeds |  |
|  |  |  |  | - Lack of advisory services |  |
|  |  |  | - Nutrition | - Lack of awareness on health, hygiene and nutrition | - Awareness on nutrition, balanced diet, deficiency diseases |
| 3. | Ron | Totaganti Cluster (Comprising of Totaganti, Nai Mallapur & Bachalapur) | - Greengram | - Abiotic stress | - In-situ soil moisture conservation - Introduction of Selection-4 variety - Management of pod borer & powdery mildew - Introduction of Twin wheel hoe weeder |
|  |  |  |  | - Cultivation of local variety |  |
|  |  |  |  | - Incidence of pod borer and powdery mildew |  |
|  |  |  |  | - Labour problem in pod picking |  |
|  |  |  | - Drudgery | - Drudgery in weeding and labour problem in Greengram crop |  |
|  |  |  | - Groundnut | - Abiotic stress | - In-situ soil moisture conservation - INM - Introduction of GPBD-4 - Management of collar rot & leaf minor |
|  |  |  |  | - Imbalanced nutrition |  |
|  |  |  |  | - Incidence of leaf spot |  |
|  |  |  |  | - Incidence of collar rot and leaf minor |  |
|  |  |  | - Sunflower | - Abiotic stress | - In-situ soil moisture conservation - Wider row spacing - INM - Management of caterpillar & powdery mildew |
|  |  |  |  | - Imbalanced nutrition |  |
|  |  |  |  | - Incidence of leaf eating caterpillar & powdery mildew |  |
|  |  |  | - Onion | - Abiotic stress | - In-situ soil moisture conservation - INM - Introduction of Arka Kalyan - Seed production - INM |
|  |  |  |  | - Low keeping quality of bulb |  |
|  |  |  |  | - High incidence of purple blotch |  |
|  |  |  |  | - Non availability of quality seeds |  |
|  |  |  |  | - Imbalanced nutrition |  |
|  |  |  | - Bengalgram | - Incidence of wilt | - Introduction of JG-11 variety - Management of pod borer |
|  |  |  |  | - Incidence of pod borer |  |
|  |  |  | - Drudgery | - Drudgery in harvesting of crop | - Introduction of Cotton hand gloves |
|  |  |  | - Rabi Jowar | - Moisture stress | - Spacing management - Seed priming - Introduction of CSV-22 variety |
|  |  |  |  | - Poor fodder quality |  |
|  |  |  | - Value addition | - Lack of value addition | - Value addition in Jowar |
|  |  |  | - Nutrition | - Lack of awareness on health & hygiene and nutrition | - Awareness on health & hygiene and nutrition |
|  |  |  | - Drudgery | - Drudgery in cooking & collecting firewood | - Introduction of Envirofit Chulha |
|  |  |  | - Dairy (Buffaloe) | - Less intake of feed | - Enrichment of dry fodder - Balanced nutrition |
|  |  |  |  | - Low milk yield |  |
|  |  |  | - Sheep | - Low productivity of wool & meat | - Introduction of Ramboullete breed |
|  |  |  | - Goat | - Low milk production | - Introduction of Bidari breed |
| 4. | Naragund | Banahatti Cluster (Comprising of Banahatti, Kurlageri & Muganur) | - Maize | - Low productivity of crops due to soil sodicity - Incidence of stem borer and armyworm | - Soil reclamation - INM - Management of armyworm & stem borer |
|  |  |  | - Wheat | - Improper irrigation | - Water management - Introduction of GW-322 variety - INM - Introduction of improved Sickle |
|  |  |  |  | - Cultivation of non descript variety (Nirmal) |  |
|  |  |  |  | - Imbalanced nutrition |  |
|  |  |  |  | - Drudgery in harvesting of Wheat stalks |  |
|  |  |  | - Sunflower | - Imbalanced nutrition | - Poor seed setting - INM - Management of caterpillar & powdery mildew - Cotton hand gloves for harvesting of earhead |
|  |  |  |  | - Incidence of caterpillar and powdery mildew |  |
|  |  |  |  | - Drudgery in cutting earhead |  |
|  |  |  | - Bengalgram | - High incidence of wilt | - ICM - Introduction of JG-11 variety - Rust management - Irrigation management - Cotton hand gloves for harvesting - Introduction of Twin Wheel Hoe Weeder |
|  |  |  |  | - Incidence of pod borer |  |
|  |  |  |  | - High incidence of rust |  |
|  |  |  |  | - Improper schedule of irrigation |  |
|  |  |  |  | - Drudgery in harvesting of Bengalgram |  |
|  |  |  |  | - Drudgery in weeding |  |
|  |  |  | - Drudgery | - Drudgery in cooking | - Introduction of Envirofit Chulha |
|  |  |  | - Dairy Cow | - Low milk production due to imbalanced nutrition | - Balanced nutrition - Promotion of green fodder cultivation - Introduction of Butter churner |
|  |  |  |  | - Drudgery in churning of Butter |  |
|  |  |  | - Self employment | - Lack of employment | - Vocational training in dairy |
| 5. | Mundaragi | Petalur cluster (Comprising of Petalur, Ramenahalli, Janthli Sirur, Kadampur & Churchihal) | - Problematic Soil | - Low productivity due to sodicity of soil | - Reclamation of sodic soils |
|  |  |  | - Greengram | - Unsustainable production due to moisture stress | - Sustainable management practices - Pod borer and powdery mildew management - Introduction of Twin Wheel How Weeder |
|  |  |  |  | - Incidence of pod borer and powdery mildew |  |
|  |  |  |  | - Labour problem for weeding |  |
|  |  |  | - Spreading Groundnut | - Imbalanced nutrition | - INM - Management of rootgrub and leaf minor |
|  |  |  |  | - Incidence of rootgrub |  |
|  |  |  |  | - Incidence of leaf minor |  |
|  |  |  | - Sunflower | - Abiotic stress | - Wider row spacing and in-situ soil moisture conservation - INM - Management of caterpillar and powdery mildew - Irrigation management - Introduction of cotton hand gloves |
|  |  |  |  | - Imbalanced nutrition |  |
|  |  |  |  | - High incidence of caterpillar and powdery mildew |  |
|  |  |  |  | - Improper Irrigation |  |
|  |  |  |  | - Drudgery in earhead cutting |  |
|  |  |  | - Onion | - Moisture stress | - In-situ soil moisture conservation - Single row sowing - Chemical weed management - INM - Introduction of Arka Kalyan variety - Seed production |
|  |  |  |  | - Inter cultivation not possible due to criss- cross sowing |  |
|  |  |  |  | - Non availability of labours for weeding |  |
|  |  |  |  | - Poor keeping quality |  |
|  |  |  |  | - Incidence of purple blotch |  |
|  |  |  |  | - Non availability of quality seeds |  |
|  |  |  | - Maize | - Low productivity due to imbalanced nutrition | - INM - Armyworm management - Water management - Introduction of improved sickle |
|  |  |  |  | - Incidence of army worm |  |
|  |  |  |  | - Improper Irrigation |  |
|  |  |  |  | - Drudgery in cutting of Maize stalk |  |
|  |  |  | - Rabi Jowar | - Abiotic stress | - Spacing management - In-situ soil moisture conservation and seed priming |
|  |  |  | - Self Employment | - Lack of self employment opportunities | - Vocational trainings through Dairy and Vermicompost |
|  |  |  | - Drudgery | - Drudgery in cooking and collecting firewood | - Introduction of Envirofit Chulha |
|  |  |  | - Nutrition | - Problematic drinking water | - Soaking of drumstic seeds in water - Awareness on health, hygiene and Nutrition |
|  |  |  |  | - Lack of awareness on health & hygiene and Nutrition & Balanced Diet |  |
|  |  |  | - Goat | - Low productivity of milk | - Introduction of Bidari breed |
|  |  |  | - Sheep | - Low productivity of wool & meat | - Introduction of Rabmoullete breed |
|  |  |  | - Poultry birds | - Low egg productivity | - Introduction of Swarnadhara breed birds |

SUMMARY OF LIST OF THRUST AREAS FOR THE KVK FOR 2010-11

- Abiotic stress management strategies in Greengram, Groundnut, Sunflower, Rabi Jowar.

- Soil Reclamation

- Soil and Water Conservation

- Soil Fertility Management

- Integrated Crop Management strategies in Greengram, Groundnut, Onion & Chilli

- Seed production activities in Greengram, Groundnut, Onion, Bengalgram and Vegetable Crops

- Organization of Kharif and Rabi campaign for knowledge dissemination

- Establishment of resource centre in the selected villages for knowledge dissemination and input supply

- Up-gradation of local Sheep and Goat for high meat,  wool and milk production

- Introduction of improved poultry birds

- Value addition

- Introduction of drudgery reduction equipments

- Women and child health, hygiene and nutrition

## TABLE.2 Abstract of Interventions Proposed Based On the Identified Problems during 2010-11

| Sl. No. | Crop/Enterprise | Identified Problem | ###### Interventions |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Title of OFT if any | Title of FLD if any | Title of Training if any | Title of Training for extension personnel if any | Others |
| 1 | Greengram | - Abiotic stress | Refinement of resource conservation technologies for sustainable production | ICM in greengram | ICM | ICM | Field day |
|  |  | - Powdery mildew and yellow vein mosaic disease - Imbalanced nutrition | - | - | As above | As above | As above |
|  |  | - Labour problem for weeding | - | Introduction of Twin Wheel Hoe Weeder | Drudgery reducing equipments | - | Method demonstration |
|  |  | - Non availability of quality seeds | - | - | Seed production in greengram | - | Seed production |
|  |  | - Incidence of pulse beetles | Management of pulse beetles | - | - | - | - |
| 2 | Bunch groundnut | - Abiotic stress | Assessment of K-6 variety and ICGV-91114 for drought tolerance | - | ICM | - | Field day |
|  |  | - Imbalanced nutrition - Incidence of leaf minor - Cultivation of low productive local variety | Micro nutrient management |  | ICM | ICM | - Field day - Seed production |
|  |  | - Collar rot | Collar rot management | - | Collar rot management | - | - |
|  |  | - Drudgery in shelling | - | Demonstration of groundnut decorticator with separator | - | - | - |
| 3 | Spreading groundnut | - Low productivity due to moisture stress | Resource conservation technologies for sustainable production | - | Resource conservation technologies | Resource conservation technologies | - |
| 3 | Summer groundnut | - Low production of local variety - Imbalanced nutrition | - | - | ICM | ICM | - Field day - Seed production |
|  |  | - Poor keeping quality - High incidence of purple blotch | - Assessment of Agri found light red variety - Thrips management | Introduction of Arka Kalyan | ICM | ICM | Field day, literature |
|  |  | - Non availability of quality seed | - | - | Seed production | - | Seed production & seed supply |
| 5 | Chilli | - Murda complex | Management of murda complex | - | Management of murda complex | - | Field day |
|  |  | - High incidence of Anthracnose | Anthracnose management | - | Management of Anthracnose | - |  |
| 6 | Bt. Cotton | - Imbalanced nutrition - High incidence of sucking pest | - |  | ICM | - | - |
|  |  | - Lack of knowledge on production technology | - | - | - | - | Campaigns & development of literature |
| 7 | Desi cotton | - Low productivity of Jayadhar cotton - Moisture stress - Non availability of quality seed | - | ICM in DDHC-11 variety | ICM | ICM | - Field day - Seed production |
| 8 | Sunflower | - Moisture stress - Imbalanced nutrition - Incidence of powdery mildew and leaf spot | Bio-fertilizer management |  | ICM | ICM | - Field day - Literature |
|  |  | - Drudgery in cutting of ear head | Assessment of Cotton cloth hand gloves | - | - | - | Supply of Cotton cloth hand gloves |
| 9 | Bengalgarm | - Incidence of wilt - Incidence of pod borer - Drudgery in harvesting | Assessment of various types of hand gloves | Introduction of JG-11 variety along with ICM | ICM | ICM | Field day, Seed production |
| 10 | Rabi jowar | - Moisture stress - Low productivity of Maladandi (M35-1) | - Assessment of Anuradha variety for higher productivity - Resource conservation technologies for sustainable production | - Introduction of CSV-22 | - ICM - Resource conservation technologies | - ICM - Resource conservation technologies | - Field day |
|  |  | - Drudgery in cutting of jowar stalks | - | Serrated sickle | Serrated sickle | - | Supply of serrated sickle |
| 11 | Maize | - Low productivity due to soil sodicity | - | - | Soil fertility management | Soil fertility management | - |
|  |  | - Imbalanced nutrition and incidence of stem borer and army worm | - | ICM | ICM | - | - Field day - Literature |
| 12 | Wheat | - Improper irrigation | - | - INM - Stem borer management | Water management | Water management | - |
|  |  | - Cultivation of non descript variety (Nirmala) | - | Introduction of GW-322 and UAS-304 variety | ICM | ICM | Field day |
|  |  | - Drudgery in harvesting of wheat stalks | - | Serrated sickle | - | - | Supply of sickle |
| 13 | Brinjal | - High incidence of shoot & fruit borer | - | Shoot & fruit borer management | Shoot & fruit borer management | - | - Field day - Literature |
| 14 | Chrysanthemum | - Imbalanced nutrition | Boron nutrition | INM | INM | INM | - |
|  |  | - Non opening of buds | Usage of potassium nitrate & GA for bud opening | - | INM | - | - |
|  |  | - Fluctuation of prices of Chrysanthemum | - | Introduction of Aster for better market price | ICM | - | - Field day - Literature |
| 15 | Tomato | - Leaf curl incidence | - | Introduction of Arka Abha variety | ICM | - | Field day |
| 16 | French bean | - Low productivity of local variety | - | Introduction of Arka Suvida variety | ICM | - | Field day |
| 17 | Ridge gourd | - Low productivity of local variety | - | Introduction of Arka Sujata and Sumit varieties | ICM | - | Field day |
| 18 | Mango | - Improper nutrition | Assessment of foliar application of nutrients | - | INM | INM | - |
|  |  | - Incidence of powdery mildew | - | Management of powdery mildew | Management of powdery mildew | - | - |
|  |  | - Incidence of mango hopper | - | Management of mango hopper | Management of mango hopper | - | - |
|  |  | - Improper orchard management | - | - | Orchard management | - | - |
| 18 | Goat | - Low productivity of milk of local breeds | - |  | Goat management | - | Supply of bucks |
| 19 | Sheep | - Low productivity of meat & wool - Endoparasite incidence | Management of endoparasites | - Ecto and endo parasite management | Sheep management | - | Supply of Rams |
| 20 | Poultry birds | - Low egg production | - | Introduction of Swarnadhara breed of poultry birds | Management of backyard poultry | - | Supply of birds |
| 21 | Cattle | - Incidence of tick | Tick management | - | Management of tick | - | - |
| 22 | Nutrition and Balanced Diet | - Lack of awareness | - | - | Awareness on nutrition, diet and deficiency diseases | Awareness on nutrition, diet and deficiency diseases | - |
| 23 | Self employment | - Lack of self employment opportunities | - | - | Vocational training in dairy, goat, seed production, value addition in major crops and vermicomposting |  |  |

TABLE 2A. Target set for number of interventions to be implemented during 2010-11

| S. No | Particulars of intervention | Target number / Quantity |
| --- | --- | --- |
| 01 | On Farm Trial | 21 |
| 02 | Front Line Demonstration (other than oil seeds, pulses and cotton) | 377 |
| 03 | Front Line Demonstration (Oilseeds) | 115 |
| 04 | Front Line Demonstration (Pulses) | 100 |
|  | Training Programmes |  |
| 01 | Farmers and farm women | 82 Courses |
| 02 | Extension personnel | 12 Courses |
| 03 | Sponsored programmes | 36 Courses |
| 04 | Vocational Programmes | 11 Courses |
|  | Extension Programmes |  |
| 01 | Field Day | 12 |
| 02 | Kisan Mela (Technology Week) | 02 |
| 03 | Kisan Ghosthi | 02 |
| 04 | Exhibition | 01 |
| 05 | Film Show | 15 |
| 06 | Method Demonstrations | 35 |
| 07 | Farmers Seminar on Azolla cultivation | 01 |
| 08 | Workshop | 02 |
| 09 | Group meetings | 20 |
| 10 | Lectures delivered | 02 |
| 11 | Newspaper coverage | 15 |
| 12 | Radio coverage | 06 |
| 13 | TV coverage | 05 |
| 14 | Radio Programmes | 07 |
| 15 | TV Programmes | 06 |
| 16 | Publications | 05 |
| 17 | Popular articles | 08 |
| 18 | Extension Literature | 10 |
| 19 | Advisory Services | 60 |
| 20 | Scientific visit to farmers field | 50 |
| 21 | Farmers visit to KVK | 15 |
| 22 | Diagnostic visits | 10 |
| 23 | Field visits | 100 |
| 24 | Exposure visits | 05 |
| 25 | Ex-trainees Sammelan | 05 |
| 26 | Agriculture Camps | 02 |
| 27 | Clinic day | -- |
| 28 | Soil health Camp | 02 |
| 29 | Animal Health Camp | 02 |
| 30 | Agri mobile clinic | -- |
| 31 | Soil test campaigns | 03 |
| 32 | Farm Science Club Conveners meet | -- |
| 33 | Self Help Group Conveners meetings | 10 |
| 34 | Mahila Mandals Conveners meetings | -- |
| 35 | Celebration of Nutrition week | 01 |
| 36 | PRA exercise conducted | 05 |
| 37 | Survey on socio economic improvement through Animal Science to SHG women | -- |
| 38 | Awareness on Cotton contract farming | -- |
| 39 | Distribution of BT cotton seeds under contract farming in collaboration with Cotton Corporation of India | -- |
| 40 | Insect trap awareness campaign | -- |
| 41 | AIDS awareness campaign | -- |
| 42 | Awareness on KVK activities to Tribes | -- |
| 43 | Formation of Joint Liability Groups | 10 |
|  | Production and supply of seed materials |  |
| 01 | 1) Cereals | 25 Qts. |
| 02 | ii) Oilseeds | 45 Qts. |
| 03 | iii) Pulses | 50 Qts. |
| 04 | iv) Vegetables | 17 Qts. |
| 05 | v) Flower crops | -- |
| 06 | vi) Others (Specify) | -- |
|  | Production and supply of Planting materials |  |
| 01 | Fruits | 4000 |
| 02 | Spices |  |
| 03 | Vegetables |  |
| 04 | Forest species |  |
| 05 | Ornamental crops |  |
| 06 | Plantation crops |  |
| 07 | Others (Simaroubha) | 2000 |
|  | Production and supply of bio-products |  |
| 01 | Bio agents | 1.20 Qts. |
| 02 | Bio fertilizers |  |
| 03 | Bio pesticides |  |
|  | Production and supply of livestock material |  |
| 01 | Sheep |  |
| 02 | Goat |  |
| 03 | Fisheries |  |
| 04 | Others (Specify) |  |
| 01 | Number of soil samples to be analyzed | 630 |
| 02 | Number of water samples to be analyzed | 130 |
| 03 | Number water samples to be analyzed | 10 |

## TABLE. 3   PLAN OF ON FARM TESTING FOR 2010-11

| ASSESSMENT NO. 01 |  |  |
| --- | --- | --- |
| - Title of the On Farm Trial | : | Evaluation of Kadiri-6 and ICGV-91114 Groundnut (Bunch) varieties for drought tolerance |
| - State whether it is Assessment / Refinement | : | Assessment |
| - Agro-Ecological Zone | : | Northern dry zone-3, Region-2 |
| - Production System | : | Medium and big farmers production system under rainfed situation |
| - Problem identified | : | Erratic rainfall & long dry spells results in low productivity in existing varieties of Groundnut |
| - Number of farmers and area affected in the operational villages | : | 5000 farmers in an area of 15000 ha |
| - Thrust areas | : | Assessment of Kadari-6 and ICGV-91114 variety against drought tolerance |
| - Rationale for proposing the OFT | : | Kadari-6 variety is drought tolerant having bold kernals, high oil content & high yielding. ICGV-91114 is also drought resistant, has high oil content and resistant to tikk disease. |
| - Technology Option-1 with Source {Recommended practice and extent of its adoption} | : | Local variety (TMV-2) Extent of yield loss 35-40% |
| - Technology Option-2 with Source {Recommended practice and extent of its adoption} | : | GPBD-4 variety Extent of its adoption : 35% Level of yield loss during long dry spells : 25-30% |
| - Technology Option-3 being assessed along with justification with Source | : | - Evaluation of K-6 variety which is drought tolerant having bold kernals, high oil content and high yielding - Evaluation of ICGV-91114 variety which also can withstand long dry spells and yield better Source : ARS, Kadari and ANGRAU, Anatapur district and ICRISAT, Hyderabad |

- Budget proposed : 0.4 ha

| Sl. No. | Critical Inputs for Technology Option 2 (Recommended Practice) |  |  |  | Critical inputs for other technology Options |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) |
| 1. | GPBD-4 (Pods) | 0.75 Qt. | 3500/- | 2625/- | K-6 (Pods) ICGV-91114 | 0.75 Qt. 0.75 Qt. | 5500/- 5500/- | 4125/- 4125/- |

- Area (ha.)  for implementing  : 1.2  ha

- Technology Option 1 (Farmer’s Practice)  		: 0.4 ha

- Technology Option 2 (Recommended Practice) 	: 0.4 ha

- Technology option  3 				: 0.4 ha

- Grand Total Cost proposed per OFT 	: Rs. 4125/-

- Total Number of OFTs proposed       	: 03

- Total budget required                         : Rs. 12375/-

ASSESSMENT NO.2

| 1. | Title of the On Farm Trial | : | Micronutrient management in groundnut |
| --- | --- | --- | --- |
| 2. | State whether it is Assessment / Refinement | : | Assessment |
| 3. | Agro-Ecological Zone | : | North dry zone-3, Region-2 |
| 4. | Production System | : | Medium & big farmers production system under irrigation system |
| 5. | Problem identified | : | Micronutrient deficiency |
| 6. | Number of farmers and area affected in the operational villages | : | 5000 farmers in an area of 15000 ha. |
| 7. | Thrust areas | : | Micronutrient management |
| 8. | Rationale for proposing the OFT | : | Major part of soils are deficit in Fe, Zn and Boron. Hence its management can ensure better yield. |

9. Technology Option I

| Sl. No | Technological Options | Details of technology |
| --- | --- | --- |
| 1. | Farmer’s Practice | Application of only major nutrients |
| 2. | Name of the fertilizer & quantity | DAP @ 50 kg/ ha |
| 3 | Extent of Yield loss | 30 % |
| 4 | Method of use | Basal application during sowing in seed rows |

10. Technology Option II

| Sl. No | Technological Options | Details of technology |
| --- | --- | --- |
| 1 | Recommended Practices | Soil application of FeSO4 and ZnSO4 @ 25kg/ha each |
| 2 | Extent of its adoptions | 20% |
| 3 | Source of technology | UAS, Dharwad |
| 4 | Reasons for low adoptions | Increasing multi micronutrient deficiency in groundnut ecosystem will not be rectified by use of one or two nutrients, hence its adoption will not increase the crop yield to significant level which can be rectified by use of multi micro nutrients application. |

11. Technology Option III

| Details of Technology | Source of Technology | Justification |
| --- | --- | --- |
| Soil application of FeSO4 and ZnSO4 @ 25kg/ha each & Boran @ 4 kg/ha | ICRISAT, Hyderabad | Balanced use of micronutrient along with major nutrient helps in getting higher yield, better quality and incidence of diseases will be less. |

12.  Budget proposed for OFT

| Sl. No | Critical Inputs for Technology Option 2 (Recommended Practice) |  |  |  | Critical inputs for other technology Options |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Name | Qty (Kg) | Unit Cost (Rs.) | Total Cost (Rs.) | Name | Qty (Kg) | Unit Cost (Rs.) | Total Cost (Rs.) |
| 1 | FeSO4 | 10 | 60 | 600 | FeSO4 | 10 | 60 | 600 |
| 2 | ZnSO4 | 10 | 38 | 380 | ZnSO4 | 10 | 38 | 380 |
| 3 |  |  |  |  | Boran | 2 | 300 | 600 |
|  | Total |  |  | 980 | Total |  |  | 1580 |

13. Area (ha.)  For implementing

- Technology Option 1 (Farmer’s Practice) 		: 0.4 ha

- Technology Option 2 (Recommended Practice)	 :0.4 ha

- Technology option  3 					: 0.4 ha

14. Grand Total Cost proposed per OFT 			: Rs. 2560/-

15. Total Number of OFTs proposed       			: 3

16. Total budget required                        				: Rs. 7680/-

| ASSESSMENT NO. 3 |  |  |
| --- | --- | --- |
| - Title of the On Farm Trial | : | Collar rot management in Groundnut |
| - State whether it is Assessment / Refinement | : | Assessment |
| - Agro-Ecological Zone | : | Northern dry zone |
| - Production System | : | Medium and big farmers production system under rainfed condition |
| - Problem identified | : | Incidence of collar rot disease is affecting the Groundnut productivity. The disease occurs immediately after germination of crop and it will continue throughout the crop season. The yield loss is about 35-40% |
| - Number of farmers and area affected in the operational villages | : | More than 3000 farmers in about 8000 ha area |
| - Thrust areas | : | Management of collar rot in Groundnut |
| - Rationale for proposing the OFT | : | Seed treatment with Vitawax and Trichoderma controls the disease within the seed (seed borne) as well as externally by suppressing the colonization of Rhizosphere at root zone |
| - Technology Option-1 with Source {Farmers practice} | : | Seed treatment with captan @ 2gm/kg of seed Extent of yield loss 15-25% |
| - Technology Option-2 with Source {Recommended practice and extent of its adoption} | : | Seed treatment with Trichoderma @ 4 gm/kg seed Source : UAS, Dharwad Extent of its adoption : 15-20% |
| - Technology Option-3 being assessed along with justification with Source | : | Seed treatment with Vitawax @ 3gms + Trichoderma Viridae @ 4 gm/kg seed. Source : UAS, Dharwad Justification : Vitawax & Trichoderma are combination of systematic and contact bio-fungicide. These both effectively control diseases within the seed as well as externally by suppressing the colonization of rhizosphere at the root zone. |

- Budget proposed : (For 1 Ha)

| Sl. No. | Critical Inputs for Technology Option 2 (Recommended Practice) |  |  |  | Critical inputs for other technology Options |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) |
| 1. | Trichoderma | 400gm | 200/kg | 80/- | Trichoderma | 400gm | 200/kg | 80/- |
|  |  |  |  |  | Vitawax | 300gm | 140/100gm | 420/- |
|  | Total |  |  | 80/- |  |  |  | 500/- |

- Area (ha.)  for implementing  :

- Technology Option 1 (Farmer’s Practice)  		: 1 ha

- Technology Option 2 (Recommended Practice) 	: 1 ha

- Technology option  3 				: 1 ha

- Grand Total Cost proposed per OFT 	: Rs. 580/-

- Total Number of OFTs proposed       	: 3

- Total budget required                         : Rs. 1740/-

ASSESSMENT NO.4

| 1. | Title of the On Farm Trial | : | Use of biofertilizer in sunflower |
| --- | --- | --- | --- |
| 2. | State whether it is Assessment / Refinement | : | Assessment |
| 3. | Agro-Ecological Zone | : | Northern dry zone-3, Region-2 |
| 4. | Production System | : | Medium and big farmers production system under irrigation system |
| 5. | Problem identified | : | Increased cost of chemical fertilizer |
| 6. | Number of farmers and area affected in the operational villages | : | More than 400 farmers in an area of about 500 ha. |
| 7. | Thrust areas | : | Biofertilizer use |
| 8. | Rationale for proposing the OFT | : | Cost incurred on chemical fertilizers is more. Besides it is causing environmental pollution. Hence there is a need to reduce the use of chemical fertilizers. On the contrary, biofertilizers are available with low cost and help in reducing environmental pollution and increase the crop yield. |

9. Technology Option I

| Sl. No | Technological Options | Details of technology |
| --- | --- | --- |
| 1 | Farmer’s Practice | Very less farmers are using biofertilizer (10%) |
| 2 | Name of the fertilizer & quantity | DAP-125 Kg/ha (22-57-0 NPK Kg/ha) |
| 3 | Extent of Yield loss | 30 % |
| 4 | Method of use | Seed treatment |

10. Technology Option II

| Sl.No | Technological Options | Details of technology |
| --- | --- | --- |
| 1 | Recommended Practices | Application of NPK @ 60:75:60 kg/ha and Azospirillum @ 500gr/ha |
| 2 | Extent of its adoptions | 20 % |
| 3. | Source of technology | UAS, Dharwad |
| 4. | Reasons for low adoptions | Increasing cost of inorganic fertilizers and unavailability at right time |

- Technology Option III

| Details of Technology | Source of Technology | Justification |
| --- | --- | --- |
| Application of NPK @ 30:75:60 kg/ha and Azospirillum & Azotobactor @ 500g/ ha each | DOR, Hyderabad | Combined use of Azospirillum and Azotobact or helps in reducing 50 % recommended nitrogen without reducing the yield. |

- Budget proposed for OFT: 0.4 ha

| Sl. No | Critical Inputs for Technology Option 2 (Recommended Practice) |  |  |  | Critical inputs for other technology Options |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Name | Qty (Kg) | Unit Cost (Rs.) | Total Cost (Rs.) | Name | Qty (Kg) | Unit Cost (Rs.) | Total Cost (Rs.) |
| 1 |  |  |  |  | Azospirillum | 0.50 | 30 | 15 |
| 2 | Azospirillum | 0.50 | 30 | 15 | Azotobactor | 0.50 | 30 | 15 |
|  | Total |  |  | 15 | Total |  |  | 30 |

- Area (ha.)  For implementing

- Technology Option 1 (Farmer’s Practice) 		: 2.0 ha

- Technology Option 2 (Recommended Practice)	: 2.0 ha

- Technology option  3 					: 2.0 ha

14. Grand Total Cost proposed per OFT 			: Rs. 45

15. Total Number of OFTs proposed       			: 10

16. Total budget required                        				: Rs. 450

ASSESSMENT NO.5

1. Title of the On Farm Trial                           :  Introduction of new variety  for increasing productivity of rabi sorghum in shallow soils

2. State whether it is Assessment / 		: Assessment

Refinement

3. Agro-Ecological Zone			: Northern Dry Zone-3, Region-2

4. Production System 				: Rainfed production System

5. Problem identified 				: Yields are very low in shallow soils

6. Number of farmers and area affected   	: More than 850 farmers in about 2640 ha.

In the operational villages

7. Thrust areas 				: Introduction of new variety

8. Rationale for proposing the OFT 		: This new variety Anuradha  is early

maturing and  this helps in

overcoming the problem of  receeding

moisture regime during rabi season

9.Technology Option 1			 : M 35-1, yield  loss 40-45%

10.Technology Option 2

| Recommended practice | Source | Level of Adoption | Reasons for no/low adoption |
| --- | --- | --- | --- |
| M 35-1 | UAS, Dharwad | 100 % | - |

11.Technology Option 3

| Assessment planned | Source | Justification |
| --- | --- | --- |
| Variety - Anuradha | MPKV, Rahuri | Anuradha is early maturing, drought tolerant and high yielding variety |

12.Budget proposed : (For 0.4 ha)

| S. No | Critical Inputs for Technology Option 2 (Recommended Practice) |  |  |  | Critical inputs for other technology Options |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Name | Qty. (Kg) | Unit Cost (Rs.) | Total Cost (Rs.) | Name | Qty. (kg) | Unit Cost (Rs.) | Total Cost (Rs.) |
|  | Seeds (M-35-1) | 3.0 | 25 | 75 | Seeds(Anuradha) | 3.0 | 50 | 150 |
|  |  |  |  | 75 |  |  |  | 150 |

13.Area (ha.)  for implementing :

  - Technology Option 1 (Farmer’s Practice)		 : 4.0 ha

ii)      Technology Option 2 (Recommended Practice) 	 : 4.0 ha

  - Technology option  3 					 : 4.0 ha

14. Grand Total Cost proposed per OFT 			 : Rs. 225/-

15. Total Number of OFTs proposed      				 : 10

16. Total budget required                         			 : Rs. 2250/-

| - ASSESSMENT NO. 6 - Title of the On Farm Trial; :; Evaluation of Agrifound light red variety of onion for high yielding & better keeping quality bulbs. - State whether it is Assessment / Refinement; :; Assessment. - Agro-Ecological Zone; :; Northern dry zone-3, Region-2. - Production System; :; Big farmers production system under dry land condition. - Problem identified; :; In identified villages farmers are using local onion variety (Bellary red) since long time and its bulbs are having low keeping quality. Hence this variety is fetching less price in the market and farmers incur losses.. - Number of farmers and area affected in the operational villages; :; More than 3000 farmers in an area of 10000 ha.. - Thrust areas; :; Evaluation of new high yielding onion variety. - Rationale for proposing the OFT; :; Agrifound light red variety produce good keeping quality bulb & it is high yielding variety. - Technology Option 1 with Source; :; Cultivating Bellary red and there is more than 20-25% yield loss (Farmers’ practice). - Technology Option 2 with Source; :; - Recommending certified Bellary red variety seeds and 40-50% adoption is observed - Source: UAS, Dharwad. - Technology Option 3 being assessed along with justification with Source; :; Introduction of Agrifound light red onion variety Source: National Horticultural Research & Development Foundation (NHRDF), Nasik Justification: Agrifound light red variety is a high yielder and produces good quality bulbs. Hence it fetches higher market price.. - Budget proposed for OFT : (0.4 ha) S. No; Critical Inputs for Technology Option 2 (Recommended Practice); Critical inputs for other technology Options. Name; Qty.; Unit Cost (Rs.); Total Cost (Rs.); Name; Qty.; Unit Cost (Rs.); Total Cost (Rs.). 1; Seed (Bellary red variety); 1 Kg; 350; 350; Seed (Agrifound light red variety); 1 Kg; 450; 450. Total; 350; Total; 450. - Area (ha.) for implementing : - Technology Option 1 (Farmer’s Practice) : 0.4 ha - Technology Option 2 (Recommended Practice) : 0.4 ha - Technology option 3 (Alternate practice) : 0.4 ha - Grand Total Cost proposed per OFT : Rs.800 - Total Number of OFTs proposed : 3 - Total budget required : Rs.2400/- ASSESSMENT NO. 7. - Title of the On Farm Trial; :; Thrips management in onion. - State whether it is Assessment / Refinement; :; Assessment. - Agro-Ecological Zone; :; Northern dry zone-3, Region-2. - Production System; :; Rainfed. - Problem identified; :; Severe thrips infestation is reducing the yield. - Number of farmers and area affected in the operational villages; :; More than 3000 farmers in an area of 10000 ha.. - Thrust areas; :; Pest management in vegetables. - Rationale for proposing the OFT; :; Lamda cyhalothrin @ 0.5 ml/lit is found to be effective chemical resulting in higher yield per unit area. - Technology Option 1 with Source; :; Dimethoate (1.75 ml/lit) Yield loss: 35-40%. - Technology Option 2 with Source; :; - Dimethoate @ 1.75 ml/lit - Extent of adoption: 60-70% - Source: UAS, Dharwad. - Technology Option 3 being assessed along with justification with Source; :; Maize as a boarder crop Spray of (Lamda) α -Cyholothrin @ 0.5 ml/lit (two sprays) Source: NRC for onion and garlic, Pune Justification: α –Cyholothrin is a contact and fumigant insecticide. Hence it effectivelyt reduces the thrips infestation in onion. Thereby the productivity of onion crop increases.. - Budget proposed for OFT : (1 Ha) S. No; Critical Inputs for Technology Option 2 (Recommended Practice); Critical inputs for other technology Options. Name; Qty.; Unit Cost (Rs.); Total Cost (Rs.); Name; Qty.; Unit Cost (Rs.); Total Cost (Rs.). 1; Dimethoate; 750; 550; 413; L-cyholothrin; 200; 60; 120. Total; 413; Total; 120. - Area (ha.) for implementing : - Technology Option 1 (Farmer’s Practice) : 1.4 ha - Technology Option 2 (Recommended Practice) : 1.4 ha - Technology option 3 (Alternate practice) : 1.4 ha - Grand Total Cost proposed per OFT : Rs.533 - Total Number of OFTs proposed : 03 - Total budget required : Rs.1599/- ASSESSMENT NO. 08 |
| --- |
| - Title of the On Farm Trial | : | Management of Anthracnose in Chilli |
| - State whether it is Assessment / Refinement | : | Assessment |
| - Agro-Ecological Zone | : | Northern dry zone |
| - Production System | : | Medium and big farmers production system under rainfed condition |
| - Problem identified | : | The disease appear on ripened fruit, fruit stalk and spread along with the stem and in severe cases cause die-back symptom on the Chilli plant. The fruit with many spots drop off prematurely, resulting in crop losses up to 30-45%. |
| - Number of farmers and area affected in the operational villages | : | More than 3000 farmers in about 6000 ha area |
| - Thrust areas | : | Management of Anthracnose in Chilli |
| - Rationale for proposing the OFT | : | It is possible to reduce the incidence of Anthracnose in Chilli by spraying Difenconazole and Trichoderma. These reduce the infestation by suppressing the colonization of conidial spores and thus helps in getting better quality Chilli fruit. |
| - Technology Option-1 with Source (Farmers’ Practice) | : | Spraying Dithane M-45 @ 2gm/ltr. |
| - Technology Option-2 with Source (Recommended Practice and extent of its adoption) | : | Spraying COC (Copper Oxy Chloride) @ 3gms/ltr or Mancozeb @ 3gm/ltr of water two times. Source : UAS, Dharwad Adoption : 10-15% |
| - Technology Option-3 being assessed along with justification with Source | : | Foliar spray of Difenconazole @ 1ml/ltr (UAS,Dharwad) with Trichoderma viridae @ 3gm/ltr. (TNAU, Coimbatore) Source : UAS, Dharwad and TNAU, Coimbatore Justification: Spraying Difenconazole fungicide with Trichoderma viridae suppress the colonization of conidial spores on fruits & twigs during cloudy weather and thereby increase the production of good quality dry Chilli fruits. |

- Budget proposed : (For 0.4 ha )

| Sl. No. | Critical Inputs for Technology Option 2 (Recommended Practice) |  |  |  | Critical inputs for other technology Options |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) |
| 1. | Copper Oxy Chloride | 1 kg. | 450/- | 450/- | Difenconazole | 300 ml | 320/100ml | 960/- |
|  |  |  |  |  | Trichoderma viridae | 1 Kg. | 200/Kg. | 200/- |
|  | Total |  |  | 450/- |  |  |  | 1160/- |

- Area (ha.)  for implementing : 12 ha

- Technology Option 1 (Farmer’s Practice)  		: 4 ha

- Technology Option 2 (Recommended Practice) 	: 4 ha

- Technology option  3 				: 4 ha

- Grand Total Cost proposed per OFT 	: Rs. 1610/-

- Total Number of OFTs proposed       	: 03

- Total budget required                         : Rs. 4830/-

| ASSESSMENT NO. 09 |  |  |
| --- | --- | --- |
| - Title of the On Farm Trial | : | Murda disease management in Chilli |
| - State whether it is Assessment / Refinement | : | Assessment |
| - Agro-Ecological Zone | : | Northern dry zone |
| - Production System | : | Medium and big farmers production system under rainfed condition |
| - Problem identified | : | The upward and downward curling of leaf due to heavy infestation of thrips and mites in Chilli resulted in yield loss up to 35-40%. |
| - Number of farmers and area affected in the operational villages | : | More than 3000 farmers in about 6200 ha Area |
| - Thrust areas | : | Management of murda disease |
| - Rationale for proposing the OFT | : | There is heavy incidence of thrips and mites resulting into murda complex disease in Chilli crop. An assessment is proposed as to how a package of technologies can reduce the pest population. Hence, four treatments are proposed to reduce the thrips and mite population, (i) Treat the seeds with imidachloprid, (ii)Soil application of Neemcake, (iii) Jowar as a barrier crop and (iv)Foliar application of imidacloprid and Garlic + Chilli extract. |
| - Technology Option-1 with Source {Farmers practice} | : | Spraying with Dimethoate @ 1.7 ml/ltr Extent of yield loss @ 50% |
| - Technology Option-2 with Source {Recommended practice and extent of its adoption} | : | - Spraying of Dimethoate @ 1.7 ml/ltr of water at 20-25 days after sowing - Second Spraying of Dimethoate @ 1.7 ml/ltr of water at 35-40 days after sowing - Spray of Dicofol @ 2.5 ml/ltr of water at 60-70 days after sowing - Extent of adoption 20-30% Source : UAS, Dharwad |
| - Technology Option-3 being assessed along with justification with Source | : | - Seed treatment with Imidachloprid @ 5 gm per kg seed - Soil application of neem cake @ 250 kg/ha+ Vermicompost @ 5 Qtl/ha ( UAS, Dharwad) - Sorghum as boarder crop (Six row on all four sides of the cropped field) (Farmers’ practice) - Mixing Coriander with Chilli (100gm in one kg of Chilli seeds) (Farmers’ practice) - Foliar spray of Imidachloprid @ 0.25ml per liter of water (TNAU, Coimbatore) - Foliar spray of Garlic + Green Chilli (1:1) 2.5% with Nimbicidin @ 2.5 ml/litr + Cow urine 10% (CIKS, Chennai) Source : (i)UAS, Dharwad, (ii)CIKS, Chennai & (iii)TNAU, Coimbatore (iv) ITKs followed by farmers Justification: Seed treatment with imidachloprid and soil application of neemcake suppress the thrips & mite pest build-up in the crop. Neemcake has got a repellent and ovicidal effect. Mixed cropping with coriander has repelling effect on the insect. Sorghum as boarder crop checks the thrips and mite spread from field to field. Timely spray of imidachloprid and Garlic+Chilli extract will reduce the spread of the incidence. |

- Budget proposed : (For 0.4 ha)

| Sl. No. | Critical Inputs for Technology Option 2 (Recommended Practice) |  |  |  | Critical inputs for other technology Options |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) |
| 1. | Dimethoate | 0.6 ltr. | 355/ltr. | 213/- | Neemcake | 1 Qt. | 650/Qt. | 650/- |
| 2. | Dicofol | 0.3 ltr. | 430/ltr. | 129/- | Coriander | 100 gm | 150/250gm | 60/- |
|  |  |  |  |  | Garlic | 2 Kg. | 70/Kg. | 140/- |
|  |  |  |  |  | Green Chilli | 2 Kg. | 25/Kg. | 50/- |
|  |  |  |  |  | Imidachloprid (liquid) | 40 ml. | 213/100ml | 85/- |
|  |  |  |  |  | Imidachloprid | 5gm | Rs. 55/5gm | 55/- |
|  | Total |  |  | 342/- |  |  |  | 1040/- |

- Area (ha.)  for implementing  : 06 ha

- Technology Option 1 (Farmer’s Practice)  		: 2.4 ha

- Technology Option 2 (Recommended Practice) 	: 2.4 ha

- Technology option  3 				: 2.4 ha

- Grand Total Cost proposed per OFT 	: Rs. 1382/-

- Total Number of OFTs proposed       	: 03

- Total budget required                         : Rs. 4146/-

| ASSESSMENT NO. 10 |  |  |
| --- | --- | --- |
| - Title of the On Farm Trial | : | Boron nutrition for higher productivity of flowers in Chrysanthemum |
| - State whether it is Assessment / Refinement | : | Assessment |
| - Agro-Ecological Zone | : | Northern dry zone-3, Region-2 |
| - Production System | : | Medium and Big farmers production system under irrigation situation |
| - Problem identified | : | Due to boron deficiency peripheral flowers loose turgidity before central flowers fully open & the petals are twisted and turn to cup shape. |
| - Number of farmers and area affected in the operational villages | : | More than 100-120 farmers in an area of about 150-170 ha affected in the operational villages |
| - Thrust areas | : | Nutrition |
| - Rationale for proposing the OFT | : | Application of boron @ 2kg/ha (12 kg borosoil-soil fertiliser) and foliar spray of 0.2% Boric acid for two times at 21 days after planting & at 25% flower bud emergence. This treatment reduces the deficiency of boron in Chrysanthemum and results in good quality and quantity of flowers. |
| - Technology Option-1 with Source {Farmers’ Practice} | : | Application of 99:105:57 NPK Kg/ha & 0.5 ton FYM/ha |
| - Technology Option-2 with Source {Recommended practice and extent of its adoption} | : | - Application of RDF is 100:150:100 NPK kg/ha - 20 tons FYM/ha - Extent of its adoption : 30-35% Source: UAS, Dharwad |
| - Technology Option-3 being assessed along with justification with Source | : | Technology Option-2 + Following treatments - Boron application @ 2 kg/ha - Foliar spray of boric acid 0.2% at 21 days of planting and at 25% flower bud emergence Source: IIHR, Bangalore |

- Budget proposed : (For 0.4 Ha)

| Sl. No. | Critical Inputs for Technology Option 2 (Recommended Practice) |  |  |  | Critical inputs for other technology Options |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) |
|  |  |  |  |  | Borosoil | 5 kg | 180 | 900 |
|  |  |  |  |  | Boric acid | 250 gm | 150 kg | 37 |
|  | Total |  |  |  |  |  |  | 937 |

- Area (ha.)  for implementing  : 3.60 ha

- Technology Option 1 (Farmer’s Practice)  		: 1.20 ha

- Technology Option 2 (Recommended Practice) 	: 1.20 ha

- Technology option  3 				: 1.20 ha

- Grand Total Cost proposed per OFT 	: Rs. 937

- Total Number of OFTs proposed       	: 03

- Total budget required                         : Rs. 2811

| ASSESSMENT NO. 11 |  |  |
| --- | --- | --- |
| - Title of the On Farm Trial | : | Usage of Potassium nitrate and Gibberellic Acid for inducing bud opening in Chrysanthemum |
| - State whether it is Assessment / Refinement | : | Assessment |
| - Agro-Ecological Zone | : | Northern dry zone-3, Region-2 |
| - Production System | : | Medium and Big farmers production system under irrigation situation |
| - Problem identified | : | Due to short stem length and poor growth, there is poor quality of flowers and late flowering in chrysanthemum crop. Hence, the farmers are not getting good market value. |
| - Number of farmers and area affected in the operational villages | : | More than 100-120 farmers in an area of about 150-170 ha affected in the operational villages |
| - Thrust areas | : | Growth regulation & nutrition |
| - Rationale for proposing the OFT | : | Recommended dose of soil application of potassium & foliar spray of potassium at 25-30 days after planting will enhance the quality of flowers. Further, the foliar spray of growth regulators (Gibberellic acid) will increase the stem length & early flowering and good quality of flowers. |
| - Technology Option-1 with Source {Farmers’ Practice} | : | Application of 99:105:57 NPK Kg/ha & 0.5 ton FYM/ha |
| - Technology Option-2 with Source {Recommended practice and extent of its adoption} | : | Application of RDF i.e. 100:150:100 NPK kg/ha Extent of its adoption : 30-35% Source: UAS, Dharwad |
| - Technology Option-3 being assessed along with justification with Source | : | - Application of RDF i.e. 100:150:100 NPK kg/ha - Foliar spray of potassium nitrate @ 5% two times i.e. at 25-30 days after planting and second time at 5 days interval. - Foliar spray of GA @ 1% at 25-30 days after planting Source: IIHR, Bangalore |

- Budget proposed : (For 0.4 Ha)

| Sl. No. | Critical Inputs for Technology Option 2 (Recommended Practice) |  |  |  | Critical inputs for other technology Options |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) |
|  |  |  |  |  | Potassium Nitrate (KNO3) | 300 gm | 120/kg | 36 |
|  |  |  |  |  | GA(Gibberellic Acid) | 2 gm | 50/gm | 100 |
|  |  |  |  |  | Total |  |  | 136 |

- Area (ha.)  for implementing  : 3.60 ha

- Technology Option 1 (Farmer’s Practice)  		: 1.20 ha

- Technology Option 2 (Recommended Practice) 	: 1.20 ha

- Technology option  3 				: 1.20 ha

- Grand Total Cost proposed per OFT 	: Rs. 136/-

- Total Number of OFTs proposed       	:  03

- Total budget required                         : Rs. 408

| ASSESSMENT NO. 12 |  |  |
| --- | --- | --- |
| - Title of the On Farm Trial | : | Nutrition management in Mango for higher productivity |
| - State whether it is Assessment / Refinement | : | Assessment |
| - Agro-Ecological Zone | : | Northern dry zone-3, Region-2 |
| - Production System | : | Big farmers production system under dry land condition |
| - Problem identified | : | Imbalanced nutrition due to the maintenance of crop under rainfed condition |
| - Number of farmers and area affected in the operational villages | : | More than 300 farmers in about 450 ha area |
| - Thrust areas | : | Assessment of foliar nutrition in Mango under dry land condition |
| - Rationale for proposing the OFT | : | Farmers do not apply nutrients through soil. This has resulted in low production of Mango. Hence foliar application is tested to enhance Mango production |
| - Technology Option 1 with Source | : | Application of FYM @ 40 Kg/tree |
| - Technology Option 2 with Source | : | - Application of FYM @ 50 Kg/tree and chemical fertilizer dose of 1.0:1.0:1.5 Kg NPK/tree - Source: UAS, Dharwad |
| - Technology Option 3 being assessed along with justification with Source | : | Technology Option-2 + Following treatments Spraying of water soluble fertilizer (19:19:19 NPK) @ 1% solution- 2 times (June-July & August-September) + spraying of K Rich (13:0:46 NPK) water soluble fertilizer 1% solution 2 times (Dec-Jan and Feb-March) + IIHR Mango special nutrient mixture @ 0.5% - 3 times/year (June-July, Nov-Dec, February-March) Source: IIHR, Bangalore Justification: Due to rainfed condition the farmers over look the fertilizer application. So the application of the nutrient to both soil and as foliar sprays would ensure the crop for its required nutrients to some extent for getting good yield |

- Budget proposed for OFT : (For 10 trees each)

| S. No | Critical Inputs for Technology Option 2 (Recommended Practice) |  |  |  | Critical inputs for other technology Options |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) |
| 1 |  |  |  |  | 1) Foliar Spray - 19:19:19 NPK water soluble fertilizer | 02 kg | 80/kg | 160/- |
|  |  |  |  |  | - ‘K’ rich fertiliser 13:0:46 NPK | 02 kg | 120/kg | 240/- |
|  |  |  |  |  | - Mango special from IIHR | 02 kg | 100/kg | 200/- |
| Total |  |  |  | 450 | Total |  |  | 600/- |

- Area (ha.)  for implementing 	:

- Technology Option 1 (Farmer’s Practice) 		: 10 trees

- Technology Option 2 (Recommended Practice) 	: 10 trees

- Technology option  3 (Alternate Practice)		: 10 trees

- Grand Total Cost proposed per OFT : Rs.600/-

- Total Number of OFTs proposed       : 3

- Total budget required                         : Rs.1800/-

ASSESSMENT NO. 13

| - Title of the On Farm Trial | : | Management of grain storage pest incidence in cereals and pulses at household level |
| --- | --- | --- |
| - State whether it is Assessment / Refinement | : | Assessment |
| - Agro-Ecological Zone | : | Northern dry zone-3, Region-2 |
| - Production System | : | Small and big production system |
| - Problem identified | : | Loss in stored grains (Greengram, Moth bean Cowpea etc.) of pulses due to incidence of pulse beetle |
| - Number of farmers and area affected in the operational villages | : | More than 90% of families face this problem. |
| - Thrust areas | : | Pulse storage at household level. |
| - Rationale for proposing the OFT | : | Recommended practice of using Aluminium Phosphide is not practical for storage of smaller quantities. Moreover, usage of chemical pesticides may pose health hazards to human beings. Hence the OFT is proposed for assessment. |
| - Technology Option 1 with Source (Farmers’ practice) | : | - Farmers are using boric powder for storage of pulses. As Boric powder is chemical, it causes health hazards |
| - Technology Option 2 with Source | : | - Aluminium Phosphide @ 2-3 tablets/ton (Not relevant at household level) - Source: UAS, Dharwad - Extent of adoption: 10-15% |
| - Technology Option 3 being assessed along with justification with Source | : | Preparation of baits from mixture of ginger powder (30gm), neem leaves (50gm) and sweet flag (Aquarious Culmus) (10 gms) per kg of cereals or pulses. Source: Centre for Indian Knowledge Systems (CIKS), Chennai Justification: The neem and ginger act as repellent and have ovicidal effect on insect and antifeedent. These reduce the incidence of pulse beetles. In addition the raw materials are available locally with less cost and there will not be any adverse effect on health |

- Budget proposed for OFT

| S. No | Critical Inputs for Technology Option 2 (Recommended Practice) |  |  |  | Critical inputs for other technology Options |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) |
| 1 | - | - | - | - | Plastic Moulds | 3 | 250 | 250 |
| 2 |  |  |  |  | Ginger powder | 200 gms | 75 | 75 |
| 3 |  |  |  |  | Sweet flag | 60 gms | 25 | 25 |
| 4 |  |  |  |  | Air tight containers | 3 | 300 | 300 |
| 3 |  |  |  |  | Labour charges for the preparation of baits | 2 | 100 | 200 |
| Total |  |  |  |  |  |  |  | 850 |

- Area (ha.)  for implementing 		: Nil

- Grand Total Cost proposed per OFT : Rs.850

- Total Number of OFTs proposed       : 5

- Total budget required                         : Rs.4250

ASSESSMENT NO. 14

| 1. | Title of the On Farm Trial | : | Use of Flumethrin 1% Pour-on against tick infestation in Cattle |
| --- | --- | --- | --- |
| 2. | State whether it is Assessment / Refinement | : | Assessment |
| 3. | Agro-Ecological Zone | : | Northern dry zone |
| 4. | Production System | : | Dairy enterprise |
| 5. | Problem identified | : | Tick infestation |
| 6. | Number of farmers and area affected in the operational villages | : | 70 %. |
| 7. | Thrust areas | : | Effective management of ticks and to check the production loss |
| 8. | Rationale for proposing the OFT | : | Though the tick infestation in cattle can be effectively controlled by topical application of butox, but here the prevention of licking of chemical is difficult, strong concentration may cause death of animal and also hazardous to humans who handle it. So the new concept of application of a topical ectoparacites through Pour-on method using flumethrin 1% comes in handy for the farmers |

9. Technology Option I

| Sl.No | Technological Options | Details of technology |
| --- | --- | --- |
| 1 | Farmer’s Practice | Application of tobacco filtered water |
| 2 | Name of the chemical & quantity | Tobacco filtered water and no specific quantity |
| 3 | Extent of effectiveness | 20 % |
| 4 | Method of use | Topical application |

10. Technology Option II

| Sl.No | Technological Options | Details of technology |
| --- | --- | --- |
| 1 | Recommended Practices | Topical application of Butox |
| 2 | Extent of its adoptions | 40 % |
| 3. | Source of technology | KVAFSU, Bidar |
| 4. | Reasons for low adoptions | Lack of awareness and because of its hazardous effect |

11. Technology Option III

| Sl.No | Technological Options | Details of Technology | Source of Technology | Justification |
| --- | --- | --- | --- | --- |
| 1 | Farmer’s Practice | Application of tobacco filtered water | - | - Though the effectiveness is equal in both the technology options, the application of Pour-on is easy and requires less skill - Health hazards due to leaking are less - Longer residual effect |
| 2 | Technology option (Recommended) | Topical application of Butox | KVAFSU, Bidar |  |
| 3 | Technology selected for Assessment | Topical application of flumethrin 1 % by Pour-on method | TANUVAS, Chennai |  |

12. Budget proposed for OFT

| Sl. No | Critical Inputs for Technology Option 2 (Recommended Practice) |  |  |  | Critical inputs for other technology Options |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) |
| 1 | Butox | 50 ml | 70 | 70 | Flumethrin 1% | 100 ml | 140 | 140 |

13. Area (ha.)  For implementing

- Technology Option 1 (Farmer’s Practice) 	: 3 animals

- Technology Option 2 (Recommended Practice) 	: 3 animals

- Technology option  3				: 3 animals

14. Grand Total Cost proposed per OFT 				:  Rs. 210

15. Total Number of OFTs proposed      				:  03

16. Total budget required                       				:  Rs. 630

ASSESSMENT NO. 15

| 1. | Title of the On Farm Trial | : | Control of Endoparasites in Sheep |
| --- | --- | --- | --- |
| 2. | State whether it is Assessment / Refinement | : | Assessment |
| 3. | Agro-Ecological Zone | : | Northern dry zone |
| 4. | Production System | : | Animal Husbandry |
| 5. | Problem identified | : | Worms |
| 6. | Number of farmers and area affected in the operational villages | : | 500 Nos., 30-50% animals affected |
| 7. | Thrust areas | : | Livestock Disease Management |
| 8. | Rationale for proposing the OFT | : | Worm infestation is common in sheep. So mortality is common in lambs. Hence combination of Alvendazole and Niclosamide will remove the worms (Trematodes, Cestodes and Nematodes) from the Gut and Intestine. So, it increases the growth rate and wool production. |

9. Technology Option I

| Sl.No | Technological Options | Details of technology |
| --- | --- | --- |
| 1 | Farmer’s Practice | Castor oil |
| 2 | Extent of yield loss | 30-40% |
| 3 | Name of the variety | - |
| 4 | Method of use | Oral Drenching |

10. Technology Option II

| Sl.No | Technological Options | Details of technology |
| --- | --- | --- |
| 1 | Recommended Practices | Albendazole |
| 2 | Extent of its adoptions | 10-20% |
| 3. | Source of technology | KVAFSU, Bidar |
| 4. | Reasons for low adoptions | Low efficacy |

11. Technology Option III

| Sl.No | Technological Options | Details of Technology | Source of Technology | Justification |
| --- | --- | --- | --- | --- |
| 1 | Farmer’s Practice | Administration of castor oil | - | Castor oil will evacuate calf bowel |
| 2 | Technology selected for assessment | Administration of Albendazole and Niclosamide combination @ 5 mg/Kg body weight orally | TANUVAS, Chennai | Broad Spectrum Anthelmintic |
| 3 | Technology Option 1 | - | - |  |

12. Budget proposed for OFT (10 sheep)

| Sl. No | Critical Inputs for Technology Option 2 (Recommended Practice) |  |  |  | Critical inputs for other technology Options |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) |
| 1 | Albendazole | 1000 ml | 400/- | 30/- | Albendazole + Niclosamide | 1000 ml | 600/- | 30/- |

13. Area (ha.)  For implementing

- Technology Option 1 (Farmer’s Practice) 	: 10 sheep

- Technology Option 2 (Recommended Practice) 	: 10 sheep

- Technology option  3				: 10 sheep

14. Grand Total Cost proposed per OFT 				:  Rs. 60/-

15. Total Number of OFTs proposed      				:  5

16. Total budget required                       				:  Rs. 180/-

| REFINEMENT NO. 01 |  |  |
| --- | --- | --- |
| - Title of the On Farm Trial | : | Resource conservation technologies for sustainable production in greengram |
| - State whether it is Assessment / Refinement | : | Refinement |
| - Agro-Ecological Zone | : | Northern dry zone-3, Region-2 |
| - Production System | : | Small, Medium and Big farmers production system under rainfed situation |
| - Problem identified | : | Erratic rainfall and long dry spell during the crop growth period results in moisture stress. This leads to low productivity of the Greengram crop. This phenomenon recurs almost every year. |
| - Number of farmers and area affected in the operational villages | : | More than 1000 farmers in an area of about 2850 ha affected in the operational villages |
| - Thrust areas | : | Resource conservation |
| - Rationale for proposing the OFT | : | Compartment Bunding, opening of conservation furrows and application of vermicompost will enhance the moisture availability during crop growth period. Seed priming with CaCl2 induces the drought tolerance to the crops. The seed treatment with bio-fertilizers enhances the nutrient availability to the crop. Application of neemcake will supply nutrients to the crops, reduces the incidence of soil borne pathogen and works as organic matter to hold more moisture in the soil. Further, the incorporation of crop residue will enhance the moisture availability and nutrients to the next crop. |
| - Technology Option-1 with Source {Farmers’ Practice} | : | Cultivation of Greengram with 5:12:0 NPK Kg/ha Extent of yield loss : 40-45% |
| - Technology Option-2 with Source {Recommended practice and extent of its adoption} | : | - Seed priming with 2% CaCl2 - Seed treatment with Bio-fertilizers - Rhizobium 500 gm/12 kg of seed - PSB 1250 gm/12 of seeds - Application of 12.5:25:0 NPK Kg/ha Extent of it’s adoption is 25-30% Level of yield loss is 30-35% |
| - Technology Option-3 being assessed along with justification with Source | : | - Compartment Bunding - Application of vermicompost @ 1 qt/ha - Application of neemcake @ 2.5 Qt/ha - Seed priming with 2% CaCl2 - Seed treatment with Bio-fertilizers @ - Rhizobium 500gm/12kg of seeds - PSB 1250 gm/12kg of seeds - Application of 125:25:0 NPK kg/ha - Opening of conservation furrows (At every 10 mtrs interval) - Using Twin wheel hoe weeder at weekly interval - Incorporation of crop residue |

- Budget proposed : (For  0.4 ha)

| Sl. No. | Critical Inputs for Technology Option 2 (Recommended Practice) |  |  |  | Critical inputs for other technology Options |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) |
| 1. | CaCl2 | 200gm | 90/kg | 18 | Bund former (for compartment bunding) | 1 No. | 950/- | 950 |
| 2. | Rhizobium | 200gm | 30/kg | 06 | Neemcake | 01 Qt. | 650/Qt. | 650 |
| 3. | PSB | 500gm | 30/kg | 15 | CaCl2 | 200gm | 90/kg | 18 |
| 4. | Seeds S-4 variety | 05 kg | 60/kg | 300 | Rhizobium | 200gm | 30/kg | 06 |
|  |  |  |  |  | PSB | 500gm | 30/kg | 15 |
|  |  |  |  |  | Seeds (S-4 variety ) | 05 Kg | 60/kg | 300 |
|  | Total |  |  | 339.00 |  |  |  | 1939.00 |

- Area (ha.)  for implementing  : 3.60 ha

- Technology Option 1 (Farmer’s Practice)  		: 1.20 ha

- Technology Option 2 (Recommended Practice) 	: 1.20 ha

- Technology option  3 				: 1.20 ha

- Grand Total Cost proposed per OFT 	: Rs. 2278/-

- Total Number of OFTs proposed       	: 03

- Total budget required                         : Rs. 6834/-

| REFINEMENT NO. 02 |  |  |
| --- | --- | --- |
| - Title of the On Farm Trial | : | Resource conservation technologies for sustainable production in spreading groundnut |
| - State whether it is Assessment / Refinement | : | Refinement |
| - Agro-Ecological Zone | : | Northern dry zone-3, Region-2 |
| - Production System | : | Small, Medium and Big farmers production system under rainfed situation |
| - Problem identified | : | Erratic rainfall and long dry spell during the crop growth stages result in moisture stress. In turn, this leads to low productivity of Spreading Groundnut |
| - Number of farmers and area affected in the operational villages | : | More than 600 farmers in an area of about 1350 ha affected in the operational villages |
| - Thrust areas | : | Resource conservation |
| - Rationale for proposing the OFT | : | Compartment bunding & opening of conservation furrows and repeated harrowing with Twin Wheel Hoe Weeder will conserve the moisture throughout the crop growth period even during long dry spells. Vermicompost and Bio-fertilizers will enhance the nutrients to the crop besides conserving soil moisture. Seed treatment with trichoderma and application of neemcake will reduce the incidence of soil borne pathogens. Neemcake will also supply nutrients to the crop. |
| - Technology Option-1 with Source {Farmers’ Practice} | : | Application of 22:60:0 NPK Kg/ha Extent of yield loss : 35-40 percent |
| - Technology Option-2 with Source {Recommended practice and extent of its adoption} | : | - Application of Vermicompsot 1 ton/ha - Seed treatment with Trichoderma @ 4gms/kg of seeds - Seed treatment with bio-fertilizer - Rhizobium 2.5 kg/75 kg of seeds - PSB 2.5 kg/75 kg of seeds - Application of 25:50:25 NPK Kg/ha & ZnSO4 25 kg/ha and Gypsum 500 kg/ha |
| - Technology Option-3 being assessed along with justification with Source | : | Technology Option-2 + Following treatments - Compartment Bunding (6X6mtr) - Opening of conservation furrows (10mtr interval) - Seed treatment with Trichoderma 10gm/kg of seeds - Application of neemcake @ 2.50 Qt/ha - Inter cultivation with Twin Wheel Hoe Weeder at weekly interval |

- Budget proposed :  (For 0.4 Ha.)

| Sl. No. | Critical Inputs for Technology Option 2 (Recommended Practice) |  |  |  | Critical inputs for other technology Options |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) |
| 1. | Trichoderma | 120 gm | 150/kg | 18 | Trichoderma | 300gm | 150/kg | 45 |
| 2. | Rhizobium | 1 kg | 30 | 30 | Neemcake | 1.00 Qt | 650/Qt | 650 |
| 3. | PSB | 1 kg | 30/- | 30 | Rhizobium | 1.00 Kg | 30/- | 30 |
| 4. | Gypsum | 2 Qt. | 300/Qt. | 600 | PSB | 1.00 Kg | 30/- | 30 |
| 5. | ZnSO4 | 10 Kg | 40/kg | 400 | Gypsum | 2 Qt. | 300/Qt. | 60 |
|  |  |  |  |  | ZnSO4 | 10 Kg | 40/kg | 400 |
|  |  |  |  |  | Twin Wheel Hoe Weeder | 1 No. | 850/- | 850 |
|  | Total |  |  | 1078 |  |  |  | 2605 |

- Area (ha.)  for implementing  : 3.60 ha

- Technology Option 1 (Farmer’s Practice)  		: 1.20 ha

- Technology Option 2 (Recommended Practice) 	: 1.20 ha

- Technology option  3 				: 1.20 ha

- Grand Total Cost proposed per OFT 	: Rs. 3683

- Total Number of OFTs proposed       	: 03

- Total budget required                         : Rs. 11049

| REFINEMENT NO. 03 |  |  |
| --- | --- | --- |
| - Title of the On Farm Trial | : | Resource conservation technologies for sustainable production in rabi jowar |
| - State whether it is Assessment / Refinement | : | Refinement |
| - Agro-Ecological Zone | : | Northern dry zone-3, Region-2 |
| - Production System | : | Small, Medium and Big farmers production system under rainfed situation |
| - Problem identified | : | In rabi season, receeding soil moisture during the crop growth stages results in moisture stress and this leads to low productivity of the Jowar crop in the rabi season. |
| - Number of farmers and area affected in the operational villages | : | More than 850 farmers in an area of about 2640 ha affected in the operational villages |
| - Thrust areas | : | Resource conservation |
| - Rationale for proposing the OFT | : | In Rabi season, compartment bunding & opening of conservation furrows and repeated harrowing with Twin Wheel Hoe Weeder will conserve the moisture throughout the crop growth period. Seed treatment with CaCl2 will induce the drought tolerance to the crop. Seed treatment with bio-fertilizers will enhance the nutrients availability to the crop. |
| - Technology Option-1 with Source {Farmers’ Practice} | : | Application of 5:12:0 NPK Kg/ha Extent of yield loss : 30-35% |
| - Technology Option-2 with Source {Recommended practice and extent of its adoption} | : | - Application of 2 tons FYM/ha - Seed priming with CaCl2 - Seed treatment with Sulphur & Endosulphan - Seed treatment with trichoderma - Application of 50:25:0 NPK Kg/ha & ZnSo4 15 kg/ha - Compartment Bunding at 21 DAS (5X5Mtrs) |
| - Technology Option-3 being assessed along with justification with Source | : | Technology Option-2 plus following treatments - Compartment Bunding 15 days before sowing - Opening of conservation furrows at 10 mtr interval - Application of vermicompost @ 50 Kg/ha - Adoption of paired row method of sowing - Inter cultivation with Twin Wheel Hoe Weeder at weekly interval |

- Budget proposed : (For 0.4 Ha)

| Sl. No. | Critical Inputs for Technology Option 2 (Recommended Practice) |  |  |  | Critical inputs for other technology Options |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) |
| 1. | CaCl2 | 9 gm | 90/kg | 8 | CaCl2 | 90 gm | 90/kg | 8 |
| 2. | Endosulphan | 9 ml | 350/ltr | 3 | Endosulphan | 9 ml | 350/ltr. | 3 |
| 3. | Sulphur | 12 gm | 80/kg | 1 | Sulpher | 120 gm | 80/kg | 1 |
| 4. | Trichoderma | 10 gm | 120/kg | 1 | Trichoderma | 10 gm | 120/kg | 1 |
| 5. | ZnSO4 | 6 kg. | 40 | 240 | ZnSO4 | 6 kg. | 40/- | 240 |
| 6. | Vermicompost | 20 kg. | 3 | 60 | Vermicompost | 20 kg. | 3/- | 60 |
|  |  |  |  |  | Twin Wheel Hoe Weeder | 1 No. | 850 | 850 |
|  | Total |  |  | 313 |  |  |  | 1163 |

- Area (ha.)  for implementing  :  3.60 ha

- Technology Option 1 (Farmer’s Practice)  		: 1.20 ha

- Technology Option 2 (Recommended Practice) 	: 1.20 ha

- Technology option  3 				: 1.20 ha

- Grand Total Cost proposed per OFT 	: Rs. 1476/-

- Total Number of OFTs proposed       	: 03

- Total budget required                         : Rs. 4428/-

| REFINEMENT NO. 4 |  |  |
| --- | --- | --- |
| - Title of the On Farm Trial | : | Refinement of cotton cloth hand gloves for harvesting of bengalgram & sunflower for drudgery reduction |
| - State whether it is Assessment / Refinement | : | Refinement |
| - Agro-Ecological Zone | : | Northern dry zone-3, Region-2 |
| - Production System | : | Small and big production system |
| - Problem identified | : | Scratching and Injury to palms due to pricking while harvesting bengalgram & sunflower crops result in reduced harvesting efficiency |
| - Number of farmers and area affected in the operational villages | : | All farm women involved in harvesting sunflower and bengalgram crops |
| - Thrust areas | : | Drudgery reduction and enhancing harvesting efficiency |
| - Rationale for proposing the OFT | : | Bare hand cutting of sunflower earhead and Bengalgram plants cause injury to palms due to scratches and irritation to skin thereby reduces harvesting efficiency. Hence OFT is proposed on assessment of Cotton cloth hand gloves. |
| - Technology Option 1 with Source | : | - Harvesting with bare hand and it causes scratches & injury to palm |
| - Technology Option 2 with Source | : | - Source: K.H.Patil KVK, Hulkoti Justification: In 2009-10 an assessment on use of cotton hand gloves for harvesting of bengalgram was conducted. Farm women gave the opinion that the hand gloves are good. Their efficiency in harvesting of bengalgarm is more and the drudgery is less as there is less injury and pain to the palms. They also expressed that the durability of the gloves must be increased by the use of thick cloth, with easy and flexible movement of fingers to increase the harvesting efficiency. |
| - Technology Option 3 being assessed along with justification with Source | : | Refinement of cotton cloth hand gloves with thick cotton cloth, jeans cloth & rexine material with different patterns/shapes of gloves for cutting of earhead in sunflower and uprooting of bengalgram. Justification: Based on the farm women’s feed back, thick cotton cloth, jeans material and rexine material with two different models of hand gloves were proposed for more durability, to increase the harvesting efficiency and to reduce the drudgery of farm women in harvesting, the refinement is planned. |

- Budget proposed for OFT

| S. No | Critical Inputs for Technology Option 2 (Recommended Practice) |  |  |  | Critical inputs for other technology Options |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) | Name | Qty. | Unit Cost (Rs.) | Total Cost (Rs.) |
| 1 | By hand | - | - | - | Thick cotton cloth hand gloves Model – I Model – II | 1 pair 1 pair | 150 150 | 150 150 |
|  |  |  |  |  | Jeans cloth hand gloves Model-I Model-II | 1 pair 1 pair | 200 200 | 200 200 |
|  |  |  |  |  | Rexine material hand gloves Model-I Model-II | 1 pair 1 pair | 200 200 | 200 200 |
| Total |  |  |  |  |  |  |  | 1100 |

- Area (ha.)  for implementing 	: Nil

- Technology Option 1 (Farmer’s Practice) 		: 10 ha

- Technology Option 2 (Recommended Practice) 	: -

- Technology option  3 				: 10 ha

- Grand Total Cost proposed per OFT : Rs.1100

- Total Number of OFTs proposed       : 5

- Total budget required                         : Rs.5500/-

Table 4. Season-wise plan of Front Line Demonstrations (FLD) for 2010-11

(Minimum of two technologies and 20 demonstrations in each discipline)

A. Other than oil seeds pulses and cotton

KHARIF

| Thrust area | Crop / livestock / enterprises | Yield gap (q/ha) or (number/unit) |  |  | Reasons for yield gap | Technology to be demonstrated | Critical inputs to be provided |  | Area (ha) / Number | No. of farmers |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | District average yield | Potential yield | Farmers’ yield |  |  | Name & Quantity (kg/ha) or number/unit | Cost (Rs./ha) or Rs./unit |  |  |
| Management of stem borer and army worm in maize | Maize | 53 | 58 | 48 | - Incidence of stem borer and army worm (Farmers do not take spray) | - Spraying of Profenophos - Broad casting of rice or wheat bran and monocrotophos with Jaggery | Profenophos – 750 ml | 350 | 5 | 12 |
|  |  |  |  |  |  |  | Monocrotophos – 250 ml | 125 |  |  |
|  |  |  |  |  |  |  | Wheat or rice bran – 62.5 Kg | 220 |  |  |
|  |  |  |  |  |  |  | Jaggery – 4 Kg | 128 |  |  |
| Total |  |  |  |  |  |  |  | 823 |  |  |
| Integrated Nutrient Management | Maize | 53 | 58 | 48 | - Application of 120:60:30 NPK Kg/ha - Non application of micro nutrients like FeSO4 & ZnSO4 | - Application of 150:75:37.5 NPK Kg/ha - ZnSO4 – 25 Kg/ha - FeSO4 – 25 Kg/ha | ZnSO4 – 25 Kg | 1000 | 4 | 10 |
|  |  |  |  |  |  |  | FeSO4 – 25 Kg | 600 |  |  |
| Total |  |  |  |  |  |  |  | 1600 |  |  |
| Management of Shoot and fruit borer in Brinjal | Brinjal | 178 | 460 | 300 | - Incidence of shoot and fruit borer (Farmers do not take up spray) | - Installation of water traps | Water traps – 8 Nos. | 360 | 4 | 10 |
|  |  |  |  |  |  |  | Lucin lures – 24 No. | 288 |  |  |
|  |  |  |  |  |  | - Spraying of Carbosulfan | Carbosulfan – 750 ml | 560 |  |  |
| Total |  |  |  |  |  |  |  | 1208 |  |  |
| ICM in onion | Onion | 67 | 150 | 80 | - Cultivation of local variety - Improper nutrition - No use of Potash - Incidence of thrips and purple blotch (No spray is taken) | - Introduction of high yielding Arka Kalyan onion variety along with ICM | Seeds 3 Kgs | 1200 | 13 | 33 |
|  |  |  |  |  |  |  | Trichoderma – 25 gm/ha | 5 |  |  |
|  |  |  |  |  |  |  | Difenconazole – 500 ml/ha | 1420 |  |  |
|  |  |  |  |  |  |  | Total | 2625 |  |  |
| Introduction of high yielding variety | Ridge gourd | 58 | 85 | 36 | - Cultivation of low yielding local variety | - Introduction of high yielding Ridge gourd variety Arka Sumit | Seeds 4 Kg | 1200 | 06 | 15 |
| Introduction of high yielding variety in flower crop | Aster | NA | 100 | NA | - Introduction of crop for replacement of chrysanthemum for getting better market price | - Introduction of high yielding variety Chaina Aster Kamini | Seeds 500 gm | 2500 | 1.2 | 03 |
| Integrated Nutrient management | Chrysanthemum | 35 | 80 | 46 | - Application of 99:105:57 NPK Kg/ha | - Application of 100:150:100 NPK Kg/ha - Foliar spray of water soluble 19:19:19 NPK - Foliar spray of multiplex | Water soluble 19:19:19 – 4.5 Kg | 450 | 4 | 10 |
|  |  |  |  |  |  |  | Multiplex – 2.5 Kg | 550 |  |  |
| Total |  |  |  |  |  |  |  | 1000 |  |  |
| Drudgery | Twin wheel hoe weeder | - | - | - | - - | - Twin wheel hoe weeder | 20 weeders | 900 | 10 Nos. | 10 SHGs |
| Drudgery | Fuel saving device | - | - | - | - - | - Demonstration of Envirofit chulha | S-4100 model | 2600 | 3 Nos. | 3 |
| Drudgery | Groundnut decorticator with separator | - | - | - | - - | - Groundnut decorticator with separator | 3 units | 3000 | 3 Nos. | 30 |
| Total |  |  |  |  |  |  |  | 1110 |  |  |
| Introduction of new poultry bird | Poultry | - | 180-190 eggs/hen/year | 155-160 eggs/hen/year | - Low productivity of egg in local breeds | - Introduction of new poultry breed- -Swarnadhara | Swarnadhara breed 5 +1 (Hen + cock) (6 weeks old) | 210 | 25 units (5+1) | 25 |
| Ecto-endo parasite management | Sheep | 15-20 Kg | 25-30 Kg | 21-24 Kg | - Loss of body weight | - Drenching of closantal suspension | Closantal oral suspension @ 15 mg/Kg body weight on ‘0’ day & repeat after 60 days | 200/unit | 30 units | 30 |
|  |  |  |  |  |  |  |  | Cost/unit Rs.200 For 30 unit Rs.6000 |  |  |
| Endoparasite management | Buffaloe | 2.7 lit/ day | 7 lit/day | 5 lit/day | - Reduced milk yield | - Application of vetfen (oral dosage) | Vetfen Bolus-1.5 gm 1 bolus/animal Repeat after 21 days (5 mg/kg) | Rs.150/unit | 30 units | 36 |

RABI

| Thrust area | Crop / livestock / enterprises | Yield gap (q/ha) or (number/unit) |  |  | Reasons for yield gap | Technology to be demonstrated | Critical inputs to be provided |  | Area (ha) / Number | No. of farmers |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | District average yield | Potential yield | Farmers’ yield |  |  | Name & Quantity (kg/ha) or number/unit | Cost (Rs./ha) or Rs./unit |  |  |
| Demonstration of CSV-22 variety | Rabi jowar | 5.75 | 14-15 | 8-10 | - Poor fodder quality - Lack of high yielding variety for deep black soil | - Introduction of CSV-22 variety for higher production in deep black soil | Seeds – 8 Kg (CSV-22) | 240 | 10 | 25 |
| Introduction of high yielding variety | Wheat | 10.50 | 30-35 | 24-25 | - Cultivation of non descript variety (Nirmal) (low yielding) | - Introduction of GW-322 and UAS-304 varieties for rust resistant & higher productivity | Seeds – 75 Kg (GW-322) Seeds-UAS-304 | 3750 | 5 | 12 |
| Stem borer management in wheat | Wheat | 10.50 | 30-35 | 24-25 | - Incidence of stem borer in wheat (No spray is taken) | - Spraying of Profenophos | Profenophos – 750 ml | 350 | 10 | 25 |
| Introduction of high yielding improved variety | Tomato | 75 | 200 | 110 (Hybrid) | - Introduction of high yielding variety for replacement of hybrids as they are susceptible to pest & disease and costs of seeds is high | - Promotion of Arka Abha for leaf curl & wilt resistance | Seeds 400 gm | 2000 | 4 | 10 |
| Introduction of high yielding variety | French bean | 65 | 100 | 48 | - Local variety winged bean is low yielding | - Introduction of new high yielding variety Arka Suvidha | Seeds 75 Kgs | 9000 | 1.2 | 03 |
| Drudgery reduction | Rabi Jowar | - | - | - | - - | - Demonstration of serrated sickle developed by Dev Agro. Bangalore | Serrated sickle | 150 | 20 | 20 |
| Drudgery reduction | Irrigated wheat | - | - | - | - - | - Serrated sickle in harvesting of wheat | Improved sickle | 150 | 20 | 20 |

SUMMER

| Thrust area | Crop / livestock / enterprises | Yield gap (q/ha) or (number/unit) |  |  | Reasons for yield gap | Technology to be demonstrated | Critical inputs to be provided |  | Area (ha) / Number | No. of farmers |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | District average yield | Potential yield | Farmers’ yield |  |  | Name & Quantity (kg/ha) or number/unit | Cost (Rs./ha) or Rs./unit |  |  |
| Mango hopper fruit fly and powdery mildew management | Mango | 350 | 750 | 420 | - Untimely spray for hopper management and do not take spray for fruit fly - Spray of sulphur is taken only once | - Spraying with neem seed kernel extract at bud burst stage - Spraying of Carbaryl @ 3 gm/lit - Spraying of Thiomethoxam @ 0.25 ml/ltr - Hanging of fligh-T trap with bador lures - Spraying sulphur @ 3 gm/lt - Spraying Hexaconazole @ 1 ml/lit | NSKE – 50 Kg | 325 | 4 | 10 |
|  |  |  |  |  |  |  | Carbaryl – 2 Kg gm | 840 |  |  |
|  |  |  |  |  |  |  | Imidacloprid – 250 ml | 575 |  |  |
|  |  |  |  |  |  |  | Fligh – T traps – 10 Nos. | 670 |  |  |
|  |  |  |  |  |  |  | Bador lures – 20 Nos. | 700 |  |  |
|  |  |  |  |  |  |  | Sulphur – 1.25 Kg | 160 |  |  |
|  |  |  |  |  |  |  | Hexaconazole – 1.5 L | 690 |  |  |
| Total |  |  |  |  |  |  |  | 3960 |  |  |

B. Oil seeds

KHARIF

| Thrust area | Crop | Yield gap (q/ ha ) |  |  | Reasons for yield gap | Technology to be demonstrated | Critical inputs to be provided |  | Area (ha) | No. of farmers |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | District average yield | Potential yield | Farmers’ yield |  |  | Name & Quantity (kg/ha) | Cost (Rs./ha) |  |  |
| Insitu soil moisture conservation | Groundnut (Bunch) | 5-7 | 15-16 | 10-12 | - Abiotic stress during Peg initiation stage | - Compartment bunding - Paired row method of sowing |  |  |  |  |
| Introduction of GPBD-4 variety along with ICM | Groundnut (Bunch) | 5-7 | 15-16 | 10-12 | - Incidence of leaf spot disease (Farmers do not take up spray) | - Introduction of GPBD-4 variety | - GPBD-4 Pods – 200 | 3500 | 10 10 | 15 25 |
|  |  |  |  |  | - Imbalanced nutrition (Potash and gypsum are not applied by farmers) | - Application of micro nutrient & biofertilisers | - Rhizobium – 2.5 | 88 |  |  |
|  |  |  |  |  |  |  | - PSB – 2.5 | 88 |  |  |
|  |  |  |  |  |  |  | - ZnSO4 – 2.5 | 900 |  |  |
|  |  |  |  |  |  |  | - Gypsum – 500 | 1375 |  |  |
|  |  |  |  |  | - Incidence of collar rot (No seed treatment by farmers) | - Seed treatment with Trichoderma | - Trichoderma – 1.250 | 200 |  |  |
|  |  |  |  |  |  | - Soil application of Trichoderma & FYM | - Trichoderma – 2.5 | 400 |  |  |
|  |  |  |  |  | - Incidence of leaf minor (No spray is taken by farmers) | - Spraying of monocrotophos | - Monocrotophos – 1 lit | 385 |  |  |
| Introduction of KBSH-53 along with ICM | Sunflower | 5.1 | 10-12 | 7-8 | - Abiotic stress | - Compartment bunding - Wider row method of sowing | - | - | 10 | 25 |
|  |  |  |  |  | - Imbalanced nutrition (NPK 11:29:0 Kg/ha) | - CaCl2 seed priming - Application of micronutrients & biofertilisers | - Calcium Chloride – 150 gm | 18 |  |  |
|  |  |  |  |  |  |  | - Azospirillum – 500 gm | 18 |  |  |
|  |  |  |  |  |  |  | - ZnSO4 – 10 Kg | 360 |  |  |
|  |  |  |  |  |  |  | - Boron – 1 Kg | 215 |  |  |
|  |  |  |  |  | - Incidence of SND | - SND management | - Imidacloprid – 100 ml | 230 |  |  |
|  |  |  |  |  | - Incidence of leaf eating caterpillar (No spray is taken) | - Spray of Profenophos | - Profenophos – 750 ml | 375 |  |  |
|  |  |  |  |  | - High incidence of powdery mildew (No spray is taken) | - Introduction of KBSH-53 | - Seeds – KBSH-53 – 5 Kg | 1250 |  |  |
|  |  |  |  |  |  | - Spray of Propiconazole | - Propiconazole – 500 ml | 574 |  |  |

RABI  : Nil

| Thrust area | Crop | Yield gap (q/ ha ) |  |  | Reasons for yield gap | Technology to be demonstrated | Critical inputs to be provided |  | Area (ha) | No. of farmers District average yield |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | District average yield | Potential yield | Farmers yield |  |  | Name & Quantity (kg/ha) | Cost (Rs./ha) or Rs./unit |  |  |

SUMMER

| Thrust area | Crop | Yield gap (q/ ha ) |  |  | Reasons for yield gap | Technology to be demonstrated | Critical inputs to be provided |  | Area (ha) | No. of farmers District average yield |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | District average yield | Potential yield | Farmers yield |  |  | Name & Quantity (kg/ha) | Cost (Rs./ha) or Rs./unit |  |  |
| Introduction of TAG-24 variety along with ICM | Groundnut | 10.00 | 22-25 | 15-16 | - Low productivity of local variety | - Introduction of TAG-24 variety - Broad bed furrow method of sowing | Pods TAG-24 – 200 Kg | 3500 | 5 | 10 |
|  |  |  |  |  | - Imbalanced nutrition (Non application of gypsum and Zinc) | - Application of micronutrients & usage of biofertiliser | Rhizobium – 2.5 Kg | 88 | 10 | 25 |
|  |  |  |  |  |  |  | PSB-2.5 Kg | 88 |  |  |
|  |  |  |  |  |  |  | ZnSO4 – 25 Kg | 900 |  |  |
|  |  |  |  |  |  |  | Gypsum – 500 Kg | 1375 |  |  |
|  |  |  |  |  | - Incidence of leaf eating caterpillar | - Spray of profenophos | Profenophos – 750 ml | 375 |  |  |
|  |  |  |  |  | - Incidence of collar rot (No seed treatment) | - Seed treatment with trichoderma | Trichoderma – 1.25 Kg | 200 |  |  |
|  |  |  |  |  |  | - Soil application of trichoderma + FYM | Trichoderma-2.5 Kg | 400 |  |  |
|  |  |  |  |  | - Incidence of leaf minor | - Spray of monocrotophos | Monocrotophos – 1 lit | 385 |  |  |
|  |  |  |  |  | - Improper schedule of irrigation | - Irrigation management | - | - |  |  |
| Introduction of KBSH-53 along with ICM | Sunflower | 8.5 | 15-20 | 15-16 | - Imbalanced nutrition (Non application of Zinc, Boron and Gypsum) | - Application of micro nutrients & biofertiser | Azospirillum – 500 gm | 18 | 15 | 25 |
|  |  |  |  |  |  |  | ZnSO4 – 10 Kg | 360 |  |  |
|  |  |  |  |  |  |  | Gypsum – 100 Kg | 275 |  |  |
|  |  |  |  |  |  |  | Boron – 1 Kg | 215 |  |  |
|  |  |  |  |  | - Incidence of SND | - Spray of Imidacloprid | Imidacloprid – 100 ml | 230 |  |  |
|  |  |  |  |  | - Incidence of leaf eating caterpillar (No spray is taken) | - Spray of Profenophos | Profenophos – 750 ml | 375 |  |  |
|  |  |  |  |  | - Incidence of powdery mildew | - Introduction of KBSH-53 | Seeds(KBSH-53) – 5 Kg | 1250 |  |  |
|  |  |  |  |  |  | - Spray of Propiconozole | Proiconozole – 500 ml | 574 |  |  |
|  |  |  |  |  | - Improper schedule of irrigation | - Irrigation management | - | - |  |  |

C. Pulses

KHARIF

| Thrust area | Crop | Yield gap (q/ ha ) |  |  | Reasons for yield gap | Technology to be demonstrated | Critical inputs to be provided |  | Area (ha) | No. of farmers District average yield |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | District average yield | Potential yield | Farmers yield |  |  | Name & Quantity (kg/ha) | Cost (Rs./ha or Rs./unit) |  |  |
| Introduction of Selection-4 & ICM | Greengram | 2.89 | 8-10 | 3-4 | - Moisture stress - Cultivation of local variety - Incidence of leaf defoliator (Sphingid moth) - Incidence of powdery mildew & leaf spot (No control measures are taken) | - Compartment bunding - Seed priming with CaCl2 - Opening of conservation furrows at the interval of 8-10 mtr - Demonstration of Selection-4 variety - Usage of bio-fertiliser, seed treatment & soil application - Spraying of Profenophos - Spraying of Propiconazole | Greengram seed (Selection-4) -12.5 Kg | 750 | 20 | 50 |
|  |  |  |  |  |  |  | Bio-fertiliser - Azospirillum-10 Kg - PSB – 10 Kg - Rhizobium – 500 gm | 400 400 25 |  |  |
|  |  |  |  |  |  |  | Vermicompost – 5 Qtl. | 1350 |  |  |
|  |  |  |  |  |  |  | Profenophos -0.25 lit | 267 |  |  |
|  |  |  |  |  |  |  | Propiconazole – 0.25 lit | 287 |  |  |
|  |  |  |  |  |  |  | CaCl2 – 360 gm | 28 |  |  |

RABI

| Thrust area | Crop | Yield gap (q/ ha ) |  |  | Reasons for yield gap | Technology to be demonstrated | Critical inputs to be provided |  | Area (ha) | No. of farmers District average yield |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | District average yield | Potential yield | Farmers yield |  |  | Name & Quantity (kg/ha) | Cost (Rs./ha) or Rs./unit |  |  |
| Introduction of JG-11 & ICM | Bengalgram | 10 | 25 | 15-18 | Incidence of pod borer wilt and rust (High dosage of chemicals for control of pod borer and no control measures for rust and wilt) | - Seed treatment with Trichoderma - Seed treatment with Rhizobium - Soil application - Azospirillum - PSB - Vermicompost - Installation of pheromone traps with lures - Spraying of profenophos - Spraying of NPV - Spraying of Acephate - Spraying of Propiconozole - Bird perches - Jowar as border crop - Putting water pots - Broadcasting of puffed rice | JG-11 seeds – 62.5 Kg | 2500 | 20 | 50 |
|  |  |  |  |  |  |  | Trichoderma – 625 gm | 120 |  |  |
|  |  |  |  |  |  |  | Rhizobium – 1 kg | 40 |  |  |
|  |  |  |  |  |  |  | Pheromone traps – 8 No. | 144 |  |  |
|  |  |  |  |  |  |  | Lures – 24 No. | 192 |  |  |
|  |  |  |  |  |  |  | NPV – 250 LE | 405 |  |  |
|  |  |  |  |  |  |  | Propiconazole – 0.25 lit | 287 |  |  |

SUMMER

| Thrust area | Crop | Yield gap (q/ ha ) |  |  | Reasons for yield gap | Technology to be demonstrated | Critical inputs to be provided |  | Area (ha) | No. of farmers District average yield |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | District average yield | Potential yield | Farmers yield |  |  | Name & Quantity (kg/ha) | Cost (Rs./ha) or Rs./unit |  |  |

D. Cotton

KHARIF

| Thrust area | Crop | Yield gap (q/ ha ) |  |  | Reasons for yield gap | Technology to be demonstrated | Critical inputs to be provided |  | Area (ha) | No. of farmers District average yield |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | District average yield | Potential yield | Farmers yield |  |  | Name & Quantity (kg/ha) | Cost (Rs./ha) or Rs./unit |  |  |
| Introduction of Bt. Cotton along with ICM | Bt. Cotton | 10-12 | 25-30 | 20-22 |  |  | Seeds – 1.25 Kg | 1875 | 10 | 25 |
|  |  |  |  |  | - Incidence of sucking pest | - Spray of Imidacloprid (2 times) | Imidacloprid -300 ml | 645 |  |  |
|  |  |  |  |  | - Incidence of alterneria leaf spot | - Spray of Hexaconazole (2 times) | Hexaconazole – 500 ml | 225 |  |  |
|  |  |  |  |  | - Square & tender bolls dropping - Leaf reddening | - Spray of MgSO4 & NAA (2 times) - Spray of potassium nitrate | MgSO4 – 1.250 Kg | 150 |  |  |
|  |  |  |  |  |  |  | NAA – 400 ml | 200 |  |  |
|  |  |  |  |  |  |  | Potassium nitrate – 2 Kg | 220 |  |  |

RABI

| Thrust area | Crop | Yield gap (q/ ha ) |  |  | Reasons for yield gap | Technology to be demonstrated | Critical inputs to be provided |  | Area (ha) | No. of farmers District average yield |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | District average yield | Potential yield | Farmers yield |  |  | Name & Quantity (kg/ha) | Cost (Rs./ha) or Rs./unit |  |  |
| ICM in desi cotton | Cotton | 2.75 | 8-10 | 4-5 | - Moisture stress | - Compartment bunding - Opening of conservation furrow | - | - | 20 | 50 |
|  |  |  |  |  | - Low productivity of local variety | - Demonstration of DDHC-11 variety | Seeds (DDHC-11) – 10 Kg Azospirillum – 12.5 Kg PSB-12.5 Kg Vermicompost – 5 Qtl | 500 500 500 1500 |  |  |
|  |  |  |  |  | - Square dropping | - Spray of NAA | NAA – 200 ml | 100 |  |  |
|  |  |  |  |  |  | - Spray of Potassium nitrate | Potassium nitrate – 2 Kg | 220 |  |  |

SUMMER : Nil

| Thrust area | Crop | Yield gap (q/ ha ) |  |  | Reasons for yield gap | Technology to be demonstrated | Critical inputs to be provided |  | Area (ha) | No. of farmers District average yield |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | District average yield | Potential yield | Farmers yield |  |  | Name & Quantity (kg/ha) | Cost (Rs./ha) or Rs./unit |  |  |

### TAble- 5 : Plan For Training Programmes For Extension Functionaries During 2010-11

| Crop / Enterprise | Identified Thrust Area | Organization | Training Course Title | No. of Courses | Skill to be transferred |
| --- | --- | --- | --- | --- | --- |
| In-situ soil moisture conservation | Moisture stress management | Karnataka State Department of Agriculture | In-situ soil moisture conservation practices | 02 | Methods of In-situ soil moisture conservation practices |
| Groundnut | Enhancement of productivity | Karnataka State Department of Agriculture | Integrated Crop Management Practices | 02 | Relevant skills based on the need assessment |
| Sunflower | Caterpillar and Powdery mildew management | Karnataka State Department of Agriculture | Management of Caterpillar and powdery mildew | 02 |  |
| Bt Cotton | Integrated Crop Management | Karnataka State Department of Agriculture | ICM | 01 |  |
| Maize | Soil fertility management | Karnataka State Department of Agriculture | Soil fertility management | 01 |  |
| Onion + Chilli | Post harvest technology | Karnataka State Department of Agriculture | Post harvest management in Onion and Chilli | 01 |  |
| Nutrition | Health | - Mahila Samukhya - Department of Women & Child Welfare | Importance of Balanced diet, Nutrition, Health, Hygiene and Deficiency diseases | 03 | Layout of Kitchen Garden |
| Drudgery | Drudgery reduction | Department of Women & Child Welfare | Drudgery reducing equipments | 05 | Demonstration of drudgery reducing equipments |
| High value Horticulture crop | Protected cultivation of high value crop with flower and vegetable | State Department of Horticulture | Cultivation of high value Horticulture crop under protected condition | 01 | Layout, planting and fertigation method |
| Bio- Pesticides | Preparation & usage of bio-pesticides to crops | Karnataka State Department of Agriculture | Preparation and usage of bio-pesticides | 01 | Method demonstration on preparation of Neem & Pongamia paste |

* Training title should specify the major technologies/skills to be transferred / refreshed.

## Table- 6:  Plan of vocational training programmes for Young Farmers (Rural Youth)

## during 2010-11

| Crop / Enterprise | Identified Thrust Area | Training title* | No. of programmes | Duration (days) | Skill to be transferred |
| --- | --- | --- | --- | --- | --- |
| Dairy | Self Employment | Scientific dairy farming | 03 | 05 | Dairy management skills |
| Gardening | Self Employment | Gardening Techniques | 01 | 10 | Gardening Skills |
| Entrepreneurship | EDP Skills | EDP in Agriculture | 03 | 05 | Skills in Production, Processing and Marketing of agriculture produce |
| Value addition | Food processing | EDP & Food processing | 01 | 30 | Preparation of value added products and instant mixes |
| Vermicompost Technology | Usage and preparation of vermicompost | Vermicompost production technology and usage | 02 | - | - Preparation of bed - Value addition to vermicompost |
| Bio-pesticides | Preparation of Bio-pesticides | Preparation and usage of Bio- pesticides | 01 | - | Preparation methods & schedule of usage |

* Training title should specify the major technology/skill to be transferred.

Table – 7  :  Plan of training programmes for farmers/farm women during 2010-11

| Crop / Enterprise | Major problem | Identified Thrust Area | Training Course Title* | No. of Courses | Skill to be transferred |
| --- | --- | --- | --- | --- | --- |
| Greengram | Abiotic stress | In-situ soil moisture conservation | In-situ soil moisture conservation practice | 02 | In-situ soil moisture conservation method |
|  | Low productivity due to powdery mildew and pod borer | Management of powdery mildew & pod borer | Management of pod borer and powdery mildew | 02 | Identification of disease, pod borer and chemicals for control |
|  | Low productivity of local variety | Introduction of S-4 variety | ICM in S-4 variety | 02 | Identification of morphological characteristics of S-4 variety |
| Bengalgram | Incidence of wilt | Introduction of JG-11 variety along with ICM | ICM | 02 | Identification of wilt and varietal characters of JG-11 variety |
|  | Incidence of pod borer | IPM | IPM | 02 | Identification of pest & IPM Package |
|  | Drudgery in harvesting | Use of cotton hand gloves | Use of cotton hand gloves | 02 | Method of harvesting |
| Groundnut | Abiotic stress | Moisture conservation | In-situ moisture conservation | 02 | Moisture conservation methods |
|  | Imbalanced nutrition | ICM and introduction of GPBD- 4 & TAG-24 varieties | ICM | 03 | Identification of characters of varieties |
|  | Low productivity of local variety |  |  |  |  |
|  | Incidence of leaf minor | Leaf minor management | Leaf minor management | 02 | Identification of disease and chemicals for control |
| Sunflower | Imbalanced nutrition | Balanced nutrition | INM | 02 | Symptoms of deficiency & quantity and method of application of nutrients |
|  | Powdery mildew | - Management of powdery mildew - Introduction of KBSH-53 | ICM in KBSH-53 | 02 | Identification of disease and it’s management |
|  | Drudgery in cutting of ear head | Drudgery reduction | Use of Cotton cloth hand gloves for harvesting | 02 | Use of cotton cloth hand gloves |
| Hybrid Cotton | Lack of Knowledge on production technology | ICM | ICM in Bt. Cotton | 02 | Identification of ICM practices |
| Desi Cotton | Low productivity of Jayadhar and imbalanced nutrition | Introduction of DDHC-11 variety | ICM | 02 | Identification of characteristics of DDHC-11 |
| Maize | Problematic soils and Improper irrigation | Soil & Water management | Soil fertility and irrigation management | 02 | Methods of soil fertility management & irrigation |
|  | Imbalanced nutrition | INM | INM in Maize | 02 | Deficiency symptoms & nutrient application |
|  | Drudgery in cutting of stalks | Improved sickle for harvesting | Harvesting tools in Maize | 01 | Method of cutting |
| Rabi Jowar | Moisture stress | Moisture conservation | Soil moisture conservation practices and seed priming | 03 | Methods of soil moisture conservation practices and seed treatment with CaCl2 |
|  | Low productivity of Maladandi (M35-1)variety | Introduction of CSV-22 variety | ICM in CSV-22 | 02 | Morphological characteristics of CSV-22 variety |
| Wheat | Low productivity of local variety | Introduction of improved variety (GW-322) | ICM | 01 | Morphological characteristics of variety (GW-322) |
|  | Drudgery in harvesting of stalks | Improved Sickles | Harvesting of Wheat stalks with improved sickle | 01 | Method of harvesting |
| Onion | Poor quality of bulb | Introduction of Arka Kalyan variety | ICM in Onion | 02 | Characteristics of Arka Kalyan variety |
| Chilli | Anthracnose disease | Management of anthracnose | Management of anthracnose | 02 | Identification of disease and methods of control |
|  | Murda complex | Murda complex management | Murda complex management | 02 | Identification of disease and chemicals for control |
|  | Poor quality of dry Chilli | Post harvest management | PHT in Chilli | 02 | Ideintification of PHT technology |
| Mango | Improper orchard management | Orchard management | Orchard management | 02 | Relevant skills |
|  | No diversification | Promotion of dry land horticulture | dry land horticulture | 02 | Relevant skills |
|  | Incidence of hoppers & powdery mildew | Management of hoppers and powdery mildew | Management of hoppers and powdery mildew | 02 | Identification of disease and chemicals for control |
| Tomato | Poor keeping quality on leafcurl incidence | Introduction of Arka Vikas | ICM | 01 | Morphological characteristics of variety |
| Brinjal | Shoot & fruit borer | Management of shoot & fruit borer | Management of shoot & fruit borer | 01 | Identification of symptoms, pest and chemicals for control |
| Frenchbean | Low productivity of local variety | Introduction of Arka Suvida variety | ICM | 01 | Identification of Morphological characteristics of variety |
| Ridge gourd | Low productivity of local variety | Introduction of Arka Sujit and Sumit variety | ICM | 01 | Identification of characteristics of variety |
| Chrysanthemum | Imbalanced nutrition | INM | INM | 01 | Dosage &method of application of nutrients |
|  | Improper pinching | Pinching management | Pinching in Chrysanthemum | 01 | Method of pinching |
| Aster | Introduction of Aster crop | Introduction of Aster crop | ICM | 01 | Relevant skills in production technology |
| Dairy Enterprises | Imbalanced nutrients | Nutrient management | Nutrient management | 04 | Type and methods of preparation of nutrients |
|  | Worm Infestation | Management of worms | Ecto and endo parasite management | 02 | Identification of ecto & endo parasite management |
| Sheep | Low productivity of meat & wool | Up gradation of local sheep with Ramboullete breed | Up gradation of local sheep | 02 | Identification & characteristics of Ramboullete breed |
| Goat | Low productivity of milk | Up gradation of local goat with Bidari breed buck | Up gradation of local goat | 02 | Identification & characteristics of Bidari breed buck |
| Poultry | Low productivity of eggs in local breeds | Introduction of Swarnadhara breed | Rearing of improved breed | 02 | Identification of breed characteristics |
| Fuel saving devices | Drudgery & non availability of fuels | Fuel efficiency & to reduce drudgery | Drudgery reducing tools | 03 | Operation of envirofit chulha |
| Human nutrition | Nutrition deficiency | Nutrition | Balanced diet | 03 | Deficiency symptoms |
| Farm implements | Drudgery in weeding | Drudgery reduction | Drudgery reduction equipments | 02 | Operation of weeder & Sickle |

* Training title should specify the major technology/skill to be transferred.

## Table 8. Plan for sponsored training programme during 2010-11

| Crop/ Enterprise | Identified Thrust Area | Sponsored Organization | Training course title* | No. of Courses | Sponsored Agency | Skill to be transferred |
| --- | --- | --- | --- | --- | --- | --- |
| Soil | Soil fertility management | KSDA (Agriculture Department) | Soil fertility management | 03 | -- | Relevant skill will be transferred based on need assessment |
| All crops | Soil moisture conservation | Watershed Development Department | In-situ soil moisture conservation | 3 | -- |  |
| Oil seeds | ICM | KSDA | ICM | 3 | -- |  |
| Pulses | ICM | KSDA | ICM | 2 | -- |  |
| Soil, Water & Crop Management | Water Management | CADA | Soil, Water & crop management in command area | 5 | -- |  |
| Vocational Training | Self Employment | NABARD | Income Generation Progarmme | 5 | -- |  |
| Dairy Enterprises | To increase Milk Production | Zilla Panchayat | Management of milch animals | 8 | -- |  |
| Horticulture Crops | To enhance Productivity | NABARD (VVV clubs) | ICM in fruit and vegetable crops | 5 | -- |  |
| Fruits & vegetables | Processing | State Department of Horticulture | Fruit and vegetable processing | 02 | -- |  |

* Programme title should specify the major technologies/skills to be transferred /refreshed.

Table 9: Details of Extension programmes planned for 2010-11

| Month | Block & village | Extension programme* | Its relation to KVK activities (Tables 2 to 6)** | Expected category of participants | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 |
| April | Gadag Asundi Binkadakatti Mallasamudra Mundargi Petalur Ramenahalli Shirahatti Bannikoppa Tarikoppa Sugenahalli | - Kharif Campaign - Soil Testing | - Training & Demonstration - Front Line Demonstration | 600 100 |  |
| May | Ron Totaganti Nai Mallapur Bachalapur Naragund Kurlageri Banahatti | - Kharif Campaign - Soil testing | Training & Demonstration | 500 |  |
| June | All the identified villages of Gadag | - Seminar on Simaroubha | Training & value addition | 300 |  |
| August | Shirahatti Bannikoppa | - Field Day on Greengram | FLD | 100 |  |
| September | Mundaragi Peta Alur | - Field Day on Groundnut | FLD | 100 |  |
|  | All the identified villages | - Technology Week Celebration | Mandated activities | 2000 |  |
|  | Naragund Kurlageri | - Field Day on Maize | FLD | 150 |  |
|  | Gadag Asundi | - Field Day on Ridge gourd | FLD | 100 |  |
| October | All the identified villages of the Gadag district | - Rabi Campaign - Demonstration of envirofit chulha - World Food Celebration Day | Training & Demonstration | 800 300 |  |
|  | Gadag Asundi | - Field Day on Chrysanthemum & Aster | FLD | 150 |  |
| November | Shirahatti Bannikoppa | - Field Day on Onion - Demonstration of Azolla | FLD FLD | 150 100 |  |
|  | Gadag Asundi | - Field Day on Chilli | FLD | 150 |  |
| December | Naragund Banahatti | - Field Day on Sunflower - Demonstration on Azolla | FLD FLD | 100 100 |  |
|  | Shirahatti Bannikoppa | - Field Day on Bt Cotton - Demonstration on Azolla | FLD FLD | 150 100 |  |
|  | MUNDARAGI Peta Alur | - Women in Agriculture Day | Celebration | 150 |  |
|  | Gadag Mallasamudra | - Field Day on Tomato | FLD | 100 |  |
| January | Ron Totaganti Mallapur Bachalapur | - Animal Health Camp | Training | 150 |  |
|  | Naragund Kurlageri | - Field Day on Bengalgram | FLD | 100 |  |
|  | All the identified villages | - Technology Week Celebration | Mandated activities | 2000 |  |
| February | Shirahatti Bannikoppa | - Field Day on Desi Cotton & rabi Jowar | FLD | 100 |  |
| March | Ron Totaganti | - Field Day on Summer Groundnut | FLD | 150 |  |

Table 10:  Details of print & electronic media coverage planned for 2010-11

| Sl. No. | Nature of literature/publications and no. of copies | Proposed title of the publication |
| --- | --- | --- |
| 1 | Leaflet – 2000 | - Importance of value addition in Amla |
|  | Leaflet – 2000 | - Drudgery reduction equipments |
| 2 | Leaflet – 5000 | - In-situ soil moisture conservation practices |
| 3 | Leaflet – 3000 | - Production technology in Onion |
| 4 | Leaflet – 3000 | - Grain Storage |
| 5 | Handouts-5000 | - Management of pest and disease in Groundut, Sunflower, Bengalgram, Greengram, Chilli and Mango |
| 6 | Handouts-5000 | - Production technology in Groundnut, Sunflower, Cotton, rabi Jowar, Wheat, Maize |
| 7 | Handouts-2000 | - Technology for high meat and wool production in Sheep |
| Sl. No. | Nature of media coverage | Proposed title of the programme to be telecasted/ broadcast |
| 1 | Radio talk | Dry land agronomic practices |
| 2 | Radio talk | INM in Oilseeds |
| 3 | Radio talk | ICM in Bt Cotton |
| 4 | Radio talk | Quality bulb production in Onion |
| 5 | Radio talk | Soil fertility management |
| 6 | Television | Dry land Mango orchard management |
| 7 | Television | Anthracnose management in Chilli |

Table 11:  Nature of collaborative activities planned for 2010-11

| Thrust area | Collaborative Organizations | Nature of activities* | No. of Activities |
| --- | --- | --- | --- |
| - Productivity enhancement & self employment | NABARD & Nationalized Banks | Training | 06 |
| - ICM in Oilseeds, Pulses and Cotton | Karnataka State Department of Agriculture | Training | 10 |
| - Establishment of Resource Centre | Deshpande Foundation, USA | Resource Centre for disseminating of knowledge & inputs | 01 |
| - Transfer of technology | Karnataka State Department of Agriculture | Implementation of Filed School | 01 |
| - Self Employment | Zilla Panchayat, SGSY Programme | Training | 10 |
| - Soil and Water Conservation | District Watershed Development Department | Training | 10 |
| - Soil, crop & water management | CADA, Belgaum | Training | 05 |

*Specify the activity like training, meetings, seminars, campaigns, workshops

Table 12:  Financial status of revolving fund and plan for its utilization               (Rs. In lakhs)

| Opening balance as on 01.04.2009 | Expenditure incurred during 2009-10 | Receipts during 2009-10 | Closing balance as on 31.03.2010 | Proposed expenditure during 2010-11 | Proposed receipts during 2010-11 |
| --- | --- | --- | --- | --- | --- |
| 1.84 | 3.83 | 4.00 | 2.01 | 5.00 | 8.00 |

Table 13:  Physical status of revolving fund and plan for its utilization

| Opening stock position of materials* as on 01.04.2009 (Quantity in Quintals) | Quantity produced during 2009-10 (in Qtls.) | Quantity sold during 2009-10 (in Qtls.) | Closing stock position as on 31.03.2010 (in Qtls.) | Expected production during 2010-11 (in Qtls.) | Expected number of beneficiaries |
| --- | --- | --- | --- | --- | --- |
| Vermicompost:5 | Vermicompost 280.0 | Vermicompost 270.50 | Vermicompost 5.0 | 400 | 15 |
| Earthworms | Earthworms : 1.16 | 1.16 | - | 1.20 | 50 |
| Amla Products | 0.45 | 0.36 | 0.09 | 0.50 | -- |
| Cotton: 45.0 | Cotton : 45.00 | Cotton : 45.0 | Nil | Cotton : 50.0 | 260 |
| Groundnut : 3.0 | Groundnut : 13.0 | Groundnut : 13.0 | Nil | Groundnut : 20.0 | 10 |
| Greengram : 4.0 | Greengram : 4.0 | Greengram : 4.0 | Nil | Greengram : 6.0 | 95 |
| Rabi Jowar : 2.50 Qt | Rabi Jowar : 2.50 | Rabi Jowar : 2.50 | Nil | Rabi Jowar : 8.0 | 60 |
| Onion : 2.50 Qt | Onion : 2.50 | Onion : 2.50 | Nil | Onion : 6.0 | 225 |
| Ridge gourd : 0.30 | Ridge gourd : 0.30 | Ridge gourd: 0.30 | Nil | Ridge gourd : 0.60 | 40 |
| Mango grafts : 5000 nos. | Mango grafts : 5000 nos. | Mango grafts : 5000 nos. | Nil | Mango grafts : 4000 nos. | 150 |

Table 14. Plan for utilization of Revolving Fund (2010-11)

| Amount to be invested (Rs.) | Purpose | Expected production | Approximate value of the produce (Rs.) |
| --- | --- | --- | --- |
| 50,000/- | Preparation & sale of Neem soap and Pongamia soap | 500 kg | 50,000/- |
| 25,000/- | Value addition of vermicompost with bio-fertilizer and Vam Culture | 20 tonns | 60,000/- |
| 150000/- | Seed production of Bengalgram (JG-11) | 50.00 Qt. | 175000/- |
| 125000/- | Cotton (DDHC-11) seed production | 30.00 Qt. seed 18.00 Qt. Kapas | 90000/- 99000/- |
|  | Seed grading (processing) (Greengram, Bengalgram, Rabi Jowar & Wheat) | 1000 bags @ Rs. 50/- | 50000/- |
| 450000/- | Onion seed production | 1710 kgs. | 684000/- |
| 6000/- | Preparation of Amla products | 30 kg Amla Candy 10 kgs Amla powder 10 Kg Amla Supari | 12000/- |
| 40000/- | Purchase of Twin wheel hoe weeders | 50 nos. | 42500/- |
| 15000/- | Fabrication of Kissan Cookers | 30 nos. | 18000/- |
| 15000/- | Soil & Water Testing | Soil Samples 630 | 31500/- |
|  |  | Analysis of water samples – 60 | 4500/- |

## Table 15:  Status of KVK farm and Demonstration units

| No. of blocks | Area | Source of irrigation | Season | Crop/enterprise/demonstration units | Size (no. of units/area) | Expected output |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Quantity | Value (Rs.) |
| 14 | 20 ha | Bore well as protective irrigation for about 4 ha. land | Kharif | Onion + Chilli Chilli Cotton Green gram Ground nut | 2.00 - 2.00 1.20 5.20 | 120 Qt 5 Qt 12 Qt 5 Qt 43 Qt | 60000 25000 30000 15000 107500 |
|  |  |  | Rabi | Rabi Jowar Wheat Bangalgram | 2.00 0.40 0.40 | 25 Qt 3 Qt 3 Qt | 25000 6000 9000 |
|  |  |  | Perennial | Simaroubha Amla Guava Mango | 0.40 0.10 1.20 0.80 | 3 Qt 10 Qt 45 Qt 2 ton | 1500 20000 22500 80000 |
| 01 | - | - | - | Vermicompost & Earthworms production Units | 100’ X 40’ | 50 tons | 125000 |

16 .  Are there any activities planned for production and supply (Either buy back or directly farmer to farmer) of seeds/ planting material/Bio-agents etc. In villages (other than KVK farm) so that public private partnership is utilized. Please give details in the following format

| Sl. No | Seeds/Planting material/Bio-agent | Name of the public-private partnership arranged | Quantity of output expected (Qtl) |
| --- | --- | --- | --- |
| 1. | Onion seed production | KVK identified JLG/SHG members | 17 |
| 2. | Groundnut | KVK Identified JLG/SHG member | 35 |
| 3. | Bengalgram | KVK identified JLG/SHG members | 50 |
| 4. | Greengram | KVK identified JLG/SHG members | 15 |

17. What is the extent of cultivable wasteland in your district? Are there any specific activities planned to be implemented in these wastelands by the KVK during 2010-11. Please give details.

Cultivable wasteland in Gadag district is very less.  Hence no activities are proposed.

18. National Horticulture Mission (NHM) is being implemented through out the country. You are requested plan for implementing some of the activities envisaged in NHM in your district in collaboration with district head of department of horticulture. Please give details of any such plans for 2010-11

National Horticultural Mission is being implemented in Gadag district from 2009-10.   During 2010-11, KVK has planned to organize training programmes for NHM assisted farmers in collaboration with State Department of Horticulture.  Apart from training, KVK has planned farm advisory services for farmers covered under National Horticultural Mission.

19. Whether ATMA is functioning in your district? YES/NO

Agricultural Technology Management Agencies (ATMA) is in operation in Gadag district since 2008-09.   Under ATMA, KVK proposed to organize field school and training programmes.

Strategic Research and Extension Plan (SREP) has been prepared.

20.  What type of scientist-Farmer linkages are proposed by your KVK for 2010-11?

KVK proposed to establish Resource Centres in the identified villages for speedy technology dissemination.  This centre acts as a platform for scientist-farmer linkage.    Apart from this, KVK has network of farmer groups and field school programmes which facilitate for scientist-farmer linkage.

Mobile based farm advisory, weather and marketing services are already being rendered to the farmers.  A total of 600 farmers have registered for the service.

21.   Activities of soil, water and plant testing laboratory

| Year of establi-shment of lab | Equipments available | No. of samples planned To be analyzed and reported 2009-10 |  |  |  | No. of farmers benefited | Revate realized (Rs.) | Target for the year 2010-11 | Availability of chemical and glass work satisfactory or not |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Soil | Plant | Water | Other |  |  |  |  |
| 2005-06 | - pH Meter - Conductivity bridge - Spectro photometer - Flame photometer - Physical balance - Chemical balance - Water Distillation Unit - Kjeldal digestion and distillation unit - Shakers (2 No’s) - Refrigerator - Oven - Hot plate - Grinder | 426 | 28 | 37 | - | 394 | 26175 | Soil samples-650 Water samples-130 Plant samples-250 Other samples -40 | Satisfa-ctory |

22. Details of budget utilization (2009-10)

| Sl. No. | Particulars | Sanctioned | Released | Expenditure |
| --- | --- | --- | --- | --- |
| A. Recurring Contingencies |  |  |  |  |
| 1 | Pay & Allowances | 5100000 | 5100000 | 5098985 |
| 2 | Traveling allowances | 100000 | 100000 | 99946 |
| 3 | Contingencies |  |  |  |
| A | Stationery, telephone, postage and other expenditure on office running, publication of Newsletter and library maintenance (Purchase of News Paper & Magazines) | 195000 | 195000 | 194992 |
| B | POL, repair of vehicles, tractor and equipments | 160000 | 160000 | 159948 |
| C | Meals/refreshment for trainees (ceiling upto Rs.40/day/trainee be maintained) | 105000 | 105000 | 140960 |
| D | Training material (posters, charts, demonstration material including chemicals etc. required for conducting the training) | 65000 | 65000 | 64678 |
| E | Frontline demonstration except oilseeds and pulses (minimum of 30 demonstration in a year) | 161000 | 161000 | 160471 |
| F | On farm testing (on need based, location specific and newly generated information in the major production systems of the area) | 109000 | 109000 | 108911 |
| G | Training of extension functionaries | 10000 | 10000 | 9850 |
| H | Maintenance of buildings | 30000 | 30000 | 30000 |
| I | Extension activities | 30000 | 30000 | 29622 |
| J | Farmers’ Field School | 25000 | 25000 | 25000 |
| K | Library | 10000 | 10000 | 9886 |
| TOTAL (A) |  | 6100000 | 6100000 | 6097249 |
| B. Non-Recurring Contingencies |  |  |  |  |
| 1 | Works | - | - | - |
| 2 | Equipments including SWTL & Furniture | - | - | - |
| 3 | Vehicle (Four wheeler/Two wheeler, please specify) | - | - | - |
| 4 | Library (Purchase of assets like books & journals) | - | - | - |
| TOTAL (B) |  | - | - | - |
| C. REVOLVING FUND |  | - | - | - |
| GRAND TOTAL (A+B+C) |  | 6100000 | 6100000 | 6097249 |

23.  Details of Budget Estimate (2010-11) - ICAR KVKs alone may consider Pay and

Allowances based on VI Pay Commission Orders from ICAR, for rest of the KVKs

please estimate based on the existing norms, since ICAR is yet to take decision in

this regard.

(Rs. In lakhs)

| Sl. No. | Particulars | Budget estimate |
| --- | --- | --- |
| A. Recurring Contingencies |  |  |
| 1 | Pay & Allowances | 55.067 |
| 2 | Traveling allowances | 3.000 |
| 3 | Contingencies |  |
| A | Stationery, telephone, postage and other expenditure on office running, publication of Newsletter and library maintenance (Purchase of News Paper & Magazines) | 2.500 |
| B | POL, repair of vehicles, tractor and equipments | 1.750 |
| C | Meals/refreshment for trainees (ceiling upto Rs.40/day/trainee be maintained) | 1.250 |
| D | Training material (posters, charts, demonstration material including chemicals etc. required for conducting the training) | 1.500 |
| E | Frontline demonstration except oilseeds and pulses (minimum of 30 demonstration in a year) | 2.000 |
| F | On farm testing (on need based, location specific and newly generated information in the major production systems of the area) | 1.250 |
| G | Training of extension functionaries | 0.300 |
| H | Maintenance of buildings | 0.500 |
| I | Establishment of Soil, Plant & Water Testing Laboratory |  |
| J | Library | 0.300 |
| K | Maintenance of STL | 0.250 |
| TOTAL (A) |  | 70.267 |
| B. Non-Recurring Contingencies |  |  |
| 1 | Works | 53.000 |
| 2 | Equipments & Furnitures | 5.000 |
| 3 | Vehicle (Four wheeler/Two wheeler, please specify) | - |
| 4 | Library (Purchase of assets like books & journals) | 0.250 |
| TOTAL (B) |  | 58.250 |
| C. REVOLVING FUND |  | - |
| GRAND TOTAL (A+B+C) |  | 128.267 |

24. Targets for E-linkage activities for 2010 - 11

| Sl. No | Nature of activities | Likely period of completion (please set the time frame) | Remarks if any |
| --- | --- | --- | --- |
| 01 | Final installation of E-Linkage facility | June 2010 | Need training on use of all the facilities provided under e-linkage |
| 02 | Creation of web-site | Updation of Website – May 2010 | - |
| 03 | Development of Technological Models with modules in major disciplines | January – 2011 | Need training on development of technological models. |
| 04 | Creation and maintenance of relevant database system for KVK as follows - OFT - FLD - Training database - Seeds & planting material - Extension activities - Database of farmers visiting to our KVK - District database - Database of SHGs - Database of soil test - Database of survey made for need based trainings | Feb – 2011 |  |
| 05 | Any other (Please specify) | - | - |

25. Activities planned under Rainwater Harvesting Scheme during 2010-11 (only to those KVKs which are already having scheme under Rain Water Harvesting)

| S. No | Activities planned during 2009-10 | Remarks if any |
| --- | --- | --- |
| 1 | Training of farmers on various rain water harvesting structures | No. of courses : 12 No. of farmers : 360 |
| 2 | Establishment of rain water harvesting structures in farmers field under KVK guidance | No. of farmers : 25 |

26. Please give details of activities planned, other than those listed above.

Activities Proposed under Farmers Field School (FFS)

Title of FFS: Integrated Crop Management in Bt Cotton

Problem Definition: In Gadag district area under Bt Cotton is picking up and it  contributes to the district economy to considerable extent.   The farmers are not fully aware about Bt Cotton production aspects.   Incidence of sucking pest and mired bug problems are affecting the net income of farmers.  Farmers have been using mixture of 2-3 pestcides to control the pest menace,  which resulted  in increasing the cost of production apart from destroying the beneficial natural predators,   parasitoides and fungus.    This calls for an approach to involve the farmers in management of pest through eco-friendly means i.e., Integrated Crop Management through Farmers’ Field School concept.

MAIN OBJECTIVES OF FARMERS’ FIELD SCHOOL

- To provide basic agro-ecological knowledge and skills on Bt Cotton production throughout the crop season through participatory means.

- To reduce the cost of cultivation incurred mainly on pesticides

- To enhance Farmers’ participatory decisions on the management of pest.

- To increase the net income of farmers

- To conserve the natural predators, parasitoids and fungus.

SCIENTIFIC RATIONALE OF FARMERS’ FIELD SCHOOL

The FFS approach helps to understand the problem and its causes through participatory approach.   It helps to study the agro-ecological system of the production and adopt environment friendly measures to tackle the problem.

THE LEARNING PROCESS INVOLVED IN FARMERS’ FIELD SCHOOL

Integrated Crop Management training through FFS approach is unique in many ways.  It holds farmers interest till end of the programme.    The training which stretches throughout the Bt Cotton season addresses the production technology and  more importance to pest menace and its control through   eco-friendly methods.   Life cycle and nature of damage of each pest is studied by the farmers.   They understand the beneficial and non-beneficial insects.   Farmers can be able to study the agro-ecological analysis of their production system and learn the role of community in addressing the pest menace.

ACTORS IN FARMERS’ FIELD SCHOOL

Participants of Farmers’ Field School:  These are the leading farmers selected by villagers

Collaborator: Is farmer/farmwomen who gives land for conducting field studies in throughout the cropping season.

Facilitator:  Facilitator is a technically competent farmer to lead the group of leading farmers through exercises.  The facilitator will participate in discussion sessions as contributor rather than a leader in arriving at an agreed consensus.

Priorities of Farmers’ Field School:

- Agro-eco-system analysis of Bt Cotton production system

- Management of pest through  eco-friendly means

- Reduction of cost of production

- Community role in addressing the problem

Budget details:

| Sl. No. | Particulars | Amount (Rs.) |
| --- | --- | --- |
| 1. | Critical input for conducting ICM in Bt Cotton | 4000.00 |
| 2. | Refreshment during Ten Training Programme @ 600/programme | 6000.00 |
| 3. | Farmers’ Field School Kits | 2500.00 |
| 4. | Bags & Caps | 2000.00 |
| 5. | Field day expenditure | 3000.00 |
| 6. | Publishing material expenditure | 1500.00 |
| 7. | Honorariums for one facilitator for 10 visits @ 400/visit | 4000.00 |
| 8. | Stationary & other expenditure | 2000.00 |
|  | Total | 25000.00 |