###### ZONAL PROJECT DIRECTORATE – ZONE VIII BANGALORE

###### ACTION PLAN OF KVKs IN ZONE VIII FOR 2014-15

###### 1. General information about the Krishi Vigyan Kendra

| 1.1 | Name and address of KVK with Phone, Fax and e-mail | : | Bapooji Krishi Vigyan Kendra, Santhanpara P.O, Idukki (Dt.), Kerala, PIN-685619. Email: kvksanthanpara@gmail.com Web url: www.kvkidukki.org |
| --- | --- | --- | --- |
| 1.2 | Name and address of host organization | : | Bapooji Sevak Samaj, Kakkattu House, Meenadom P.O., Pampady, Kottayam (Dt.), Pin-686 516, Kerala. Phone: 0481-2506271, Mob: +919446826019 Email: bkvkchairperson@gmail.com |
| 1.3 | Year of sanction | : | 1994 |
| 1.4 | Website address of KVK and date of last update |  | www.kvkidukki.org (11/02/2014) |

2. Details of staff as on date

| Sl. No. | Sanctioned post | Name of the incumbent | Discipline | Existing Pay band | Grade Pay | Date of joining | Permanent / Temporary |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2.1 | Programme Coordinator | Vacant | - | - | - | - | - |
| 2.2 | Subject Matter Specialist | Dr. S. Jayababu | S.M.S. (Animal Science) | 15600-39100 | 5400 | 19-06-1995 | Permanent |
| 2.3 | Subject Matter Specialist | Manju Jincy Varghese | S.M.S. (Soil Science) | 15600-39100 | 5400 | 10-01-2011 | Permanent |
| 2.4 | Subject Matter Specialist | Dr. Benjamin Mathew | S.M.S. (Horticulture/ Extension) | 15600-39100 | 5400 | 17-01-2011 | Permanent |
| 2.5 | Subject Matter Specialist | Vacant | Agronomy | - | - | - | - |
| 2.6 | Subject Matter Specialist | Dr. Binu John Sam | S.M.S. (Horticulture) | 15600-39100 | 5400 | 17-01-2011 | Permanent |
| 2.7 | Subject Matter Specialist | Sudhakar Soundarajan | S.M.S. (Plant Protection) | 15600-39100 | 5400 | 27-01-2011 | Permanent |
| 2.8 | Programme Assistant | Jayisy Joseph | Programme Assistant (Home Science) | 9300-34800 | 4200 | 20-06-1995 | Permanent |
| 2.9 | Computer Programmer | Biju Narayanan | Programme Assistant (Computer) | 9300-34800 | 4200 | 01-10-2007 | Permanent |
| 2.10 | Farm Manager | Rachel Skariakutty | Programme Assistant | 9300-34800 | 4200 | 05-06-1995 | Permanent |
| 2.11 | Accountant/Superintendent | Shaji K. Kakkattu | - | 9300-34800 | 4200 | 05-06-1995 | Permanent |
| 2.12 | Stenographer | Daisy Daniel | - | 5200-20200 | 1900 | 05-06-1995 | Permanent |
| 2.13 | Driver 1 | P. Nandagopal | - | 5200-20200 | 2000 | 05-06-1995 | Permanent |
| 2.14 | Auxiliary staff | K.T. Mathew | - | 5200-20200 | 1800 | 05-06-1995 | Permanent |
| 2.15 | Supporting staff 1 | K.O. Jose | - | 5200-20200 | 1800 | 05-06-1995 | Permanent |
| 2.16 | Supporting staff 2 | P. Sabu | - | 5200-20200 | 1800 | 05-06-1995 | Permanent |

3. Details of SAC meeting conducted during 2013-14

| Sl. No | Date | Major recommendations | Status of action taken in brief | Tentative date of SAC meeting proposed during 2014-15 |
| --- | --- | --- | --- | --- |
| 3.1 | 11/12/2013 | - Recommendation of micro-nutrient sprays should be based only on soil test reports - Organic management in Cabbage & Cauliflower should be emphasized - More importance should be given to soil test based fertilizer recommendations to crops - Demonstration units on Animal Husbandry should be strengthened - More stress to promote organic farming - Increase the number of demonstration units - Production of vegetable seed and quality planting materials should be improved - Women empowerment should be emphasized - Zinc and Boron deficiency is reported in many parts of Idukki district. A scientific intervention and compilation of soil test reports should be done by Bapooji KVK with the support of State Agriculture Department, VFPCK & ICRI to solve this problem - Home Science FLD/OFTs should be linked with other disciplines - Awareness on methods of proper hygiene should be given during food processing training programmes - Manual Chaff cutter should be included in fodder crops interventions - Animal health campaigns should be given more emphasis - More emphasis should be given on Hi-Tech vegetable cultivation and mechanization in paddy - Lead bank officials suggested to improve the linkages on financial literacy centre’s | - FLDs are proposed for 2014-15 - Awareness campaigns are planned - OFTs & FLDs are proposed - Initiated demo units of poultry, rabbit etc. - Awareness campaigns are planned - Activities initiated - Participatory mode of seed production planned - Action initiated - Action initiated - FLDs proposed - Awareness method of proper hygienic are included in food processing training schedules - FLDs proposed - FMD awareness campaigns planned during next month - Training programmes are included on hi-tech vegetable cultivation - EDP training programmes are included with the consultant of FLC | 15th October, 2014 |

4. Capacity Building of KVK Staff

4.1. Plan of Human Resource Development of KVK personnel during 2014-15

| S. No | New Areas of Training | Institution proposed to attend | Justification |
| --- | --- | --- | --- |
| 4.1.1 | Hi-tech agriculture | CPCT (IARI), New Delhi | To update the recent advancement in Fertigation and green house cultivation |
| 4.1.2 | Integrated Pest Management in vegetables | IIHR | To learn skill on Advance Techniques of IPDM in vegetables |
| 4.1.3 | Integrated Pest Management in cardamom | ICRI | To update the knowledge on IPM in cardamom |
| 4.1.4 | Scientific nutrition management | National Institute of Animal Nutrition & Physiology, Adugodi, Bangalore | To update the new technologies in livestock nutrition |
| 4.1.5 | Poultry production | University poultry farm, Mannuthy, Thrissur | For new poultry breeding & feeding technologies |
| 4.1.6 | Livestock production and management | NIRD, Hyderabad | New strategies in livestock production in rural household |
| 4.1.7 | Value addition in livestock products | TANUVAS, Chennai | Value addition in milk, meat and eggs |
| 4.1.8 | Fodder production | TANUVAS, Veterinary College, Namakkal | For new fodder production technologies |
| 4.1.9 | Advanced soil health assessment techniques | CTCRI | To learn skills on advanced techniques in soil health assessment |
| 4.2.0 | Micronutrient analysis | IIHR, Bangalore | Micronutrient analysis |

4.2. Cross-learning across KVKs during 2014-15

| S. No. | Name of the KVK proposed | Specific learning areas |
| --- | --- | --- |
| 4.2.1 | Within ring – KVK Thrissur & KVK Ernakulam | Vegetable seed production, collection of new fodder seeds, poultry breeds & fisheries |
| 4.2.2 | Within the zone – KVK-Namakkal, KVK Erode & KVK Karur | New trends in livestock and fodder production, IFS |
| 4.2.3 | Outside zone – KVK Srinagar, Pondicherry, Goa, Guwahati | Temperate fruits, hi-tech horticulture, piggery production technologies |

5. Proposed cluster of KVKs (3 to 5 neighboring KVKs) to be formed for sharing knowledge/expertise, resources and activities during 2014-15

| S. No. | Name of the KVKs included in the cluster | What do you intend to share with Cluster KVKs | What do you expect from Cluster KVKs |
| --- | --- | --- | --- |
| 5.1 | KVK Thrissur | Advanced information on spice crops & its value addition | Vegetable seed production |
| 5.2 | KVK Ernakulam | Advanced information on spice crops & its value addition | Vegetable top up technology, technology transfer on fisheries |
| 5.3 | KVK Alappuzha | Advanced information on spice crops & its value addition | NICRA project |

6. Operational areas details proposed during 2014-15

| S. No. | Major crops & enterprises being practiced in cluster villages | Prioritized problems in these crops/ enterprise | Extent of area (Ha/No.) affected by the problem in the district | Names of Cluster Villages identified for intervention | Proposed Intervention (OFT, FLD, Training, extension activity etc.)* |
| --- | --- | --- | --- | --- | --- |
| 6.1 | Cardamom | Indiscriminate use of PPC | 40 ha | Bison Valley & 20 acre | FLD |
| 6.2 | Cardamom | Snails damage on the flower and capsules, leading to heavy losses. | 70 ha | Pottancad & 20 acre | OFT |
| 6.3 | Cardamom | Heavy infestation of root grub leading to heavy usage of PPC | 35 ha | Bison Valley, Pottancad & 20 acre | FLD |
|  |  | Indiscriminate use of chemical fertilizers leads to decline in soil fertility | 40 ha | Pottancad | FLD, Training, extension activity |
| 6.4 | Black pepper | Heavy dosage of fungicides are applied for the control of quick wilt | 60 ha | Santhanpara | OFT |
|  |  | Less berry filling, non-uniform ripening and berry shedding | 40 ha | Pottancad | FLD, Training, extension activity |
| 6.5 | Banana | Poor soil fertility, High acidity leading to micro-nutritional disorders | 5 ha | Pottancad | FLD, Training, extension activity |
| 6.6 | Cowpea | Low yield due to incidence of stem fly | 5 ha | Bison Valley & Pottancad | OFT on Management of stem fly in cowpea |
| 6.7 | Bitter gourd | Indiscriminate use of PPC | 15 ha | Bison Valley & 20 acre | FLD on IPDM in Bitter gourd |
| 6.8 | Tapioca | Soil acidity leading to Mg, Zn deficiency resulting in low yield | 5 ha | Bison Valley | OFT, Training, extension activity |
| 6.9 | Rodent and wild boar management | Crop loss due to rodents and wild boars | 5 ha | Bison Valley | FLD, Training, extension activity |
| 6.10 | Mushroom | Mushrooms are highly perishable | 5 units | Bison Valley | FLD, Training |
| 6.11 | Vegetables & Banana | Unscientific crop management | 25 ha | Pottancad, Muttukad, Josegiri | FLD, Training, extension activity |
| 6.12 | Vegetables | Non-availability of quality vegetables | 10 ha | Kurangupara & 20 acre | FLD, OFT, Training, extension activity |
| 6.13 | Dairy cattle, goat, poultry & dairy cows | 1) Poor growth performance. 2) Low body weight. 3) Unaware of new technologies. 4) Low production. | 100 nos. | Bison Valley, Pottancad | FLD, Training & extension activities |

7. Technology Assessment during 2014-15

| S. No. | Crop/ enterprise | Prioritized problem | Title of intervention | Technology options | Source of Technology | Name of critical input | Qty per trial | Cost per trial | No. of trials | Total cost for the intervention (Rs.) | Parameters to be studied | Team members |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 7.1 | Black pepper | Chengannoor is highly susceptible to quick wilt & heavy dosage of fungicides | Assessment of suitable Black Pepper Foot rot (Quick wilt) resistant variety for Idukki District | 1.Farmers practice (Chengannoor) | - | - | - | - | - | - | - | Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
|  |  |  |  | 2.IISR Thevam | IISR | Fertilizers &PPC chemicals | LS | 500.00 | 5 | 2500.00 | 1. Percentage reduction in quick wilt incidence 2. Yield ( is already their in the sw no need to input further) |  |
|  |  |  |  | 3.Ashwati | Farmer developed variety-Wynad |  |  |  |  |  |  |  |
|  |  |  |  | 4.Suvarna |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Total | 2,500.00 |  |  |
| 7.2 | Black pepper | High incidence of pest & disease in living standards of black pepper | Use of concrete poles as standards in black pepper | 1. Farmers practice (Live standards of Glyricidia) | - | - | - | - | - | - | - | Dr. Binu John Sam (SMS-Horticulture), Mr. Biju Narayanan (Computer Programmer) & Mr. K.O. Jose (Skilled Support Staff) |
|  |  |  |  | 2. Live standards of Erythrina | KAU | - | - | - | - | - | BCR Specify another |  |
|  |  |  |  | 3. Concrete poles | IISR | Fertilizers, PP chemicals etc. | LS | 1000.00 | 3 | 3000.00 |  |  |
|  |  |  |  |  |  |  |  |  | Total | 3,000.00 |  |  |
| 7.3 | Cardamom | Snails & slugs damage on the flowers and young berries of cardamom plants, leading to considerable economic loss | Management of snails & slugs in cardamom plantation | 1. Farmers practice | - | - | - | - | - | - | - | Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
|  |  |  |  | 2. Vinegar @ 1ml /litre | ITK - KVK, Idukki - ATMA assessment 2012-13 | Vinegar | 2 litre | 300.00 | 5 | 1500.00 | 1. Reduction in snail & slug population at different days (30, 40 & 60) after treatment |  |
|  |  |  |  | 3. Coffee powder @ 1 g/litre |  | Coffee powder | 2kg | 400.00 |  | 2000.00 |  |  |
|  |  |  |  | 4. Yeast & Honey Mixture @ (10g:10ml) / litre |  | Yeast | 1kg | 100.00 |  | 500.00 |  |  |
|  |  |  |  |  |  | Honey | 1kg | 130.00 |  | 650.00 |  |  |
|  |  |  |  |  |  |  |  |  | Total | 4,650.00 |  |  |
| 7.4 | Cowpea | Low yield due to the incidence of stem fly | Management of stem fly in cowpea | 1. Farmers practice (Quinalphos spray) | - | - | - | - | - | - | - | Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
|  |  |  |  | 2. Spray IIHR-Neem soap @ 10g /litre | IIHR | IIHR-Neem Soap | 500g | 70.00 | 5 | 350.00 | 1. Percentage reduction in shoot fly at different days (15,30 & 45) after treatment |  |
|  |  |  |  | 3. Spray Acephate 75 WP @ 0.75g /litre |  | Acephate | 150g | 210.00 |  | 1050.00 |  |  |
|  |  |  |  |  |  |  |  |  | Total | 1,400.00 |  |  |
| 7.5 | Tapioca | Soil acidity leading to Mg, Zn deficiency resulting in low yield | Management practices for secondary & micronutrient disorders for Tapioca in acid soils | 1. Farmers Practice (No secondary & micronutrients application) | - | - | - | - | - | - | - | Ms. Manju Jincy Varghese (SMS-Soil Science), Mr. Sudhakar Soundarajan (SMS-Plant Protection), Dr. Binu John Sam (SMS-Horticulture) & Mr. Biju Narayanan (Computer programmer) |
|  |  |  |  | 2. Foliar spray of 0.5% MgSO4 + 0.5% ZnSO4 at 60 to 90 days after planting | TNAU | 1. Lime | 1kg | 15.00 | 5 | 75.00 | 1. Weight of tubers / clump 2. Yield (t/ha) 3. BCR |  |
|  |  |  |  |  |  | 2. MgSO4 | 1kg | 30.00 |  | 150.00 |  |  |
|  |  |  |  |  |  | 3. ZnSO4 | 1kg | 80.00 |  | 400.00 |  |  |
|  |  |  |  | 3. Soil application of Mg as MgSO4 @ 20kg /ha (1.62g / plant) + Zn as ZnSO4 @ 12.5kg/ha (1g / plant) within 2 months of planting | KAU, CTCRI | 1. Lime | 1kg | 15.0 |  | 75.00 |  |  |
|  |  |  |  |  |  | 2. MgSO4 | 1kg | 30.00 |  | 150.00 |  |  |
|  |  |  |  |  |  | 3. ZnSO4 | 1kg | 80.00 |  | 400.00 |  |  |
|  |  |  |  |  |  |  |  |  | Total | 1,250.00 |  |  |

## 8. Technology Refinement during 2014-15: Nil.

9. Frontline Demonstrations during 2014-15

| S. No. | Category | Crop/ enterprise | Prioritized problem | Technology to be demonstrated | Specify Hybrid or Variety | Name of the Hybrid or Variety | Source of Technology | Name of critical input | Qty per Demo | Cost per Demo | No. of Demo | Total cost for the Demo (Rs.) | Parameters to be studied | Team members |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 9.1 | Cereals |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9.2 | Millets |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9.3 | Oilseeds |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9.4 | Pulses |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9.5 | Commercial crops |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Cardamom | Heavy infestation of root grub leading to heavy usage of PPC | Management of cardamom root grub with Entomopathogenic Nematodes (EPN) | Variety | Njallani | ICRI & OFT KVK, Idukki | EPN | 1600 nos. | 2400.00 | 5 | 12000.00 | 1) % reduction in root grub attack 2)Yield | Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
|  |  |  |  |  |  |  |  |  |  |  | Total | 12,000.00 |  |  |
|  |  | Cardamom | Young suckers with dead heart symptoms & Indiscriminate use of PPC | Management of shoot fly (Formosina flavipes Mall.) in small cardamom | - | - | OFT KVK, Idukki | Thiamethoxam | 200g | 500.00 | 10 | 5000.00 | 1) % reduction in shoot fly attack | Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
|  |  |  |  |  |  |  |  |  |  |  | Total | 5,000.00 |  |  |
|  |  | Cardamom | Indiscriminate use of chemical fertilizers leads to decline in soil fertility | Site specific nutrient management in cardamom | Variety | Njallani | ICRI & KAU | Lime | 40kg | 600.00 | 5 | 3000.00 | 1) Yield 2) BCR 3) % reduction in insecticide spray | Ms. Manju Jincy Varghese (SMS-Soil Science), Mr. Sudhakar Soundarajan (SMS-Plant Protection), Dr. Binu John Sam (SMS-Horticulture) & Mr. Biju Narayanan (Computer programmer) |
|  |  |  |  |  |  |  |  | Neem Cake | 40kg | 800.00 |  | 4000.00 |  |  |
|  |  |  |  |  |  |  |  | 19:19:19 | 2kg | 250.00 |  | 1250.00 |  |  |
|  |  |  |  |  |  |  |  | Azospirillum | 2kg | 160.00 |  | 800.00 |  |  |
|  |  |  |  |  |  |  |  | VAM | 2kg | 160.00 |  | 800.00 |  |  |
|  |  |  |  |  |  |  |  | CAN | 2kg | 120.00 |  | 600.00 |  |  |
|  |  |  |  |  |  |  |  | Soil test |  | 100.00 |  | 500.00 |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Total | 10,950.00 |  |  |
|  |  | Black pepper | Less berry filling, non-uniform ripening & berry shedding | Management of berry drop in Black Pepper | - | - | IISR | KNO3 | 5 kg | 300.00 | 10 | 3000.00 | 1) Yield 2) BCR | Ms. Manju Jincy Varghese (SMS-Soil Science), Mr. Sudhakar Soundarajan (SMS-Plant Protection), Dr. Binu John Sam (SMS-Horticulture) & Mr. Biju Narayanan (Computer programmer) |
|  |  |  |  |  |  |  |  | NAA | 50g | 500.00 |  | 5000.00 |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Total | 8,000.00 |  |  |
| 9.6 | Horticultural crops | Bitter gourd | Indiscriminate use of pesticides leads to pesticide residual effect | Integrated Pest and Disease Management (IPDM) in Bitter gourd | Variety | Preethi | IIHR | Trichoderma | 750g | 75.00 | 5 | 375.00 | 1) Yield 2) BCR | Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
|  |  |  |  |  |  |  |  | Neem cake | 40kg | 800.00 |  | 4000.00 |  |  |
|  |  |  |  |  |  |  |  | IIHR-Neem soap | 1kg | 140.00 |  | 700.00 |  |  |
|  |  |  |  |  |  |  |  | Cuelure trap | 4 nos. | 600.00 |  | 3000.00 |  |  |
|  |  |  |  |  |  |  |  | Indoxacarb | 100 ml | 370.00 |  | 1850.00 |  |  |
|  |  |  |  |  |  |  |  | Imidachloprid | 100 ml | 200.00 |  | 1000.00 |  |  |
|  |  |  |  |  |  |  |  | Mancozeb | 200g | 150.00 |  | 750.00 |  |  |
|  |  |  |  |  |  |  |  | Zineb | 200g | 170.00 |  | 850.00 |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Total | 12,525.00 |  |  |
|  |  | Vegetables (Cowpea & bitter gourd) | Micronutrient deficiency due to the soil acidity | Demonstration of IIHR Vegetable special in cowpea & bitter gourd | Variety | Vellayani Jothika & Preethi | IIHR | IIHR Vegetable special | 10kg | 200 | 10 | 2000.00 | 1) Yield 2) BCR | Dr. Benjamin Mathew (Programme Coordinator i/c.) |
|  |  |  |  |  |  |  |  | Soil test |  |  |  | 500.00 |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Total | 2,500.00 |  |  |
|  |  | Vegetables (Home stead) | Non availability of year round quality vegetables | Ensuring nutritional security through family farming | - | - | KAU | Seeds | 30 pkts. | 300.00 | 5 | 1500.00 | 1) Availability of year round organic vegetable production | Dr. Binu John Sam (SMS-Horticulture) |
|  |  |  |  |  |  |  |  | Bio-agents | LS | 300.00 |  | 1500.00 |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Total | 3,000.00 |  |  |
|  |  | Banana | Lodging of banana plants nearing maturity | Management of lodging / breaking of banana pseudostem nearing maturity | Cultivar | Nendran | Result of OFT conducted by KVK, Idukki | Bamboo/ casuarina / eucalyptus props | 50 | 6000.00 | 5 | 30000.00 | 1) Extent of wind damage 2) BCR | Dr. Binu John Sam (SMS-Horticulture) |
|  |  |  |  |  |  |  |  | Tying material | 20 | 600.00 |  | 3000.00 |  |  |
|  |  |  |  |  |  |  |  | ¾ inch nylon / polythene tapes | 20 | 5000.00 |  | 25000.00 |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Total | 58,000.00 |  |  |
|  |  | Banana | Poor soil fertility, high acidity leading to micro nutritional disorders | INM in banana cv. Nendran for high ranges | Cultivar | Nendran | KAU | Lime | 20kg | 500.00 | 10 | 5000.00 | 1) Yield 2) BCR | Ms. Manju Jincy Varghese (SMS-Soil Science), Mr. Sudhakar Soundarajan (SMS-Plant Protection), Dr. Binu John Sam (SMS-Horticulture) & Mr. Biju Narayanan (Computer programmer) |
|  |  |  |  |  |  |  |  | Bio- fertilizers | 2kg | 300.00 |  | 3000.00 |  |  |
|  |  |  |  |  |  |  |  | ZnSO4 | 2kg | 200.00 |  | 2000.00 |  |  |
|  |  |  |  |  |  |  |  | Borax | 1kg | 300.00 |  | 3000.00 |  |  |
|  |  |  |  |  |  |  |  | Soil testing | - | 100.00 |  | 1000.00 |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Total | 14,000.00 |  |  |
|  |  | Tapioca & Banana | Crop loss due to rodents & wild boars | Castor based herbal extract for the management of rodents & wild boars | - | - | NIPHM, Hyderabad & OFT- KVK, Idukki | Castor based herbal extract | 2 litres | 1080.00 | 10 | 10800.00 | Reduction of rodents and wild boars attack | Ms. Manju Jincy Varghese (SMS-Soil Science), Mr. Sudhakar Soundarajan (SMS-Plant Protection), Dr. Binu John Sam (SMS-Horticulture) & Mr. Biju Narayanan (Computer programmer) |
|  |  |  |  |  |  |  |  | Jute rope | LS | 200.00 |  | 2000.00 |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Total | 12,800.00 |  |  |
|  |  | Mushroom | Improper disposal of SMC | Utilization of Spent Mushroom Compost (SMC) as a medium for vegetable production | Mushroom | - | TNAU, Coimbatore | Seeds | 30 pkts. | 300.00 | 5 | 1500.00 | 1) Visual stand of the crop 2) Yield | Dr. Binu John Sam (SMS-Horticulture) |
|  |  |  |  |  |  |  |  | Bio-agents | LS | 300.00 |  | 1500.00 |  |  |
|  |  |  |  |  |  |  |  | Grow bags | 30 | 750.00 |  | 3750.00 |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Total | 6,750.00 |  |  |
|  |  | Mushroom | Mushrooms are highly perishable | Packaging of mushrooms in tray packs with cling film cover | Oyster mushroom | - | OFT conducted by KVK, Idukki | Tray packs | 200 nos. | 600.0 | 5 | 3000.00 | BCR | Ms. Jayisy Joseph (Programme Assistant-Home Science) |
|  |  |  |  |  |  |  |  | Cling film roll | 70 meter | 400.00 |  | 2000.00 |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Total | 5,000.00 |  |  |
| 9.7 | Livestock | Dairy cattle | Unaware of mixed fodder system & low milk production | Popularization of mixed fodder system & demonstration of electric chaff cutter | Cross breeds | Jersey & HF crosses | KAU | Seeds of COFS-29 | 250g | 100.00 | 10 | 1000.00 | 1) % of wastage in feed. 2) Palatability of feeds. 3) Quality & quantity of milk production | Dr. S. Jayababu, (SMS-Animal Husbandry) |
|  |  |  |  |  |  |  |  | Seeds of Desmanthus | 250g | 125.00 |  | 1250.00 |  |  |
|  |  |  |  |  |  |  |  | Seeds of Agathi | 275g | 125.00 |  | 1250.00 |  |  |
|  |  |  |  |  |  |  |  | Seeds of Subabul | 600g | 75.00 |  | 750.00 |  |  |
|  |  |  |  |  |  |  |  | CO3 slips | 2486 slips | 621.50 |  | 6215.00 |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Total | 10,465.00 |  |  |
|  | Livestock | Dairy cattle | High incidence of mastitis | Prophylactic management of mastitis in dairy cows using antiseptic solution in teat cups | Crossbred cattle | Crossbred cattle | KAU | Teat cups, dye, test tubes, cotton etc. | 2 | 400.00 | 10 | 4000.00 | 1) Quantity and quality milk production. 2) Incidence of mastitis | Dr. S. Jayababu, (SMS-Animal Husbandry) |
|  |  |  |  |  |  |  |  | Dipol / antiseptic solution | 1 | 200.00 |  | 2000.00 |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Total | 6,000.00 |  |  |
|  | Livestock | Poultry | Low egg & meat production | Demonstration of Broad Breasted Large White turkey for meat purpose in backyard system | Broad Breasted Large White turkey | Broad Breasted Large White turkey | Regional poultry farm, Kureepuzha, Kollam | 1. Two to three month old poults | 5 bird / demo | 1750.00 | 5 (5 bird / farmer) | 8750.00 | 1) Body weight 2) Mortality rate 3) BCR | Dr. S. Jayababu, (SMS-Animal Husbandry) |
|  |  |  |  |  |  |  |  | 2. Deworming & vitamin supplement | LS | 250.00 |  | 1250.00 |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Total | 10,000.00 |  |  |
|  | Livestock | Dairy cattle | Poor digestibility due to acid indigestion & low milk yield | Assessment of Gruel Rooted Additive Nourishment Drops (GRAND) supplement in crossbred cows | Crossbred cattle | Crossbred cattle | TANUVAS | GRAND supplement (20 ml sachet) | 600 nos. | 1.00 | 10 | 6000.00 | 1) Growth rate 2) Milk production | Dr. S. Jayababu, (SMS-Animal Husbandry) |
|  |  |  |  |  |  |  |  | Miscellaneous (Cost for transporting, packing material, lab test) | LS | 400.00 |  | 4000.00 |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Total | 10,000.00 |  |  |
| 9.8 | Others | Mushroom | Specialized EDP mode training on production and value addition |  |  |  |  | Media for bed preparation |  |  | - | 5000.00 | - | Dr. Binu John Sam (SMS-Horticulture) & Ms. Jayisy Joseph (Programme Assistant-Home Science) |
|  |  |  |  |  |  |  |  | Additives (Urea, green gram powder, ground nut cake) |  |  |  | 2500.00 |  |  |
|  |  |  |  |  |  |  |  | Bed covers & accessories |  |  |  | 5000.00 |  |  |
|  |  |  |  |  |  |  |  | Chemicals for sterilization |  |  |  | 2500.00 |  |  |
|  |  |  |  |  |  |  |  | Mushroom shed modification |  |  |  | 5000.00 |  |  |
|  |  |  |  |  |  |  |  | Raw-materials |  |  |  | 10000.00 |  |  |
|  |  |  |  |  |  |  |  | First class preservatives |  |  |  | 1000.00 |  |  |
|  |  |  |  |  |  |  |  | Ingredients, spices |  |  |  | 6000.00 |  |  |
|  |  |  |  |  |  |  |  | Packaging materials |  |  |  | 5000.00 |  |  |
|  |  |  |  |  |  |  |  | Printing & stationary |  |  |  | 3000.00 |  |  |
|  |  |  |  |  |  |  |  | Miscellaneous |  |  |  | 3000.00 |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Total | 48,000.00 |  |  |

10. Training for Farmers/ Farm Women during 2014-15

| S. No. | Thematic area | Crop / Enterprise | Major problem | Linked field intervention (Assessment/Refinement/ FLD)* | Training Course Title** | No. of Courses | Expected No. of participants | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 10.1 | Crop Production |  |  |  |  |  |  |  |
| 10.2 | Horticulture Production | Vegetables | Non availability of quality vegetables | FLD | Organic Kitchen Gardening in Homesteads | 2 | 40 | Dr. Binu John Sam (SMS-Horticulture) & Dr. Benjamin Mathew (Programme Coordinator i/c.) |
|  |  | Banana | Unscientific crop management | - | Integrated Crop Management in banana | 2 | 50 | Dr. Benjamin Mathew (Programme Coordinator i/c.) & Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
|  |  | Cowpea & bitter gourd | Unscientific nutrient management leads to micro-nutrient deficiency | FLD | Demonstration of IIHR vegetable special in cowpea & bitter gourd | 2 | 40 | Dr. Benjamin Mathew (Programme Coordinator i/c.) & Ms. Manju Jincy Varghese (SMS-Soil Science) |
| 10.3 | Livestock Production | Dairy cattle | Unaware of mixed fodder system & low milk production | FLD | Fodder management & hygienic milk production | 3 | 90 | Dr. S. Jayababu, SMS (Animal Husbandry) |
|  |  | Poultry – Turkey | Low egg & meat production | FLD | Demonstration of new poultry breeds in backyard | 5 | 125 | Dr. S. Jayababu, SMS (Animal Husbandry) |
|  |  | Poultry | Low body weight and growth performance | FLD | Poultry management techniques | 3 | 120 | Dr. S. Jayababu, SMS (Animal Husbandry) |
| 10.4 | Home Science | Fruit & Vegetables | Wastage of fruits | - | Diversified products from fruits & vegetables | 3 | 20 | Ms. Jayisy Joseph, Programme Assistant (Home Science) |
|  |  | Mushroom | Mushrooms are perishable | OFT | Value added mushroom products | 2 | 30 |  |
| 10.5 | Plant Protection | Cardamom | Heavy infestation of root grub | FLD | Root grub management | 5 | 150 | Mr. Sudhakar Soundarajan SMS-Plant Protection |
|  |  | Cardamom | Incidence of cardamom clump rot | Training | Integrated disease management | 5 | 100 | Mr. Sudhakar Soundarajan SMS-Plant Protection |
|  |  | Black Pepper | Incidence of quick wilt | OFT | Suitable Black Pepper Foot rot resistance variety for Idukki district. | 5 | 100 | Mr. Sudhakar Soundarajan SMS-Plant Protection |
|  |  | Black Pepper | Lack of knowledge in identification of pest and disease | Training | IPDM on Black Pepper | 5 | 70 | Mr. Sudhakar Soundarajan SMS-Plant Protection |
|  |  | Banana | Indiscriminate use of PP chemicals | Training | Organic pest management of Banana | 5 | 100 | Mr. Sudhakar Soundarajan SMS-Plant Protection |
|  |  | Rice | Unscientific Pest and Disease Management | Training | Integrated Pest Management package for Organic Rice Ecosystem | 5 | 80 | Mr. Sudhakar Soundarajan SMS-Plant Protection |
|  |  | Bitter gourd | Lack of knowledge in organic pest and disease | FLD | Integrated Pest and Disease Management in bitter gourd | 5 | 170 | Mr. Sudhakar Soundarajan SMS-Plant Protection |
| 10.6 | Production of Inputs at Site |  |  |  |  |  |  |  |
| 10.7 | Soil Health and Fertility | Cardamom | Indiscriminate use of chemical fertilizers leading to decline in soil fertility | FLD | Soil health management in cardamom | 5 | 125 | Ms. Manju Jincy Varghese (SMS-Soil Science) |
|  |  | Tapioca | Soil acidity leading to Mg and Zn deficiency/ attack of rodents and wild boars | OFT, FLD | Secondary and micronutrient deficiency correction and control of rodents and wild boars in Tapioca | 3 | 90 | Ms. Manju Jincy Varghese (SMS-Soil Science |
|  |  | Banana | Poor soil fertility, high acidity leading to micronutrient deficiency in banana | FLD | INM in Banana | 3 | 105 | Ms. Manju Jincy Varghese (SMS-Soil Science) |
|  |  | Pepper | Less berry filling, non-uniform ripening and berry shedding | FLD | Management of berry drop in black pepper | 2 | 60 | Ms. Manju Jincy Varghese (SMS-Soil Science) |
| 10.8 | PHT and value addition | Home Science | Limited processing units | - | Value added products for income generation | 3 | 60 | Ms. Jayisy Joseph, Programme Assistant (Home Science) |
| 10.9 | Capacity Building Group Dynamics |  |  |  |  |  |  |  |
| 10.10 | Farm Mechanization |  |  |  |  |  |  |  |
| 10.11 | Fisheries Production Technologies |  |  |  |  |  |  |  |
| 10.12 | Mushroom production | Mushrooms | Unscientific and non-commercial cultivation of mushrooms | OFT & Trainings | Scientific Mushroom cultivation | 3 | 50 | Dr. Binu John Sam (SMS-Horticulture) & Dr. Benjamin Mathew (Programme Coordinator i/c) |
| 10.13 | Agro forestry |  |  |  |  |  |  |  |
| 10.14 | Bee Keeping |  |  |  |  |  |  |  |
| 10.15 | Sericulture |  |  |  |  |  |  |  |
|  | Others, pl. specify |  |  |  |  |  |  |  |

* Title of intervention/title of technology, ** Training title should specify the major technology/skill to be transferred.

11. Training for Rural Youth during 2014-15

| S. No. | Thematic area | Crop / Enterprise | Major problem | Linked field intervention (Assessment/Refinement/FLD)* | Training Course Title** | No. of Courses | Expected No. of participants | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 11.1 | Crop Production |  |  |  |  |  |  |  |
| 11.2 | Horticulture Production | Vegetables | Non availability of quality vegetables | Ensuring nutritional security through family farming | Organic Kitchen Gardening in Homesteads | 2 | 40 | Dr. Binu John Sam (SMS-Horticulture) & Dr. Benjamin Mathew (Programme Coordinator i/c.) |
|  |  | Hi-tech vegetable production | Lack of awareness | - | Hi-tech vegetable production | 2 | 50 | Dr. Benjamin Mathew (Programme Coordinator i/c.) & Dr. Binu John Sam (SMS-Horticulture) |
| 11.3 | Livestock Production |  |  |  |  |  |  |  |
|  |  | Dairy cattle | Low body weight, growth performance & milk production | Popularization of mixed fodder system | Livestock production and management | 4 | 120 | Dr. S. Jayababu, SMS (Animal Husbandry) |
| 11.4 | Home Science | Banana | Pseudostem is wasted | - | Value added banana products | 1 | 25 | Ms. Jayisy Joseph, Programme Assistant (Home Science) |
|  |  | Crochet work | - | - | Crochet making course | 1 | 30 | Ms. Jayisy Joseph, Programme Assistant (Home Science) |
| 11.5 | Plant Protection | Cardamom | Heavy infestation of root grub | Popularization of EPN to reduce the root grub in cardamom | Cardamom Root Grub Management | 5 | 100 | Mr. Sudhakar Soundarajan SMS-Plant Protection |
| 11.6 | Production of Inputs at Site |  |  |  |  |  |  |  |
| 11.7 | Soil Health and Fertility | Cardamom | Indiscriminate use of chemical fertilizers leading to decline in soil fertility | Site specific nutrient management in cardamom | Soil health management in cardamom | 5 | 125 | Ms. Manju Jincy Varghese (SMS-Soil Science) |
|  |  | Tapioca | Soil acidity leading to Mg and Zn deficiency/ attack of rodents and wild boars | Management practices for secondary and micronutrient disorders for Tapioca in acid soils & castor based herbal extract for the management of rodents & wild boars | Secondary and micronutrient deficiency correction and control of rodents and wild boars in Tapioca | 3 | 120 | Ms. Manju Jincy Varghese (SMS-Soil Science |
| 11.8 | PHT and value addition | Jack fruit | Wastage of fruit | - | Value added jack products | 2 | 30 | Ms. Jayisy Joseph, Programme Assistant (Home Science) |
| 11.9 | Capacity Building Group Dynamics | Mushroom | Lack of value addition | - | Value addition in mushroom | 2 | 20 | Ms. Jayisy Joseph, Programme Assistant (Home Science) |
| 11.10 | Farm Mechanization |  |  |  |  |  |  |  |
| 11.11 | Fisheries Production Technologies |  |  |  |  |  |  |  |
| 11.12 | Agro forestry |  |  |  |  |  |  |  |
| 11.13 | Bee Keeping |  |  |  |  |  |  |  |
| 11.14 | Sericulture |  |  |  |  |  |  |  |
|  | Others, pl. specify |  |  |  |  |  |  |  |

* Title of intervention/title of technology, ** Training title should specify the major technology/skill to be transferred.

### 12. Trainings for Extension Personnel during 2014-15

| S. No. | Thematic area | Training Course Title** | No. of Courses | Expected No. of participants | Names of the team members involved |
| --- | --- | --- | --- | --- | --- |
| 12.1 | Crop Production |  |  |  |  |
| 12.2 | Home Science | Value added banana products | 1 | 20 | Ms. Jayisy Joseph, Programme Assistant (Home Science) |
| 12.3 | Capacity Building and Group Dynamics | Training on fruit & vegetable preservation | 1 | 25 | Ms. Jayisy Joseph, Programme Assistant (Home Science) |
| 12.4 | Horticulture | Scientific Mushroom Cultivation and Post Harvest Handling | 1 | 20 | Dr. Binu John Sam (SMS-Horticulture) & Ms. Jayisy Joseph (Technical Assistant – Home Science) |
|  |  | INM in Banana | 3 | 30 | Ms. Manju Jincy Varghese (SMS-Soil Science) |
|  |  | ICM in vegetables | 1 | 25 | Dr. Benjamin Mathew (Programme Coordinator i/c) |
| 12.5 | Livestock Production & Management |  |  |  |  |
|  | Feed and fodder technology | 1) Importance of mineral supplementation in cattle field. 2) Importance of mixed fodder system in dairy cattle ration. | 2 | 40 | Dr. S. Jayababu, SMS (Animal Husbandry) |
|  | Animal disease management | 1) Infectious and contagious diseases of dairy cattle and their management. 2) Zoonotic diseases and their management. | 1 | 30 | Dr. S. Jayababu, SMS (Animal Husbandry) |
| 12.6 | Plant Protection | Alternatives for banned chemicals in cardamom | 3 | 60 | Mr. Sudhakar Soundarajan SMS-Plant Protection |
| 12.7 | Farm Mechanization |  |  |  |  |
| 12.8 | PHT and value addition | Product diversification in fruits & vegetables | 1 | 20 | Ms. Jayisy Joseph, Programme Assistant (Home Science) |
| 12.9 | Production of Inputs at Site |  |  |  |  |
| 12.10 | Sericulture |  |  |  |  |
| 12.11 | Fisheries |  |  |  |  |

* Title of intervention/title of technology, ** Training title should specify the major technology/skill to be transferred.

## 13. Vocational trainings during 2014-15

| Sl. No. | Thematic area and the Crop/Enterprise | Training title* | No. of programmes and Duration (days) | Type of Clientele (SHGs, NYKs, School students, Women, Youth etc.) | Expected No. of participants | Sponsoring agency if any | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 13.1 | Crop Production | Importance of soil testing | 1 (3 days) | SHGS, Rural youth and school students | 20 | - | Ms. Manju Jincy Varghese (SMS-Soil Science) |
|  |  | Organic farming | 2 (3 days) | SHGS, Rural youth and school students | 40 | - | Ms. Manju Jincy Varghese (SMS-Soil Science) |
|  |  | Integrated nutrient management | 2 (3 days) | SHGS, Rural youth and school students | 40 | - | Ms. Manju Jincy Varghese (SMS-Soil Science) |
| 13.2 | Home Science | Fruit & vegetable processing | 1 (6 days) | SHGS, Youth & Women | 15 | - | Ms. Jayisy Joseph, Programme Assistant (Home Science) & Dr. Binu John Sam (SMS-Horticulture) |
| 13.3 | Capacity Building and Group Dynamics | Product diversification in fruits & vegetables | 1 (6 days) | SHGS, Youth & Women | 16 | - | Ms. Jayisy Joseph, Programme Assistant (Home Science) & Dr. Binu John Sam (SMS-Horticulture) |
| 13.4 | Horticulture | Scientific Mushroom Cultivation and Processing | 1 (3 days) | Farm Women, Rural Youth | 40 | Dept. of Agriculture / ATMA | Dr. Binu John Sam (SMS-Horticulture), Dr. Benjamin Mathew (Programme Coordinator i/c) & Ms. Jayisy Joseph (Technical Assistant – Home Science) |
|  |  | Organic production of cool season vegetable production | 1(3 days) | Rural Youth & Farm Women | 25 | SHM | Dr. Benjamin Mathew(Programme Coordinator i/c) Mr. Sudhakar Soundarajan SMS-Plant Protection |
| 13.5 | Livestock Production & Management | Development and improvement of technology for value addition | 2 (3 days) | SHGS, Rural youth and school students | 50 | - | Dr. S. Jayababu, SMS (Animal Husbandry) |
|  | Scientific goat management | Scientific goat production and management | 3 (3 days) | SHGS, Rural youth and school students | 60 | - | Dr. S. Jayababu, SMS (Animal Husbandry) |
|  | Poultry production | Scientific poultry management | 2 (3 days) | SHGS, Rural youth and school students | 70 | - | Dr. S. Jayababu, SMS (Animal Husbandry) |
| 13.6 | Plant Protection | Popularization of EPN against cardamom root grub | 2 (3 days) | SHGs & School students | 40 | - | Mr. Sudhakar Soundarajan SMS-Plant Protection |
| 13.7 | Farm Mechanization |  |  |  |  |  |  |
| 13.8 | PHT and value addition | EDP on processing of fruit & vegetables | 1 (6 days) | SHGs, Youth & Women | 12 | Lead bank | Ms. Jayisy Joseph, Programme Assistant (Home Science) & Dr. Binu John Sam (SMS-Horticulture) |
| 13.9 | Production of Inputs at Site |  |  |  |  |  |  |
| 13.10 | Sericulture |  |  |  |  |  |  |
| 13.11 | Fisheries |  |  |  |  |  |  |

* Training title should specify the major technology/skill to be transferred.

## 14. Sponsored trainings during 2014-15

| S. No. | Thematic area and the Crop/Enterprise | Training title* | No. of programmes and Duration (days) | Type of Clientele (SHGs, NYKs, School students, Women, Youth etc.) | Expected No. of participants | Sponsoring agency | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 14.1 | Crop Production | Soil health management | 3 (1day) | SHGS, Rural youth | 125 | Lead bank, VFPCK, Department of Agriculture | Ms. Manju Jincy Varghese (SMS-Soil Science) |
|  |  | Awareness of soil testing and soil campaign | 4 (1 day) | SHGS, Rural youth | 90 | Department of Agriculture | Ms. Manju Jincy Varghese (SMS-Soil Science) |
|  |  | Organic farming | 2 (1 day) | SHGS, Rural youth | 60 | HOPS, Department of Agriculture | Ms. Manju Jincy Varghese (SMS-Soil Science) |
| 14.2 | Home Science | Value addition in fruits & vegetables | 3 (1 day) | SHGs, Women | 25 | Coffee Board | Ms. Jayisy Joseph, Programme Assistant (Home Science) |
| 14.3 | Capacity Building and Group Dynamics | Preservation of fruits & vegetables | 3 (1 day) | SHGs, Women | 30 | ATMA | Ms. Jayisy Joseph, Programme Assistant (Home Science) |
|  |  | Group Formation and Dynamics | 1 (1 day) | SHGs | 30 | DIC | Dr. Binu John Sam (SMS-Horticulture) & Ms. Jayisy Joseph (Technical Assistant – Home Science) |
|  |  | Entrepreneurship Development Programme | 2 (1 day) | SHGs, NYKs | 40 | DIC | Dr. Binu John Sam (SMS-Horticulture) & Ms. Jayisy Joseph (Technical Assistant – Home Science) |
| 14.4 | Horticulture | Scientific Mushroom Cultivation | 2 (1 day) | Farm Women, Rural Youth | 40 | Dept. of Agriculture / ATMA | Dr. Binu John Sam (SMS-Horticulture), Dr. Benjamin Mathew (Programme Coordinator i/c.) & Ms. Jayisy Joseph (Technical Assistant – Home Science) |
|  |  | Hi tech vegetable production | 2 (1day) | Rural Youth &Farm Women | 50 | Dept. of Agriculture / ATMA | Dr. Benjamin Mathew (Programme Coordinator i/c.) & Dr. Binu John Sam (SMS-Horticulture) |
|  |  | ICM in vegetables | 2 (1day) | SHGs, Rural Youth & Farm Women |  | Dept. of Agriculture / ATMA & VFPCK | Dr. Benjamin Mathew (Programme Coordinator i/c.) & Dr. Binu John Sam (SMS-Horticulture) |
| 14.5 | Livestock Production & Management |  |  |  |  |  |  |
|  | Livestock production and management | 1) EDP and value addition of milk 2) Preparation of milk based products 3) Scientific dairy cattle management | 2 (1day) 2 (1 day) 3 (1 day) | SHGS, Rural youth and school students | 175 | Lead bank | Dr. S. Jayababu, SMS (Animal Husbandry) |
|  | Goat production | Scientific goat management | 3 (1 day) | SHGs, Rural youth | 90 | Grama Panchayat | Dr. S. Jayababu, SMS (Animal Husbandry) |
|  | Rabbit management | Rabbit rearing techniques | 2 (1 day) | SHGS, Rural youth | 60 | HDS | Dr. S. Jayababu, SMS (Animal Husbandry) |
|  | Poultry production | Poultry farming, broiler and layer management | 4 (1 day) | SHGS, Rural youth | 120 | HDS | Dr. S. Jayababu, SMS (Animal Husbandry) |
| 14.6 | Plant Protection | Integrated disease management in Cardamom | 5 (1 day) | SHGs, NYKs, Women, Youth | 150 | ATMA | Mr. Sudhakar Soundarajan SMS-Plant Protection |
|  |  | Integrated Pest and Disease management in Black pepper | 3 (1 day) | SHGs, NYKs, Women, Youth | 90 | ATMA | Mr. Sudhakar Soundarajan SMS-Plant Protection |
|  |  | Integrated Crop Management in Black Pepper | 5 (1 day) | SHGs, NYKs, Women, Youth | 150 | ATMA and Spices Board | Mr. Sudhakar Soundarajan SMS-Plant Protection |
|  |  | IPDM in Cowpea | 3 (1 day) | SHGs, NYKs, Women, Youth | 90 | VFPCK | Mr. Sudhakar Soundarajan SMS-Plant Protection |
|  |  | IPDM in Banana | 5 (1 day) | SHGs, NYKs, Women, Youth | 150 | VFPCK and ATMA | Mr. Sudhakar Soundarajan SMS-Plant Protection |
| 14.7 | Farm Mechanization |  |  |  |  |  |  |
| 14.8 | PHT and value addition | Value added products in mushroom | 1 (1 day) | SHGs, Youth & Women | 20 | - | Ms. Jayisy Joseph, Programme Assistant (Home Science) |
| 14.9 | Production of Inputs at Site |  |  |  |  |  |  |
| 14.10 | Sericulture |  |  |  |  |  |  |
| 14.11 | Fisheries |  |  |  |  |  |  |

* Programme title should specify the major technologies/skills to be transferred /refreshed.

## 15. Extension programmes during 2014-15

| S. No. | Extension programme* | No. of programmes or activities | Expected No. of participants | Names of the team members involved |
| --- | --- | --- | --- | --- |
| 15.1 | Advisory Services | 175 | 175 | All tech staff |
| 15.2 | Diagnostic visits | 85 | 170 | All tech staff |
| 15.3 | Field Day | 10 | 250 | All tech staff |
| 15.4 | Group discussions | 5 | 100 | All tech staff |
| 15.5 | Kisan Ghosthi |  |  |  |
| 15.6 | Film Show | 1 | 300 | All tech staff |
| 15.7 | Self -help groups | 2 | 24 | All tech staff |
| 15.8 | Kisan Mela | 1 |  |  |
| 15.9 | Exhibition | 3 | 5000 | All staff |
| 15.10 | Scientists' visit to farmers field | 150 | 450 | All tech staff |
| 15.11 | Plant/Soil health/Animal health camps | 2 | 300 | Ms. Manju Jincy Varghese (SMS-Soil Science), Dr. S. Jayababu (SMS-Animal Husbandry) |
| 15.12 | Farm Science Club |  |  |  |
| 15.13 | Ex-trainees Sammelan | 1 | 50 | All tech staff |
| 15.14 | Farmers' seminar/workshop (Workshop on specialty fertilizers) | 1 | 150 | Ms. Manju Jincy Varghese (SMS-Soil Science) |
| 15.15 | Method Demonstrations (Soil health enhancement programme) | 2 | 40 | Ms. Manju Jincy Varghese (SMS-Soil Science) |
| 15.16 | Celebration of important days |  |  |  |
| 15.17 | Special day celebration (World Food Day) | 1 | 100 | Ms. Jayisy Joseph, Programme Assistant (Home Science) |
| 15.18 | Exposure visits | 1 | 25 | Dr. Benjamin Mathew (Programme Coordinator i/c.) |
| 15.19 | Technology week, | 1 | 750 | All tech staff |
| 15.20 | FFS | 1 | 5 | All tech staff |
| 15.21 | Farm innovators meet |  |  |  |
| 15.22 | Awareness programs | 1 | 150 | All tech staff |
|  | Others, pl. specify |  |  |  |

## 16. Activities proposed as Knowledge and Resource Centre during 2014-15

16.1 Technological knowledge

| S. No. | Category | Details of technologies | Area (ha)/ Number | Names of the team members involved |
| --- | --- | --- | --- | --- |
| 16.1.1 | Technology Park/ Crop cafeteria | Vegetable Seed Production Unit | 0.1 ha | Dr. Binu John Sam, SMS (Horticulture), Mr. Sudhakar Soundarajan, SMS (Plant Protection) |
|  |  | Cardamom Nursery | 0.2 ha | Mr. Sudhakar Soundarajan, SMS (Plant Protection) & Dr. Binu John Sam, SMS (Horticulture), Dr. Benjamin Mathew (Programme Coordinator i/c) & Mr. Biju Narayanan (Computer Programmer) |
|  |  | Medicinal plant | 0.04 ha | Dr. Benjamin Mathew (Programme Coordinator i/c), Dr. Binu John Sam (SMS-Horticulture), Ms. Manju Jincy Varghese (SMS – Soil Science) & Ms. Rachel Skaria (Farm Manager) |
|  |  | Anthurium | 0.02 ha |  |
|  |  | Rose | 0.012 ha |  |
|  |  | Seed production in annual ornamental plants | 0.01 ha |  |
|  |  | Fodder crops | 0.2 ha |  |
| 16.1.2 | Demonstration Units | Cardamom varietal plot | 0.4 ha | All Staff |
|  |  | Pepper mother nursery | 0.012 |  |
|  |  | Pepper poly bag nursery | 0.012 |  |
|  |  | Farm machineries | - |  |
|  |  | Vermicomposting unit | 1 no. |  |
|  |  | Azolla multiplication unit | 1 no. |  |
|  |  | Mushroom Production Unit | 1 no. |  |
|  |  | Terrace garden | 0.012 ha |  |
|  |  | HDP in banana | 0.20 ha |  |
|  |  | Beekeeping | 1 ha |  |
|  |  | Poultry | 1 unit |  |
|  |  | Kitchen garden | 0.01 ha |  |
|  |  | Bio-control lab | 1 unit |  |
|  |  | Cardamom | 0.40 ha |  |
|  |  | Pepper | 0.2 ha |  |
|  |  | Processing unit | 1 unit |  |
|  |  | Duck cum fish culture unit | 1 unit |  |
|  |  | Rabbit unit | 1 unit |  |
|  |  | Azolla unit | 1 unit |  |
|  |  | EPN | 1 unit |  |
|  |  | Mushroom spawn production unit | 1 unit |  |
|  |  | Poultry hatchery unit | 1 no. |  |
|  |  | Duck unit | 1 no. |  |
| 16.1.3 | Lab Analytical services | Soil | 1 unit | Ms. Manju Jincy Varghese, SMS (Soil Science) |
|  |  | Water | 1 unit |  |
|  |  | Manure | 1 unit |  |
| 16.1.4 | Technology Week | Livestock production & management | - | All Staff |
|  |  | Mushroom production & value addition | - |  |
|  |  | Organic farming technologies | - |  |
|  |  | Hi-tech agriculture | - |  |
|  |  | IPDM in Cardamom & Pepper | - |  |

16.2 Technological Products

| S. No. | Category | Name of the Production Partner Agency, if any | Name of the product | Quantity (Qtl.)/ Number planned to be produced during 2014-15 | Names of the team members involved |
| --- | --- | --- | --- | --- | --- |
| 16.2.1 | Seeds | - | Vegetable Seeds | 0.5q | Mr. Sudhakar Soundarajan, SMS (Plant Protection), Dr. Benjamin Mathew (Programme Coordinator i/c.), Dr. Binu John Sam (SMS-Horticulture) & Ms. Rachel Skaria (Farm Manager) |
|  |  |  | Ornamental Flower seeds | 0.1q |  |
| 16.2.2 | Planting materials | - | Rooted Pepper cuttings | 25000 nos. | Dr. Benjamin Mathew (Programme Coordinator i/c.) & Ms. Rachel Skaria (Farm Manager) |
|  |  | - | Cardamom tillers | 1000 nos. |  |
|  |  | - | Vegetable seedlings | 3000 nos. |  |
|  |  | - | Ornamental seedlings | 7000 nos. |  |
|  |  | - | Medicinal plants | 250 nos. |  |
|  |  | - | Forest species | 2000 nos. |  |
| 16.2.3 | Bio-products | - | Trichoderma | 2500 litres | Mr. Sudhakar Soundarajan, SMS (Plant Protection) |
|  |  | - | Pseudomonas | 5000 litres |  |
|  |  | - | EPN | 15000 cadavers |  |
|  |  | - | Mushroom spawn | 10000 packets | Mr. Sudhakar Soundarajan (SMS-Plant Protection), Dr. Benjamin Mathew (Programme Coordinator i/c), Dr. Binu John Sam (SMS-Horticulture) |
|  |  | - | Edible mushroom | 200 kg |  |
|  |  | - | Vermicompost | 1500 kg |  |
|  |  | - | Azolla seed | 250 kg |  |
| 16.2.4 | Livestock strains | - | Rabbit kit and bunnies | 250 nos. | Dr. S. Jayababu, SMS (Animal Husbandry) |
|  |  | - | Ducks | 200 nos. |  |
|  |  | - | Poultry birds | 2500 nos. |  |
|  |  | - | Rabbit | 250 nos. |  |
| 16.2.5 | Fish fingerlings | - | - | - | - |

16.3 Technological Information

|  | Category | Technological capsules / Number | Names of the team members involved |
| --- | --- | --- | --- |
| 16.3.1 | Technology backstopping to line departments |  |  |
|  | Agriculture | 10 | All tech staff |
|  | Horticulture | 3 | Dr. Benjamin Mathew (Programme Coordinator i/c), Dr. Binu John Sam (SMS-Horticulture) |
|  | Animal Husbandry | 2 | Dr. S. Jayababu, SMS (Animal Husbandry) |
|  | Fisheries | - |  |
|  | Agricultural Engineering | - |  |
|  | Sericulture | - |  |
|  | Others, pl. specify | - |  |
| 16.3.2 | Literature/publication | 5 | All tech staff |
| 16.3.4 | Electronic Media | 2 | All tech staff |
| 16.3.5 | Kisan Mobile Advisory Services | 100 | All tech staff |
| 16.3.6 | Information on centre/state sector schemes and service providers in the district. | Data may be collected from different agencies. Also indicate time of completion. |  |

## 17. Additional Activities Planned during 2014-15

| S. No. | Name of the agency / scheme | Name of activity | Technical programme with quantification | Financial outlay (Rs.) | Names of the team members involved |
| --- | --- | --- | --- | --- | --- |
| 17.1 | State Planning Board | Development of pest surveillance based crop advisory for plant health management | To create awareness among the farmers about integrated crop management practices including IPDM | 6,00,000.00 | Mr. Sudhakar Soundarajan (SMS-Plant Protection) & All technical staffs |
| 17.2 | Fertilizer Association of India, Chennai | Soil health enhancement | - | 40,000.00 | Ms. Manju Jincy Varghese (SMS-Soil Science) |

18. Revolving Fund

18.1 Financial status

| Opening balance as on 01.04.2013 (Rs.in Lakh) | Expenditure incurred during 2013-14 (Rs.in Lakh) | Receipts during 2013-14 (Rs.in Lakh) | Closing balance as on 31.01.2014 (Rs.in Lakh) | Expected closing balance by 31.01.2014 (Including value of material in stock) |
| --- | --- | --- | --- | --- |
| 6,87,195.00 | 9,44,568.00 | 8,14,846.00 | 5,57,473.00 | 6,57,473.00 |

18.2 Plan of activities under Revolving Fund

| S. No. | Proposed activities | Expected output | Anticipated income (Rs.) | Names of the team members involved |
| --- | --- | --- | --- | --- |
| 18.2.1 | Rabbit unit (Cage unit) | Kits – 250 nos. & bunnies – 250 nos. | 75,000.00 | Dr. S. Jayababu, SMS (Animal Husbandry) |
| 18.2.2 | Poultry hatchery unit | Birds – 2500 nos. | 2,25,000.00 | Dr. S. Jayababu, SMS (Animal Husbandry) |
| 18.2.3 | Vegetable seeds | 0.5 qtl. | 30000.00 | Dr. Benjamin Mathew (Programme Coordinator i/c), Dr. Binu John Sam (SMS-Horticulture), Mr. Sudhakar Soundarajan (SMS-Plant Protection) & Ms. Rachel Skaria (Farm Manager) |
|  | Ornamental Flower seeds | 0.1 qtl. | 3750.00 |  |
|  | Vegetable seedlings | 3000 nos. | 12000.00 |  |
|  | Rooted Pepper cuttings | 25000 nos. | 175000.00 |  |
|  | Cardamom tillers | 1000 nos. | 30000.00 |  |
|  | Spices | 500 nos. | 5000.00 |  |
|  | Forest species | 2000 nos. | 4000.00 |  |
|  | Medicinal plants | 250 nos. | 2500.00 |  |
|  | Pseudomonas | 5000 L | 500000.00 |  |
|  | Trichoderma | 2500 L | 250000.00 |  |
|  | EPN | 15000 cadavers | 18000.00 |  |
|  | Mushroom Spawn | 10000 pkts. | 300000.00 |  |
|  | Edible mushroom | 200kg | 60000.00 |  |
|  | Vermicompost | 1500 kg | 12000.00 |  |
|  | Azolla | 250 kg | 2000.00 |  |
| 18.2.4 |  | Total | 14,79,250.00 |  |

## 19. Activities of soil, water and plant testing laboratory during 2014-15

| S. No. | Type | No. of samples to be analyzed | Names of the team members involved |
| --- | --- | --- | --- |
| 19.1 | Soil | 500 | Ms. Manju Jincy Varghese (SMS-Soil Science) |
| 19.2 | Water | - |  |
| 19.3 | Plant | - |  |
| 19.4 | Others | - |  |

## 20. E-linkage during 2014-15

| S. No | Nature of activities | Likely period of completion (please set the time frame) | Remarks if any |
| --- | --- | --- | --- |
| 20.1 | Title of the technology module to be prepared |  |  |
| 20.2 | Creation and maintenance of relevant database system for KVK | Farmers database creation & updation – year-around | - |
| 20.3 | Any other (Please specify) |  |  |
| 20.4 |  |  |  |

21. Activities planned under Rainwater Harvesting Scheme (only to those KVKs which are already having scheme under Rain Water Harvesting): Nil.

22. Innovative Farmer’s Meet

| S. No. | Particulars | Details |
| --- | --- | --- |
| 22.1 | Are you planning for conducing Farm Innovators meet in your district? | No |
| 22.2 | If Yes likely month of the meet |  |
| 22.3 | Brief action plan in this regard |  |

23. Farmer’s Field School planned

| S. No | Thematic area | Title of the FFS | Budget proposed in Rs. |
| --- | --- | --- | --- |
| 23.1 | Pest and Disease Management | Integrated Pest & Disease Management (IPDM) in cowpea | 25,000.00 |
| 23.2 |  |  |  |

24. Budget - Details of budget utilization (2013-14) up to 31 January 2014

(Rs. in lakhs)

| S. No. | Particulars | Sanctioned | Released | Expenditure |
| --- | --- | --- | --- | --- |
| 24.1 | Recurring Contingencies |  |  |  |
| 24.1.1 | Pay & Allowances | 75.00 |  | 62.09455 |
| 24.1.2 | Traveling allowances | 1.75 |  | 1.295 |
| 24.1.3 | Contingencies |  |  |  |
| 24.1.4.1 | Stationery, telephone, postage and other expenditure on office running, publication of Newsletter and library maintenance | 2.5 |  | 2.458 |
| B | POL, repair of vehicles, tractor and equipments | 1.6 |  | 1.46193 |
| C | Meals/refreshment for trainees | 0.70 |  | 0.68259 |
| D | Training material | 0.65 |  | 0.64855 |
| E | Frontline demonstration except oilseeds and pulses | 2.70 |  | 1.43 |
| F | On farm testing | 0.60 |  | 0.41 |
| G | Training of extension functionaries | 0.25 |  | 0.24351 |
| H | Maintenance of buildings | 0.50 |  | 0.50 |
| I | Establishment of Soil, Plant & Water Testing Laboratory | 0.00 |  | 0.00 |
| J | Library | 0.05 |  | 0.0372 |
| K | Extension activities | 0.50 |  | 0.50 |
| L | Farmers Field School (FFS) | 0.30 |  | 0.185 |
| 24.1 | Total Recurring | 87.10 | 56.8125 | 71.94633 |
| 24.2 | Non-Recurring Contingencies |  |  |  |
| 24.2.1 | Works |  |  |  |
| 24.2.2 | Equipments including SWTL & Furniture |  |  |  |
| 24.2.3 | Vehicle (Four wheeler/Two wheeler, please specify) |  |  |  |
| 24.2.4 | Library |  |  |  |
| 24.2 | Total Non Recurring | 0.00 | 0.00 | 0.00 |
| 24.3 | REVOLVING FUND | - | - | - |
| 24.4 | GRAND TOTAL (A+B+C) | 87.10 | 56.8125 | 71.94633 |

25. Details of Budget Estimate (2014-15) based on proposed action plan

| S. No. | Particulars | BE 2014-15 proposed (Rs. in lakhs) |
| --- | --- | --- |
| 25.1 | Recurring Contingencies |  |
| 25.1.1 | Pay & Allowances | 90.00 |
| 25.1.2 | Traveling allowances | 2.50 |
| 25.1.3 | Contingencies |  |
| A | Stationery, telephone, postage and other expenditure on office running, publication of Newsletter and library maintenance (Purchase of News Paper & Magazines) | 3.50 |
| B | POL, repair of vehicles, tractor and equipments | 2.50 |
| C | Meals/refreshment for trainees (ceiling upto Rs.40/day/trainee be maintained) | 2.00 |
| D | Training material (posters, charts, demonstration material including chemicals etc. required for conducting the training) | 1.50 |
| E | Frontline demonstration except oilseeds and pulses (minimum of 30 demonstration in a year) | 3.00 |
| F | On farm testing (on need based, location specific and newly generated information in the major production systems of the area) | 2.00 |
| G | Training of extension functionaries | 0.30 |
| H | Maintenance of buildings | 1.50 |
| I | Establishment of Soil, Plant & Water Testing Laboratory | 0.00 |
| J | Library | 0.15 |
| K | Extension activities | 0.50 |
| L | Farmers Field School (FFS) | 0.50 |
| 25.1 | TOTAL Recurring Contingencies | 109.95 |
| 25.2 | Non-Recurring Contingencies |  |
| 25.2.1 | Works | 73.00 |
| 25.2.2 | Equipments including SWTL & Furniture | 1.50 |
| 25.2.3 | Vehicle (Four wheeler/Two wheeler, please specify) | 0.00 |
| 25.2.4 | Library (Purchase of assets like books & journals) | 0.25 |
| 25.2 | TOTAL Non-Recurring Contingencies | 74.75 |
| 25.3 | REVOLVING FUND | - |
| 25.4 | GRAND TOTAL | 184.70 |