###### ZONAL PROJECT DIRECTORATE – ZONE VIII BANGALORE

###### ACTION PLAN OF KVKs IN ZONE VIII FOR 2015-16

###### 1. General information about the Krishi Vigyan Kendra

| 1.1 | Name and address of KVK with Phone, Fax and e-mail | : | Bapooji Krishi Vigyan Kendra, Santhanpara P.O, Idukki (Dt.), Kerala, PIN-685619. Email: kvksanthanpara@gmail.com Web url: www.kvkidukki.org |
| --- | --- | --- | --- |
| 1.2 | Name and address of host organization | : | Bapooji Sevak Samaj, Kakkattu House, Meenadom P.O., Pampady, Kottayam (Dt.), Pin-686 516, Kerala. Phone: 0481-2506271, Mob: +919446826019 Email: bkvkchairperson@gmail.com |
| 1.3 | Year of sanction | : | 1994 |
| 1.4 | Website address of KVK and date of last update |  | www.kvkidukki.org (13/03/2015) |

2. Details of staff as on date

| Sl. No. | Sanctioned post | Name of the incumbent | Discipline | Existing Pay band | Grade Pay | Date of joining | Permanent / Temporary |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2.1 | Programme Coordinator | Vacant | - | - | - | - | - |
| 2.2 | Subject Matter Specialist | Dr. S. Jayababu | S.M.S. (Animal Science) | 15600-39100 | 5400 | 19-06-1995 | Permanent |
| 2.3 | Subject Matter Specialist | Manju Jincy Varghese | S.M.S. (Soil Science) | 15600-39100 | 5400 | 10-01-2011 | Permanent |
| 2.4 | Subject Matter Specialist | Dr. Benjamin Mathew | S.M.S. (Agri. Extension) | 15600-39100 | 5400 | 17-01-2011 | Permanent |
| 2.5 | Subject Matter Specialist | Vacant | Agronomy | - | - | - | - |
| 2.6 | Subject Matter Specialist | Dr. Binu John Sam | S.M.S. (Horticulture) | 15600-39100 | 5400 | 17-01-2011 | Permanent |
| 2.7 | Subject Matter Specialist | Sudhakar Soundarajan | S.M.S. (Plant Protection) | 15600-39100 | 5400 | 27-01-2011 | Permanent |
| 2.8 | Programme Assistant | Jayisy Joseph | Programme Assistant (Home Science) | 9300-34800 | 4200 | 20-06-1995 | Permanent |
| 2.9 | Computer Programmer | Biju Narayanan | Programme Assistant (Computer) | 9300-34800 | 4200 | 01-10-2007 | Permanent |
| 2.10 | Programme Assistant | Rachel Skariakutty | Programme Assistant (Rural Craft) | 9300-34800 | 4200 | 05-06-1995 | Permanent |
| 2.11 | Accountant/Superintendent | Shaji K. Kakkattu | - | 9300-34800 | 4200 | 05-06-1995 | Permanent |
| 2.12 | Stenographer | Daisy Daniel | - | 5200-20200 | 1900 | 05-06-1995 | Permanent |
| 2.13 | Driver 1 | P. Nandagopal | - | 5200-20200 | 2000 | 05-06-1995 | Permanent |
| 2.14 | Peon/Messenger | K.T. Mathew | - | 5200-20200 | 1800 | 05-06-1995 | Permanent |
| 2.15 | Supporting staff 1 | K.O. Jose | - | 5200-20200 | 1800 | 05-06-1995 | Permanent |
| 2.16 | Supporting staff 2 | P. Sabu | - | 5200-20200 | 1800 | 05-06-1995 | Permanent |

3. Details of SAC meeting conducted during 2014-15

| Sl. No | Date | Major recommendations | Status of action taken in brief | Tentative date of SAC meeting proposed during 2015-16 |
| --- | --- | --- | --- | --- |
| 3.1 | 08/10/2014 | - More stress to promote organic farming. - Micro-nutrient deficiency reported should be tackled through concerted efforts involving relevant line departments. - Castor based biorepellents (Ecodon) to be promoted on a wider scale. - Serpentine method of propagation in black pepper to be promoted so as to have rapid multiplication of region specific varieties like Panniyur 5 & 6. - The wilt tolerant variety of black pepper, “Kumbukkal” to be popularized. - Soil test based nutrient recommendations should be encouraged to reduce the indiscriminate use of chemical inputs. - Mass campaigns in association with ATMA on the correct usage of fertilizers and PP chemicals. - Underutilized production units have to be improved. - Popularization of cool season vegetables for crop diversification. | - Training and other extension programmes for the next year are planned, giving more emphasis to reduction of chemical inputs and making aware of the various organic inputs that can go into the existing farming practices. - Awareness on the different micro-nutrient deficiencies of major and minor crops of Idukki district and its prophylactic and curative measures are being taken up primarily with the help of field level extension functionaries of line departments. - Castor based bio-repellant is being promoted on a wider scale during the current year. Efforts are on to generate an indigenous bio-repellant with similar properties. - Dearth of planting material in black pepper is being tackled this year with the introduction of the advanced column method of propagation developed by IISR, Kasargod. This is claimed to be superior to the existing serpentine method of propagation. - “Kumbukkal” variety of black pepper is getting popular for its unique property of wilt tolerance in the endemic areas. Efforts are on to procure cuttings from this variety and mass multiply the same through the newly developed column method. - The need for soil test based nutrient management is being emphasized through various mass campaigns and training programmes. Its effects are being seen in the different tracts where such deficiencies were noted. Concerted efforts have been initiated for scaling up these activities in the other parts of Idukki district. - Crop based nutrient management strategies are being undertaken to reduce the over usage of chemical fertilizers and PP chemicals. This, coupled with soil health management strategies have gone a long way in improving the crop and soil health of Idukki district. These efforts shall be given more momentum in the coming years too. - Many production units of agriculture and allied sectors have been idled due to manifold reasons and which could have been rectified with an early intervention. BKVK has started cohering efforts of line departments in strengthening these units on a scheduled basis so that they may get back to the mainstream production line within a couple of years. - Crop diversification has been given timely importance among the farmers of Idukki district as the district is suitable for a wide range of cool season fruits and vegetables. Broccoli and Brussels sprouts are being planned as a diversity in these areas. | 14/10/2015 |

4. Capacity Building of KVK Staff

4.1. Plan of Human Resource Development of KVK personnel during 2015-16

| S. No | New Areas of Training | Institution proposed to attend | Justification |
| --- | --- | --- | --- |
| 4.1.1 | IPDM in Cardamom and Black pepper | ICRI, Myladumpara | To update knowledge on IPDM in Cardamom and Black pepper |
| 4.1.2 | Post harvest technologies of fresh fruits and vegetables for commercial trade | CFTRI, Mysore | Update new technologies |
| 4.1.3 | Good Agricultural Practices | NIPHM, Hyderabad | Update new technologies |
| 4.1.4 | Mushrooms | IIHR, Bangalore | New varieties and species and their cultivation aspects |
| 4.1.5 | Ornamental Horticulture | TNAU / IIHR | Hi-Tech production of cut flowers |
| 4.1.6 | Advances in Horticultural Production Technology | IIHR | Newer frontiers in horticulture production - need of the hour |
| 4.1.7 | Cool season fruits and vegetables | TNAU / IIHR | Advances in cultivation of cool season fruits and vegetables |
| 4.1.8 | Micronutrient mixture preparation of Banana & Vegetable | IIHR, Bangalore | To learn the technology to prepare micronutrient top-up of Banana & Vegetable |
| 4.1.9 | Mixed fodder production | TANUVAS, Chennai & Namakkal | For new fodder production technologies |
| 4.2.0 | Livestock production and management | KVASU, Pookode, Wyanad | New strategies in livestock production in rural household |
| 4.2.1 | Scientific nutrition management | National Institute of Animal Nutrition & Physiology, Adugodi, Bengaluru | To update the new technologies in livestock nutrition |
| 4.2.2 | Poultry production and management | University Poultry Farm, Mannuthy, Thrissur | For new poultry breeding & feeding technologies |
| 4.2.3 | Advanced technologies in banana processing | NRCB, Trichy | To learn techniques on diversified banana products |

4.2. Cross-learning across KVKs during 2015-16

| S. No. | Name of the KVK proposed | Specific learning areas |
| --- | --- | --- |
| 4.2.1 | Within ring – KVK Thrissur & Ernakulam | Vegetable seed production, collection of new fodder seeds, poultry breeds & fisheries |
| 4.2.2 | Within the zone – KVK-Namakkal & Erode | New trends in livestock and fodder production |
| 4.2.3 | Outside zone – KVK Srinagar, Pondicherry, Goa & Guwahati | Temperate fruits, hi-tech horticulture, piggery production technologies |

5. Proposed cluster of KVKs (3 to 5 neighboring KVKs) to be formed for sharing knowledge/expertise, resources and activities during 2015-16

| S. No. | Name of the KVKs included in the cluster | What do you intend to share with Cluster KVKs | What do you expect from Cluster KVKs |
| --- | --- | --- | --- |
| 5.1 | KVK Thrissur | Advanced information on spice crops & its value addition | Vegetable seed production |
| 5.2 | KVK Ernakulam | Advanced information on spice crops & its value addition | Vegetable top up technology, technology transfer on fisheries |
| 5.3 | KVK Alappuzha | Advanced information on spice crops & its value addition | NICRA project |

6. Operational areas details proposed during 2015-16

| S. No. | Major crops & enterprises being practiced in cluster villages | Prioritized problems in these crops/ enterprise | Extent of area (Ha/No.) affected by the problem in the district | Names of Cluster Villages identified for intervention | Proposed Intervention (OFT, FLD, Training, extension activity etc.)* |
| --- | --- | --- | --- | --- | --- |
| 6.1 | Cardamom | Indiscriminate use of PPC | 100 ha | Chembalam / Kallar | FLD |
| 6.2 | Cardamom | Snails damage on the flower and capsules, leading to heavy losses. | 25 ha | Bethel / Ponnamala | OFT |
| 6.3 | Black pepper | Heavy dosage of fungicides are applied for the control of quick wilt | 60 ha | Santhanpara | OFT |
| 6.4 | Bitter gourd | Indiscriminate use of PPC | 25 ha | Mavady | FLD |
| 6.5 | Cardamom | Indiscriminate use of chemical fertilizers leads to decline in soil fertility | 1 ha | Chembalam / Kallar | FLD, Training |
| 6.6 | Banana | INM in banana cv. Nendran for high ranges | 1 ha | Melechinnar / Mavady | FLD, Training |
| 6.7 | Carrot | Non-availability of high yielding varieties | 0.4 ha | Ponnamala | OFT |
| 6.8 | Tapioca | Mg & Zn deficiency due to high soil acidity resulting in low yield | 5 ha | Valiya Thovala | OFT, Training, extension activity |
| 6.9 | Mushrooms | Large demand & inadequate supply | 8 units | Nedumkandam | OFT, Training |
| 6.10 | Banana | Lodging or breaking of banana pseudostem inspite of propping with single casuarina prop | 25 ha | Nedumkandam | OFT |
| 6.11 | Mushrooms | Improper disposal of SMC | 8 units | Nedumkandam | FLD |
| 6.12 | Black Pepper | Dearth of adequate quality planting materials | 28 ha | Nedumkandam | FLD |
| 6.13 | Jack fruit | Jack fruit wastage in season | 2 ha | Murickasserry, Nedumkandam, Cheruthoni & Vathikudy | Orientation, Trainings, Method demonstration |
| 6.14 | Cocoa | 1) Lack of value addition 2) Low domestic demand | 3 ha | Konnathady & Adimali | Training, Method demonstration |
| 6.15 | Dairy cattle, goat & poultry | 1) Poor growth performance 2) Low body weight 3) Unaware of new technologies 4) Low milk & meat production | Above 300 nos. | Nedumkandam | FLD, Training & extension activities |

* Support with problem-cause and interventions diagram

7. Technology Assessment during 2015-16

| S. No. | Crop/ enterprise | Prioritized problem | Title of intervention | Technology options | Source of Technology | Name of critical input | Qty per trial | Cost per trial | No. of trials | Total cost for the intervention (Rs.) | Parameters to be studied | Team members |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 7.1 | Black pepper | Chengannoor is highly susceptible to quick wilt & heavy dosage of fungicides | Assessment of suitable Black Pepper Foot rot (Quick wilt) resistant variety for Idukki District | 1.Farmers practice (Chengannoor) | - | - | - | - | 5 | - | - | Mr. Sudhakar Soundarajan (SMS-Plant Protection) & Dr. Binu John Sam (SMS-Horticulture) |
|  |  |  |  | 2.IISR Thevam | IISR | Azospirillum | 2.5kg | 200 |  | 1000.00 | 1. Percentage reduction in quick wilt incidence |  |
|  |  |  |  | 3.Aswathi | Farmer developed variety-Wynad |  |  |  |  |  |  |  |
|  |  |  |  | 4.Suvarna |  | Phosphobacteria | 2.5kg | 200 |  | 1000.00 |  |  |
|  |  |  |  |  |  | VAM | 6kg | 540 |  | 2700.00 |  |  |
|  |  |  |  |  |  | Trichoderma | 2.5 litre | 250 |  | 1250.00 |  |  |
|  |  |  |  |  |  | Pseudomonas | 2.5 litre | 250 |  | 1250.00 |  |  |
|  |  |  |  |  |  |  |  |  | Total | 7,200.00 |  |  |
| 7.2 | Mushroom | Large demand & inadequate supply. | Preparation of cropping calendar with two types of mushrooms for year round production in Idukki district | 1. Oyster Mushroom | KAU | 1. Spawn 2. PP covers | 50 Nos. 100 Nos. | 1750 300 | 4 | 8200.00 | - | Dr. Binu John Sam (SMS-Horticulture), Dr. Benjamin Mathew (Programme Coordinator i/c.) & Mr. Biju Narayanan (Computer Programmer) |
|  |  |  |  | 2. Milky Mushroom | KAU | 1. Spawn 2. PP covers 3. CaCO3 4. Vermi compost | 50 Nos. 100 Nos. 1 kg 6 kg | 1750 300 250 180 |  | 9920.00 | 1. Yield 2. BCR |  |
|  |  |  |  |  |  |  |  |  | Total | 18,120.00 |  |  |
| 7.3 | Cardamom | Snails & slugs damage on the flowers and young berries of cardamom plants, leading to considerable economic loss | Management of snails & slugs in cardamom plantation | 1. Farmers practice (Use of chemicals as directed by pesticide retail shops) | - | - | - | - | 5 | - | - | Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
|  |  |  |  | 2. Vinegar @ 10ml /litre | ITK - KVK, Idukki - ATMA assessment 2012-13 | Vinegar | 10 litre | 300 |  | 1500.00 | 1. Reduction in snail & slug population at different days (30,40 & 60) after treatment |  |
|  |  |  |  | 3. Coffee powder @ 10g/litre |  | Coffee powder | 5kg | 1000 |  | 5000.00 |  |  |
|  |  |  |  | 4. Yeast & Honey Mixture @ (100g : 100ml) / litre |  | Yeast | 5kg | 500 |  | 2500.00 |  |  |
|  |  |  |  |  |  | Honey | 5kg | 650 |  | 3250.00 |  |  |
|  |  |  |  |  |  |  |  |  | Total | 12,250.00 |  |  |
| 7.4 | Broccoli | 1) Low marketability of the conventional vegetables 2) Non popularity of exotic vegetables | Assessment of suitable varieties of broccoli (Brassica oleracea var. italica) for high ranges | 1. F1 Green Magic | Sakata | Seeds | 2g | 50 | 5 | 250.00 | 1) Days to head formation 2) Days to harvesting 3) Weight of the head (g) 4) Yield (kg/ha) | Dr. Benjamin Mathew (Programme Coordinator i/c.) |
|  |  |  |  |  |  | Bioagents | 5 litre | 750 |  | 3750.00 |  |  |
|  |  |  |  | 2. Palam Samridhi | IARI | Seeds | 2g | 50 |  | 250.00 |  |  |
|  |  |  |  |  |  | Bioagents | 5 litre | 750 |  | 3750.00 |  |  |
|  |  |  |  |  |  |  |  |  | Total | 8,000.00 |  |  |
| 7.5 | Tapioca | Mg & Zn deficiency due to high soil acidity resulting in low yield | Management practices for secondary & micronutrient disorders for Tapioca in acid soils | 1. Farmers Practice (No application of secondary & micronutrients) | - | - | - | - | 5 |  | - | Ms. Manju Jincy Varghese (SMS-Soil Science), Mr. Sudhakar Soundarajan (SMS-Plant Protection) & Dr. Binu John Sam (SMS-Horticulture) |
|  |  |  |  | 2. Foliar spray of 0.2% MgSO4 + 0.5% ZnSO4 + 0.25% lime at 60 to 90 days after planting | KAU | 1. Lime | 1kg | 15 |  | 75.00 | 1. Weight of tubers / clump 2. Yield (t/ha) 3. BCR |  |
|  |  |  |  |  |  | 2. MgSO4 | 1kg | 30 |  | 150.00 |  |  |
|  |  |  |  |  |  | 3. ZnSO4 | 1kg | 80 |  | 400.00 |  |  |
|  |  |  |  |  |  | 4. Soil testing | 1 no. | 100 |  | 500.00 |  |  |
|  |  |  |  | 3. Soil application of Mg as MgSO4 @ 20kg /ha (1.62g / plant) + Zn as ZnSO4 @ 12.5kg/ha (1g / plant) within 2 months of planting | CTCRI | 1. Lime | 1kg | 15 |  | 75.00 |  |  |
|  |  |  |  |  |  | 2. MgSO4 | 1kg | 30 |  | 150.00 |  |  |
|  |  |  |  |  |  | 3. ZnSO4 | 1kg | 80 |  | 400.00 |  |  |
|  |  |  |  |  |  | 4. Soil testing | 1 no. | 100 |  | 500.00 |  |  |
|  |  |  |  |  |  |  |  |  | Total | 2,250.00 |  |  |
| 7.6 | Carrot | Non- availability of high yielding varieties | Assessment of suitable carrot varieties for Idukki district | 1. Farmers Practice (Super Kuroda) | - | - | - | - | 5 | - | - | Ms. Manju Jincy Varghese (SMS-Soil Science), Mr. Sudhakar Soundarajan (SMS-Plant Protection) & & Dr. Binu John Sam (SMS-Horticulture) |
|  |  |  |  | 2. Pusa Nayanjyothi | IARI | Seeds of Pusa Nayanjyothi | 50 g | 175 |  | 875.00 | 1. Average weight of tuber 2. Yield (kg/ha) |  |
|  |  |  |  |  |  | Bioagents | 5 litre | 500 |  | 2500.00 |  |  |
|  |  |  |  | 3. Pusa Rudhira | IARI | Seeds of Pusa Rudhira | 50 g | 175 |  | 875.00 |  |  |
|  |  |  |  |  |  | Bioagents | 5 litre | 500 |  | 2500.00 |  |  |
|  |  |  |  |  |  |  |  |  | Total | 6,750.00 |  |  |
| 7.7 | Banana | Lodging of banana plants nearing maturity | Management of lodging / breaking of banana pseudostem nearing maturity | - 1.Farmers' practice (Single propping) | - | - | - | - | - 5 | - | - | Dr. Binu John Sam (SMS-Horticulture) & Dr. Benjamin Mathew (Programme Coordinator i/c.) |
|  |  |  |  | 2.Single propping coupled with tying with nylon rope | FLD conducted by KVK, Idukki | Bamboo/ casuarina / eucalyptus props | 50 | 6500 |  | 32500.00 | 1) Extent of wind damage 2) BCR |  |
|  |  |  |  |  |  | Tying material | 10 nos. | 1000 |  | 5000.00 |  |  |
|  |  |  |  | 3.Banana collar ring method | KAU | Collar ring | 50 nos. | 1250 |  | 6250.00 |  |  |
|  |  |  |  |  |  |  |  |  | Total | 43,750.00 |  |  |

## 8. Technology Refinement during 2015-16: Nil.

9. Frontline Demonstrations during 2015-16

| S. No. | Category | Crop/ enterprise | Prioritized problem | Technology to be demonstrated | Specify Hybrid or Variety | Name of the Hybrid or Variety | Source of Technology | Name of critical input | Qty per Demo | Cost per Demo | No. of Demo | Total cost for the Demo (Rs.) | Parameters to be studied | Team members |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 9.1 | Cereals |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9.2 | Millets |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9.3 | Oilseeds |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9.4 | Pulses |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9.5 | Commercial crops |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Cardamom | Heavy infestation of root grub leading to heavy usage of PPC | Management of cardamom root grub with Entomopathogenic Nematodes (EPN) | Variety | Njallani | ICRI & OFT KVK, Idukki | EPN | 1600 nos. | 2400 | 10 | 24000.00 | 1) % reduction in root grub attack | Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
|  |  |  |  |  |  |  |  |  |  |  | Total | 24,000.00 |  |  |
|  |  | Cardamom | Indiscriminate use of chemical fertilizers leading to decline in soil fertility | INM in Cardamom | Variety | Njallani | ICRI | Lime | 40kg | 600 | 10 | 6000.00 | 1) % increase in yield | Ms. Manju Jincy Varghese (SMS-Soil Science) & Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
|  |  |  |  |  |  |  |  | Azospirillum | 2kg | 160 |  | 1600.00 |  |  |
|  |  |  |  |  |  |  |  | VAM | 2kg | 160 |  | 1600.00 |  |  |
|  |  |  |  |  |  |  |  | CAN | 2kg | 120 |  | 1200.00 |  |  |
|  |  |  |  |  |  |  |  | Soil testing | - | 100 |  | 1000.00 |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Total | 11,400.00 |  |  |
| 9.6 | Horticultural crops | Bitter gourd | Indiscriminate use of pesticides leads to pesticide residual effect | Integrated Pest and Disease Management (IPDM) in Bitter gourd | Variety | Preethi | IIHR | Trichoderma | 750g | 75 | 10 | 750.00 | 1) % reduction in pest & disease | Mr. Sudhakar Soundarajan (SMS-Plant Protection) & Dr. Binu John Sam (SMS-Horticulture) |
|  |  |  |  |  |  |  |  | IIHR-Neem soap | 1kg | 140 |  | 1400.00 |  |  |
|  |  |  |  |  |  |  |  | Cuelure trap | 4 nos. | 400 |  | 4000.00 |  |  |
|  |  |  |  |  |  |  |  | Indoxacarb | 100 ml | 370 |  | 3700.00 |  |  |
|  |  |  |  |  |  |  |  | Imidachloprid | 100 ml | 200 |  | 2000.00 |  |  |
|  |  |  |  |  |  |  |  | Mancozeb | 200g | 150 |  | 1500.00 |  |  |
|  |  |  |  |  |  |  |  | Zineb | 200g | 170 |  | 1700.00 |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Total | 15,050.00 |  |  |
|  |  | Cowpea | Micronutrient deficiency & Low productivity of existing varieties | Demonstration of IIHR vegetable special in cowpea var. Arka Mangala | Variety | Arka Mangala | IIHR | IIHR Vegetable special | 2 kg | 300 | 10 | 3000.00 | 1) Pod length (cm) 2) No. of pods for 1 kg 3) Yield (kg/ha) | Dr. Benjamin Mathew (Programme Coordinator i/c.) |
|  |  |  |  |  |  |  |  | Arka Mangala seeds | 250 g | 450 |  | 4500.00 |  |  |
|  |  |  |  |  |  |  |  | Bioagents | 10 litre | 1000 |  | 10000.00 |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Total | 17,500.00 |  |  |
|  |  | Black Pepper | Dearth of adequate quality planting materials | Column Method for production of quality planting materials in Black Pepper | Variety |  |  | Poles | 2 | 3000 | 3 | 9000.00 | 1) Visual stand of the nursery 2) No. of each type of cuttings obtained 3) BCR | Dr. Binu John Sam (SMS-Horticulture) & Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
|  |  |  |  |  |  |  |  | Mesh | 10 m | 1500 |  | 4500.00 |  |  |
|  |  |  |  |  |  |  |  | Compost | 200 kg | 4000 |  | 12000.00 |  |  |
|  |  |  |  |  |  |  |  | Rooted Pepper Cuttings | 20 | 400 |  | 1200.00 |  |  |
|  |  |  |  |  |  |  |  | Irrigation lines | 10 m | 1000 |  | 3000.00 |  |  |
|  |  |  | PPT CORRECTED UPTO THIS POINT |  |  |  |  |  |  |  | Total | 29,700.00 |  |  |
|  |  | Black pepper | Low yield and deficiency of secondary and micronutrients in black pepper | Demonstration of IISR nutrient mix in black pepper | Variety | Local | IISR | IISR Nutrient mix | 2 kg | 400 | 10 | 4000.00 | 1. Yield 2. BCR | Dr. Benjamin Mathew (Programme Coordinator i/c.) |
|  |  |  |  |  |  |  |  | Lime | 10 kg | 150 |  | 1500.00 |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Total | 5,500.00 |  |  |
|  |  | Vegetables (Home stead) | Non availability of year round quality vegetables | Popularization of Organic Kitchen Garden in homesteads for nutritional security | - | - | - | Seeds | 30 pkts. | 300 | 5 | 1500.00 | 1) Availability of year round organic vegetable production | Ms. Jayisy Joseph (Programme Assistant-Home Science) & Dr. Binu John Sam (SMS-Horticulture) |
|  |  |  |  |  |  |  |  | Bioagents | 10 litre | 1000 |  | 5000.00 |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Total | 6,500.00 |  |  |
|  |  | Mushroom | Improper disposal of SMC | Utilization of Spent Mushroom Compost (SMC) as a medium for vegetable production in grow bags | Mushroom | - | TNAU, Coimbatore | Seeds | 30 pkts. | 300 | 5 | 1500.00 | 1) Visual stand of the crop 2) Yield | Dr. Binu John Sam (SMS-Horticulture) & Dr. Benjamin Mathew (Programme Coordinator i/c.) |
|  |  |  |  |  |  |  |  | Bio-agents | 5 litre | 500 |  | 2500.00 |  |  |
|  |  |  |  |  |  |  |  | Grow bags | 30 | 750 |  | 3750.00 |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Total | 7,750.00 |  |  |
|  |  | Banana | Poor soil fertility, high acidity leading to micro nutrient disorders | INM in banana cv. Nendran | Cultivar | Nendran | KAU | Lime | 20kg | 500 | 10 | 5000.00 | 1) Yield 2) BCR | Ms. Manju Jincy Varghese (SMS-Soil Science), Mr. Sudhakar Soundarajan (SMS-Plant Protection) & Dr. Binu John Sam (SMS-Horticulture) |
|  |  |  |  |  |  |  |  | Bio- fertilizers | 2kg | 300 |  | 3000.00 |  |  |
|  |  |  |  |  |  |  |  | ZnSO4 | 2kg | 200 |  | 2000.00 |  |  |
|  |  |  |  |  |  |  |  | Borax | 1kg | 300 |  | 3000.00 |  |  |
|  |  |  |  |  |  |  |  | Soil testing | 2 samples | 200 |  | 2000.00 |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Total | 15,000.00 |  |  |
| 9.7 | Livestock | Dairy cattle | Ecto-endo parasitic infestation | Demonstration of Ivermectin injection for control of ecto- endo parasitic infestation in dairy cattle | Crossbred | Crossbred | TANUVAS | Ivermectin Injection | 5 vials (7 ml each) | 750 | 10 | 7500.00 | % increase in body weight | Dr. S. Jayababu, (SMS-Animal Husbandry) |
|  |  |  |  |  |  |  |  |  |  |  | Total | 7,500.00 |  |  |
|  |  | Dairy cattle | Inadequate knowledge on mixed fodder system & low milk production | Popularization of fodder cafeteria in rural households of Idukki district | Cross breeds | Jersey & HF cross | TNAU | Seeds of COFS-29 | 200g | 80 | 10 | 800.00 | 1) Quality & quantity of milk production | Dr. S. Jayababu, (SMS-Animal Husbandry) |
|  |  |  |  |  |  |  |  | Seeds of Guinea grass (CoGG3) | 200 nos. | 400 |  | 4000.00 |  |  |
|  |  |  |  |  |  |  |  | Seeds of Agathi | 200g | 100 |  | 1000.00 |  |  |
|  |  |  |  |  |  |  |  | Seeds of Hedge Lucerne | 200g | 100 |  | 1000.00 |  |  |
|  |  |  |  |  |  |  |  | Stylosanthes | 200g | 70 |  | 700.00 |  |  |
|  |  |  |  |  |  |  |  | Fodder cowpea | 200g | 30 |  | 300.00 |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Total | 7,800.00 |  |  |
|  |  | Poultry | Low meat production | Popularization of Vigova Super M duck in backyard system | Vigova Super M duck | Vigova Super M duck | CPDO, Hesaraghatta | 1. Two to three day old ducklings | 10 birds / demo | 700 | 10 | 7000.00 | 1) Average weight / bird (weekly interval) 2) Disease incidence | Dr. S. Jayababu, (SMS-Animal Husbandry) |
|  |  |  |  |  |  |  |  | 2. Supplements | 1 litre | 300 |  | 3000.00 |  |  |
|  |  |  |  |  |  |  |  | 3. Feed | 50 kg | 800 |  | 8000.00 |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Total | 18,000.00 |  |  |
|  |  | Poultry | High incidence of Newcastle disease | Prophylactic management of Newcastle disease (Ranikhet) in poultry using oral pellet vaccine | Commercial poultry birds | Poultry hybrid | TANUVAS | 1. Oral pellet vaccine against Newcastle disease | 100 doses | 300 | 10 | 3000.00 | 1) Disease incidence 2) Mortality rate | Dr. S. Jayababu, (SMS-Animal Husbandry) |
|  |  |  |  |  |  |  |  |  |  |  | Total | 3,000.00 |  |  |
| 9.8 | Others | Mango | 1) Under utilization of mangos in households of Idukki district | Dehydrated sweet mango pickle mix | - | - | UAS, Dharwad | Cabinet dryer (5 kg capacity) | 1 | 30000 | 8 | 30000.00 | 1) Income through value addition 2) Acceptability based on sensory evaluation | Ms. Jayisy Joseph (Programme Assistant-Home Science) |
|  |  |  |  |  |  |  |  | Pickling ingredients | 3 kg | 450 |  | 3600.00 |  |  |
|  |  |  |  |  |  |  |  | Trays | 8 nos. | 200 |  | 1600.00 |  |  |
|  |  |  |  |  |  |  |  | Packaging materials | 30 nos. | 240 |  | 1920.00 |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Total | 37,120.00 |  |  |
|  | Nursery production | Vegetables | 1) High cost 2) Incidence of damping off | Demonstration of Arka Microbial Consortium enriched Coco peat for protray vegetable nursery | - | - | IIHR | Protray | 20 nos. | 600 | 5 | 3000.00 | 1) Germination percentage 2) Percentage incidence of damping off 3) Height of the seedling at the time of transplanting | Dr. Benjamin Mathew (Programme Coordinator i/c.) |
|  |  |  |  |  |  |  |  | Coco peat | 5 kg | 500 |  | 2500.00 |  |  |
|  |  |  |  |  |  |  |  | Arka microbial consortium | 5 kg | 500 |  | 2500.00 |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Total | 8,000.00 |  |  |

10	Training for Farmers/ Farm Women during 2015-16

| S.No. | Thematic area | Crop / Enterprise | Major problem | Linked field intervention (Assessment/Refinement/ FLD)* | Training Course Title** | No. of Courses | Expected No. of participants | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 10.1 | Crop Production |  |  |  |  |  |  |  |
| 10.2 | Horticulture Production | Vegetables | Unscientific disposal of Spent Mushroom Compost | Utilization of Spent Mushroom Compost (SMC) as a medium for vegetable production | Organic Vegetable Cultivation | 2 | 40 | Dr. Binu John Sam (SMS-Horticulture) & Dr. Benjamin Mathew (Programme Coordinator i/c.) |
| 10.3 | Livestock Production | Dairy cattle | Unaware of mixed fodder system & low milk production | FLD | Fodder management & hygienic milk production | 3 | 90 | Dr. S. Jayababu, SMS (Animal Husbandry) |
|  |  | Poultry – Duck | Low egg & meat production | FLD | Demonstration of new poultry breeds in backyard | 5 | 125 | Dr. S. Jayababu, SMS (Animal Husbandry) |
|  |  | Poultry – Chicken | Occurrence of Ranikhet disease | FLD | Poultry disease management techniques | 3 | 120 | Dr. S. Jayababu, SMS (Animal Husbandry) |
| 10.4 | Home Science | Fruit & Vegetables | Wastage of fruits in season | - | Agro based value added products from fruits and vegetables | 5 | 150 | Ms. Jayisy Joseph, Programme Assistant (Home Science) |
| 10.5 | Plant Protection | Cardamom | Heavy infestation of root grub | FLD | Root grub management in Cardamom | 5 | 150 | Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
|  |  | Cardamom | Incidence of cardamom clump rot | Training | Integrated disease management in Cardamom | 5 | 100 | Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
|  |  | Black Pepper | Lack of knowledge in identification of pest and disease | Training | IPDM on Black Pepper | 5 | 75 | Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
|  |  | Banana | Indiscriminate use of PP chemicals | Training | Organic Pest & Disease Management of Banana | 5 | 100 | Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
|  |  | Rice | Unscientific Pest and Disease Management | Training | IPM in Rice | 5 | 80 | Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
|  |  | Bitter gourd | Indiscriminate use of PP chemicals | FLD | Integrated Pest and Disease Management in bitter gourd | 5 | 100 | Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
| 10.6 | Production of Inputs at Site |  |  |  |  |  |  |  |
| 10.7 | Soil Health and Fertility | Cardamom | Indiscriminate use of chemical fertilizers leading to decline in soil fertility | FLD | Soil health management in cardamom | 5 | 125 | Ms. Manju Jincy Varghese (SMS-Soil Science) & Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
|  |  | Banana | Poor soil fertility, high acidity leading to micronutrient deficiency in banana | FLD | INM in Banana | 3 | 105 | Ms. Manju Jincy Varghese (SMS-Soil Science) & Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
|  |  | Wild boars and rodents | Heavy crop damage due to rodents & wild boars | Training & demonstration | Castor based herbal extract for control of rodents & wild boars | 3 | 90 | Ms. Manju Jincy Varghese (SMS-Soil Science) & Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
| 10.8 | PHT and value addition | Fruit & vegetables | Wastage of fruits in season | - | Value added products from fruits & vegetables | 2 | 50 | Ms. Jayisy Joseph, Programme Assistant (Home Science) |
| 10.9 | Capacity Building Group Dynamics |  |  |  |  |  |  |  |
| 10.10 | Farm Mechanization |  |  |  |  |  |  |  |
| 10.11 | Fisheries Production Technologies |  |  |  |  |  |  |  |
| 10.12 | Mushroom production | Mushrooms | Large demand & inadequate supply | Preparation of cropping calendar with two types of mushrooms for year round production in Idukki district | Scientific Mushroom cultivation | 3 | 45 | Dr. Binu John Sam (SMS-Horticulture) & Dr. Benjamin Mathew (Programme Coordinator i/c.) |
| 10.13 | Agro forestry |  |  |  |  |  |  |  |
| 10.14 | Bee Keeping |  |  |  |  |  |  |  |
| 10.15 | Sericulture |  |  |  |  |  |  |  |
| 10.16 | Others (Rural craft) | Jewellery making | Low income of rural women folk | Training | Jewellery making | 4 | 100 | Ms. Rachel Skaria, Programme Assistant (Rural craft) |
|  |  | Homecare products | Low income of rural women folk | Training | Preparation of homecare products | 3 | 75 | Ms. Rachel Skaria, Programme Assistant (Rural craft) |
|  | Others, pl. specify |  |  |  |  |  |  |  |

* Title of intervention/title of technology, ** Training title should specify the major technology/skill to be transferred.

11. Training for Rural Youth during 2015-16

| S. No. | Thematic area | Crop / Enterprise | Major problem | Linked field intervention (Assessment/Refinement/ FLD)* | Training Course Title** | No. of Courses | Expected No. of participants | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 11.1 | Crop Production |  |  |  |  |  |  |  |
| 11.2 | Horticulture Production | Vegetables | Unscientific disposal of Spent Mushroom Compost | Utilization of Spent Mushroom Compost (SMC) as a medium for vegetable production | Organic Vegetable Cultivation by utilizing SMC | 2 | 40 | Dr. Binu John Sam (SMS-Horticulture) & Dr. Benjamin Mathew (Programme Coordinator i/c.) |
| 11.3 | Livestock Production |  |  |  |  |  |  |  |
|  |  | Dairy cattle | Low body weight, growth performance & milk production | Popularization of mixed fodder system | Livestock production and management | 4 | 120 | Dr. S. Jayababu, SMS (Animal Husbandry) |
|  |  | Poultry | Poor growth performance | Popularization of new poultry breeds | Scientific poultry management | 2 | 70 | Dr. S. Jayababu, SMS (Animal Husbandry) |
| 11.4 | Home Science |  |  |  |  |  |  |  |
| 11.5 | Plant Protection | Cardamom | Heavy infestation of root grub | Popularization of EPN to reduce the root grub infestation in cardamom | Organic Pest & Disease Management in Cardamom | 5 | 100 | Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
| 11.6 | Production of Inputs at Site |  |  |  |  |  |  |  |
| 11.7 | Soil Health and Fertility | Cardamom | Indiscriminate use of chemical fertilizers leading to decline in soil health | Site specific nutrient management in cardamom | Soil health management in cardamom | 5 | 125 | Ms. Manju Jincy Varghese (SMS-Soil Science) |
| 11.8 | PHT and value addition | Fruits & vegetables | Inadequate value addition | - | Product diversification and by-product utilization in fruits & vegetables | 3 | 60 | Ms. Jayisy Joseph, Programme Assistant (Home Science) |
|  |  | Dairy products | Insufficient value addition | - | Milk products preparation | 2 | 30 | Ms. Jayisy Joseph, Programme Assistant (Home Science) |
| 11.9 | Capacity Building Group Dynamics | Mushroom | Lack of value addition | - | EDP in post harvest handling & value addition in mushroom | 2 | 40 | Ms. Jayisy Joseph, Programme Assistant (Home Science) |
| 11.10 | Farm Mechanization |  |  |  |  |  |  |  |
| 11.11 | Fisheries Production Technologies |  |  |  |  |  |  |  |
| 11.12 | Mushroom production | Mushrooms | Large demand & inadequate supply | Preparation of cropping calendar with two types of mushrooms for year round production in Idukki district | Scientific Mushroom cultivation | 3 | 45 | Dr. Binu John Sam (SMS-Horticulture) & Dr. Benjamin Mathew (Programme Coordinator i/c.) |
| 11.13 | Agro forestry |  |  |  |  |  |  |  |
| 11.14 | Bee Keeping | Cardamom | Poor pollination | - | Apiculture | 1 | 50 | Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
| 11.15 | Sericulture |  |  |  |  |  |  |  |
| 11.16 | Others (Rural craft) | Interior decoration articles | Underemployment | Training | Dry flower arrangement & wall hangings | 5 | 100 | Ms. Rachel Skaria, Programme Assistant (Rural craft) |
|  |  | Toys making | Underemployment | Training | Soft toys making | 4 | 100 | Ms. Rachel Skaria, Programme Assistant (Rural craft) |
|  |  | Jewellery making | Underemployment | Training | Paper & terracotta jewellery making | 5 | 125 | Ms. Rachel Skaria, Programme Assistant (Rural craft) |
|  | Others, pl. specify |  |  |  |  |  |  |  |

* Title of intervention/title of technology, ** Training title should specify the major technology/skill to be transferred.

### 12 Trainings for Extension Personnel during 2015-16

| S. No. | Thematic area | Training Course Title** | No. of Courses | Expected No. of participants | Names of the team members involved |
| --- | --- | --- | --- | --- | --- |
| 12.1 | Crop Production |  |  |  |  |
|  |  | INM in Cardamom | 1 | 20 | Ms. Manju Jincy Varghese (SMS-Soil Science) & Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
| 12.2 | Home Science | Diversified products from fruits | 1 | 15 | Ms. Jayisy Joseph, Programme Assistant (Home Science) |
| 12.3 | Capacity Building and Group Dynamics | EDP in post harvest handling & processing of fruits and vegetables | 1 | 20 | Ms. Jayisy Joseph, Programme Assistant (Home Science) & Dr. Binu John Sam (SMS-Horticulture) |
| 12.4 | Horticulture | Scientific Mushroom Cultivation and Post Harvest Handling | 1 | 20 | Dr. Binu John Sam (SMS-Horticulture) & Ms. Jayisy Joseph (Technical Assistant – Home Science) |
|  |  | ICM in vegetables | 1 | 25 | Dr. Benjamin Mathew (Programme Coordinator i/c) |
| 12.5 | Livestock Production & Management |  |  |  |  |
|  | Feed and fodder technology | Importance of mineral supplementation in cattle feed | 1 | 20 | Dr. S. Jayababu, SMS (Animal Husbandry) |
|  | Feed and fodder technology | Importance of mixed fodder system in dairy cattle ration | 1 | 20 | Dr. S. Jayababu, SMS (Animal Husbandry) |
|  | Poultry disease management | Control of Ranikhet disease by oral pellet vaccine | 1 | 30 | Dr. S. Jayababu, SMS (Animal Husbandry) |
| 12.6 | Plant Protection | IPDM in cardamom & black pepper | 2 | 40 | Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
| 12.7 | Farm Mechanization |  |  |  |  |
| 12.8 | PHT and value addition |  |  |  |  |
| 12.9 | Production of Inputs at Site |  |  |  |  |
| 12.10 | Sericulture |  |  |  |  |
| 12.11 | Fisheries |  |  |  |  |

* Title of intervention/title of technology, ** Training title should specify the major technology/skill to be transferred.

## 13 Vocational trainings during 2015-16

| Sl. No. | Thematic area and the Crop/Enterprise | Training title* | No. of programmes and Duration (days) | Type of Clientele (SHGs, NYKs, School students, Women, Youth etc.) | Expected No. of participants | Sponsoring agency if any | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 13.1 | Crop Production | Importance of soil testing | 1 (3 days) | Rural youth | 20 | - | Ms. Manju Jincy Varghese (SMS-Soil Science) & Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
|  |  | Integrated Nutrient Management in different crops | 2 (3 days) | SHGs, Rural youth and school students | 40 | - | Ms. Manju Jincy Varghese (SMS-Soil Science) & Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
| 13.2 | Home Science | Skill development training | 1 (6 days) | Youth & Women | 20 | - | Ms. Jayisy Joseph, Programme Assistant (Home Science) |
| 13.3 | Capacity Building and Group Dynamics | Diversified products from fruits & vegetables | 1 (6 days) | Youth & Women | 18 | - | Ms. Jayisy Joseph, Programme Assistant (Home Science) |
| 13.4 | Horticulture | Scientific Mushroom Cultivation and Processing | 1 (3 days) | Farm Women, Rural Youth | 40 | Dept. of Agriculture / ATMA | Dr. Binu John Sam (SMS-Horticulture), Dr. Benjamin Mathew (Programme Coordinator i/c) & Ms. Jayisy Joseph (Technical Assistant – Home Science) |
|  |  | Organic production of cool season vegetable production | 1 (3 days) | Rural Youth & Farm Women | 25 | SHM | Dr. Benjamin Mathew (Programme Coordinator i/c) Mr. Sudhakar Soundarajan SMS-Plant Protection |
| 13.5 | Scientific goat management | Scientific goat production and management | 3 (3 days) | Rural youth and school students | 60 | - | Dr. S. Jayababu, SMS (Animal Husbandry) |
|  | Poultry production | Scientific poultry management | 2 (3 days) | Rural youth and school students | 70 | - | Dr. S. Jayababu, SMS (Animal Husbandry) |
| 13.6 | Plant Protection | Bio-agents production technology | 2 (5 days) | Rural youth & School students | 40 | - | Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
| 13.7 | Farm Mechanization |  |  |  |  |  |  |
| 13.8 | PHT and value addition | EDP on processing of fruit & vegetables | 1 (5 days) | Youth & Women | 15 | ATMA | Ms. Jayisy Joseph, Programme Assistant (Home Science) & Dr. Binu John Sam (SMS-Horticulture) |
| 13.9 | Production of Inputs at Site |  |  |  |  |  |  |
| 13.10 | Sericulture |  |  |  |  |  |  |
| 13.11 | Fisheries |  |  |  |  |  |  |
| 13.12 | Others (Rural craft) | Jewellery making | 6 (4 days) | SHGs, Youth, School students & Women | 120 | - | Ms. Rachel Skaria, Programme Assistant (Rural craft) |
|  |  | Fabric painting & fabric printing | 3 (10 days) | SHGs, Youth, School students & Women | 45 | - | Ms. Rachel Skaria, Programme Assistant (Rural craft) |
|  |  | Soft toys making | 2 (10 days) | SHGs, Youth, School students & Women | 40 | - | Ms. Rachel Skaria, Programme Assistant (Rural craft) |
|  |  | Interior decoration articles | 3 (10 days) | SHGs, Youth, School students & Women | 60 | - | Ms. Rachel Skaria, Programme Assistant (Rural craft) |

* Training title should specify the major technology/skill to be transferred.

## 14 Sponsored trainings during 2015-16

| Sl. No. | Thematic area and the Crop/Enterprise | Training title* | No. of programmes and Duration (days) | Type of Clientele (SHGs, NYKs, School students, Women, Youth etc.) | Expected No. of participants | Sponsoring agency | Names of the team members involved |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 14.1 | Crop Production | Soil health management | 3 (1day) | SHGS, Rural youth | 125 | Lead bank, VFPCK, Department of Agriculture | Ms. Manju Jincy Varghese (SMS-Soil Science) |
|  |  | Awareness of soil testing and soil campaign | 4 (1 day) | SHGS, Rural youth | 90 | Department of Agriculture | Ms. Manju Jincy Varghese (SMS-Soil Science) |
| 14.2 | Home Science | Value added products from fruits & vegetables | 3 (1 day) | SHGs, Women | 25 | Coffee Board | Ms. Jayisy Joseph (Programme Assistant-Home Science) |
|  |  | Skill development programme (EDP mode) | 2 (2 days) | SHGs, Women | 20 | District Industries Centre (DIC) | Ms. Jayisy Joseph (Programme Assistant-Home Science) |
| 14.3 | Capacity Building and Group Dynamics | Popularization of jack products | 3 (1 day) | SHGs, Women | 30 | ATMA | Ms. Jayisy Joseph (Programme Assistant-Home Science) |
|  |  | Group Formation and Dynamics | 1 (1 day) | SHGs | 30 | DIC | Dr. Binu John Sam (SMS-Horticulture) & Ms. Jayisy Joseph (Programme Assistant-Home Science) |
|  |  | Entrepreneurship Development Programme | 2 (1 day) | SHGs, NYKs | 40 | DIC | Dr. Binu John Sam (SMS-Horticulture) & Ms. Jayisy Joseph (Programme Assistant-Home Science) |
| 14.4 | Horticulture | Scientific Mushroom Cultivation | 2 (1 day) | Farm Women, Rural Youth | 40 | Dept. of Agriculture / ATMA | Dr. Binu John Sam (SMS-Horticulture) |
|  |  | Hi tech vegetable production | 2 (1day) | Rural Youth &Farm Women | 50 | Dept. of Agriculture / ATMA | Dr. Benjamin Mathew (Programme Coordinator i/c.) |
|  |  | ICM in vegetables | 2 (1day) | SHGs, Rural Youth & Farm Women |  | Dept. of Agriculture / ATMA & VFPCK | Dr. Benjamin Mathew (Programme Coordinator i/c.) |
| 14.5 | Livestock Production & Management |  |  |  |  |  |  |
|  | Livestock production and management | Scientific dairy cattle management | 2 (1day) | SHGS, Rural youth and school students | 80 | Lead bank | Dr. S. Jayababu, SMS (Animal Husbandry) |
|  | Goat production | Scientific goat management | 3 (1 day) | SHGs, Rural youth | 90 | Grama Panchayat | Dr. S. Jayababu, SMS (Animal Husbandry) |
|  | Fodder management | Mixed fodder cultivation techniques | 2 (1 day) | SHGS, Rural youth | 60 | Dept. of Dairy | Dr. S. Jayababu, SMS (Animal Husbandry) |
|  | Poultry production | Scientific management of broiler and layer poultry | 4 (1 day) | SHGS, Rural youth | 120 | HDS | Dr. S. Jayababu, SMS (Animal Husbandry) |
| 14.6 | Plant Protection | Integrated Pest & Disease Management in Cardamom | 5 (1 day) | SHGs, Women, Youth | 150 | ATMA | Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
|  |  | Integrated Pest and Disease management in Black pepper | 3 (1 day) | SHGs, Women, Youth | 90 | ATMA | Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
|  |  | Integrated Crop Management in Black Pepper | 5 (1 day) | SHGs, Women, Youth | 150 | ATMA and Spices Board | Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
|  |  | IPDM in Cowpea | 3 (1 day) | SHGs, Women, Youth | 90 | VFPCK | Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
|  |  | IPDM in Banana | 5 (1 day) | SHGs, Women, Youth | 150 | VFPCK and ATMA | Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
| 14.7 | Farm Mechanization |  |  |  |  |  |  |
| 14.8 | PHT and value addition | Value added mushroom products | 1 (1 day) | SHGs, Youth & Women | 20 | - | Ms. Jayisy Joseph, Programme Assistant (Home Science) |
| 14.9 | Production of Inputs at Site |  |  |  |  |  |  |
| 14.10 | Sericulture |  |  |  |  |  |  |
| 14.11 | Fisheries |  |  |  |  |  |  |

* Programme title should specify the major technologies/skills to be transferred /refreshed.

## 15. Extension programmes during 2015-16

| Sl. No. | Extension programme* | No. of programmes or activities | Expected No. of participants | Names of the team members involved |
| --- | --- | --- | --- | --- |
| 15.1 | Advisory Services | 460 | 460 | All tech staff |
| 15.2 | Diagnostic visits | 150 | 175 |  |
| 15.3 | Field Day | 10 | 200 |  |
| 15.4 | Group discussions | 12 | 60 |  |
| 15.5 | Kisan Ghosthi | 1 | 30 |  |
| 15.6 | Film Show | 1 | 50 |  |
| 15.7 | Self -help groups | 7 | 35 |  |
| 15.8 | Kisan Mela (Jack mela) | 1 | 500 | All staff |
| 15.9 | Exhibition (Participation only) | 2 | 600 |  |
| 15.10 | Scientists' visit to farmers field | 186 | 220 | All tech staff |
| 15.11 | Plant/Soil health/Animal health camps | 2 | 150 | Dr. S. Jayababu (SMS-Animal Husbandry) & Ms. Manju Jincy Varghese (SMS-Soil Science) |
| 15.12 | Farm Science Club |  |  |  |
| 15.13 | Ex-trainees Sammelan | 2 | 40 | All tech staff |
| 15.14 | Farmers' seminar/workshop | 10 | 140 |  |
| 15.15 | Method Demonstrations | 15 | 175 |  |
| 15.16 | Celebration of important days | 2 | 100 |  |
| 15.17 | Special day celebration (World Food Day) | 1 | 125 | Ms. Jayisy Joseph, Programme Assistant (Home Science) |
| 15.18 | Exposure visits | 2 | 50 | All tech staff |
| 15.19 | Technology week | 1 | 600 |  |
| 15.20 | FFS | 1 | 25 |  |
| 15.21 | Farm innovators meet | 1 | 25 |  |
| 15.22 | Awareness programs | 5 | 85 |  |
|  | Others, pl. specify |  |  |  |

## 16.	Activities proposed as Knowledge and Resource Centre during 2015-16

16.1 Technological knowledge

| Sl. No. | Category | Details of technologies | Area (ha)/ Number | Names of the team members involved |
| --- | --- | --- | --- | --- |
| 16.1.1 | Technology Park/ Crop cafeteria | Vegetable Seed Production Unit | 0.1 ha | All Staff |
|  |  | Cardamom Nursery | 0.1 ha |  |
|  |  | Medicinal plant | 0.04 ha |  |
|  |  | Fodder crops | 0.05 ha |  |
| 16.1.2 | Demonstration Units | Cardamom varietal plot | 0.2 ha | All Staff |
|  |  | Pepper mother nursery | 0.012 |  |
|  |  | Pepper poly bag nursery | 0.012 |  |
|  |  | Farm machineries | - |  |
|  |  | Vermicomposting unit | 1 no. |  |
|  |  | Azolla multiplication unit | 1 no. |  |
|  |  | Mushroom Production Unit | 1 no. |  |
|  |  | HDP in banana | 0.20 ha |  |
|  |  | Beekeeping | 0.1 ha |  |
|  |  | Poultry | 1 unit |  |
|  |  | Kitchen garden | 0.01 ha |  |
|  |  | Bio-control lab | 1 unit |  |
|  |  | Cardamom | 0.40 ha |  |
|  |  | Pepper | 0.2 ha |  |
|  |  | Processing unit | 1 unit |  |
|  |  | Duck cum fish culture unit | 1 unit |  |
|  |  | EPN | 1 unit |  |
|  |  | Pheromone trap | 1 unit |  |
|  |  | Mushroom spawn production unit | 1 unit |  |
|  |  | Poultry rearing unit | 1 no. |  |
|  |  | Ornamental fish unit | 1 no. |  |
| 16.1.3 | Lab Analytical services | Soil | 1 unit | Ms. Manju Jincy Varghese, SMS (Soil Science) |
|  |  | Water | 1 unit |  |
| 16.1.4 | Technology Week | Livestock production & management | - | All Staff |
|  |  | Mushroom production & value addition | - |  |
|  |  | Organic farming technologies | - |  |
|  |  | Hi-tech agriculture | - |  |
|  |  | IPDM in Cardamom & Pepper | - |  |

16.2 Technological Products

| Sl. No. | Category | Name of the Production Partner Agency, if any | Name of the product | Quantity (Qtl.)/ Number planned to be produced during 2015-16 | Names of the team members involved |
| --- | --- | --- | --- | --- | --- |
| 16.2.1 | Seeds | - | Vegetable Seeds | 0.5 qtl. | Dr. Binu John Sam (SMS-Horticulture), Mr. Sudhakar Soundarajan, SMS (Plant Protection) & Dr. Benjamin Mathew (Programme Coordinator i/c.) |
| 16.2.2 | Planting materials | - | Rooted Pepper cuttings | 50000 nos. | Mr. Sudhakar Soundarajan, SMS (Plant Protection), Dr. Benjamin Mathew (Programme Coordinator i/c), Dr. Binu John Sam (SMS-Horticulture), Ms. Manju Jincy Varghese (SMS - Soil Science) |
|  |  | - | Cardamom tillers | 1000 nos. |  |
|  |  | - | Vegetable seedlings | 3000 nos. |  |
|  |  | - | Ornamental seedlings | 3000 nos. |  |
|  |  |  | Medicinal plants | 250 nos. |  |
| 16.2.3 | Bio-products | - | Pseudomonas | 2500 L | Mr. Sudhakar Soundarajan, SMS (Plant Protection) |
|  |  | - | Trichoderma | 1000 L |  |
|  |  | - | EPN | 25000 cadavers |  |
|  |  | - | Pheromone Trap | 1000 nos. |  |
|  |  | - | Metarhizium | 200 L |  |
|  |  | - | Mushroom spawn | 10000 pkts. | Mr. Sudhakar Soundarajan (SMS-Plant Protection), Dr. Benjamin Mathew (Programme Coordinator i/c), Dr. Binu John Sam (SMS-Horticulture) & Dr. S. Jayababu (SMS-Animal Husbandry) |
|  |  | - | Edible mushroom | 100 kg |  |
|  |  | - | Vermicompost | 500 kg |  |
|  |  | - | Azolla seed | 50 kg |  |
| 16.2.4 | Livestock strains | - | Goat | 10 nos. | Dr. S. Jayababu, SMS (Animal Husbandry) |
|  |  | - | Ducks | 100 nos. |  |
|  |  | - | Poultry birds | 750 nos. |  |
| 16.2.5 | Fish fingerlings | - | Fingerlings | 3000 nos. |  |

16.3 Technological Information

| Sl. No. | Category | Technological capsules / Number | Names of the team members involved |
| --- | --- | --- | --- |
| 16.3.1 | Technology backstopping to line departments |  |  |
|  | Agriculture | 10 | All tech staff |
|  | Horticulture | 3 | Dr. Benjamin Mathew (Programme Coordinator i/c), Dr. Binu John Sam (SMS-Horticulture) |
|  | Animal Husbandry | 2 | Dr. S. Jayababu, SMS (Animal Husbandry) |
|  | Fisheries | - |  |
|  | Agricultural Engineering | - |  |
|  | Sericulture | - |  |
|  | Soil Science & Plant Protection | 2 | Ms. Manju Jincy Varghese, SMS (Soil Science) & Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
|  | Others, pl. specify |  |  |
| 16.3.2 | Literature/publication | 5 | All tech staff |
| 16.3.4 | Electronic Media | 2 | All tech staff |
| 16.3.5 | Kisan Mobile Advisory Services | 100 | All tech staff |
| 16.3.6 | Information on centre/state sector schemes and service providers in the district. | MTA capsule of ATMA, prepared, scrutinized and disseminated on a monthly basis | All tech staff |

## 17.	Additional Activities Planned during 2015-16: Nil.

18.	Revolving Fund

18.1	Financial status

| Opening balance as on 01.04.2014 (Rs.in Lakh) | Expenditure incurred during 2014-15 (Rs.in Lakh) | Receipts during 2014-15 (Rs.in Lakh) | Closing balance as on 31.01.2015 (Rs.in Lakh) | Expected closing balance by 31.01.2015 (Including value of material in stock) |
| --- | --- | --- | --- | --- |
| 3,88,428.60 | 14,57,935.00 | 12,52,635.00 | 1,83,129.00 | 2,62,509.00 |

18.2 	Plan of activities under Revolving Fund

| S. No. | Proposed activities | Expected output | Anticipated income (Rs.) | Names of the team members involved |
| --- | --- | --- | --- | --- |
| 18.2.1 | Duck unit | Ducklings – 75 nos. | 7500.00 | Dr. S. Jayababu, SMS (Animal Husbandry) |
| 18.2.2 | Poultry hatchery unit | Birds – 750 nos. | 75000.00 | Dr. S. Jayababu, SMS (Animal Husbandry) |
| 18.2.3 | Vegetable seeds | 500 kg | 30000.00 | Dr. Benjamin Mathew (Programme Coordinator i/c.), Dr. Binu John Sam (SMS-Horticulture), Mr. Sudhakar Soundarajan (SMS-Plant Protection) |
|  | Nursery plants | 1000 nos. | 25000.00 |  |
|  | Vegetable seedlings | 3000 nos. | 12000.00 |  |
|  | Rooted Pepper cuttings | 50000 nos. | 500000.00 |  |
|  | Cardamom tillers | 1000 nos. | 30000.00 |  |
|  | Spices | 500 nos. | 5000.00 |  |
|  | Forest species | 2000 nos. | 4000.00 |  |
|  | Medicinal plants | 250 nos. | 2500.00 |  |
|  | Pseudomonas | 2500 L | 250000.00 |  |
|  | Trichoderma | 1000 L | 100000.00 |  |
|  | EPN | 25000 cadavers | 25000.00 |  |
|  | Pheromone Trap | 1000 nos. | 150000.00 |  |
|  | Metarhizium | 250 L | 37500.00 |  |
|  | Mushroom Spawn | 10000 pkts. | 300000.00 |  |
|  | Edible mushroom | 100 kg | 30000.00 |  |
|  | Vermicompost | 500 kg | 3500.00 |  |
|  | Azolla | 50 kg | 2500.00 |  |
|  | Value added products | 100 kg | 25000.00 |  |
|  | Homecare products | 100 L | 7000.00 |  |
|  | Rural craft products | 150 nos. | 13000.00 |  |
|  |  | Total | 16,34,500.00 |  |

## 19.	Activities of soil, water and plant testing laboratory during 2015-16

| S. No. | Type | No. of samples to be analyzed | Names of the team members involved |
| --- | --- | --- | --- |
| 19.1 | Soil | 500 | Ms. Manju Jincy Varghese (SMS-Soil Science) |
| 19.2 | Water | - |  |
| 19.3 | Plant | - |  |
| 19.4 | Others | - |  |

## 20.	E-linkage during 2015-16

| S. No | Nature of activities | Likely period of completion (please set the time frame) | Remarks if any |
| --- | --- | --- | --- |
| 20.1 | Title of the technology module to be prepared |  |  |
| 20.2 | Creation and maintenance of relevant database system for KVK | Farmers database creation & updation – year-around | - |
| 20.3 | Any other (Please specify) |  |  |
| 20.4 |  |  |  |

21. Activities planned under Rainwater Harvesting Scheme (only to those KVKs which are already having scheme under Rain Water Harvesting): Nil.

22.	Innovative Farmer’s Meet

| S. No. | Particulars | Details |
| --- | --- | --- |
| 22.1 | Are you planning for conducing Farm Innovators meet in your district? | Yes |
| 22.2 | If Yes likely month of the meet | October |
| 22.3 | Brief action plan in this regard | We are plan to organize a meet & exhibition of Farmer Innovators from Idukki district |

23.	Farmer’s Field School planned

| S. No | Thematic area | Title of the FFS | Budget proposed in Rs. |
| --- | --- | --- | --- |
| 23.1 | Crop Management | Integrated Crop Management (ICM) in black pepper | 30,000.00 |
| 23.2 |  |  |  |

23.A     Innovative Extension Methodology / Technology Delivery Mechanism proposed: Nil.

| S. No | Problem to be intervened | Thematic area | Major technological interventions / methodology to be adopted | Budget proposed in Rs.* |
| --- | --- | --- | --- | --- |
| 23.A1 |  |  |  |  |

*Maximum of Rs. One lakh

24. Budget - Details of budget  utilization (2014-15) up to 31 January 2015(Rs. in lakhs)

| S. No. | Particulars | Sanctioned | Released | Expenditure |
| --- | --- | --- | --- | --- |
| 24.1 | Recurring Contingencies |  |  |  |
| 24.1.1 | Pay & Allowances | 85.50 |  | 4873334 |
| 24.1.2 | Traveling allowances | 1.30 |  | 131303 |
| 24.1.3 | Contingencies |  |  |  |
| 24.1.4.1 | Stationery, telephone, postage and other expenditure on office running, publication of Newsletter and library maintenance | 0.30 |  | 213577 |
| B | POL, repair of vehicles, tractor and equipments | 0.30 |  | 183016 |
| C | Meals/refreshment for trainees | 0.20 |  | 26277 |
| D | Training material | 0.20 |  | 49431 |
| E | Frontline demonstration except oilseeds and pulses | 1.70 |  | 193268 |
| F | On farm testing | 0.30 |  | 36290 |
| G | Training of extension functionaries | 0.10 |  | 0 |
| H | Maintenance of buildings | 0.10 |  | 2000 |
| I | Establishment of Soil, Plant & Water Testing Laboratory | 0.00 |  | 0 |
| J | Library | 0.00 |  | 2520 |
| K | Extension activities | 0.10 |  | 49505 |
| L | Farmers Field School (FFS) | 0.10 |  | 1000 |
| M | Integrated Farming System (IFS) | 0.10 |  | 0 |
| 24.1 | Total Recurring | 90.30 | 48.48131 | 57,61,521 |
| 24.2 | Non-Recurring Contingencies |  |  |  |
| 24.2.1 | Works |  |  |  |
| 24.2.2 | Equipments including SWTL & Furniture |  |  |  |
| 24.2.3 | Vehicle (Four wheeler/Two wheeler, please specify) |  |  |  |
| 24.2.4 | Library |  |  |  |
| 24.2 | Total Non Recurring | 0.00 | 0.00 | 0.00 |
| 24.3 | REVOLVING FUND | - | - | - |
| 24.4 | GRAND TOTAL (A+B+C) | 90.30 | 48.48131 | 57,61,521 |

25.Details of Budget Estimate (2015-16) based on proposed action plan

| S. No. | Particulars | BE 2015-16 proposed (Rs. in lakhs) |
| --- | --- | --- |
| 25.1 | Recurring Contingencies |  |
| 25.1.1 | Pay & Allowances | 102.60 |
| 25.1.2 | Traveling allowances | 3.22 |
| 25.1.3 | Contingencies |  |
| A | Stationery, telephone, postage and other expenditure on office running, publication of Newsletter and library maintenance (Purchase of News Paper & Magazines) | 3.90 |
| B | POL, repair of vehicles, tractor and equipments | 3.42 |
| C | Meals/refreshment for trainees (ceiling upto Rs.40/day/trainee be maintained) | 2.25 |
| D | Training material (posters, charts, demonstration material including chemicals etc. required for conducting the training) | 1.53 |
| E | Frontline demonstration except oilseeds and pulses (minimum of 30 demonstration in a year) | 3.75 |
| F | On farm testing (on need based, location specific and newly generated information in the major production systems of the area) | 1.10 |
| G | Training of extension functionaries | 0.50 |
| H | Maintenance of buildings | 1.50 |
| I | Establishment of Soil, Plant & Water Testing Laboratory | 0.00 |
| J | Library | 0.10 |
| K | Extension activities | 1.00 |
| L | Farmers Field School (FFS) | 0.50 |
| M | Integrated Farming System (IFS) | 0.50 |
| 25.1 | TOTAL Recurring Contingencies | 125.87 |
| 25.2 | Non-Recurring Contingencies |  |
| 25.2.1 | Works | 115.00 |
| 25.2.2 | Equipments including SWTL & Furniture | 2.00 |
| 25.2.3 | Vehicle (Four wheeler/Two wheeler, please specify) | 0.00 |
| 25.2.4 | Library (Purchase of assets like books & journals) | 0.50 |
| 25.2 | TOTAL Non-Recurring Contingencies | 117.50 |
| 25.3 | REVOLVING FUND | - |
| 25.4 | GRAND TOTAL | 243.37 |